- Technical Support – Work Order Specification

Title: Provision of control and instrumentation technical support to UK HPR1000 GDA step 3

Background to the project In January 2017 ONR formally started the Generic Design Assessment (GDA) of the UK HPR1000. The GDA process calls for a step-wise assessment of the Requesting Party's (RP) safety submissions with the assessments increasing in detail as the project progresses. General Nuclear System Ltd (GNS) has been established to act on behalf of the three joint Requesting Parties (China General Nuclear Power Corporation (CGN), Électricité de France (EDF) and General Nuclear International (GNI)) to implement the GDA of the UK HPR1000 reactor. For practical purposes GNS is referred to as the ‘UK HPR1000 GDA Requesting Party (RP)’ in this specification. Step 1 of GDA is the preparatory part of the process where the RP established its project management and technical teams and made arrangements for the GDA of the UK HPR1000 reactor. Step 1 was completed in November 2017. Step 2 of GDA commenced in November 2017. Step 2 comprises an overview of the acceptability, in accordance with the regulatory regime of Great Britain; of the design fundamentals, including review of key nuclear safety claims with the aim of identifying; any fundamental safety shortfalls that could prevent the issue of a Design Acceptance Confirmation (DAC). Step 2 is scheduled to be completed in November 2018 with all of ONR’s supporting reports published on the ONR website. Step 3 of GDA of the UK HPR1000 commenced in November 2018 and is expected to conclude in December 2019. A key part of Step 3 is for ONR inspectors responsible for assessing the UK HPR1000 design to identify areas where timely input from technical support contractors (TSCs) is required to enable GDA to progress to programme, and to ultimately inform ONR’s regulatory decision on the acceptability, or otherwise, of the UK HPR1000 design for construction in the UK. ONR has identified control and instrumentation (C&I) as one such area where TSC support is required to assist with the assessment of technical submissions to understand the arguments (or ‘reasoning’) behind the RP’s claims. Further background information can be found on the RP and ONR websites: - http://www.ukhpr1000.co.uk/ - http://www.onr.org.uk/new-reactors/uk-hpr1000/index.htm

SCOPE OF THE SERVICES REQUIRED ONR is seeking to engage one of the TSCs appointed in Lot 2 of its technical support framework agreement. The TSC is required to provide technical support to ONR during Step 3 of GDA, in order to assess independently the C&I aspects of UK HPR1000 Pre-Construction Safety Report (PCSR) and supporting documents. The scope of services required during Step 3 includes: - Familiarisation with ONR’s Step 2 C&I Assessment Report findings and recommendations, relevant RP Step 2 submissions, and existing Regulatory Queries (RQ) and Regulatory Observations (RO) as defined in the ONR GDA Guidance to Requesting Parties. - http://www.onr.org.uk/new-reactors/guidance-assessment.htm - Undertake an independent detailed technical review of the Step 3 C&I submissions (see Appendix 1) in line with ONR’s regulatory expectations and modern standards. The review should confirm: - Safety claims, arguments and supporting evidence have a clear structure and hierarchy so that the design basis is set out logically in specific and measurable statements that show that C&I aspects of the UK HPR1000 meet the relevant ONR Safety Assessment Principles 2014 (SAPs). - The design of the overall C&I architecture as well as individual systems has taken due account of key principles including, but not limited to, defence-in-depth, common cause failure, separation, diversity and redundancy. - The categorisation of safety functions and classification of C&I systems is appropriate taking into account UK context. - The required safety functions and performance requirements of the C&I systems under normal operating, fault and accident conditions have been specified; i.e design basis and beyond design basis conditions. - Internationally recognised standards and Relevant Good Practice (RGP) have been adopted. - The codes and standards used for the design of each C&I are appropriate given the classification of that system. - The codes and standards used have been correctly and appropriately applied. - The UK context has been fully recognised and addressed. - Confirmation that appropriate safety evidence has been presented and addressed in the design. - The adequacy of the output from the reports regarding interfacing disciplines and identification of any cross-cutting issues. - The adequacy of the PCSR and consistency with it in the supporting documents. - Suitable resolution of areas identified during GDA Step 2 that require follow-up. The documents listed in Appendix 1 will form the basis of the review for the C&I assessment. Appendix 1 provides the timescales from the RP’s schedule for the submission of documentation, although it should be noted that these dates are merely indicative and are subject to change. The personnel engaged will work as integral members of the ONR GDA C&I assessment team. It is expected that they will work remotely from ONR office locations but they are expected to interact effectively by email/telephone, and they should be available to attend face-to-face meetings at ONR offices or RP offices as required. ONR is looking for experienced individuals with knowledge of nuclear reactor C&I safety cases to review RP submissions, and this work will include but may not be limited to: - Review RP's C&I submissions against ONR's SAPs, ONR's technical assessment guides, relevant international standards, and UK/international relevant good practice, seeking evidence to confirm that ONR expectations as outlined in paragraph 2.2 are met. - Support ONR (including any required preparation) during teleconferences, videoconferences and / or face-to-face meetings (in the UK or China) with the RP to discuss progress of the reviews, findings from the reviews, emerging issues, etc, and / or to request additional information and / or analysis from the RP. - Identification of any necessary UK HPR1000 information required from the RP. ONR will formally submit these to the RP as regulatory queries, but the TSC is expected to identify the information and to draft the regulatory requests. - Review of the responses provided by the RP in answer to any queries raised, and advice ONR on the adequacy of the responses and on the way forward if the responses are incomplete or inadequate. - Provide C&I progress updates to internal ONR meetings where necessary. - The TSC should fully consider the available baseline information and carry out a review of the first revision of each report delivered during the contract period. For later revisions of reports, only changes and additional information should be reviewed. - Assist in the authoring of the C&I input to the Step 3 Summary Report, capturing ONR's assessment of RP submissions and responses to technical questions. An examples report for a previous GDA can be found at: - http://www.onr.org.uk/new-reactors/uk-abwr/reports/step3/uk-abwr-step-3-summary-report.pdf - It should be assumed that one regulatory query, each comprising multiple questions may be raised for each report reviewed. - It should be assumed that four regulatory observations may be raised during step 3 for C&I engineering. Individuals engaged in the work should have knowledge of relevant nuclear power plant standards, guidance, and regulatory expectations. The individuals should be able to demonstrate the ability to review safety cases, to quickly identify relevant claims, arguments and evidence, identify any shortfalls against relevant good practice and evaluate their implications, and then to express their conclusions clearly in a written report. In addition, individuals should be able to demonstrate the ability to draft technical questions, review responses, and come to a conclusion on adequacy within the context of the ONR GDA process. The TSC should develop a fully resourced work programme, with planned tasks, deliverables, milestones, timeframes and project costs. Deliverables are to be in the form of technical reports documenting the findings and results of the TSC review of the RP’s step 3 C&I submissions. Note it is not expected that a separate report will be produced for each document reviewed; the TSC should propose the number of technical reports to be delivered, based on ta logical grouping of the document list provided in Appendix 1 (for example, it may be appropriate to produce one report for each of the main C&I systems in the UK HPR1000 architecture).The reports should contain - Full details of the work undertaken - A description of the TSC assessment methodology - A description of the RP’s Safety Case - Information on the TSC review; queries raised; suitability of the RP’s responses; consideration of RGP; and consideration of compliance with the ONR SAPs - Summary and conclusions - Full reference list The TSC should; - Obtain ONR acceptance of the technical review scope, supporting programme and project costs. This will be undertaken upon award of contract and the subsequent project kick-off meeting. - Deliver the defined scope as set out in the programme and to the project cost. - Routinely review the programme scope, deliverables, milestones, timeframes, project costs and indicative invoice forecast. - Attend meetings and technical workshops to support ONR during the course of the contract as defined in this specification.

OBJECTIVES The objective of this task is to provide experienced support ONR’s control and instrumentation assessment, to allow it to deliver its regulatory objectives for the UK HPR1000 GDA. This will be done as described in section 2. The contract output should be technical reports (number to be proposed by the TSC for agreement with ONR, as per paragraph 2.10), documenting the findings and results of the TSC review of the RP’s step 3 C&I submissions. ONR will use these findings to judge if the claims, arguments and evidence made by the RP are adequate and can be substantiated, and to inform its regulatory judgement as to the adequacy of the UK HPR1000 C&I design.

CONSTRAINTS - The following constraints will apply: A start date of January 2019 is initially proposed for the assessment of the Civil Engineering evidence. The C&I work package is assumed to be approximately 10 months in duration. This is to be agreed and fixed when the contract is awarded, as will key project milestones and delivery dates for the various reports: - Start of GDA Step 3: November 2018. - TSC proposals received: December 2018. - TSC selection and approvals process: December 2018 – January 2019. - Contract awarded: January 2019. - Kick-off meeting between ONR and TSC: within 10 working days of award of contract. - TSC’s Step 3 draft reports are required before 16th August 2019 (this is to inform authoring of ONR reports which are required by 27th September 2019). - End of the GDA Step 3: December 2019. The timing of RP submissions is stated in Appendix 1. However, the precise timing of RP submissions may be varied by the RP and as a result the TSC should ensure the arrangements are flexible in terms of its ability to plan and adapt to the timing of the actual submissions. The work is expected to start in January 2019 and conclude in October 2019. Individuals put forward for this work should, insofar as is possible, be free from relevant conflicts of interest. Where a potential conflict exists, the contractor should describe how this will be managed. The working location should be as flexible as possible but individuals must be available to respond to emails/telephone calls within normal working hours, and be available to attend face-to-face meetings at reasonable notice. The work is expected to start and conclude in accordance with the overall timescales given above, and a project programme is to be agreed with the contractor upon contract award. ONR will provide the latest versions of any relevant documentation submitted by the RP. Further information may need to be identified and requested by the contractor through technical questions (via ONR). The timescales for both of these processes are largely outside of ONR's direct control and therefore delays to the receipt of information may occur. Similarly the quality of any response cannot be guaranteed. A pragmatic and flexible approach should be adopted by the contractor to deal with this, both technically and contractually. It is expected that the successful contractor may also draw upon their experience, resources and publically available information to perform this work. All information received from the RP should be treated in accordance with the ONR Technical Support Contact Framework agreement and non-disclosure agreement. The information or a certificate of destruction should be returned to ONR at the end of the contract. The arrangements for security vetting and IT security established in the Technical Support Contract framework agreement will need to be followed. No information with a security marking above UK OFFICAL - SENSITIVE is anticipated as part of this contract. Most information may carry the RP's commercial marking. The contractor and where applicable, its sub-contractors, should provide assurances that it has, or is able to obtain, all necessary export control licenses, where required to transfer relevant information out of the UK and return it. The transmittal of all documents between ONR and the contractor should be through ONR's Joint Programme Office (JPO). This will be through encrypted DVDs, regardless of the security marking (unless the documents are publically available on the internet). The aim of this work package is to inform and advise ONR. However, it is ONR's intention to brief the RP on the conclusions of the work. The RP should be provided with copies of any reports produced for information and will be invited to comment on their factual accuracy. It is not ONR's intention to publish the reports produced through this contract. However, it is likely they will be referenced in publically available reports and therefore subject to freedom of information requests. This should not constrain or limit the produced reports but should be taken into account with the style and format. Attendance at meetings will be required, and travel and subsistence will be reimbursed at cost by ONR, following the initial outlay by the TSC. Their location may include but not be limited to: - ONR offices, Bootle and Cheltenham - GNS/EDF offices, Barnwood - GNS offices, Regent St London.

CONTRACT MANAGEMENT ONR requires that it be kept updated about progress and delivery of the required work via monthly meetings, to include a contract start-up meeting at ONR’s offices at Bootle. Subsequent progress meeting should be arranged with the ONR Project Office and can be held at ONR’s office in Bootle, or the contractor’s premises.

TECHNICAL RESPONSE

Response The Technical Response should demonstrate a clear understanding of the work required. Please provide: - a description of how you will deliver the scope of work (methodology) and the proposed delivery team you will use, clearly signposting to relevant sections within your Capability Prospectus where appropriate/relevant ; - a description of proposed deliverables and/or outputs - an outline of anticipated engagement (project meetings & management) - details of proposed cost and associated effort assumptions - a project delivery plan showing activities and milestones - a planned invoice schedule - details of any assumptions or constraints

APPENDIX 1:  Step 3 – Submissions for Assessment

| Number | Document Title | Indicative submission date | Description |
| --- | --- | --- | --- |
|  | Safety Requirements of the Diverse Actuation System (KDS [DAS]) | 31/12/2018 | Present the safety requirement of the KDS [DAS] in UK HPR1000. Specifies the system role, classification, design principles, design requirements (e.g. the general requirements for the technology used for the KDS [DAS]) and the reference list of codes and standards. |
|  | Comparison of UK HPR1000 Overall C&I Architecture with IEC 61513 | 30/01/2019 | Presents the comparison analysis of the overall C&I architecture with the relevant requirements of IEC 61513. |
|  | Diversity Analysis between C&I Platforms | 30/01/2019 | This report presents supporting information for the analysis between C&I platforms. |
|  | Defence in Depth and Diversity Analysis Report | 30/01/2019 | This report is used to analyse and evaluate the Defence-in-Depth & Diversity for the UK HPR1000 C&I. |
|  | Interface Specification of Level 0 Equipment | 30/01/2019 | This report presents supporting information for the interface requirement of typical level 0 sensors and actuators. |
|  | Isolation Analysis of C&I Systems | 30/01/2019 | Presents supporting information for the analysis of isolation measures between C&I systems. |
|  | Topic Report of FirmSys Platform | 30/01/2019 | Presents detailed and supplementary information of the FirmSys platform used for the Protection System and Secondary Automation System. |
|  | Simple Hardware Based Platform Technical Research Summary Report | 30/03/2019 | To describe simple hardware technologies as potential options for the KDS [DAS]. The report will include: - A survey and feasibility analysis of simple hardware technologies. - A list of potential technologies to be used in the KDS [DAS]. - A methodology for selection of the platform technology for the KDS [DAS]. |
|  | Requirement Analysis of CIM Responding to CCF in UK HPR1000 | 30/03/2019 | Based on the current CIM technology and fault schedule, this report will present the potential risk and possible countermeasures, e.g. design requirements, to mitigate the risk in UK HPR1000. |
|  | FMEA Report of Protection System(PS) | 30/04/2019 | Demonstrate that the PS system meets the single-failure criterion and fail-safe criterion based on failure modes of the DCS. |
|  | SAPs Conformance Assessment of C&I Architecture | 30/04/2019 | Provides a comparison of the overall C&I architecture with the related SAPs. The comparison analysis focuses on the centralised C&I systems important to safety. |
|  | Methodology of SMART Devices Substantiation | 30/04/2019 | Presents the approach for justification of smart devices for use in nuclear safety applications. Describes the approach to demonstration of smart devices in terms of PE and ICBM. Describes the general approach to the selection and application of ICBMs for smart devices. |
|  | Equipment Qualification Plan of FirmSys Platform | 30/04/2019 | Comprises detailed information for the scope and the method of the qualification work or the FirmSys platform used for the Protection System and Secondary Automation System. |
|  | Equipment Qualification Plan of HOLLiAS-N Platform | 30/05/2019 | Comprises detailed information for the scope and the method of the qualification work or the HOLLiAS-N platform used for the Plant Standard Automation System. |
|  | Protection System (PS) Requirement Specification | 30/06/2019 | Identifies the requirements of PS architecture, functions, performance , maintenance, etc. |
|  | Periodic Test Requirement of Protection System (PS) | 30/06/2019 | Identifies the requirements for periodic tests (including the instrument channel, special device interface tests. etc) and self-diagnosis of the PS. |
|  | Design Scheme Analysis of CIM Response to CCF in UK HPR1000 | 30/06/2019 | Following the CIM requirements analysis, identifies alternative design schemes for optioneering and analysis to justify how design requirements will be satisfied. |
|  | Software Verification and Validation Plan | 30/07/2019 | This document specifies the software Verification and Validation activities in the software development process of the FirmSys platform products, and explains the relationship between the V&V activities and the R&D activities. Its purpose is to determine the V&V general technical requirements, the V&V process, the activity phase division, tasks at each activity phase, input and output, V&V management, V&V report, exception report process flow, V&V document requirements, and also defines the V&V organizational structure and duties and the associated work schedule. |
|  | Topic Report of HOLLiAS-N Platform | 30/07/2019 | Presents detailed and supplementary information of the HOLLiAS-N platform used for the Plant Standard Automation System. |
|  | Design Specification of Protection System (PS) | 30/09/2019 | Presents detailed information about the Protection System design scheme. Describes the system architecture of the PS and functions, performance, interfaces, etc. |
|  | Periodic Test of Protection System (PS) | 30/09/2019 | Describes the scope and methodology of Periodic Tests. |
|  | Design Specification of Safety Automation System (SAS) | 30/09/2019 | Presents detailed information of the SAS. Describes the system architecture of the SAS and functions, performance, interfaces, etc. |