## Template new eu regs (4) (hidden)
To populate the dates enter the cabinet date, implementation period and contract start date manually
Rows filled with grey are optional if these are not required strike through the text and enter "O" into the Days Column (do not delete the row or leave the days blank)
The standard timeframes are for guidance only and can be changed as required
Automaically generated dates should not fall on Saturdays/Sundays and changes reflecting full weeks (7,14,21, 28 days ect) will maintain this. Other alterations may require subsequent "Days" to be adjusted or dates to be manually overwritten to avoid non-working days.
Contract Title:
Responsibilities:
|  |  | Highlight Actions as follows: | Department | Preparation
|  |  |  | Procurement Services | Tender
|  |  |  | Joint | Evaluation
Dialogue/Negotiations
Award
Implementation
|  |  | Action | Standard Timeframe | Days | Start Date | End Date
Open, Formal Quotation | If "yes" to 2a | If yes to 4a | Consulation period | Number of days required | user defined | user defined | user defined
Open, Formal Quotation | If "yes" to 2a | If yes to 1c | Publish PIN notice | 52 - 365 days prior to OJEU notice despatch | user defined | user defined
Open, Formal Quotation | If "yes" to 2a |  | Social Value Act consideration | 7 days | 7 | 2015-05-15 | 2015-05-22
Open, Formal Quotation | If "yes" to 2a |  | Risk analysis | 7 days | 7 | 2015-05-22 | 2015-05-29
Open, Formal Quotation | If "yes" to 2a |  | Agree procurement route & responsibilities | 7 days | 7 | 2015-05-29 | 2015-06-05
Open, Formal Quotation | If "yes" to 2a | If Yes to 4b | Contact Legal Services to prepare draft contract | 7 days | 7 | 2015-06-05 | 2015-06-12
Open, Formal Quotation | If "yes" to 2a |  | Stakeholder to prepare draft specification / requirements and KPI's | 28 days | 28 | 2015-06-12 | 2015-07-10
Open, Formal Quotation | If "yes" to 2a | If "Yes" to 4c | Issue advertisment for marketing event |  |  | 2015-07-10 | 2015-07-10
Open, Formal Quotation | If "yes" to 2a | If "Yes" to 4c | Prepare presentation for market engagement event | 20 days | 21 | 2015-07-10 | 2015-07-31
Open, Formal Quotation | If "yes" to 2a | If "Yes" to 4c | Marketing engagement event | 7 days | 7 | 2015-07-31 | 2015-08-07
Open, Formal Quotation | If "yes" to 2a |  | Stakeholder to complete specification / requirements (and submit to procurement when complete) | 14 days | 14 | 2015-08-07 | 2015-08-21
Open, Formal Quotation | If "yes" to 2a |  | Prepared and complete tender documents and scorecard | 14 days | 14 | 2015-08-21 | 2015-09-04
Open, Formal Quotation | If "yes" to 2a |  | Upload project to Due North |  |  | 2015-09-04 | 2015-09-04
Open, Formal Quotation | If "yes" to 2a | and "yes" to 1a | Issue Advert to OJEU |  |  | 2015-09-04 | 2015-09-04
Open, Formal Quotation | If "yes" to 2a | and "yes" to 1a | (Allow one day for submission to OJEU) | 1 day | 1 | 2015-09-04 | 2015-09-05
Open, Formal Quotation | If "yes" to 2a | If "yes" to 4d | Book in financial vetting with Techincal Finance |  |  | 2015-09-05 | 2015-09-05
Open, Formal Quotation | If "yes" to 2a |  | Publish Project on Due North Advertise on Source Derbyshire Email advert to identified prospective companies |  |  | 2015-09-05 | 2015-09-05
Open, Formal Quotation | If "yes" to 2a |  | (Number of days: Pre-questions deadline) | 5, 18 or 20 days |  | 2015-09-05 | 2015-09-05
|  |  | Finalise questions and answers log | 5 days | 5 | 2015-09-05 | 2015-09-10
Open, Formal Quotation | If "yes" to 2a |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-09-10 | 2015-09-10
|  |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-09-10 | 2015-09-15
Open, Formal Quotation | If "yes" to 2a |  | Tender Return Date OJEU with PIN or Urgent OJEU (15 days) Non-OJEU (28 days) OJEU (30 days) |  |  | 2015-09-15 | 2015-09-15
Open, Formal Quotation | If "yes" to 2a |  | Evaluation and clairfication of tender (and financial vetting) | 28 days | 28 | 2015-09-15 | 2015-10-13
Open, Formal Quotation | If "yes" to 2a | and "yes" to 4e | Agree who to invite to bidder meetings/interviews and issue invitations | 3 days | 3 | 2015-10-13 | 2015-10-16
Open, Formal Quotation | If "yes" to 2a | and "yes" to 4e | Confirm responses to bidder meeting/interviews | 7 days | 7 | 2015-10-16 | 2015-10-23
Open, Formal Quotation | If "yes" to 2a | and "yes" to 4e | bidder meetings | 7 days | 7 | 2015-10-23 | 2015-10-30
Open, Formal Quotation | If "yes" to 2a | and "yes" to 4f | Further clarification | 7 days | 7 | 2015-10-30 | 2015-11-06
Open, Formal Quotation | If "yes" to 2a |  | Agree preferred bidder(s) | 14 days | 14 | 2015-11-06 | 2015-11-20
Open, Formal Quotation | If "yes" to 2a | and "yes" to 4g | Negotiate terms & conditions with preferred bidder(s) | 28 days | 28 | 2015-11-20 | 2015-12-18
Open, Formal Quotation | If "yes" to 2a |  | Complete report to award contract | 7 days | 7 | 2015-12-18 | 2015-12-25
Restricted | If "yes" to 2b | If yes to 4a | Consulation period | Number of days required | user defined | user defined | user defined
Restricted | If "yes" to 2b | If yes to 1c | Publish PIN notice | 52 - 365 days prior to OJEU notice despatch | user defined | user defined
Restricted | If "yes" to 2b |  | Social Value Act consideration | 7 days | 7 | 2015-03-14 | 2015-03-21
Restricted | If "yes" to 2b |  | Risk analysis | 7 days | 7 | 2015-03-21 | 2015-03-28
Restricted | If "yes" to 2b |  | Agree procurement route & responsibilities | 7 days | 7 | 2015-03-28 | 2015-04-04
Restricted | If "yes" to 2b | If Yes to 4b | Contact Legal Services to prepare draft contract | 7 days | 7 | 2015-04-04 | 2015-04-11
Restricted | If "yes" to 2b |  | Stakeholder to prepare draft specification / requirements and KPIs | 28 days | 28 | 2015-04-11 | 2015-05-09
Restricted | If "yes" to 2b | If "Yes" to 4c | Issue advertisment for marketing event |  |  | 2015-05-09 | 2015-05-09
Restricted | If "yes" to 2b | If "Yes" to 4c | Prepare presentation for market engagement event | 20 days | 20 | 2015-05-09 | 2015-05-29
Restricted | If "yes" to 2b | If "Yes" to 4c | Marketing engagement event | 7 days | 7 | 2015-05-29 | 2015-06-05
Restricted | If "yes" to 2b |  | Stakeholder to complete EOI/PQQ Requirements (and submit to procurement when complete) | 14 days | 14 | 2015-06-05 | 2015-06-19
Restricted | If "yes" to 2b |  | Prepared and complete EOI/PQQ documents and scorecard | 14 days | 14 | 2015-06-19 | 2015-07-03
| If "yes" to 2b |  | Upload Project to Due North |  |  | 2015-07-03 | 2015-07-03
Restricted | If "yes" to 2b |  | Issue Advert to OJEU |  |  | 2015-07-03 | 2015-07-03
Restricted | If "yes" to 2b |  | (Allow one day for submission to OJEU) | 1 day | 1 | 2015-07-03 | 2015-07-04
Restricted | If "yes" to 2b | If "yes" to 4d | Book in financial vetting with techincal finance |  |  | 2015-07-04 | 2015-07-04
Restricted | If "yes" to 2b |  | Publish project on Due North Advertise EOI/PQQ on Source Derbyshire Email advert for EOI/PQQ to identified prospective companies |  |  | 2015-07-04 | 2015-07-04
Restricted | If "yes" to 2b |  | (Number of days: Pre-questions deadline) | 5 or 20 days |  | 2015-07-04 | 2015-07-04
|  |  | Finalise questions and answers log | 5 days | 5 | 2015-07-04 | 2015-07-09
Restricted | If "yes" to 2b |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-07-09 | 2015-07-09
Restricted | If "yes" to 2b |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-07-09 | 2015-07-14
Restricted | If "yes" to 2b |  | EOI/PQQ Return Date Urgent OJEU (15 days) OJEU or OJEU with PIN (30 days) |  |  | 2015-07-14 | 2015-07-14
Restricted | If "yes" to 2b |  | Evaluation and clairfication of PQQ/EOI (and financial vetting) | 28 days | 28 | 2015-07-14 | 2015-08-11
Restricted | If "yes" to 2b |  | Agree potential bidder list | 6 days | 6 | 2015-08-11 | 2015-08-17
Restricted | If "yes" to 2b |  | Stakeholder to complete specification / requirements (and submit to procurement when complete) | 14 days | 14 | 2015-08-17 | 2015-08-31
Restricted | If "yes" to 2b |  | Prepared and complete tender documents and scorecard | 14 days | 14 | 2015-08-31 | 2015-09-14
Restricted | If "yes" to 2b |  | Upload project to Due North |  |  | 2015-09-14 | 2015-09-14
Restricted | If "yes" to 2b |  | Pulish Tender to agreed bidders |  |  | 2015-09-14 | 2015-09-14
Restricted | If "yes" to 2b |  | (Number of days: Pre-questions deadline) | 2 or 15 days |  | 2015-09-14 | 2015-09-14
Restricted | If "yes" to 2b |  | Finalise questions and answers log | 3 or 5 days |  | 2015-09-14 | 2015-09-14
Restricted | If "yes" to 2b |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-09-14 | 2015-09-14
Restricted | If "yes" to 2b |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-09-14 | 2015-09-19
Restricted | If "yes" to 2b |  | Tender Return Date OJEU with PIN or Urgent OJEU (10 days) OJEU (25 days) |  |  | 2015-09-19 | 2015-09-19
Restricted | If "yes" to 2b |  | Evaluation and clairfication of tender (and financial vetting) stage | 28 days | 28 | 2015-09-19 | 2015-10-17
Restricted | If "yes" to 2b | and "yes" to 4e | Agree who to invite to bidder meetings/interviews and issue invitations | 3 days | 3 | 2015-10-17 | 2015-10-20
Restricted | If "yes" to 2b | and "yes" to 4e | Responses to bidder meeting/interviews | 7 days | 3 | 2015-10-20 | 2015-10-23
Restricted | If "yes" to 2b | and "yes" to 4e | bidder meetings | 7 days | 7 | 2015-10-23 | 2015-10-30
Restricted | If "yes" to 2b | and "yes" to 4f | Further clarification | 7 days | 7 | 2015-10-30 | 2015-11-06
Restricted | If "yes" to 2b |  | Agree preferred bidder(s) | 14 days | 14 | 2015-11-06 | 2015-11-20
Restricted | If "yes" to 2b | and "yes" to 4g | Negotiate terms & conditions with preferred bidder(s) | 28 days | 28 | 2015-11-20 | 2015-12-18
Restricted | If "yes" to 2b |  | Complete report to award contract | 7 days | 7 | 2015-12-18 | 2015-12-25
Competive Dialogue | If "yes" to 2c | If yes to 4a | Consulation period | Number of days required | user defined | user defined | user defined
Competive Dialogue | If "yes" to 2c | If yes to 1c | Publish PIN notice | 52 - 365 days prior to OJEU notice despatch | user defined | user defined
Competive Dialogue | If "yes" to 2c |  | Social Value Act consideration | 7 days | 7 | 2014-06-18 | 2014-06-25
Competive Dialogue | If "yes" to 2c |  | Risk analysis | 7 days | 7 | 2014-06-25 | 2014-07-02
Competive Dialogue | If "yes" to 2c |  | Agree procurement route & responsibilities | 7 days | 7 | 2014-07-02 | 2014-07-09
Competive Dialogue | If "yes" to 2c | If Yes to 4b | Contact Legal Services to prepare draft contract | 7 days | 7 | 2014-07-09 | 2014-07-16
Competive Dialogue | If "yes" to 2c |  | Stakeholder to prepare draft specification / requirements and KPIs | 28 days | 28 | 2014-07-16 | 2014-08-13
Competive Dialogue | If "yes" to 2c | If "Yes" to 4c | Issue advertisment for marketing event |  |  | 2014-08-13 | 2014-08-13
Competive Dialogue | If "yes" to 2c | If "Yes" to 4c | Prepare presentation for market engagement event | 20 days | 20 | 2014-08-13 | 2014-09-02
Competive Dialogue | If "yes" to 2c | If "Yes" to 4c | Marketing engagement event | 7 days | 7 | 2014-09-02 | 2014-09-09
Competive Dialogue | If "yes" to 2c |  | Stakeholder to complete EOI/PQQ Requirements (and submit to procurement when complete) | 14 days | 14 | 2014-09-09 | 2014-09-23
Competive Dialogue | If "yes" to 2c |  | Prepared and complete EOI/PQQ documents and scorecard | 14 days | 14 | 2014-09-23 | 2014-10-07
Competive Dialogue | If "yes" to 2c |  | Upload Project to Due North |  |  | 2014-10-07 | 2014-10-07
Competive Dialogue | If "yes" to 2c |  | Issue Advert to OJEU |  |  | 2014-10-07 | 2014-10-07
|  |  | (Allow one day for submission to OJEU) | 1 day | 1 | 2014-10-07 | 2014-10-08
Competive Dialogue | If "yes" to 2c | If "yes" to 4d | Book in financial vetting with techincal finance |  |  | 2014-10-08 | 2014-10-08
Competive Dialogue | If "yes" to 2c |  | Publish project on Due North Advertise EOI/PQQ on Source Derbyshire Email advert for EOI/PQQ to identified prospective companies |  |  | 2014-10-08 | 2014-10-08
Competive Dialogue | If "yes" to 2c |  | (Number of days: Pre-questions deadline) | 5 or 20 days |  | 2014-10-08 | 2014-10-08
Restricted | If "yes" to 2b |  | Finalise questions and answers log | 5 days | 5 | 2014-10-08 | 2014-10-13
Competive Dialogue | If "yes" to 2c |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2014-10-13 | 2014-10-13
Competive Dialogue | If "yes" to 2c |  | (Number of days: Post answers log publication) | 5 days | 5 | 2014-10-13 | 2014-10-18
Restricted | If "yes" to 2c |  | EOI/PQQ Return Date Urgent OJEU (15 days) OJEU or OJEU with PIN (30 days) |  |  | 2014-10-18 | 2014-10-18
Competive Dialogue | If "yes" to 2c |  | Evaluation and clairfication of PQQ/EOI (and financial vetting) | 28 days | 28 | 2014-10-18 | 2014-11-15
Competive Dialogue | If "yes" to 2c |  | Agree long list of bidders to be Invited to Participate in Dialogue | 6 days | 6 | 2014-11-15 | 2014-11-21
Competive Dialogue | If "yes" to 2c |  | Stakeholder to complete Project Information Memorandum (PIM) or Descriptive Document Requirements (and submit to procurement when complete) for Invitation to Participate in Dialogue Stage (ITPD) | 14 days | 14 | 2014-11-21 | 2014-12-05
Competive Dialogue | If "yes" to 2c |  | Prepare ITPD inlcuding Project Information Memorandum (PIM) / Descriptive Document, details of how the dialogue will be conducted, the award sub-criteria and weightings etc. | 14 days | 14 | 2014-12-05 | 2014-12-19
Competive Dialogue | If "yes" to 2c |  | Upload ITPD documents to Due North |  |  | 2014-12-19 | 2014-12-19
Competive Dialogue | If "yes" to 2c |  | Issue ITPD to longlisted bidders & notify unsuccessful candidates | 1 day | 1 | 2014-12-19 | 2014-12-20
Competive Dialogue | If "yes" to 2c |  | Dialogue | 28 days | 28 | 2014-12-20 | 2015-01-17
Competive Dialogue | If "yes" to 2c |  | Suspend dialogue |  |  | 2015-01-17 | 2015-01-17
Competive Dialogue | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-01-17 | 2015-01-17
Competive Dialogue | If "yes" to 2c |  | Prepare Invitation to Submit Detailed Solution (ISDS) documents | 14 days | 14 | 2015-01-03 | 2015-01-17
Competive Dialogue | If "yes" to 2c |  | Issue ISOS to bidders |  |  | 2015-01-17 | 2015-01-17
Competive Dialogue | If "yes" to 2c |  | (Number of days: Pre-questions deadline) | 18 days | 18 | 2015-01-17 | 2015-02-04
Competive Dialogue | If "yes" to 2c |  | Finalise questions and answers log | 5 days | 5 | 2015-02-04 | 2015-02-09
Competive Dialogue | If "yes" to 2c |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-02-09 | 2015-02-09
Competive Dialogue | If "yes" to 2c |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-02-09 | 2015-02-14
Competive Dialogue | If "yes" to 2c |  | ISOS Return Date |  |  | 2015-02-14 | 2015-02-14
Competive Dialogue | If "yes" to 2c |  | Evaluation of ISOS | 14 days | 14 | 2015-02-14 | 2015-02-28
Competive Dialogue | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-02-28 | 2015-02-28
Competive Dialogue | If "yes" to 2c |  | Dialogue | 28 days | 28 | 2015-02-28 | 2015-03-28
Competive Dialogue | If "yes" to 2c |  | Suspend dialogue |  |  | 2015-03-28 | 2015-03-28
Competive Dialogue | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-03-28 | 2015-03-28
Competive Dialogue | If "yes" to 2c |  | Prepare Invitation to Submit Detailed Solution (ISDS) douments | 14 days | 14 | 2015-03-28 | 2015-04-11
Competive Dialogue | If "yes" to 2c |  | Issue ISDS to bidders |  |  | 2015-04-11 | 2015-04-11
Competive Dialogue | If "yes" to 2c |  | (Number of days: Pre-questions deadline) | 18 days | 18 | 2015-04-11 | 2015-04-29
Competive Dialogue | If "yes" to 2c |  | Finalise questions and answers log | 5 days | 5 | 2015-04-29 | 2015-05-04
Competive Dialogue | If "yes" to 2c |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-05-04 | 2015-05-04
Competive Dialogue | If "yes" to 2c |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-05-04 | 2015-05-09
Competive Dialogue | If "yes" to 2c |  | ISDS Return Date |  |  | 2015-05-09 | 2015-05-09
Competive Dialogue | If "yes" to 2c |  | Evaluation of ISDS | 14 days | 14 | 2015-05-09 | 2015-05-23
Competive Dialogue | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-05-23 | 2015-05-23
Competive Dialogue | If "yes" to 2c |  | Dialogue Stage | 28 days | 28 | 2015-05-23 | 2015-06-20
Competive Dialogue | If "yes" to 2c |  | Suspend dialogue |  |  | 2015-06-20 | 2015-06-20
Competive Dialogue | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-06-20 | 2015-06-20
Competive Dialogue | If "yes" to 2c |  | Prepare Invitation to Submit Refined Solution (ISRS) documents | 7 days | 7 | 2015-06-20 | 2015-06-27
Competive Dialogue | If "yes" to 2c |  | Issue ISRS to bidders |  |  | 2015-06-27 | 2015-06-27
|  |  | (Number of days: Pre-questions deadline) | 18 days | 18 | 2015-06-27 | 2015-07-15
Competive Dialogue | If "yes" to 2c |  | Finalise questions and answers log | 5 days | 5 | 2015-07-15 | 2015-07-20
Competive Dialogue | If "yes" to 2c |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-07-20 | 2015-07-20
Competive Dialogue | If "yes" to 2c |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-07-20 | 2015-07-25
Competive Dialogue | If "yes" to 2c |  | ISRS Return Date |  |  | 2015-07-25 | 2015-07-25
Competive Dialogue | If "yes" to 2c |  | Evaluation of ISRS | 7 days | 14 | 2015-07-25 | 2015-08-08
Competive Dialogue | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-08-08 | 2015-08-08
Competive Dialogue | If "yes" to 2c |  | Dialogue | 28 days | 28 | 2015-08-08 | 2015-09-05
Competive Dialogue | If "yes" to 2c |  | Competitive dialogue closed |  |  | 2015-09-05 | 2015-09-05
Competive Dialogue | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-09-05 | 2015-09-05
Competive Dialogue | If "yes" to 2c |  | Prepare Invitation to Submit Final Tender (ITSFT) documents | 7 days | 7 | 2015-09-05 | 2015-09-12
Competive Dialogue | If "yes" to 2c |  | Issue ITSFT to bidders |  |  | 2015-09-12 | 2015-09-12
|  |  | (Number of days: Pre-questions deadline) | 18 days | 18 | 2015-09-12 | 2015-09-30
Competive Dialogue | If "yes" to 2c |  | Finalise questions and answers log | 5 days | 5 | 2015-09-30 | 2015-10-05
Competive Dialogue | If "yes" to 2c |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-10-05 | 2015-10-05
Competive Dialogue | If "yes" to 2c |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-10-05 | 2015-10-10
Competive Dialogue | If "yes" to 2c |  | ITSFT Return Date |  |  | 2015-10-10 | 2015-10-10
Competive Dialogue | If "yes" to 2c |  | Evaluation and clairfication of ITSFT | 28 days | 28 | 2015-10-10 | 2015-11-07
Competive Dialogue | If "yes" to 2c | and "yes" to 4f | Further clarification | 7 days | 7 | 2015-11-07 | 2015-11-14
Competive Dialogue | If "yes" to 2c |  | Agree preferred bidder(s) | 6 days | 6 | 2015-11-14 | 2015-11-20
Competive Dialogue | If "yes" to 2c | and "yes" to 4g | Negotiate terms & conditions with preferred bidder(s) | 28 days | 28 | 2015-11-20 | 2015-12-18
Competive Dialogue | If "yes" to 2c |  | Complete report to award contract | 7 days | 7 | 2015-12-18 | 2015-12-25
Competative Negotiated | If "yes" to 2d | If yes to 4a | Consulation period | Number of days required | user defined | user defined | user defined
Competative Negotiated | If "yes" to 2d | If yes to 1c | Publish PIN notice | 52 - 365 days prior to OJEU notice despatch | user defined | user defined
Competative Negotiated | If "yes" to 2d |  | Social Value Act consideration | 7 days | 7 | 2015-01-12 | 2015-01-19
Competative Negotiated | If "yes" to 2d |  | Risk analysis | 7 days | 7 | 2015-01-19 | 2015-01-26
Competative Negotiated | If "yes" to 2d |  | Agree procurement route & responsibilities | 7 days | 7 | 2015-01-26 | 2015-02-02
Competative Negotiated | If "yes" to 2d | If Yes to 4b | Contact Legal Services to prepare draft contract | 7 days | 7 | 2015-02-02 | 2015-02-09
Competative Negotiated | If "yes" to 2d |  | Stakeholder to prepare draft specification / requirements and KPIs | 28 days | 28 | 2015-02-09 | 2015-03-09
Competative Negotiated | If "yes" to 2d | If "Yes" to 4c | Issue advertisment for marketing event |  |  | 2015-03-09 | 2015-03-09
Competative Negotiated | If "yes" to 2d | If "Yes" to 4c | Prepare presentation for market engagement event | 20 days | 20 | 2015-03-09 | 2015-03-29
Competative Negotiated | If "yes" to 2d | If "Yes" to 4c | Marketing engagement event | 7 days | 7 | 2015-03-29 | 2015-04-05
Competative Negotiated | If "yes" to 2d |  | Stakeholder to complete EOI/PQQ Requirements (and submit to procurement when complete) | 14 days | 14 | 2015-04-05 | 2015-04-19
Competative Negotiated | If "yes" to 2d |  | Prepared and complete EOI/PQQ documents and scorecard | 14 days | 14 | 2015-04-19 | 2015-05-03
Competative Negotiated | If "yes" to 2d |  | Upload Project to Due North |  |  | 2015-05-03 | 2015-05-03
Competative Negotiated | If "yes" to 2d |  | Issue Advert to OJEU |  |  | 2015-05-03 | 2015-05-03
Competative Negotiated | If "yes" to 2d |  | (Allow one day for submission to OJEU) | 1 day | 1 | 2015-05-03 | 2015-05-04
Competative Negotiated | If "yes" to 2d | If "yes" to 4d | Book in financial vetting with techincal finance |  |  | 2015-05-04 | 2015-05-04
Competative Negotiated | If "yes" to 2d |  | Publish project on Due North Advertise EOI/PQQ on Source Derbyshire Email advert for EOI/PQQ to identified prospective companies |  |  | 2015-05-04 | 2015-05-04
Competative Negotiated | If "yes" to 2d |  | (Number of days: Pre-questions deadline) | 5 or 20 days |  | 2015-05-04 | 2015-05-04
Competative Negotiated | If "yes" to 2d |  | Finalise questions and answers log | 5 days | 5 | 2015-05-04 | 2015-05-09
Competative Negotiated | If "yes" to 2d |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-05-09 | 2015-05-09
Competative Negotiated | If "yes" to 2d |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-05-09 | 2015-05-14
|  |  | EOI/PQQ Return Date Urgent OJEU (15 days) OJEU or OJEU with PIN (30 days) |  |  | 2015-05-14 | 2015-05-14
Competative Negotiated | If "yes" to 2d |  | Evaluation and clairfcation of PQQ/EOI (and financial vetting) | 28 days | 28 | 2015-05-14 | 2015-06-11
Competative Negotiated | If "yes" to 2d |  | Agree potential bidder list | 6 days | 6 | 2015-06-11 | 2015-06-17
Competative Negotiated | If "yes" to 2d |  | Stakeholder to complete specification / requirements (and submit to procurement when complete) | 14 days | 14 | 2015-06-17 | 2015-07-01
Competative Negotiated | If "yes" to 2d |  | Prepared and complete "initial" tender documents and scorecard | 14 days | 14 | 2015-07-01 | 2015-07-15
Competative Negotiated | If "yes" to 2d |  | Upload project to Due North |  |  | 2015-07-15 | 2015-07-15
Competative Negotiated | If "yes" to 2d |  | Pulish "Initial" tender docuements to bidders |  |  | 2015-07-15 | 2015-07-15
Competative Negotiated | If "yes" to 2d |  | (Number of days: Pre-questions deadline) | 2 or 15 days |  | 2015-07-15 | 2015-07-15
Competative Negotiated | If "yes" to 2d |  | Finalise questions and answers log | 3 or 5 days |  | 2015-07-15 | 2015-07-15
Competative Negotiated | If "yes" to 2d |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-07-15 | 2015-07-15
Competative Negotiated | If "yes" to 2d |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-07-15 | 2015-07-20
Competative Negotiated | If "yes" to 2d |  | "Initial" Tender Return Date |  |  | 2015-07-20 | 2015-07-20
Competative Negotiated | If "yes" to 2d |  | Evaluation and clarifcaiton of "Initial" tenders | 14 days | 14 | 2015-07-20 | 2015-08-03
|  |  | Negotiations | 28 days | 28 | 2015-08-03 | 2015-08-31
Competative Negotiated | If "yes" to 2c |  | Conclude negotiations |  |  | 2015-08-31 | 2015-08-31
Competative Negotiated | If "yes" to 2c |  | (Notify bidders of eliminated solutions if applicable) |  |  | 2015-08-31 | 2015-08-31
Competative Negotiated | If "yes" to 2d |  | Prepare "revised" tender documents | 7 days | 7 | 2015-08-31 | 2015-09-07
Competative Negotiated | If "yes" to 2d |  | Publish "revised" tender documents |  |  | 2015-09-07 | 2015-09-07
Competative Negotiated | If "yes" to 2d |  | (Number of days: Pre-questions deadline) | 2 or 15 days |  | 2015-09-07 | 2015-09-07
Competative Negotiated | If "yes" to 2d |  | Finalise questions and answers log | 3 or 5 days |  | 2015-09-07 | 2015-09-07
Competative Negotiated | If "yes" to 2d |  | Answers deadline (minimum 6 days before tender return date) |  |  | 2015-09-07 | 2015-09-07
Competative Negotiated | If "yes" to 2d |  | (Number of days: Post answers log publication) | 5 days | 5 | 2015-09-07 | 2015-09-12
Competative Negotiated | If "yes" to 2d |  | Issue initial tender documents to selected bidders & notify unsuccessful bidders | 28 days | 28 | 2015-09-12 | 2015-10-10
Competative Negotiated | If "yes" to 2d |  | "Revised" Tender return date |  |  | 2015-10-10 | 2015-10-10
Competive Dialogue | If "yes" to 2c |  | Evaluation and clarifcations of "revised" tenders | 28 days | 28 | 2015-10-10 | 2015-11-07
Competive Dialogue | If "yes" to 2c | and "yes" to 4f | Further clarification | 7 days | 7 | 2015-11-07 | 2015-11-14
Competive Dialogue | If "yes" to 2c |  | Agree preferred bidder(s) | 6 days | 6 | 2015-11-14 | 2015-11-20
Competive Dialogue | If "yes" to 2c | and "yes" to 4g | Negotiate terms & conditions with preferred bidder(s) | 28 days | 28 | 2015-11-20 | 2015-12-18
Competive Dialogue | If "yes" to 2c |  | Complete report to award contract | 7 days | 7 | 2015-12-18 | 2015-12-25
All processes | If "yes" to 3a |  | Submit to Director for circulation | 21 days (before report to cabinet) | 21 | 2015-11-15 | 2015-12-06
All processes | If "yes" to 3a |  | Submit report to Cabinet | 19 days (before cabinet) | 19 | 2015-12-06 | 2015-12-25
All processes | If "yes" to 3a |  | Cabinet Date | Obtain cabinet date from website |  | 2015-12-25
All processes | If "yes" to 3a |  | Member call in Period | 7 days | 7 | 2015-12-25 | 2016-01-01
All processes | If "yes" to 3a |  | Notify bidders of decision / Issue award notification notices (Start of standstill period) | 1 day | 1 | 2015-12-25 | 2015-12-26
All processes | If "yes" to 3a |  | Standstill period OJEU Alcatel - 10 day mandatory / Non-OJEU - 10 day non-mandatory (plus day notices dispatched) | 11 days | 11 | 2015-12-25 | 2016-01-05
All processes | If "yes" to 3a |  | Earliest contract award date | 1 day after end standstill period | 1 | 2015-12-25 | 2015-12-26
All processes | If "yes" to 3b |  | Submit to Director for circulation by | 21 days (before report to cabinet menber) | 21 | 2015-12-04 | 2015-12-25
All processes | If "yes" to 3b |  | Submit to Cabinet Member for sign off | User defined | n/a | 2015-12-25
All processes | If "yes" to 3b |  | End of Member call in period | 7 days (after cabco) | 7 | 2015-12-25 | 2016-01-01
All processes | If "yes" to 3b |  | Notify bidders of decision / Issue award notification notices (Start of standstill period) | 1 day after call in or decision | 1 | 2015-12-25 | 2015-12-26
All processes | If "yes" to 3b |  | Standstill period OJEU Alcatel - 10 day mandatory / Non-OJEU - 10 day non-mandatory (plus day notices dispatched) | 11 days | 11 | 2015-12-25 | 2016-01-05
All processes | If "yes" to 3b |  | Earliest contract award date | 1 day after end standstill period | 1 | 2015-12-25 | 2015-12-26
All processes | If "yes" to 3c |  | Submit to Director by | 7 days | 7 | 2015-12-18 | 2015-12-25
All processes | If "yes" to 3c |  | Submit to Strategic Director for sign off | User defined | n/a | 2015-12-25
All processes | If "yes" to 3c |  | Notify bidders of decision / Issue award notification notices (Start of standstill period) | 1 day after cabinet member sign off | 1 | 2015-12-25 | 2015-12-26
All processes | If "yes" to 3c |  | Standstill period OJEU Alcatel - 10 day mandatory / Non-OJEU - 10 day non-mandatory (plus day notices dispatched) | 11 days | 11 | 2015-12-25 | 2016-01-05
All processes | If "yes" to 3c |  | Earliest Contract Award Date | 1 day after end standstill period | 1 | 2015-12-25 | 2015-12-26
All processes | If "yes" to 3c |  | Earliest contract award date | 1 day after end standstill period | 1 | 2015-12-25 | 2015-12-26
All processes | All projects |  | Implementation Period | As appropriate to contract | 366 | 2015-12-25 | 2016-12-25
All processes | All projects |  | Contract start date | As appropriate to contract | n/a | user defined
Formulas:
Start Date = [End Date]-[Preparation]
Start Date = [Start Date, row above]
End Date = [Start Date, row below]
End Date = [Start Date]+[Preparation]

## OJEU DSPCR Restricted
Contract Title: Supply of Apache AH-64E Toolkits
Contract Number: 700432376
Process Stage
Out to Market
Evaluation
Award
Implementation
| Action |  |  |  |  | Complete Date
Pre Qualification Stage | Publish PQQ | Publish Supply of Apache AH-64E Toolkits OJEU Tender Advert |  |  |  | 2020-04-08
Publish OJEU Notice
Publish Contract Finder Notice
|  | PQQ Questions Deadline | 5 | days before log issued | 2020-04-25
|  | PQQ Answers log Deadline | 7 | days before PQQ return | 2020-04-30
| PQQ Return Date - 12:00:00 Noon |  |  |  |  | 2020-05-07
Evaluation | PQQ Evaluation |  |  |  |  | 2020-05-21
Financial Checks
Deselect Bidders | Deselect Bidders |  |  |  |  | 2020-05-22
Invitation to Tender | Publish Invitation To Tender | ITT Questions Deadline | 5 | days before log issued | 2020-06-17 | 2020-05-25
|  | ITT Answers log Deadline | 7 | days before ITT return | 2020-06-22
| Tender Return Date - 12:00:00 Noon |  |  |  |  | 2020-06-29
Evaluation | Tender Evaluation |  |  |  |  | 2020-06-30
Selects Preferred Bidder and Prepare Award Report | Selects Preferred Bidder |  |  |  |  | 2020-07-22
| Prepare Report to Award Contract |  |  |  |  | 2020-07-23
Approval to Award | Approval to Award Contract |  |  |  |  | 2020-07-27
Notify bidders of award decision (Alcatel or Voluntary Standstill) | Notify bidders of award decision (Alcatel Standstill) | Start Standstill |  |  |  | 2020-07-27
|  | End Standstill |  |  |  | 2020-08-05
Notify bidders of Final Award Decision | Notify bidders of Final Award Decision |  |  |  |  | 2020-08-12
Publish Award Notice | Publish OJEU Award Notices |  |  |  |  | 2020-08-12
Publish Contract Finder Award Notice | Publish Contract Finder Award Notice |  |  |  |  | 2020-08-12
Contract Start Date | Contract Start Date |  |  |  |  | 2020-08-13