Invitation to Tender

Bidder Instructions and Specification For

The Provision of an Interim Evaluation and

Summative Assessment of the

ERDF Cheshire & Warrington Health Matters

On behalf of

Innovation Agency 
(Academic Health Science Network for the North-West Coast)

(AS COMMISSIONER)

Issue date:  3rd May 2019

Closing Date: 12pm on 24th May 2019

The purpose of this Invitation to Tender (ITT) is to provide Bidders with sufficient information to enable them to compile a Bid that meets the requirements for the Provision of a final evaluation leading to the Summative Assessment of the (European Union Development Fund) ERDF funded Cheshire & Warrington Health Matters project.

Procurement Process and Timescales

The below table provides a summary of the main procurement activities and the current timetable.  Bidders should note that whilst the Contracting Authority does not intend to depart from the timetable provided, it reserves the right to do so at any time.

Timeline for Submission

| ITT issued | 3rd May 2019 |
| --- | --- |
| Submission of Bidder clarification questions by | Noon on 15th May 2019 |
| Responses to clarification questions circulated by | 20th May 2019 |
| Submission of Bids by | Noon on 24th May 2019 |
| Evaluation of bids | 29th May 2019 |
| All Bidders informed of outcome | 31st May 2019 |
| Indicative contract signing date | 7th June 2019 |
| Service Commencement Date | 10th June 2019 |

Responses must be submitted by 5pm on Friday 24th of May 2019.  Late bids may not be accepted and it is entirely the responsibility of Bidders to ensure that bids are received on time in the format requested.

In order to ensure equality of treatment of Bidders, anonymised details of all Bidder Clarification Questions and the Contracting Authority’s clarification responses will be published to all Bidders on a regular basis via the messaging facility through the EU-Supply Portal. All Bidder Clarification Questions must be made solely via the Messaging facility through the EU-Supply Portal.  No other route to submit Clarification Questions is to be used and will not be responded to. Bidders are advised to ensure that such clarifications are made well in advance of the deadline for clarifications to ensure a response. The Contracting Authority will not be bound to respond to Bidder Clarification Questions after this deadline, but does reserve the right to do so.

In order to ensure equality of treatment of Bidders, anonymised details of all Bidder Clarification Questions and the Contracting Authority’s clarification responses will be published to all Bidders on a regular basis via the messaging facility through the EU-Supply Portal.

The Cheshire & Warrington Health Matters Programme

In 2015 the Innovation Agency match funded a pilot project with Cheshire & Warrington LEP which established a series of business breakfasts for approximately 70 companies working in the health and life science sector. A survey of 218 companies was also commissioned to understand more about the potential of businesses within the region to increase their participation within the heath sector supply chain. The sector is underserved in Cheshire & Warrington but, with the investment in the Cheshire Integrated Health Services innovation centre and the transformation of Alderley Park as a hub for SMEs since the departure of Astra Zeneca, alongside the growing needs of the healthcare sector for new and innovative technologies, there is significant scope for growth. The project proposed builds on this pilot and the results of the survey. The survey demonstrated that the sector is continuously evolving and transforming thus making it very challenging for SMEs to maintain good intelligence systems on how to respond to these changes and target their innovative solutions to the market need.

“e-health” is set to become a significant part of medical delivery in the future and tele-health is already having a significant impact on the shift from hospital-based care to a focus on patient centric diagnosis, treatment and monitoring. Development of new technologies in this area by SMEs supported to do so in Cheshire and Warrington, will increase the scale and pace of the shift from hospital-based care to community based care.

The Cheshire & Warrington Health Matters project aims to support these SMEs to co-create and bring innovative products and services to the market. This will, in turn, drive business growth and improve the region’s wider economic performance.

The project’s activities started on the 21st November 2016 and will run for three years. The practical completion date will be six months after the end of activity date.

Project Delivery Partners and Governance Structures

The members of the Innovation Agency and HinM include 33 clinical commissioners, 41 NHS Trusts and 13 Universities.  Together we can support SMEs to access a wide range of clinical experts, service users, buyers and payors across the health service as well as key partners such as regional health hubs and university initiatives such as Sensor City. The Virtual Engineering Centre, Innovate Dementia (a living lab) ,  Molecular Pathology Innovation Centre (MMPathIC) & Precision Medicines Catapult (along with the Discovery Medicines Catapult at Alderley Park),  The Graphene Engineering Innovation Centre and the Connected Health Cities Hub.

Whilst the geographies of the partners overlap in, and extend beyond, the Cheshire and Warrington region, the project will map to the LEP geography. This also reflects the geography of both the strategic academic partner University of Chester and a key service partner Cheshire and Wirral Partnership Trust both operating across the major transformational programmes that will inform SMEs of the sector procurement priorities. The partners will each recruit business support managers and both have access to an extensive network clinical specialist groups, commissioners and procurement teams.  Both partners are committed to diverting existing staff (including clinical experts, digital and interoperability experts, procurement experts and public involvement managers), to support the project when specific SMEs would benefit from such specialist expertise.

The Innovation Agency will support business located within Warrington, Chester and Cheshire West and GM AHSN will support business in East Cheshire but will benefit from a coordinated and joint management structure. The academic strategic partner will work with both AHSNs SME advisers to support the research and innovation of these new products and services in settings.

Each of the delivery partner has a particular role in the delivery of the project and specific targets / KPIs that are used for internal project management purposes. The programme’s success needs to be assessed at programme level in order to understand the effectiveness of the holistic / collaborative approach to supporting individual SMEs and the collaborative working of the delivery partners at all levels of the project.

The project’s operation is overseen by two structures:

A Strategic Steering Group:

•	The Steering Group manages the programme at a strategic level incorporating finance, communications, programme-wide issues and the management of outputs and outcomes. The Steering group is the decision-making body and is led by the Contracting Authority with a representative from each delivery partner.

An Operational Group:

•	The Operational group is again made up from representatives from each delivery partner and manages the support across the partnership to SMEs. The group is responsible for operational issues and if needed, will take issues to the Steering group for decisions.

Project Activities

The  Cheshire & Warrington Health Matters programme provides specialised business support to make it easier for Cheshire and Warrington technology, creative, digital and life science SMEs to access the health and social care market. It also seeks to generate additional finance (for SMEs and Commissioners/Procurers) to accelerate scaling up market growth and implementation of health and social care innovation.

Requirements

The Cheshire & Warrington Health Matters programme is part funded through Priority Axis 3 (investment of the European Regional Development Fund (ERDF). An ERDF grant of £580k has been approved and the total project value (including match funding) is £1.1 million.

As the project is funded via ERDF, the Contracting Authority (as the accountable body for the ERDF funding) is required to produce a Summative Assessment Report at the end of the project. This report must be fully compliant with the Summative Assessment requirements published by the Ministry of Housing, Communities and Local Government (MHCLG).  The guidance can be accessed here.  The full Summative Assessment will need to be signed off and submitted to MHCLG as part of the project closure procedure.

The Contracting Authority is looking for proposals from suitably qualified Suppliers to conduct an interim evaluation and develop this ERDF Summative Assessment which will comply fully with MHCLG’s requirements.

By the nature of the project, the Delivery Partners and supported SMEs are based in the Lancashire region.  Suppliers may utilise telephone or online meetings where suitable, but if arranged, face-to-face meetings and interviews should be conducted in Cheshire or Warrington, and that the Supplier will need to travel to these meetings.

The Supplier must assign any copyright in the overall Interim Evaluation Report and the Summative Assessment to the Contracting Authority.

The Supplier must seek the Contracting Authority’s permission to publish or reproduce any of the deliverables, materials or outputs developed as part of this work, other than is necessary to carry out the Supplier’s obligations under this contract.

We envisage that the research and analysis to inform the Summative Assessment will be undertaken in one phase, outlined below.

Instructions to Bidders

Introduction

These instructions are designed to ensure that all Bidders are given equal and fair consideration.  Therefore, it is important that Bidders provide all of the information asked for and in the format and order specified.

Failure to provide all information required or comply with the terms of the ITT may lead to the rejection of a Bid by the Contracting Authority.  All material issued in connection with this ITT shall remain the property of the Contracting Authority.

The information contained in this document is presented in good faith but does not purport to be comprehensive or to have been independently verified.

The Contracting Authority reserves the right to cancel or withdraw from the Procurement process at any stage and not to award a contract.

Bidders (or any of their subcontractors, agents or advisors) must neither disclose to, nor discuss with any other potential Bidders (whether directly or indirectly), any aspect of any response to any of the Contracting Authority’s procurement documents.

Neither the Bidder, nor any of their agents, advisors or intended subcontractors shall make contact with any employee or agent of the Contracting Authority or the CHESHIRE & WARRINGTON HEALTH MATTERS Delivery Partners who are in any way connected with this Procurement during the period of the Procurement, unless instructed otherwise.

All documentation and communication shall be in English and prices shall be in GB pounds Sterling.

Bidders must obtain for themselves, at their own responsibility and expense, all information necessary for the preparation of Bids.  All Bidders, sub-contractors, and any of their respective agents or advisers shall be responsible for all costs incurred by them in connection with all stages of this procurement.

Under no circumstances will the Contracting Authority be liable for any costs or expenses incurred by a Bidder, its sub-contractors, and/or any of their respective agents or advisors arising directly or indirectly from the procurement process or termination thereof, including, without limitation, any changes or adjustments made to the procurement process or documentation, or disqualification of a Bidder.

The Contracting Authority reserves the right to seek clarification from Bidders where there appear to be errors or omissions in the information submitted.  If, in the opinion of the Contracting Authority, the Bidder fails to provide an adequate response to one or more points of clarification, or fails to respond in a timely manner, the Bidder may be excluded from progressing further in the Procurement.

In accordance with the obligations and duties placed upon public authorities by the Freedom of Information Act 2000 (the ‘FoIA’), Bidders should be aware that a request for disclosure of information relating to this procurement may be made by members of the public pursuant to the FoIA.

Bidders are therefore asked to clearly identify any information within their submission that they consider to be commercially sensitive.  If a FoIA request is received involving this, Bidders will be asked to explain the potential implications of disclosure and justify why it should remain confidential.

The Contracting Authority shall review the Bidder’s justification alongside the information submitted in commercial confidence to apply the Public Interest test as in section (2) 43 Commercial Interest and other FoIA non-absolute exemption clauses.

Bidders shall not undertake (or permit to be undertaken) at any time, whether at this stage or after execution of Contracts, any publicity activity with any section of the media in relation to the Procurement other than with the prior written agreement of the Contracting Authority.

Summative Assessment Research and Analysis

This will provide the evidence and analysis to inform the preparation of the Summative Assessment report.  The Summative Assessment report will need to be submitted to MHCLG, in the required format.

It is expected that the Summative Assessment will be produced and signed off in three stages: an Phase 1 report, an interim report and a Final Report. The Phase 1 Report will ideally be produced to coincide with the end of business support activities on the current Health Matters project, and should be a complete stand-alone report. The interim report subject to the receipt of additional grant funding will be produced in the middle of the extended programme and should reflect on whether any lessons from the initial report have been learned. The Final Report is subject to the receipt of additional grant funding, to include any other outputs provided the programme is granted an extension and would be due by 31st of October 2022. The Bidder accepts that in the event that the project is not extended, the Phase 1 report in this scenario will become the final and only report.

In anticipation of any summative assessment guideline changes, the project reserves the right to review these changes and the impact these will have on the assessment and the procurement. It would therefore be prudent for the bidder to include a contingency budget in the event that any changes significantly alter delivery of the summative assessment.

Time is of the essence in delivering the Full Summative Assessment within the agreed timescales to ensure that the Contracting Authority meets the terms of its project and secures the agreed ERDF funding.

The Contracting Authority require the Supplier to review and update the report to include any learnings for future programmes, so that the Initial Report is completed and signed-off by 26th of July 2019.

The overall purpose of the Summative Assessment is to provide a comprehensive analysis of the performance and impact of the Cheshire & Warrington Health Matters project. The final report should provide detailed insights into how the project has performed, reliable evidence about the efficiency and effectiveness of all work packages and an assessment of the value for money that the Health Matters project has created.  It should also identify which of the project’s delivery activities have worked well (or less well) and the factors that explain this.

The specific objectives for the Summative Assessment are outlined in the table below.

Table 5: Summative Assessment Objectives and Research Questions

| 1: Critically Assess Project Rationale and Context | The final Summative Assessment report should provide a full critical analysis of the project logic model including the appropriateness of the project’s design, given its objectives and the rationale for investment. The evaluators should build upon the analysis prepared during the interim evaluation phase to provide: Analysis of whether and how the project’s context has changed during implementation, identifying any for the project’s delivery and performance and the likely realisation of outcomes and impacts. Clear and evidenced conclusions about whether the Cheshire & Warrington Health Matters project can reasonably be expected to perform well against its targets, bearing in mind any weaknesses in the original project design and any changes in context since the project began. |
| --- | --- |
| 2: Assessment of Performance Against Contractual and Internal Targets | The final Summative Assessment report should clearly outline whether the Cheshire & Warrington Health Matters project has delivered what it set out to in terms of spend and outputs. This should focus on the core ERDF indicators but also include internal project KPIs and relevant output measures. The assessment should: Project the likely final outturn in terms of all contractual ERDF targets, taking account of changes to the project budget and deliverables. Consider the contribution of each individual work package and delivery partner to the final achievements of the project. This analysis should take account of the performance of each delivery partner against internal KPIs as well as their contribution towards overall project targets. Identify the factors which explain any over or under performance against expectations, for individual delivery partners as well as the project as a whole. |
| 3: Review Project Delivery and Management | In addition to identifying what the Cheshire & Warrington Health Matters has achieved, the Summative Assessment should also explore how effectively the project was delivered. The analysis here should explore all aspects of project governance, management and delivery and consider the following in particular: Was the project well managed and were the right governance and management structures in place to manage the delivery partnership? Which factors influenced how effectively the governance and management structures worked in practice? Did all of the work packages perform as they were expected to and what was the impact of this on the project’s overall delivery performance? Have all of the project’s activities been delivered to an acceptable standard and was this standard consistent across the work packages? Was the case management / collaborative working approach successful in practice? Could this has been improved in any way? Could the quality of any aspect of project delivery be improved in any way? Were the right procedures and approaches in place to ensure the project engaged with the right beneficiaries and stakeholders? Did the project identify, engage with and provide assistance to the right number and type of beneficiaries to achieve its objectives? How is the project and its activities perceived by stakeholders and beneficiaries? What are their perceptions about the quality of activities and delivery? |
| 4: Identify Project Outcomes and Impacts | The Summative Assessment needs to draw clear and well evidenced conclusions about whether or not the project has made a difference to the challenges / problems it set out to address and how it has contributed to the results being sought by Priority Axis 1b of the ERDF programme. The assessment should identify and where possible quantify the attributable outcomes and impacts of the Cheshire & Warrington Health Matters project for all direct and indirect beneficiaries. The specific research questions here include: What are the main mechanisms by which project activities create outcomes and impacts for direct and indirect beneficiaries? What progress has the project made towards achieving the outcomes and impacts (for all beneficiary groups) set out in the impact indicator framework? What further progress can be expected in the future? To what extent are the changes in these outcome and impact measures attributable to the project’s activities? What are the gross and net additional economic, social and environmental benefits which have arisen as a result of the project? Who are the main beneficiaries / recipients of these impacts? And to what extent do these benefits contribute to achieving ERDF result indicators? What contribution have individual work packages made to the achievement of these outcomes and impacts? What will the lasting / legacy effects of the project be? How do the impacts of each work package combine to create the overall project impact? What are the main sources of Strategic Added Value that the project has created? |
| Value for Money | Drawing on the impact analysis, the Summative Assessment should provide an analysis of value for money. This should encompass all relevant impact measures which have been quantitatively assessed by the evaluation. As a minimum, this should include the outcomes and impact types which are most relevant to the ERDF programme. Depending on the impact assessment approach agreed during the interim evaluation, this might also include consideration of benefits for wider groups including (i) patients (ii) city region residents. The Assessment should seek to identify other projects with similar aims and objectives against which to benchmark the performance of the Cheshire & Warrington Health Matters project, accepting that there will inevitably be difficulties in directly comparing between projects. |

The Summative Assessment report must follow the standard format, prescribed by MHCLG in the Summative Assessment guidance. The concluding section of the report should provide a well-evidenced set of conclusions and lessons for the future. These lessons should be specifically tailored for the various audiences for the Summative Assessment. That is, separate lessons should be provided for:

Partners involved in the delivery of the project

Those designing or implementing interventions with similar objectives in the future

Policy makers, including MHCLG

Bidders should carefully consider the requirements set out above and propose a suitable methodology to deliver the insight required. We encourage Bidders carefully review the Summative Assessment guidance, taking particular note of the requirement to consider the feasibility and desirability of counterfactual impact evaluation methods as part of this piece of work.

Please note, the maximum budget for the Summative Assessment is £15,000 including VAT and all expenses.  Any bids over this amount may be disqualified.

The Supplier is being commissioned to provide the specified services and deliverables on a Fixed Fee basis by certain deadlines.  As such, Bidders are responsible for working within the overall Bid Price and project timescales, and managing any risks that may cause these to overrun.

For the avoidance of doubt, the Contracting Authority shall not be liable for any additional costs or expenses beyond those included in the Bid Price.

Note that bids will be evaluated using a Value For Money (VFM) calculation involving both the total Bid Price and the corresponding quality score total from Section C.  See below for further explanation.

Value of the contract: £15,000

Contract start date: June 2019 	Contract end date: July 2019/October 2022

Closing date for applications: 12pm 24th May 2019

Scoring of each question shall be on the basis of the following table and each of the first 7 (qualitative) questions shall be equally weighted with a score of 10% each.

| Confidence Score | Percentage awarded | Commentary |
| --- | --- | --- |
| Excellent Confidence | 100 | The bidder has addressed the question in its entirety. Their response has been tailored specifically to the question, and includes significant additional information. |
| Very Good Confidence | 80 | The bidder has addressed the question in its entirety. Their response has been tailored specifically to the question, and includes some additional information. |
| Good Confidence | 60 | The bidder has provided a response which demonstrates that they meet the criteria and have suitably addressed the question. |
| Minor Concerns | 40 | The bidder has provided a response covering most aspects of the question, however minor gaps in the response are evident. |
| Concerns | 20 | The bidder has provided a response covering some aspects of the question, but fails to demonstrate they meet the criteria. |
| Major Concerns | 0 | The bidder has failed to respond or provided a response covering minimal aspects of the question. |

The last two (financial) questions shall be scored 25% for question 8 and 5% for question 9.

Question 8 will be scored by weighted differential with the terms offered being used to arrive at an assumed weekly cost based on 5 days work including add-ons related to travel and accommodation.  The lowest value offer will score full 25% with higher value offers being scored a lower % based on the % higher their proposal is (i.e. a bid that is 10% higher will score only 15%, whereas one that is 25% higher will score 0%).

Question 9 will be scored based on 5% awarded for the strength of discounts and VBL proposals.

If you have any queries please contact:

Mike Kenny

Associate Commercial Director

Innovation Agency

Mike.kenny@innovationagencynwc.nhs.uk

07825331521

| Application Form |  |
| --- | --- |
| Applicant name and title |  |
| Organisation |  |
| E-mail |  |
| Phone |  |
| Project name |  |

- Please explain how you will meet the specifications for the Summative Assessment (1000 words maximum)

- Provide a brief summary of your work with other organisations, highlighting key exemplars (400 words maximum). Case studies may be attached as Appendices.

- How do you ensure that staff and associates (sub-contractors) hold the appropriate qualifications and experience, and remain competent and up to date? (400 words maximum)

- How do you ensure the quality of service delivered by staff or associates? (400 words maximum)

5. What are the arrangements for back‐up staff to be available if necessary in case of staff absence? (400 words maximum.)

6. If available, please provide CVs for the staff engaged in the delivery of services (Please add as appendix to the application form.)

7. From your understanding of the CHESHIRE & WARRINGTON HEALTH MATTERS project, what do you consider to be your potential “added value” to its purpose? (400 words maximum.)

- What are the costs of this Consulting work? Cost per day (including VAT) Additional Travel costs Costs for additional resources

9. Do you provide discounts for follow up works, early settlement or volume spend? (400 words maximum).