Request for Quotation

Digital aerial low tide survey and validation study of digital aerial survey methods at Morecambe Bay and Duddon Estuary Special Protection Area (SPA) in winter 2023/24

Issued 25th September 2023

# Request for Quotation

### Ref: PBDM_WP4_Task4.1_MB&DE_SPA_aerial_RFQ

Title: Digital aerial low tide survey and validation study of digital aerial survey methods at Morecambe Bay and Duddon Estuary Special Protection Area (SPA) in winter 2023/24

You are invited to submit a quotation for the requirement described in the specification, Section 2.

Please confirm by email, receipt of these documents and whether you intend to submit a quote or not.

Your response and quotation should be returned to the following email address:

Email: sarah.anthony@naturalengland.org.uk

by:

Date: 13th October 2023

Time: 17:00 BST

Ensure you include the name of the quotation and ‘Final Submission’ in the subject field to make it clear that it is your response.

### Contact Details and Timetable

Sarah Anthony will be your contact for any questions linked to the content of the quote or the process. Please submit any clarification questions via email and note that, unless commercially sensitive, both the question and the response will be circulated to all tenderers.

| Action | Date |
| --- | --- |
| Date of issue of RFQ | 25th September 2023 at 12:00 BST |
| Deadline for clarifications questions | 6th October 2023 at 17:00 BST |
| Deadline for receipt of Quotation | 13th October 2023 at 17:00 BST |
| Intended date of Contract Award | 30th October 2023 |
| Intended Contract Start Date | 30th October 2023 |
| Intended Delivery Date / Contract Duration | 31st March 2024/ 22 weeks (~6 months) |

## Section 1: General Information

### Glossary

Unless the context otherwise requires, the following words and expressions used within this Request for Quotation shall have the following meanings (to be interpreted in the singular or plural as the context requires):

| “Authority” | means Natural England who is the Contracting Authority. |
| --- | --- |
| “Contract” | means the contract to be entered into by the Authority and the successful supplier. |
| “Response” | means the information submitted by a supplier in response to the RFQ. |
| “RFQ” | means this Request for Quotation and all related documents published by the Authority and made available to suppliers. |

### Conditions applying to the RFQ

You should examine your Response and related documents ensuring it is complete and in accordance with the stated instructions prior to submission.

Your Response must contain sufficient information to enable the Authority to evaluate it fairly and effectively. You should ensure that you have prepared your Response fully and accurately and that prices quoted are arithmetically correct for the units stated.

By submitting a Response, you, the supplier, are deemed to accept the terms and conditions provided in the RFQ. Confirmation of this is required in Annex 2.

Failure to comply with the instructions set out in the RFQ may result in the supplier’s exclusion from this quotation process.

### Acceptance of Quotations

By issuing this RFQ the Authority does not bind itself to accept any quotation and reserves the right not to award a contract to any supplier who submits a quotation.

### Costs

The Authority will not reimburse you for any costs and expenses which you incur preparing and submitting your quotation, even if the Authority amends or terminates the procurement process.

### Self-Declaration and Mandatory Requirements

The RFQ includes a self-declaration response (Annex 1) which covers basic information about the supplier, as well as any grounds for exclusion. If you do not comply with them, your quotation will not be evaluated.

Any mandatory requirements will be set out in Section 2, Specification of Requirements and, if you do not comply with them, your quotation will not be evaluated.

### Clarifications

Any request for clarification regarding the RFQ and supporting documentation must be submitted via email no later than the deadline for clarifications set out in the Timetable. The Authority shall be under no obligation to respond to queries raised after the clarification deadline.

The Authority will respond to all reasonable clarifications as soon as possible but cannot guarantee a minimum response time. The Authority will publish all clarifications and its responses to all suppliers via email unless deemed commercially sensitive.

If a supplier believes that a request for clarification is commercially sensitive, it should clearly state this when submitting the clarification request. However, if the Authority considers either that:

- the clarification and response are not commercially sensitive; and

- all suppliers may benefit from its disclosure,

then the Authority will notify the supplier (via email), and the supplier will have an opportunity to withdraw the request for clarification by sending a further message requesting the withdrawal of the clarification request. If not withdrawn by the supplier within 2 working days of the Authority’s notification, the Authority may publish the clarification request and its response to all suppliers and the Authority shall not be liable to the supplier for any consequences of such publication.

The Authority reserves the right to seek clarification of any aspect of a quotation and/or provide additional information during the evaluation phase to carry out a fair evaluation. Where the Authority seeks clarification on any aspect of the quotation, the supplier must respond within the timeframe requested by the Authority.

### Amendments

The Authority may amend the RFQ at any time prior to the deadline for receipt. If it amends the RFQ the Authority will notify you via email.

Suppliers may modify their quotation prior to the deadline for Responses. No Responses may be modified after the deadline for Responses.

Suppliers may withdraw their quotations at any time by submitting a notice via the email to the named contact.

### Conditions of Contract

The Authority’s Standard Condensed Terms and Conditions (available at Procurement at Natural England - Natural England - GOV.UK (www.gov.uk)https://www.gov.uk/government/organisations/natural-england/about/procurement) provided as part of the RFQ will be included in any contract awarded as a result of this quotation process. The Authority will not accept any changes to these terms and conditions proposed by a supplier.

Suppliers should note that the quotation provided by the successful bidder will form part of the Contract.

### Prices

Prices must be submitted in £ sterling, exclusive of VAT.

### Disclosure

All Central Government Departments, their Executive Agencies and Non-Departmental Public Bodies are subject to control and reporting within Government. In particular, they report to the Cabinet Office and HM Treasury for all expenditure. Further the Cabinet Office has a cross-Government role delivering overall Government policy on public procurement, including ensuring value for money and related aspects of good procurement practice. For these purposes, the Authority may disclose within Government any details contained in your quotation. The information will not be disclosed outside Government during the procurement.

In addition, the Authority is subject to the Freedom of Information Act 2000 and the Environmental Information Regulations 2004, which provide a public right of access to information held by public bodies. In accordance with these two statutes, the Authority may be required to disclose information contained in your quotation to any person who submits a request for information pursuant to those statutes.

Further to the Government’s transparency agenda, all UK Government organisations must advertise on Contract Finder in accordance with the following publication thresholds:

- Central Contracting Authority’s: £12,000

- Sub Central Contracting Authority’s and NHS Trusts: £30,000

For the purpose of this RFQ the Authority is classified as a Central Contracting Authority with a publication threshold of £12,000 inclusive of VAT.

If this opportunity is advertised via Contracts Finder, we are obliged to publish details of the awarded contract including who has won the contract, the contract value, and indicate whether the winning supplier is a small and medium-sized enterprise (“SMEs”) or voluntary organisation or charity. A copy of the contract must also be published with confidential information redacted.

By submitting a Response, you consent to these terms as part of the procurement.

### Disclaimers

Whilst the information in this RFQ and any supporting information referred to herein or provided to you by the Authority have been prepared in good faith the Authority does not warrant that this information is comprehensive or that it has been independently verified.

The Authority does not:

- make any representation or warranty (express or implied) as to the accuracy, reasonableness or completeness of the RFQ;

- accept any liability for the information contained in the RFQ or for the fairness, accuracy or completeness of that information; or

- accept any liability for any loss or damage (other than in respect of fraudulent misrepresentation or any other liability which cannot lawfully be excluded) arising as a result of reliance on such information or any subsequent communication.

Any supplier considering entering into contractual relationships with the Authority following receipt of the RFQ should make its own investigations and independent assessment of the Authority and its requirements for the goods and/or services and should seek its own professional financial and legal advice.

### Protection of Personal Data

In order to comply with the General Data Protection Regulations 2018 the supplier must agree to the following:

You must only process any personal data in strict accordance with instructions from the Authority.

- You must ensure that all the personal data that we disclose to you or you collect on our behalf under this agreement are kept confidential.

- You must take reasonable steps to ensure the reliability of employees who have access to personal data.

- Only employees who may be required to assist in meeting the obligations under this agreement may have access to the personal data.

- Any disclosure of personal data must be made in confidence and extend only so far as that which is specifically necessary for the purposes of this agreement.

- You must ensure that there are appropriate security measures in place to safeguard against any unauthorised access or unlawful processing or accidental loss, destruction or damage or disclosure of the personal data.

- On termination of this agreement, for whatever reason, the personal data must be returned to us promptly and safely, together with all copies in your possession or control.

### General Data Protection Regulations 2018

For the purposes of the Regulations the Authority is the data processor.

The personal information that we have asked you provide on individuals (data subjects) that will be working for you on this contract will be used in compiling the tender list and in assessing your offer. If you are unsuccessful the information will be held and destroyed within two years of the award of contracts. If you are awarded a contract, it will be retained for the duration of the contract and destroyed within seven years of the contract’s expiry.

We may monitor the performance of the individuals during the execution of the contract, and the results of our monitoring, together with the information that you have provided, will be used in determining what work is allocated under the contract, and in any renewal of the contract or in the award of future contracts of a similar nature. The information will not be disclosed to anyone outside the Authority without the consent of the data subject, unless the Authority is required by law to make such disclosures.

### Equality, Diversity & Inclusion (EDI)

The Client is striving to create a diverse and inclusive working environment where every individual has equality of opportunity to progress and to apply their unique insights to making the UK a great place for living. The Service Provider is expected to respect this commitment in all dealings with Natural England staff and service users.

Suppliers are expected to;

- support Defra group to achieve its Public Sector Equality Duty as defined by the Equality Act 2010, and to support delivery of Defra group’s Equality & Diversity Strategy.

- meet the standards set out in the Government’s Supplier Code of Conduct

- work with Defra group to ensure equality, diversity and inclusion impacts are addressed (positive and negative) in the goods, services and works we procure, barriers are removed and opportunities realised.

### Sustainable Procurement

Addressing global sustainability impacts and realising additional community benefits within commercial activity is core to Defra group’s approach, working with its supply chain is key to achieving sustainable outcomes. In addition to supporting Defra group to meet its outcomes we look to understand and reduce negative sustainability impacts associated with our commercial activity and realise benefits.

The Client encourages its suppliers to share these values, work to address negative impacts and realise opportunities, measure performance and success.

Suppliers are expected to have an understanding of the Sustainable Development Goals, the interconnections between them and the relevance to the Goods, Services and works procured on the Client’s behalf.

### Conflicts of Interest

The concept of a conflict of interest includes but is not limited to any situation where an Involved Person or Relevant Body has directly or indirectly, a financial, economic or other personal interest which might be perceived to compromise their impartiality and independence in the context of the procurement procedure and/or affect the integrity of the contract award.

We expect suppliers to mitigate appropriately against any real or perceived conflict of interest through their work with government. A supplier with a position of influence gained through a contract should not use that position to unfairly disadvantage any other supplier or reduce the potential for future competition.

Where the supplier is aware of any circumstances giving rise to a conflict of interest or has any indication that a conflict of interest exists or may arise you should inform the Authority of this as soon as possible (whether before or after they have submitted a quotation). Tenderers should remain alert to the possibility of conflicts of interest arising at all stages of the procurement and should update the Authority if any new circumstances or information arises, or there are any changes to information already provided to the Authority. Failure to do so, and/or to properly manage any conflicts of interest may result in a quotation being rejected.

Provided that it has been carried out in an open, fair and transparent manner, routine pre-market engagement carried out by the Authority should not represent a conflict of interest for the supplier.

## Section 2: The Invitation

Specification of Requirements

### Background to Natural England

The Authority is Natural England. The Authority’s priorities are to secure a healthy natural environment; a sustainable, low-carbon economy; a thriving farming sector and a sustainable, healthy and secure food supply. Further information about the Authority can be found at: Natural England

### Requirement

Natural England is seeking a contractor to complete five tasks under this contract.

Task 1) To design and conduct one high resolution / definition digital aerial survey of waterbirds (divers, grebes, cormorants, herons, swans, geese, ducks, rails, waders, gulls and terns) and marine mammals within the Morecambe Bay and Duddon Estuary SPA this winter (2023/24) at low tide.

Task 2) To process the imagery collected under task 1) and analyse the data to provide robust population abundance estimates and spatial distribution maps of birds and marine mammals across the SPA.

Task 3) To design and conduct two or more high resolution/definition digital aerial surveys of waterbirds (divers, grebes, cormorants, herons, swans, geese, ducks, rails, waders, gulls and terns) of a specific sub-set of sites / low tide count sectors within the SPA at low tide this winter (2023/24), coordinated with a separately commissioned programme of ground-based counts with the specific aim of enabling a validation of the digital aerial survey method.

Task 4) To process the imagery collected under task 3) and analyse the data to provide, for each survey, robust counts, and spatial distribution maps of birds across each of the specific sub-set of sites / low tide count sectors.

Task 5) To produce a single report, using a Natural England template and following relevant guidance (see: Natural England publishing standards for commissioned reports - NECR000) outlining all methods and results, accompanied by all relevant output files, and other specified deliverables.

More detail on each task follows.

Task 1)

This should be completed using the most up to date digital aerial imagery (video or still) methods. The survey should be scheduled to occur in December 2023/January 2024 to target the peak occurrence at the site of two of the key wader species i.e., knot and dunlin and to correspond, as far as practicable, with the timing of one of the monthly ground-based low-tide surveys of sub-sites of the SPA which will be commissioned by Natural England under a separate contract.

In this RFQ, the Authority is not seeking like for like costs against a prescribed model survey. Rather, the Authority requests potential suppliers to review the available information on the abundance and distribution of the species of particular interest within the Morecambe Bay and Duddon Estuary SPA and, based on power analyses of those data, or of hypothetical species’ distribution patterns, provide the authority with their recommended approach to design of this specific SPA wide survey in the light of the statistical power achieved.

The authority does not have a specific preference for whether a transect based or grid-based methodology should be employed or for a particular % coverage. However, the Authority requires that imagery is collected at under 2cm GSD. This requirement reflects the focus of this survey on gathering information on the abundance and distribution at low tide of the many thousands of small wading birds, and the finding of a study to validate the use of digital aerial images for this purpose in The Wash in 2018 (APEM 2018) which reported that even at 1cm GSD less than 50% of small wading birds could be identified to species-level.

As stated in Section 3. Methods of this specification “Survey designs should aim to balance costs against survey coverage, image resolution and duration of survey”. Bidders should indicate which survey design corresponds to the costings provided so that Natural England can judge the relative degree of power to detect varying magnitudes of population decline of the species of principal interest that is likely to be achieved by the recommended survey design and assess that against the costs/benefits of alternative designs.

Task 2)

The imagery resulting from completion of Task 1) must be processed to provide a comprehensive digital dataset from which robust estimates of the abundance and distribution of birds and marine mammals within the whole of the Morecambe Bay and Duddon Estuary SPA can be derived under this contract. The contractor will be required to apply survey-specific, design-based abundance estimation methods, with appropriate corrections, to derive population estimates for all bird and marine mammal species recorded in the survey. Abundance estimates should be generated for the entire study area. Note that as the boundary of the SPA includes areas above and below the mean low water mark, a survey of the entire SPA conducted over the low tide period will include areas of exposed intertidal sediment and areas that remain covered by the sea. This division of the area surveyed into parts that are exposed or not exposed, and the fact that some species will be restricted totally to exposed areas while others will be restricted totally to the water, while yet other species may be distributed across both, will need to be factored into deriving species’ population abundance estimates across the whole SPA.

Maps should be produced illustrating the relative abundance of key species defined within this RFQ (see Section 3.3) i.e. all non-breeding qualifying species of the SPA plus a few additional main components of the SPA’s waterbird assemblage, and any marine mammal species/groups recorded in the survey images using Kernel Density Estimation methods (KDE) where possible. Where KDE methods cannot be applied due to lack of data, other, simpler methods of mapping relative abundance should be used.

Task 3)

The specific objectives of the validation study are, by means of collecting and subsequently comparing spatially and temporally matched survey data from both ground-based and digital arial surveys, to: (i) assess detection of birds by the aerial surveys, (ii) provide an understanding of the level of species identification achieved by aerial surveys, iii) determine if/how ability to detect and identify individuals to species level by aerial survey differs between species  and iv) determine how reliably detected birds that could not be identified to species (from the air) can nonetheless be assigned to species.

This task should be completed using the most up to date digital aerial imagery (video or still) methods. These surveys should be scheduled to occur in December 2023/January 2024 and must be coordinated with the ground-based surveys of the selected validation sites/low tide count sectors that will be conducted under a separate contract commissioned by Natural England. To ensure this, the contractor will be required to agree and implement a survey coordination protocol with whichever supplier is commissioned by Natural England to undertake the ground-based survey element of the work.

Ideally, this element of the aerial survey work would be delivered as part of the survey work to deliver Task 1). However, logistical constraints and the specific requirements of this task i.e. to conduct two (or more) repeat flights over each of the selected validation sites/low tide count sectors on a falling tide, over low tide and on a rising tide on one day (for more details see section 3.1) may require a separate approach to this task and bidders should indicate their preferred approach to delivery of both Tasks 1) & 3).

For this validation exercise, 100% coverage of the selected validation sites/low tide count sectors is required. The Authority also requires that imagery is collected at under 2cm GSD. These requirements reflect the focus of this survey on gathering information on the abundance and distribution at low tide of the many thousands of small wading birds, and the finding of a study to validate the use of digital aerial images for this purpose in The Wash in 2018 (APEM 2018) which reported that even at 1cm GSD less than 50% of small wading birds could be identified to species-level.

The validation analyses, by comparison of the survey data collected by digital aerial survey under this task, and the contemporary ground-based surveys collected under a separate contract, will be conducted by the British Trust for Ornithology after completion of both survey contracts and provision of all datasets to the BTO.

Task 4)

The imagery resulting from completion of Task 3) must be processed to provide for each repeat survey a comprehensive digital dataset from which robust estimates of the abundance and distribution of birds within selected validation sites/low tide count sectors within the Morecambe Bay and Duddon Estuary SPA can be derived under this contract. The contractor will be required to provide total counts for each bird species/species group on each repeat survey of each of the specific sub-set of sites / LTC scheme sectors used in the validation study.

Maps should be produced illustrating the distribution of individuals of each key species defined within this RFQ (see Section 3.3) i.e. all non-breeding qualifying species of the SPA plus a few additional main components of the SPA’s waterbird assemblage, and any marine mammal species/groups recorded in the survey images).

Task 5)

The contractor should produce a single report, using a Natural England template and following relevant guidance (see: Natural England publishing standards for commissioned reports - NECR000). This report should describe in detail the aerial survey methods and results, and provide a discussion evaluating survey performance, analytical limitations and placing the abundance and distributions of relevant designated features in context with historic surveys and estimates. Relevant databases, analytical code, GIS outputs and associated metadata etc. produced during the project should be provided as deliverables.

The evidence derived from this work will help inform SPA condition assessments, environmental impact assessments, habitats regulations assessments and, by improving understanding of potential overlaps between bird distributions and those of anthropogenic activities, inform place-based decision making by regulatory authorities. The evidence will also help inform future monitoring requirements including the role of volunteers, citizen science and digital aerial survey. The subsequent validation of digital aerial survey results against traditional ground-based surveys will inform consideration by Natural England and BTO of the scope for and any limitations to the wider application of digital aerial survey in monitoring of wader and waterfowl population abundance and distribution across large and/or inaccessible estuarine sites.

The following sections provide further details relating to: 1) the project background, 2) objectives, and 3) methods.

### 1. Background information

#### 1.1 Site details

The Morecambe Bay and Duddon Estuary Special Protection Area was classified in February 2017. The SPA covers 669km2 and extends between Rossall Point in Lancashire and Drigg Dunes in Cumbria (Figure 1). The site includes the former Morecambe Bay SPA and Duddon Estuary SPA and an extension to include the Ravenglass Estuary and intervening coast and the shallow offshore area off the southwest Cumbria coast. Morecambe Bay is the second largest embayment in Britain after The Wash, and has four estuaries – the Wyre, Lune, Kent and Leven. The extended Morecambe Bay & Duddon Estuary SPA also includes the estuary of the River Duddon and the River Esk at Ravenglass. It contains the largest continuous area of intertidal mudflats and sandflats in the UK which supports a variety of infaunal communities including cockle Cerastoderma edule beds. Morecambe Bay supports a wide range of other habitats including large areas of saltmarsh and transitional habitats as well as sand dune systems and coastal lagoons. Within the Bay there are areas of stony reef (known locally as scars or skears) which also support blue mussel Mytilus edulis beds and honeycomb worm Sabellaria alveolata reefs. Extensive eelgrass Zostera spp. beds are present around Foulney Island and in the south Walney Channel, the only examples in the Northwest of England. The Duddon and Ravenglass Estuaries support saltmarsh, intertidal mud and sand communities and sand dune systems with small areas of stony reef. The intermediate coast comprises extensive shingle and sand beaches. The parts of the SPA away from the coast are sandy and shallow, mostly less than 15 metres deep.

The SPA supports internationally important populations of twenty species of non-breeding waterbirds, and a non-breeding waterbird assemblage of more than 200,000 individuals.  The citation sets out all the qualifying interests at the site. Those species of particular interest in this project are the twenty species of non-breeding waterbirds that are qualifying features in their own right plus four species i.e. common eider, common goldeneye, red-breasted merganser and cormorant that are main components of the waterbird assemblage.

Morecambe Bay and Duddon Estuary SPA is a large complex estuarine system that has proved difficult to monitor for its bird life at low tide due to the extensive areas of habitat and treacherous conditions.

Under the British Trust for Ornithology (BTO)/Royal Society for the Protection of Birds (RSPB)/Joint Nature Conservation Committee (JNCC) Wetland Bird Survey (WeBS) Low Tide Counts (LTC) scheme various near-shore parts of the SPA are surveyed periodically. The most recent low tide count data from each of the areas surveyed under this scheme are as follows: Leven Estuary (2005/06), Kent Estuary (2014/15), Lune Estuary (2005/06), Wyre Estuary (2021/22), Morecambe Bay West (an area encompassing intertidal habitat from the Leven Estuary to the South Walney & Piel Channel Flats) (2005/06). These data are available through the online WeBS Report. The remainder of Morecambe Bay (although not all of the current SPA) was surveyed by visual aerial survey on four occasions in the winter of 2005/06 (Banks et al. 2006).

The aim of this work is to fill a significant evidence gap in respect of the lack of current understanding of the distributions of waders and waterfowl across the Morecambe Bay and Duddon Estuary SPA at low tide, and as part of this work to trial and validate the novel use of digital aerial imagery captured from aircraft to generate reliable data on the identity, distribution and abundance of waders and waterfowl at low tide on large estuarine sites.

1.2 Study area

For the whole SPA survey (Task 1) the data gathered must allow the production of population abundance estimates, with associated confidence intervals and distribution maps (relative density maps where data permit), for the key species (see section 3.3) within the entire Morecambe Bay and Duddon Estuary SPA boundary (Figure 1) unless operational restrictions justify excluding certain areas.

The extent of the Morecambe Bay and Duddon Estuary SPA (669km2) is shown on Defra’s MAGIC mapping portal: A shapefile of all the UK SPAs can be downloaded from the JNCC resource hub for use in GIS systems.

Figure 1. Map of the Morecambe Bay and Duddon Estuary SPA.

For the validation aerial survey work (Task 3), the focus is on the Morecambe Bay West and Morecambe Bay Kent WeBS LTC sites (Figures 2 & 3). Specifically, for this task, surveys are required of nine WeBS LTC sectors in Morecambe Bay West (BJ002-007, BJ023, BJ028, BJ029) (Figure 2) and five in Morecambe Bay Kent (DK001-005) (Figure 3). For this task, complete (100%) coverage of these count sectors is required in this project. Please note that these count sectors may be further subdivided for the purposes of the validation analyses prior to surveys.

Figure 2. Map of the Morecambe Bay and Duddon Estuary SPA low tide count sectors which are the focus of the validation study (Task 3) i.e., Morecambe Bay West (BJ002-007, BJ023, BJ028, BJ029).

Figure 3. Map of the Morecambe Bay and Duddon Estuary SPA low tide count sectors which are the focus of the validation study (Task 3) i.e., Morecambe Bay Kent (DK001-005).

### 2. Objectives

Natural England require the contractor to provide all aspects of digital aerial survey (including suitably qualified surveyors, appropriate digital camera equipment, and survey aircraft designed for offshore work over long durations), digital data processing, Quality Assurance and reporting to meet the requirements and objectives of the survey work as detailed in this specification. Natural England also require the contractor to provide all aspects of digital aerial survey data analysis by suitably qualified and experienced data analysts and GIS experts. The contractor should use appropriate software and methods and provide a clear concise report and associated deliverables as detailed in this specification.

There are 10 objectives for this contract. These are to:

- conduct one high precision digital aerial survey of the entire Morecambe Bay and Duddon Estuary SPA in December 2023/January 2024 centred around the time of low tide. Ideally the survey should occur on or as close as possible to the date/time when one of the monthly, standard ground-based low tide counts of the estuarine parts of this coastline (Rivers Kent, Leven, Lune & Wyre and Morecambe Bay West (including South Walney & Piel Channel Flats)) will be conducted under a separate contract let by Natural England. Aerial survey data are to be collected using digital video or still imagery at a resolution suitable for maximising the likelihood that a high percentage of small wader species in flight and on the ground can be identified to species level. Experience suggests this must be finer than 2cm GSD and this is therefore a requirement of this project.

- conduct two or more high precision digital aerial validation surveys of selected areas of the SPA. These surveys must be coordinated with bespoke low tide ground-based surveys of selected validation sites/low tide count sectors within the SPA that will be conducted under a separate contract let by Natural England specifically for the purpose of this validation exercise. These aerial validation surveys should be undertaken within one day at different stages of tide and delivered either through careful planning of the survey to fulfil objective a) (e.g. surveys might be undertaken on the falling tide, at low tide as part of the whole estuary survey, and on the rising tide) or, if necessary, through a separate digital aerial survey/flight. Aerial survey data are to be collected using digital video or still imagery at a resolution suitable for maximising the likelihood that a high percentage of small wader species in flight and on the ground can be identified to species level. Experience suggests this must be finer than 2cm GSD and this is therefore a requirement of this project. 100% coverage of the selected validation sites/low tide count sectors must also be achieved.

- process all imagery gathered in fulfilment of objectives a) and b) to identify all birds, and other objects of interest captured to the lowest taxonomic level possible;

- Quality Assure results so that pre-agreed data standards are met (e.g., to meet MEDIN standards or equivalent for archival in marine data repositories such as the Marine Data Exchange and for acceptance of data by the WeBS LTC scheme);

- provide robust design-based abundance estimates, with associated confidence intervals, standard deviations, and coefficients of variation, for all bird and marine mammal species identified in the SPA wide survey (Task 1) using robust design-based methods, and appropriate adjustments (e.g., for animals not identified to species level and availability bias), for the SPA as a whole;

- provide total counts for each species/species group for each survey of each of the selected validation sites/low tide count sectors surveyed under Task 3.

- provide spatial distribution maps, using a suitable method, for key features of the SPA and additional species of interest for the SPA as a whole and for each selected validation site/low tide count sector;

- compare abundance estimates from the SPA with historic data and qualitatively assess changes in the distribution of key features of the SPA;

- briefly evaluate SPA wide survey design and performance (considering power to detect changes where possible), for key features of the SPA,

- produce a single comprehensive report including survey methods, analytical methods, results, and a discussion of findings. The contractor should also provide: i) ArcGIS layers, associated metadata, accompanying .csv files etc ii) a single Microsoft Excel workbook containing all results of analyses, iii) any analytical code and associated data used in the analyses, and iv) all GIS outputs with associated metadata.

Section 3 provides further detail on the methodology required to deliver these objectives.

### 3. Methods

3.1 Aerial survey design and implementation (Tasks 1 & 3).

The successful Contractor will need to develop an appropriate survey design to meet the project aims and objectives outlined above.  Ideally, the aerial survey work under Task 3 to deliver the data to inform subsequent validation analyses (to be completed outside this project) would be delivered, through careful planning, as part of the survey work to deliver the SPA wide aerial survey (Task 1). However, logistical constraints, and the specific requirements of this task (see below), may require a separate approach to these two tasks and bidders should indicate their preferred approach to delivery of both Tasks 1 & 3. Natural England do not consider that unmanned aerial vehicles (UAVs or drones) have the capability to fulfil the requirements of this project.

The only previous aerial survey of Morecambe Bay was conducted using visual aerial survey methods in the winter of 2005/06 (Banks et al. 2006). The aircraft flew along transects (circa 12 – 15 in total) spaced 2 km apart across the open sea areas of the bay, and observers counted up to 1 km either side from the plane, enabling the whole embayment (but not the whole of the Morecambe Bay & Duddon Estuary SPA) to be covered i.e., 100% coverage. There have been no previous digital aerial surveys of the Morecambe Bay and Duddon Estuary SPA. Bidders should therefore clearly indicate, and provide supporting evidence for their degree of confidence in:

a) Survey detection of the target species (i.e. waders - especially small waders such as knot and dunlin),

b) Subsequent analysis to identify objects to species level for the target species. Information should be provided on potential confusion species and proposed categories of identification if species-level identification of all individuals detected is not possible. These categories should be nested and not overlap, e.g. a general category of ‘brown wader’ might be split into sub-categories of ‘small brown wader’, ‘medium brown wader’ and ‘large brown wader’ but each individual species should only belong to one category at each level in any hierarchy,

c) The suitability of the proposed survey design to provide a data set that can provide robust population estimates and distribution maps for the target species at both the whole SPA scale (Task 1) and within each of the selected validation sites/low tide count sectors (Task 3).

Bidders must also provide information on technical and procedural specifications, to include as a minimum, but not necessarily limited to:

- Camera specification and type.

- Camera performance in different environmental conditions (for example, comparison of bird detections during good versus poor light conditions, between different sea states, against different backgrounds e.g. sea surface vs intertidal sand/mud and in variable cloud levels) and approaches to management of variable image quality with respect to environmental conditions (e.g. sea state, cloud cover, sun altitude and surface glare).

- Choice of survey design (e.g. transect or grid based, continuous or discontinuous image capture).

- Number of transects/survey replicates.

- Transect or grid orientation and spacing and swathe / image width.

- Survey altitude and image resolution (finer than 2cm GSD required).

- Methods for ensuring accurate georeferencing of survey images.

- Time required to complete the surveys.

- Proposed survey timing in relation to daily and monthly tidal cycle.

- Proposed survey area extent in relation to the SPA boundary and validation survey sites/sectors; information on any operational restrictions or other factors that justify excluding coverage of certain areas.

- For the survey of the whole SPA (Task 1), the proposed overall percentage analysed coverage of the survey area (including actual area surveyed and percentage of images to be analysed) and commentary on implications for confidence in final population estimates. Costings may be presented for alternative coverage percentages.

- Analyses that illustrate the statistical power to detect changes in SPA-level population abundance of varying magnitudes of the target species that will be achieved by the proposed/preferred survey design, in comparison to alternative designs.

- Approach to image recognition, confusion species and species attribution, including QA procedures.

- Proposed output format of the raw data (including the fields/attributes that would be included)

A suitable survey method should consider the following points and bidders are required to consider and address each of these points in their submission:

- The surveys should target the peak occurrence of target species and be carried out in December 2023/January 2024.

- Ideally the SPA wide survey (Task 1) should occur on or as close as possible to the day in either December 2023 or January 2024 when standard ground-based WeBS low tide counts of this coastline will be conducted (under a separate contract).

- The SPA wide survey should be completed within one day.

- The SPA wide survey aims to capture information on the distribution of birds across their intertidal feeding grounds. The optimal timing of the survey may therefore be centred on the time of low tide.

- 100% coverage across the whole SPA (Task 1) will not be possible within the budget of this contract. To be able to extrapolate from the transect or grid of images obtained under task 1, it is highly desirable that the SPA wide survey is undertaken at low tide and on tides that correspond to the extent of the intertidal parts of the SPA shown by a defined GIS layer. If these are based on OS, this would be 'mean low water' i.e. low tide midway between neap and spring tides. However, the timing of low tide on such days in relation to daylight and optimal conditions for minimising sun glare in imagery may preclude surveying under those specific tidal conditions. Bidders are requested to consider survey practicalities and constraints in their submission and present alternatives if surveying the SPA at low tide on an average tide is not possible.

- The SPA boundary encompasses areas that lie above mean low water and below. Some species – e.g. all wading birds will be almost entirely restricted in their distribution to intertidal areas of the SPA that are exposed at low tide, some others e.g. seaducks and divers will be almost entirely restricted in their distribution to areas of the SPA that are not exposed, while some other species e.g. gulls may occur in either exposed or unexposed parts of the SPA. It will therefore be of value in understanding the limits to the distribution of certain species, to record in each image captured and processed (regardless of the presence/absence of any objects requiring identification) whether the area captured in each image is entirely exposed, not exposed at all or partly exposed. This will assist in mapping the boundary between exposed and unexposed areas during the survey flight.

- Two or more repeat surveys of the specific sub-sites within the SPA selected for the validation study (Task 3) should be carried out and must be coordinated with bespoke low tide ground-based surveys of those areas that will be conducted under a separate contract let by Natural England specifically for the purpose of this validation exercise.

- These aerial validation surveys (Task 3) should be undertaken within one day at different stages of tide and delivered either through careful planning of the SPA wide survey (Task 1) (e.g. surveys might be undertaken on the falling tide, at low tide as part of the whole SPA survey, and on the rising tide) or, if necessary, through separate digital aerial surveys/flights. Bidders should explain their approach to delivery of both Tasks 1) and 3).

- Survey(s) (Tasks 1 & 3) should be undertaken using digital high-definition video or high resolution still photography with a Ground Sample Distance (GSD) of under 2cm.

- 100% coverage of the selected validation sites/low tide count sectors surveyed under Task 3 must be achieved.

- The SPA wide survey (Task 1) should be designed to gain a representative sample of the population of key species across the entire study area to enable statistically robust estimates of abundance of the entire population (and associated confidence intervals) and maps of their distributions/densities to be generated under this contract.

- Distributions might best be predicted if environmental covariates were considered in modelling. Note one such covariate could be distance to the high tide mark, which could have a bearing on survey design. In the absence of environmental covariates to inform design, randomised starting locations to transects would be advantageous for statistical extrapolation.

- The survey design and sampling approach for Task 1) should establish a baseline to achieve the best power to detect trends/changes in the key species’ populations across the SPA over time. Details of number of transect/survey replicates and transect or grid orientation and spacing and swathe/image width proposed should be provided.

- Survey designs for Task 1 should aim to balance costs against survey coverage, image resolution and duration of survey. There will be a need to explicitly state the number of replicates as well as percentage coverage of the survey area along with power analysis to prove that suggested designs will provide the required robust population estimates (with confidence intervals) across the SPA. Costs should be provided for various options of replicates and coverage considered appropriate to meet the requirements.

- There is a relationship between the size of sample coefficients of variation (CVs) and the statistical power to detect differences between samples (e.g. changes in abundance over time). These analyses have indicated that the lower the CVs of individual samples i.e. the greater the precision of sample estimates, the finer is the level of detectable difference in estimates between them. Bohlin (1990) established a “class-based” approach to specifying the precision requirement: class 1 (greatest precision) - a CV no larger than 0.045 corresponds to an ability to detect a population change factor as small as 1.2, class 2 (intermediate precision) - a CV no larger than 0.098 corresponds to an ability to detect a population change factor as small as 1.5, class 3 (lower precision) - a CV no larger than 0.16 corresponds to an ability to detect a population change factor as small as 2 (i.e. a halving or doubling).

- Thaxter & Burton (2009) noted that ”Detecting a halving or doubling of the population corresponding to a CV of ≤16% is suggested as a general benchmark for all surveys and is particularly important for EIA and BACI surveys.” Consequently, a target CV of <=0.16 has been the basis on which many digital aerial survey designs have been drawn up with the aim of establishing a baseline abundance estimate from which a halving or doubling could reliably be detected.

- However, the resultant SPA population abundance estimates (from Task 1) are likely to be used to inform, amongst other things, condition assessment monitoring of the Morecambe Bay and Duddon Estuary SPA. For that purpose, it is unlikely that “standard” survey designs (which typically aim to deliver population abundance estimates with a Coefficient of Variation (CV) of 0.16 (and so the power to detect halving or doubling of populations across the SPA over time)) will be sufficiently powerful. Power to reliably detect smaller declines in populations across the SPA will be desirable to inform condition assessments.

- Bidders are therefore requested to present analyses to illustrate how the power to detect change in the population abundance of key species within the SPA varies with the magnitude of that potential change (e.g. declines of 50%, 40%, 30%, 20%, 10%) and with the number of transects flown and/or images captured and/or % coverage. Bidders should indicate which survey design corresponds to the costings provided so that Natural England can judge the relative degree of power to detect varying magnitudes of population decline that is likely to be achieved by the recommended survey design and assess that against the costs/benefits of alternative designs.

- Details of the camera specification and type, performance in different environmental conditions (for example, comparison of bird detections during good versus poor light conditions, between different sea states and in variable cloud levels and between birds on the water or intertidal exposed sediments) and approaches to management of variable image quality with respect to environmental conditions (e.g. sea state, cloud cover, sun altitude and surface glare) are important and information on these matters should be provided by bidders.

- Flight altitude and the resolution of images should maximise the probability of identification of individuals to species and should be specified in the tender. Ideally, example images of a range of relevant species at the preferred resolution should be presented in the tender submission documents. Consideration should be given to the ability to discriminate different species of birds from other “confusion” species and attempts to deal with this uncertainty should be outlined in the tender including all Quality Assurance measures.

- Full details of logistic considerations for survey work should be provided in the tender e.g. operational restrictions, or other factors that may justify excluding coverage of certain areas and how these restrictions will be addressed.

- There are various risks that may constrain the ability to complete the survey and data extraction within the required timescales, considering factors such as weather, airspace restrictions etc. Bidders should describe the potential risks and provide details of relevant contingency measures.

- Natural England will require the successful contractor to pass copies of some or all survey imagery to Natural England. Bidders should provide details of the process by and format in which this imagery will be transferred to Natural England and an estimate of the total storage capacity required.

To enable successful delivery of the surveys, the successful Contractor is expected to:

- Conduct appropriate preliminary analyses to demonstrate that the survey design/coverage across the entire SPA (Task 1) will allow robust population abundance and distribution estimates to be derived from the survey data. Those preliminary analyses are to be submitted at tendering stage. For example, simulated hypothetical distributions of the designated populations of non-breeding waterbirds could be used to explore the suitability of alternative survey designs/coverage etc. in terms of the resulting population abundance estimates, confidence intervals and costs.

- Plan the SPA wide survey design (Task 1) and submit these plans at tendering stage.

- Plan the flight(s) necessary to deliver the validation element of this project (Task 3) and submit these plans at tendering stage.

- Provide a protocol, agreed with the supplier of the ground-based validation surveys, setting out the means of coordination of the ground-based and aerial based survey of the selected validation sites/low tide count sectors to be surveyed as part of the validation study (Task 3) to maximise synchronicity of data collection.

- For the element of the survey focused on validation of the digital aerial method vs ground-based counts (Task 3), liaise closely with the ground-based survey contractors to ensure simultaneous surveys of each sub-area by both methods.

- Conduct the survey(s), including organisation and positioning of aircraft, crew and equipment and ensuring that all health and safety requirements, including Covid-19 requirements, are met.

- Submit a brief survey completion report following the completion of the SPA wide survey (Task 1) and validation study aerial surveys (Task 3).

The results of the surveys conducted under Task 3 (validation surveys) will be used in conjunction with the results of the simultaneous ground-based counts to validate (outwith this project) the digital aerial survey method and inform consideration by Natural England and the BTO of the scope for and any limitations to the wider application of the digital aerial survey methods in monitoring of waterbird population abundance and distribution across large and/or inaccessible estuarine sites such as Morecambe Bay & Duddon Estuary SPA.

#### 3.2 SPA wide abundance estimation (Task 2)

The successful Contractor will need to apply suitable analytical methods to meet the project aims and objectives outlined above. Whilst it may be possible to apply model-based approaches to deriving abundance estimates for some species/species groups recorded during the SPA wide survey (task 1), in this instance, Natural England only require the Contractor to produce design-based abundance estimates, with associated confidence limits, standard deviations and coefficients of variation.

We require that (where data permit) the Contractor produces SPA wide population abundance estimates for the entire area surveyed under Task 1) for the following species which are classified non-breeding features of the SPA or main components of the non-breeding waterbird assemblage feature that are of particular interest in this project (in italics):

- Whooper swan

- Pink footed goose

- Common eider

- Common goldeneye

- Red-breasted merganser

- Cormorant

- Shelduck

- Pintail

- Little egret

- European golden plover

- Bar-tailed godwit

- Ruff

- Eurasian oystercatcher

- Grey plover

- Ringed plover

- Eurasian curlew

- Black-tailed godwit

- Ruddy turnstone

- Red knot

- Sanderling

- Dunlin

- Redshank

- Mediterranean gull

- Lesser black-backed gull

Natural England is also interested in the production of SPA wide population abundance estimates of bird species groups (i.e. groupings of birds that cannot be identified to species level) and various species of marine mammals that may be recorded on the SPA wide survey (Task 1). These should be produced in a way that is appropriate to the quantity of sightings available for each species/species group.

When developing methods for deriving abundance estimates, consideration should be given to the following:

- appropriate methods, for example non-parametric bootstrap methods with replacement (Buckland, et al. 2001), for deriving upper and lower 95% confidence limits, standard deviations and coefficients of variation should be described and justified;

- we suggest that appropriate software (e.g. R) and analytical packages should be used by the supplier to ensure efficient, reproducible, analyses are carried out, methods should be clearly outlined and, where code is scripted, Natural England request that it is suitably annotated and provided as a deliverable with any associated databases;

- correction factors for bird and marine mammal species which spend time submerged should be applied where evidence allows,

- methods for assessing the potential for autocorrelation between transects, or nodes (still images), should be described and, if necessary, appropriate approaches to account for this detailed;

- methods for apportioning birds only assigned to a species group (e.g., large gulls, small brown waders) should be clearly described. Information should be provided on proposed categories of identification if species-level identification of all individuals detected is not possible. These categories should be nested and not overlap, e.g. a general category of ‘brown wader’ might be split into sub-categories of ‘small brown wader’, ‘medium brown wader’ and ‘large brown wader’ but each individual species should only belong to one category at each level in the hierarchy;

- whilst we require the Contractor to derive overall abundance estimates, including all behaviours, we request that the ratios of birds exhibiting different behaviours are provided for each species in each survey, and

- we require the Contractor to provide a single Microsoft Excel workbook including all abundance estimates derived for this project.

3.3 Mapping the SPA wide spatial distributions (Task 2)

As with the abundance estimates, it may be possible and more desirable to provide model-based density surfaces of bird and marine mammal distributions across the whole SPA. However, for simplicity, Natural England request that Kernel Density Estimation (KDE) methods are applied for this project. This method is commonly used to provide insights to spatial distributions of animals at-sea. For example, it has been used to help inform the delineation of Special Protection Area boundaries for red-throated diver (O’Brien, et al. 2012) and explore marine habitat use by seabirds (e.g. Perrow, et al. 2015; Lees, et al. 2016; Osborne, et al. 2020).

Where there are insufficient observations to adequately inform KDE analyses, or species are heavily constrained to the coast, alternative means of illustrating the spatial distribution of the key species defined below should be used (e.g. proportional symbols representing abundance within a defined transect section or still image node). Map figures should include the boundaries of the SPA protected area, an estimated boundary between areas exposed and not exposed during the survey flight and the location of any offshore wind farm or any other offshore man-made, structures.

We require that (where data permit) the Contractor produces spatial distribution maps (ideally of relative density) for the entire area surveyed under Task 1 for the following species which are classified non-breeding features of the SPA or main components of the non-breeding waterbird assemblage feature that are of particular interest in this project (in italics):

- Whooper swan

- Pink footed goose

- Common eider

- Common goldeneye

- Red-breasted merganser

- Cormorant

- Shelduck

- Pintail

- Little egret

- European golden plover

- Bar-tailed godwit

- Ruff

- Eurasian oystercatcher

- Grey plover

- Ringed plover

- Eurasian curlew

- Black-tailed godwit

- Ruddy turnstone

- Red knot

- Sanderling

- Dunlin

- Redshank

- Mediterranean gull

- Lesser black-backed gull

Natural England is also interested in the production of SPA wide spatial distribution maps of bird species groups (i.e. groupings of birds that cannot be identified to species level) and various species of marine mammals that may be recorded on the SPA wide survey (Task 1). These should be produced in a way that is appropriate to the quantity of sightings available for each species/species group.

When considering methods for deriving spatial distribution maps, consideration should be given to the following:

- Any software or analytical packages which will be used by the Contractor should be described and justified and, where code is used, Natural England request that it is suitably annotated and provided as a deliverable;

- bandwidth, as a critical variable in KDE analyses (Wang, et al. 2020), should be selected using appropriate methods (i.e. not just arbitrarily setting it), and the bidder should outline a preferred approach (final bandwidths adopted should be included within the report);

- a suitable, ideally consistent, grid cell resolution and orientation, using a suitable projected coordinate system, should be proposed and agreed with Natural England;

- consideration should be given as to how observations not identified to species level should be treated in relation to mapping (e.g. whether maps of unidentified small wader species should be plotted separately);

- for diving species, consideration should be given to whether mapped abundance includes adjustment for availability bias;

- the source (and any associated licensing agreements) of any additional map layers used should be clearly described and referenced;

- maps should be produced for the whole SPA boundary (Task 1);

- provision of suitable GIS outputs, including feature and/or raster layers, as shapefiles or geo-databases with comprehensive metadata.

#### 3.4 Total counts and mapping of all sightings within the validation survey flights (Task 4)

As the requirement is that 100% coverage of each of the selected validation sites/low tide count sectors is achieved on each repeat overflight, population estimation within each of these survey units is not required. Rather, the requirement is to provide the total count of each species/species grouping on each repeat survey in each count unit and maps depicting the precise location of each individual of each species/species grouping within each count unit on each of the repeat surveys. Map figures should include the boundaries of each of the selected validation sites/low tide count sectors and (if appropriate) an estimated boundary between areas exposed and not exposed during each repeat survey flight.

All count data collected under task 3 should be submitted to the WeBS LTC organiser (lowtide@bto.org) at the BTO through a standard spreadsheet (with metadata on count sector, date, time, etc) which should be obtained from the WeBS LTC organiser.

#### 3.5	Reporting (task 5)

The contractor should use the Natural England report template and follow associated guidance when producing their report (see: Natural England publishing standards for commissioned reports - NECR000). This aims to speed up the report publication process and promote rapid access to evidence where appropriate.

The Contractor should deliver a single report detailing the outcomes of the digital aerial surveys and all analyses of those data. The report should use a standard scientific layout including the following:

  - an executive summary,

  - an introduction and background to the work,

  - a methods section detailing the adopted surveying and analytical approach,

  - a results section providing tables of abundance estimates/counts and spatial distribution maps for key species across the entire SPA (Task 1) and each of the specific sub-set of sites / low tide count sectors within the SPA surveyed as part of the validation study (Task 3), with results for other species provided in appendices,

  - a discussion comparing the derived SPA wide abundance estimates and distributions for key features of the SPA (Task 1) with historic survey data, commenting on the performance of survey designs (including power to detect change where possible), species identification rates, outlining any caveats or limitations of the analyses, and providing brief recommendations for future work.

Sustainability

Natural England protects and improves the environment and is committed to reducing the sustainability impacts of its activities directly and through its supply chains. We expect the Contractor to share this commitment and adopt a sound, proactive sustainable approach in keeping with the 25-year environmental plan/our commitments compliant with all applicable legislation. This includes understanding and reducing direct and indirect sustainability impacts and realising opportunities, including but not restricted to; resilience to climate change, reducing greenhouse gas emissions, water use and quality, biosecurity, resource efficiency and waste, reducing the risk of pollution, biodiversity, modern slavery and equality, diversity & inclusion, negative community impacts.

As a delivery partner, the successful contractor is expected to pursue sustainability in their operations, thereby ensuring the Contracting Authority is not contracting with a supplier whose operational outputs run contrary to the Contracting Authority’s objectives. The successful contractor will need to approach the project with a focus on the entire life cycle of the project.

### Outputs and Contract Management

#### Project deliverables

On award of the contract, the supplier will be required to deliver the following:

- Digital aerial survey data (Tasks 1 & 3)

- A protocol agreed with the supplier of the ground surveys setting out the means of coordination of the ground-based and aerial-based survey(s) of the specific sub-set of sites / low tide count sectors to be surveyed as part of the validation study to maximise synchronicity of data collection.

- A brief survey completion report (within 7 days of survey completion) in Microsoft Word format detailing pertinent information regarding survey flight(s) (dates, time, weather, crew).

- Digital copies of all the georectified original survey photographs – please indicate available formats.

- Quality assured datasets of validated and geo-referenced observations (for all species/species groups/other objects of interest recorded) – so that pre-agreed data standards are met (e.g. to meet MEDIN standards or equivalent for archival in marine data repositories such as the Marine Data Exchange) (see guidance at https://medin.org.uk/) and/or compliance with Marine Scotland’s Digital Aerial Survey Data Standard Guidance Document (ABPmer in prep) (once finalised) and/or for acceptance of data by the WeBS LTC scheme;

- Raw data files providing details of all the objects observed within each sample frame and subsequent identification. For each object detected, data fields to include, as a minimum, georeferenced position, date, time, number of individuals, assignment to identity (bird species or broader category), confidence level in that categorisation, whether on the water or exposed intertidal surface or in flight and if flying - direction of travel. The locations of any objects such as vessels or other disturbances that might influence observed bird distributions should also be recorded within these data files.

- Analyses of the SPA wide survey data (task 2) and validation survey data (task 4)

- Analyses to derive abundance estimates, standard deviations, confidence intervals and coefficients of variation, for all bird and marine mammal species/species groups recorded in the SPA wide survey (Task 1) and maps depicting the relative density/distribution of key species across the whole SPA as specified in this RfQ.

- Analyses to derive total counts for all bird species/species groups recorded on each repeat survey in each of the specific sub-set of sites / low tide count sectors within the SPA surveyed as part of the validation study (Task 3) as specified in the RfQ and accompanying maps depicting the georeferenced location of each individual of each species/species grouping.

- ESRI ArcGIS 10.2 compatible shapefiles with attached metadata and clean of any typology errors and .csv files showing survey effort (e.g. aircraft tracks and altitude) together with log of conditions (sea state, visibility, cloud cover, glare, precipitation etc) during the survey(s), including data fields and metadata to pre-agreed standard.

- ESRI ArcGIS 10.2 compatible shapefiles with attached metadata and clean of any typology errors and .csv files showing observations of birds, marine mammals and other objects of interest, including data fields and metadata to pre-agreed standard. Point and polygon data should be supplied.

- ESRI ArcGIS 10.2 compatible shapefiles with attached metadata and clean of any typology errors and .csv files showing transects or areas surveyed, including data fields and metadata to pre-agreed standard.

- ESRI ArcGIS 10.2 compatible shapefiles with attached metadata and clean of any typology errors and .csv files recording the exposed/not exposed/partially exposed state of the surface area captured in each image processed in relation to surveys conducted under both Tasks 1 & 3 (regardless of presence/absence of objects requiring identification), including data fields and metadata to pre-agreed standard.

- ESRI ArcGIS 10.2 compatible shapefiles, or geo-database files for the relative abundance surfaces across the whole SPA derived from the KDE analyses, (or of simple geo-referenced observations where such analyses were precluded) for the key species outlined in this RfQ, where seen in the survey for Task 1. All GIS files should include suitable metadata outlining the project and methods used to derive the respective data as a minimum.

- ESRI ArcGIS 10.2 compatible shapefiles, or geo-database files for the georeferenced observations for the key species outlined in this RfQ, where seen in each of the surveys for Task 3. All GIS files should include suitable metadata outlining the project and methods used to derive the respective data as a minimum.

- A single technical report following Natural England guidance and using the Natural England Microsoft Word template (Available from: Natural England publishing standards for commissioned reports - NECR000). The report should provide the following:

  - an executive summary,

  - an introduction and background to the work,

  - a methods section detailing the adopted surveying and analytical approach,

  - a results section providing tables of abundance estimates/counts and spatial distribution maps for key species across the entire SPA (Task 1) and each of the specific sub-set of sites / low tide count sectors within the SPA surveyed as part of the validation study (Task 3), with results for other species provided in appendices,

  - a discussion comparing the derived SPA wide abundance estimates and distributions for key features of the SPA (Task 1) with historic survey data, commenting on the performance of survey designs (including power to detect change where possible), species identification rates, outlining any caveats or limitations of the analyses, and providing brief recommendations for future work.

- An accompanying Microsoft Excel workbook of results, GIS files for map outputs, any analytical code and data used in the analyses, and MEDIN metadata record. All data provided must comply with Natural England metadata and GIS standards (see Annex 3).

  - The single Microsoft Excel workbook should include all results of the analyses. As a minimum, this should include abundance estimates derived for this project, species-specific identification rates for the surveys, and behavioural splits for all species in each survey. The workbook should include a sheet with meta-data and field name explanations where applicable.

  - ESRI ArcGIS 10.2 compatible shapefiles, or geo-database files, as specified under point 2 above. All GIS files should include suitable metadata outlining the project and methods used to derive the respective data as a minimum.

  - Analytical code or script (e.g. R or Python), and associated databases, used to carry out the analyses. Any code should be clearly annotated using suitable mark-up.

  - A generic MEDIN compliant discovery metadata record for GIS files for map outputs generated.

All count data should also be submitted to the WeBS LTC organiser (lowtide@bto.org) at the BTO through a standard spreadsheet which should be obtained from the organiser.

Following agreement from Natural England, all relevant datafiles and associated metadata records to be submitted by the contractor to a pre-agreed public repository within a pre-agreed period following completion of the survey.

#### Project management

Once let, the following project milestones will apply:

| Milestone | Responsible Party | Date of completion |
| --- | --- | --- |
| Project inception meeting/ teleconference between contractor/sub-contractor and Natural England/British Trust for Ornithology (BTO)* | Natural England, BTO and Contractor* | W/C 30th October 2023 |
| Contractor agrees protocol with supplier of ground-based validation count data to ensure synchronicity between aerial survey and ground-based survey for task 3 and submits protocol to Natural England/BTO | Contractor (in collaboration with contractor supplying ground-based surveys | By 10th November 2023 |
| Contractor conducts and completes all aerial survey work | Contractor | End January 2024 |
| Contractor submits brief survey completion report (within 7 days of survey completion) | Contractor | End January 2024 |
| Teleconference between Natural England, BTO, contractor and ground-based survey contractor to discuss progress with analyses and any issues arising | Natural England, BTO, Contractor and supplier of ground-based surveys | End February 2024 |
| Contractor submits draft final technical report to NE/BTO | Contractor | 15th March 2024 |
| Natural England/BTO provide feedback on draft final technical report | Natural England and BTO | 22nd March 2024 |
| Teleconference between Natural England, BTO and contractor to discuss feedback on draft final technical report | Natural England, BTO and contractor | 22nd March 2024 |
| Contractor submits revised report addressing Natural England/BTO comments to satisfaction on NE project officer | Contractor | 29th March 2024 |
| Submission of ArcGIS layers, other associated datasets and metadata to agreed standards. | Contractor | 29th March 2024 |
| Wash-up meeting | Natural England, BTO and Contractor | 29th March 2024 |
| Contract to be completed | Natural England and Contractor | 29th March 2024 |

*Depending upon timelines, the supplier of the ground-based survey element of the validation study (Task 3) may be invited to attend this inception call.

This is the envisaged contract timetable. Bidders should highlight any proposed deviation from this timeline within their bid. Any delays to this timetable during the contract should be immediately discussed with the Project Officer.

In addition to the four meetings/teleconferences itemised in the table of project milestones, Natural England requires that short catch-up calls between the NE project officer and lead point of contact for the contractor are scheduled every two weeks to provide an opportunity to discuss any additional issues arising and provide an update on progress.

In support of this contract, Natural England will provide the successful Contractor with:

- Project support from dedicated project lead (NE project officer).

- Relevant available data from previous survey work.

- GIS files defining the location, size, shape and boundaries of each of the low tide count sectors and any other bespoke areas identified for the conduct of the validation study.

- Feedback comments on the draft final technical report

- Opportunity to feedback and discuss progress with the project lead and BTO at regular intervals throughout the project.

#### Data ownership, intellectual property rights and copyright

All data captured and produced shall be fully owned by and copyrighted to Natural England. This shall include any intellectual property rights that might otherwise impede on Natural England’s usage and data sharing of the outputs. Natural England may share any project outputs with third parties (for example the BTO) including for the purposes of additional analyses outside the final scope of any contract awarded against this statement of requirements. Any data supplied by Natural England/BTO to potential bidders and the successful contractor are for use in this project only and should not be retained once the bidding process (for unsuccessful bidders) or project (for the successful contractor) has been completed. In addition, neither bidders nor the successful contractor must pass such data on to any third parties unless with explicit prior permission from Natural England/BTO. The contractor is responsible for ensuring that all products submitted are of a satisfactory standard. The Natural England Nominated Officer may undertake a QA review of all project deliverables, including image analyses, prior to approving subsequent payment for the work. Following discussion with and agreement from Natural England, the contractor is responsible for submitting all datafiles and associated metadata records to a pre-agreed public repository within a pre-agreed period following completion of the project.

#### Payment

The Authority will raise purchase orders to cover the cost of the services and will issue to the awarded supplier following contract award.

The Authority’s preference is for all invoices to be sent electronically, quoting a valid Purchase Order number. Payment of 50% of the total contract value will be made on receipt of a detailed invoice following completion (to the satisfaction of the Natural England Nominated Officer) of the aerial survey(s) (tasks 1 & 3), and submission of brief completion reports on the survey(s). The remaining 50% of the total contract value will be made on receipt of a detailed invoice following completion (to the satisfaction of the Natural England Nominated Officer) of all the milestones detailed above, and formal acceptance by them of the specified outputs. All invoices should be dated no later than 31st March 2024.

It is anticipated that this contract will be awarded for a period of 22 weeks (~6 months) to end no later than 31st March 2024. Prices will remain fixed for the duration of the contract award period. We may at our sole discretion extend this contract to include related or further work. Any extension shall be agreed in writing in advance of any work commencing and may be subject to further competition.

### Evaluation Methodology

We will award this contract in line with the most economically advantageous tender (MEAT) as set out in the following award criteria:

Technical – 50%

Commercial – 50%

#### Evaluation criteria

Evaluation weightings are 50% technical and 50% commercial, the winning tenderer will be the highest scoring combined score.

The summary table below provides an overview of the overall evaluation breakdown.

| Award Criteria | Weighting (%) | Evaluation Topic & Weighting | Sub-Criteria | Weighted Question |
| --- | --- | --- | --- | --- |
| Technical | 50% | Service / Product Proposal | Methodology | Q1. Please provide details of the methodology proposed to deliver the requirements set out in the Specification. (60% of technical score available) |
|  |  |  | Staff Technical Expertise | Q2. Please provide details of the project team providing the requirements set out in the Specification. (30% of technical score available) |
|  |  |  | Risk assessment | Please provide a project risk assessment. (10% of technical score available) |
| Commercial | 50% | Whole life cost of the proposed Contract | Commercial Model | Q3. Please provide costs (100% of commercial score available) |

#### Technical (50%)

Technical evaluations will be based on responses to specific questions covering key criteria which are outlined below.  Scores for questions will be based on the following:

| Description | Score | Definition |
| --- | --- | --- |
| Very good | 100 | Addresses all the Authority’s requirements with all the relevant supporting information set out in the RFQ. There are no weaknesses and therefore the tender response gives the Authority complete confidence that all the requirements will be met to a high standard. |
| Good | 70 | Addresses all the Authority’s requirements with all the relevant supporting information set out in the RFQ. The response contains minor weaknesses and therefore the tender response gives the Authority confidence that all the requirements will be met to a good standard. |
| Moderate | 50 | Addresses most of the requirements with most of the relevant supporting information set out in the RFQ. The response contains moderate weaknesses and therefore the tender response gives the Authority confidence that most of the requirements will be met to a suitable standard. |
| Weak | 20 | Substantially addresses the requirements but not all and provides supporting information that is of limited or no relevance or a methodology containing significant weaknesses and therefore raises concerns for the Authority that the requirements may not all be met. |
| Unacceptable | 0 | No response or provides a response that gives the Authority no confidence that the requirement will be met. |

Technical evaluation is assessed using the evaluation topics and sub-criteria stated in the Evaluation Criteria section above.

Separate submissions for each technical question should be provided and will be evaluated in isolation. Tenderers should provide answers that meet the criteria of each technical question set out in the following tables.

| Q1. Methodology | Detailed Evaluation Criteria |
| --- | --- |
| Please submit a document with the filename: “PBDM_WP4_Task4.1_MB&DE_SPA_aerial_E01_Company Name”. Your response must not exceed a maximum of 6 sides of A4 (in addition to any title page), font size Arial 11. | The response must demonstrate the delivery method for each requirement specified in the Specification (2. Objectives) of this RFQ, and where relevant, demonstrate how these methods comply with those set out in the Specification (3. Methods) or provide reasons for why they do not. The response must include information in sufficient detail to allow a full appraisal of the suitability of the approach to deliver for the project. Your response will be evaluated on the basis of whether it: - Demonstrates a clear understanding of the nature of the requirements. - Includes a clear, practical, achievable and cost-effective methodology to deliver these requirements including: - Presents the results of preliminary analysis to inform proposed survey design (for task 1), - Presents a clear survey design (for task 1) based on such analyses, - Presents a clear plan to deliver the validation survey (task 3) either as part of the survey to deliver task 1 or as a separate exercise if necessary. - Presents anticipated levels of precision around population abundance estimates at the SPA scale (task 1) and estimates of the power to detect abundance changes of varying magnitude achieved by different survey designs, - Provides details of clear and established survey methods to ensure identification rates of target species are maximised, - Provides details of clear and established procedures for capturing, securing, storing, analysing and QA-ing seabird and mammal imagery from marine locations, with typical durations from image capture to fully available data; - Provides details of the process by which and format in which imagery will be transferred to Natural England and an estimate of the total storage capacity required. - Provides details of contingency processes for disrupted or aborted surveys; - Provides a clear, well evidenced, approach to deriving design-based abundance estimates and considering other factors which may influence the accuracy and precision of results (for both birds and marine mammals), - Demonstrates awareness of suitable software to maximise the efficiency and reproducibility of analyses, - Shows consideration of potential improvements that can be made to any established methods for deriving abundance estimates from digital aerial surveys, - Provides a clear, well evidenced, approach to producing spatial distribution maps for key species, - Demonstrates a good understanding of KDE methods, available software for analyses and suitable approaches for deriving bandwidths, - Documents any added value your organisation can bring to the project. A minimum score of 50 averaged across evaluators is required to be met for this question. Any average score below this will be scored as a Fail. |

| Q2. Staff Technical Expertise | Detailed Evaluation Criteria |
| --- | --- |
| Please submit a document with the filename “PBDM_WP4_Task4.1_MB&DE_SPA _aerial_E02_Your Company Name”. Your response must not exceed a maximum of 6 sides of A4 (in addition to any title page), font size Arial 11. | The response must demonstrate that the staff members (including any sub-contractors if appropriate) who will be assigned to delivery of this specific project have sufficient technical expertise across the broad range of technical skills required to deliver the project objectives including both generic skills and specific skills including but not limited to: - Project Management - Planning and conducting digital aerial surveys of seabirds and mammals at sea - Handling, storing and securing digital imagery - Processing digital imagery at pace - Ensuring Quality Assurance of data products - Digital aerial survey data analysis methods and software; use of KDE methods, use of GIS - Presentation of geospatial data, including implementing data standards This will include examples of skills, expertise, and relevant training. The project team should have an appropriate balance of inputs by senior and junior staff. Lines of reporting to staff (to senior staff and/or the project manager) should be clearly presented and sufficient. The information provided should include: - For each member of the Project team, information on the amount of time input to this specific project, their roles, responsibilities, levels of seniority, the value added that they will bring to the project, their lines of reporting and their availability to do the work. - The name(s) of the individual(s) who will have overall management responsibility for the project and will report to Natural England’s project officer and the person who will be responsible for ensuring that the Project is completed satisfactorily. Your response will be evaluated based on: - The level and relevance of expertise and skills, provided by the Project team and sub-contractors and the value added delivered by this. This will consider expertise and skills in: project management; ornithology; data collection and collation; digital imagery processing, digital aerial survey data analysis methods and software; use of KDE methods, use of GIS and knowledge of data standards. - The suitability and adequacy of the staff making the inputs to each stage of the Project (in terms of their expertise and skills), the quantity of their inputs and their availability to do the work. For each member of the Project team, information on the amount of time input (days/hours) to this specific project. We suggest this information is provided in a table. - The appropriateness of the balance of inputs by senior and junior staff and clarity and sufficiency of lines of reporting. Please provide the name(s) of the individual(s) who will have overall management responsibility for the project and will report to Natural England’s project officer and the person who will be responsible for ensuring that the Project is completed satisfactorily. We suggest a project specific organogram is provided. Consideration should be given to cover for key roles given any unforeseen circumstances. A minimum score of 50 averaged across evaluators is required to be met for this question. Any average score below this will be scored as a Fail. |

| #### Q3 Risk assessment | #### Detailed evaluation criteria |
| --- | --- |
| Please submit a document with the filename: “PBDM_WP4_Task4.1_MB&DE_SPA _aerial_E03_Your_Company Name”. #### Your response must not exceed a maximum of 6 sides of A4 (in addition to any title page), font size Arial 11. | Provide a project risk assessment tailored to the requirement to cover matters regarding: - Health and Safety risks associated with conducting the survey flight(s) needed to fulfil the objectives of this project, and associated mitigation measures. - All other (non-H&S) risks associated with delivery of the survey(s) and subsequent data processing, analyses, reporting etc needed to fulfil the objectives of this project, and associated mitigation measures and contingencies. Evaluation criteria: Your response will be evaluated on the basis of whether it: - Demonstrates a clear understanding of the Health & Safety issues associated with delivery of the surveys needed to fulfil the objectives of this project and describes effective measures to mitigate those risks. - Demonstrates a clear understanding of all other risks associated with delivery of the surveys specifically and the project in general to fulfil the objectives of this project and describes effective measures to mitigate those risks. Note that this response should include, but not be limited to, matters concerning H&S in conducting the survey flight(s), and should address ALL risks to project delivery. #### A minimum score of 50 averaged across evaluators is required to be met for this question. Any average score below this will be scored as a Fail. |

#### Commercial (50%)

The Contract is to be awarded as a fixed price which will be paid according to the completion of the deliverables stated in the Specification of Requirements.

Suppliers are required to submit a total cost to provide the deliverables stated in the Specification of Requirements. In addition to this, the Commercial Response template must be completed to provide a breakdown of the whole life costs against each deliverable used in the delivery of this requirement.

#### Calculation Method

The method for calculating the weighted scores is as follows:

- Commercial

Score = (Lowest Quotation Price / Supplier’s Quotation Price) x 50% (Maximum available marks)

- Technical

Score = (Bidder’s Total Technical Score / Highest Technical Score) x 50% (Maximum available marks)

The total score (weighted) (TWS) is then calculated by adding the total weighted commercial score (WC) to the total weighted technical score (WT): WC + WT = TWS.

### Information to be returned

Please note, the following information requested must be provided. Incomplete tender submissions may be discounted.

Please complete and return the following information:

- completed Commercial Response template

- separate response submission for each technical question (in accordance with the response instructions)

- completed Mandatory Requirements (Annex 1)

- completed Acceptance of Terms and Conditions (Annex 2)

### Award

Once the evaluation of the Response(s) is complete all suppliers will be notified of the outcome via email.

The successful supplier will be issued the contract, incorporating their Response, for signature. The Authority will then counter sign and generate a Purchase Order.

### References

ABPmer (in prep) Digital Aerial Survey Data Standard, Guidance Document. ABPmer Report No. R.3947.*

APEM (2018). Digital Aerial Imagery Proof of Concept Surveys – The Wash SPA. APEM Scientific Report P00002312. Natural England, May 2018, v4.0 Final, 56 pp.

Bohlin, T. (1990) Estimation of population parameters using electric fishing: aspects of the sampling design with emphasis on salmonids in streams. In, Cowx, I.G. & Lamarque, P. (eds.) Fishing with Electricity. Fishing News Books, Oxford, pp. 156-173.

Banks, A A.N., Ellis, P., Holloway, S.J., Holt, C., Horner, R., Maclean, I.M.D., Marchant, J., Musgrove, A.J., Schofield, R.A., Sheldon, J. & Stenning, J. (2006) Surveying waterbirds in Morecambe Bay for the Wetland Bird Survey (WeBS) Low Tide Count Scheme. BTO Research Report No. 443.

Buckland, S.T., Anderson, D.R., Burnham, K. P., Laake, J.L., Borchers, D.L. and Thomas, L. (2001). Introduction to Distance Sampling: Estimating Abundance of Biological Populations. Oxford University Press, Oxford.

Lees, K.J., Guerin, A.J., & Masden, E.A. (2016). Using kernel density estimation to explore habitat use by seabirds at a marine renewable wave energy test facility. Marine Policy, 63, 35-44. https://doi.org/10.1016/j.marpol.2015.09.033

O'Brien, S. H., Webb, A., Brewer, M.J. & Reid, J.B. (2012). Use of kernel density estimation and maximum curvature to set marine protected area boundaries: identifying a special protection area for wintering red-throated divers in the UK. Biological Conservation, 156: 15– 21.

Osborne, O.E., O’Hara, P.D., Whelan, S., Zandbergen, P., Hatch, S.A. & Elliott, K.H. (2020). Breeding seabirds increase foraging range in response to an extreme marine heatwave. Marine Ecology Progress Series, 646:161-173. https://doi.org/10.3354/meps13392

Perrow, M.R., Harwood, A.J., Skeate, E.R., Praca, E. & Eglington, S.M. (2015). Use of multiple data sources and analytical approaches to derive a marine protected area for a breeding seabird. Biological Conservation, 191: 729-738.

`	Thaxter, C.B. & Burton, N.H.K. (2009) High-Definition Imagery for Surveying Seabirds and Marine Mammals: A Review of Recent Trials and Development of Protocols. British Trust for Ornithology Report Commissioned by Cowrie Ltd.

Wang, S., Li, A., Wen, K., & Wu, X. (2020). Robust kernels for kernel density estimation. Economics Letters, 191: 109138. https://doi.org/10.1016/j.econlet.2020.109138

* Unfortunately, this draft report is unavailable for dissemination at this time.

### Annex 1 Mandatory Requirements

#### Part 1 Potential Supplier Information

Please answer the following self-declaration questions in full and include this Annex in your quotation response.

##### Part 1.1 Potential Supplier Information:

| Question no. | Question | Response |
| --- | --- | --- |
| 1.1(a) | Full name of the potential supplier submitting the information |  |
| 1.1(b) | Registered office address (if applicable) |  |
| 1.1(c) | Company registration number (if applicable) |  |
| 1.1(d) | Charity registration number (if applicable) |  |
| 1.1(e) | Head office DUNS number (if applicable) |  |
| 1.1(f) | Registered VAT number |  |
| 1.1(g) | Are you a Small, Medium or Micro Enterprise (SME)? | (Yes / No) |

Note: See EU definition of SME https://ec.europa.eu/growth/smes/business-friendly-environment/sme-definition_en

##### Part 1.2 Contact details and declaration

By submitting a quotation to this RFQ I declare that to the best of my knowledge the answers submitted and information contained in this document are correct and accurate.

I declare that, upon request and without delay you will provide the certificates or documentary evidence referred to in this document.

I understand that the information will be used in the selection process to assess my organisation’s suitability to be invited to participate further in this procurement.

I understand that the authority may reject this submission in its entirety if there is a failure to answer all the relevant questions fully, or if false/misleading information or content is provided in any section.

I am aware of the consequences of serious misrepresentation.

| Question no. | Question | Response |
| --- | --- | --- |
| 1.2(a) | Contact name |  |
| 1.2(b) | Name of organisation |  |
| 1.2(c) | Role in organisation |  |
| 1.2(d) | Phone number |  |
| 1.2(e) | E-mail address |  |
| 1.2(f) | Postal address |  |
| 1.2(g) | Signature (electronic is acceptable) |  |
| 1.2(h) | Date |  |

#### Part 2 Exclusion Grounds

##### Part 2.1 Grounds for mandatory exclusion

| Question no. | Question | Response |
| --- | --- | --- |
| 2.1(a) | Please indicate if, within the past five years you, your organisation or any other person who has powers of representation, decision or control in the organisation been convicted anywhere in the world of any of the offences within the summary below. |  |
|  | Participation in a criminal organisation. | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Corruption. | ((Yes / No) If yes please provide details at 2.1 (b) |
|  | Fraud. | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Terrorist offences or offences linked to terrorist activities | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Money laundering or terrorist financing | (Yes / No) If yes please provide details at 2.1 (b) |
|  | Child labour and other forms of trafficking in human beings | (Yes / No) If yes please provide details at 2.1 (b) |
| 2.1(b) | If you have answered yes to question 2.1(a), please provide further details. Date of conviction, specify which of the grounds listed the conviction was for, and the reasons for conviction. Identity of who has been convicted If the relevant documentation is available electronically please provide the web address, issuing authority, precise reference of the documents. |  |
| 2.1 (c) | If you have answered Yes to any of the points above have measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (i.e. Self-Cleaning) | (Yes / No) |
| 2.1(d) | Has it been established, for your organisation by a judicial or administrative decision having final and binding effect in accordance with the legal provisions of any part of the United Kingdom or the legal provisions of the country in which the organisation is established (if outside the UK), that the organisation is in breach of obligations related to the payment of tax or social security contributions? | (Yes / No) |
| 2.1(e) | If you have answered yes to question 2.3(a), please provide further details. Please also confirm you have paid or have entered into a binding arrangement with a view to paying, the outstanding sum including where applicable any accrued interest and/or fines. |  |

##### Part 2.2 Grounds for discretionary exclusion

| Question no. | Question | Response |
| --- | --- | --- |
| 2.2(a) | The detailed grounds for discretionary exclusion of an organisation are set out on this webpage, which should be referred to before completing these questions. Please indicate if, within the past three years, anywhere in the world any of the following situations have applied to you, your organisation or any other person who has powers of representation, decision or control in the organisation |  |
| 2.2(b) | Breach of environmental obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(c) | Breach of social obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(d) | Breach of labour law obligations? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2(e) | Shown significant or persistent deficiencies in the performance of a substantive requirement under a prior public contract, a prior contract with a contracting entity, or a prior concession contract, which led to early termination of that prior contract, damages or other comparable sanctions? | (Yes / No) If yes please provide details at 2.2 (f) |
| 2.2 (f) | If you have answered Yes to any of the above, explain what measures been taken to demonstrate the reliability of the organisation despite the existence of a relevant ground for exclusion? (Self Cleaning) |  |

### Annex 2 Acceptance of Terms and Conditions

I/We accept in full the terms and conditions appended to this Request for Quote document.

Company ____________________________________________________

Signature ____________________________________________________

Print Name ____________________________________________________

Position ____________________________________________________

Date ____________________________________________________

### Annex 3 Natural England data requirements

This Annex provides high level guidance for contractors regarding Metadata and Geographic Information System deliverables. Final details of requirements for this project, with reference to section 5 of the Specification, will be agreed with the Nominated Officer.

Natural England reserve the right to check the quality of all digital data and reserve the right to return any data that does not meet these compliance requirements. If any part of this guidance is unclear please make early contact with the Natural England Nominated Officer who will be able to provide clarification in consultation with data management colleagues.

#### Metadata

A generic MEDIN compliant discovery metadata record should be completed for the project outputs as a whole and for each GIS layer generated. By generating MEDIN compliant metadata, Natural England gain required compliance with both INSPIRE Directive and UK GEMINI 2.1 metadata requirements, while using term list vocabularies fit for marine purposes. There are a variety of mechanisms for generating MEDIN compliant metadata available at the following link along with a full description of the MEDIN standard, XML encoding, and guidance documentation: https://www.medin.org.uk/medin-discovery-metadata-standard. Metadata derived as part of this project must be submitted to Natural England in an XML file which Natural England will archive through Data Archive Centres (DACs). Guidance ‘MEDIN Guidance for Contractors’ can be provided to the winning contractor.

Beyond the discovery metadata requirement it is essential that the final GI datasets are accompanied by a detailed ‘readme.doc’ describing the file structure within submitted outputs, and clearly outlining file associations (e.g. layer files for colours/ fill patterns).

#### Geographic Information data - format for deliverables

GIS products should be compatible with ArcGIS Desktop 10.2. Data will be supplied as a series of Feature classes in a File geodatabase (.gdb) to an attribute structure to be agreed between the contractor and Natural England on commencement of the contract. One or more ArcMap Document files (.mxd) must be provided to pull out data into distinct layers based on its attribution and these will apply appropriate layer styling.

Data in the Feature classes of File geodatabases will be supplied using the following coordinate system parameters:

| Attribute | Value |
| --- | --- |
| Geographic Coordinate System | GCS_WGS_1984 |
| Datum | D_WGS_1984 |
| Prime Meridian | Greenwich |
| Angular Unit | Degree |

For the purposes of this project ArcMap document files (.mxd) are to display WGS84 data projected from requested feature classes in Lambert Azimuthal Equal Area projection based on ETRS 1989, using an appropriate (eg Petroleum EPSG) transformation between WGS 1984 and ETRS 1989.

https://magic.defra.gov.uk/