Invitation to tender

| Title | Pilot collection of the London Measure of Unplanned Pregnancy |
| --- | --- |
| Type of product (Taxonomy TOI) | Datasets and Statistical Information, Intelligence |
| Introduction, overview and context for the work | The Department of Health’s Framework for Sexual Health Improvement in England (2013) includes the ambition to reduce unwanted pregnancies among all women of fertile age through: increased knowledge and awareness of all methods of contraception among all groups in the local population; and increased access to all methods of contraception, including long-acting reversible contraception (LARC) methods and emergency contraception, for women of all ages and their partners. The Annual Report of the Chief Medical Officer, 2014 also highlighted the need for improved intelligence on unplanned pregnancies and referenced the London Measure of Unplanned Pregnancy (LMUP) (page 59). PHE needs to improve the quality of reproductive data, intelligence and the evidence base to improve reproductive health. Monitoring change in the rate of unintended / unplanned pregnancy is key to evaluating sexual and reproductive health outcomes. Now this can be achieved by using a validated robust measure that scores (from 0 to 12) the extent to which a current or recent pregnancy was planned. The London Measure of Unplanned Pregnancy (LMUP) is a six item questionnaire that has been extensively researched across five continents and is easily completed by women. The LMUP is sensitive enough to detect changes in pregnancy planning and the incidence of unplanned pregnancy over time, across diverse populations and in response to intervention (e.g. improving pre-conception care in women with diabetes). It can provide a key outcome measure for monitoring inequalities in sexual and reproductive health. If viable, it would be ideal if this measure could eventually be included in the Maternity Services Data Set which has been a mandated national collection since 1 November 2014. PHE would like to fund a pilot collection of the LMUP in order to: - test the viability of routine collection of the LMUP; - to inform inclusion of the LMUP in the Maternity Services Data Set; and - to ultimately enable evaluations of sexual and reproductive health inequalities and outcomes from sexual and reproductive health interventions. |
| Specification of work, including aims objectives, deliverables and outputs. | The deliverables required for this commissioned work are as follows: - Undertake a pilot project to test the viability of routine collection of the LMUP as part of routine maternity data collection in two large NHS Trusts who use different maternity IT systems. The data must be entered in the main maternity system and the best method found to integrate the collection with the existing data collection, avoiding or reducing duplication/overlap with existing data items where possible - Provide a report on the pilot, including example analyses of the LMUP measures and outlining issues that would need to be taken into account when extending the collection nationally. The supplier staff must have the ability to engage with relevant NHS Trust and PHE staff and possess expertise in database processing, data analysis and report writing. Prior knowledge of maternity services and maternity data collection systems would be an advantage. |
| Project management and reporting | It is expected that the supplier will appoint a named, suitably qualified individual who will be the main point of contact. PHE will act in an advisory capacity to the appointed person and there is an expectation that PHE will be fully briefed and also involved in agreeing the working methods. The PHE lead for this work is Clare Perkins, Head of Risk Factors Intelligence who will liaise with the supplier and provide day-to-day support from PHE, along with Wendi Slater. The successful supplier is expected to meet with the PHE lead at the initiation, and monthly thereafter; and also to highlight any risks or issues as soon as possible in writing to the PHE lead. |
| Risk management | Suppliers should submit, as part of their application, a summary explaining what they foresee the main risks to delivering this project are, and how they will mitigate against them. NB: A risk is defined as any factor which may delay, disrupt or prevent the full achievement of a project objective. All risks should be identified. The summary should include an assessment of each risk, together with a rating of the risks likelihood and its impact on a project objective (using a high, medium or low classification for both). The risk assessment should also identify appropriate actions that would reduce or eliminate each risk, or its impact. |
| Stakeholder engagement | It is essential that there are plans in place for collaboration and consultation with partners and stakeholders to ensure that the product meets the required deliverables. |
| Information governance | All data collected, stored or shared is in complete compliance with the Data Protection Act 2003 and conforms to the PHE policy on information governance. |
| Dissemination and branding | The lead organisation for disseminating work and communications activity is PHE. The work will be PHE branded. |
| Copyright and intellectual property | All items published on gov.uk are crown copyright. Intellectual Property “Background Intellectual Property” means any Intellectual Property and Intellectual Property Rights, other than Foreground Intellectual Property, that is used in connection with any part of the Services. “Foreground Intellectual Property” means any Intellectual Property and Intellectual Property Rights that arises or is obtained or developed by, or by the Contractor on behalf of, either party in the course of or in connection with the performance of the Services. All Foreground Intellectual Property shall vest in and be owned absolutely by the Authority and the Contractor agrees to execute all documents and assignments and do all such things as may be necessary to perfect the Authority's title to the Intellectual Property or to register the Authority as owner of registrable rights. All Background Intellectual Property owned by either Party shall remain the property of that Party but the Contractor shall, where it has the right to do so, grant the Authority and any Beneficiary a non-exclusive, perpetual, royalty free, global license to use any Background Intellectual Property to the extent necessary for the purpose of the Services and for the use or exploitation of any Foreground Intellectual Property. The Authority shall be entitled to negotiate and agree provisions for the ownership of Intellectual Property Rights which deviate from the above to the extent that such other provisions, in the authority’s opinion, are more suitable for the services under that Order. |
| Standards; - Publication standard - GDS - Ethics - Official statistics | The work must align with the principles of the PHE Publication Standard The work should be written in the GDS style if it is intended for publication on gov.uk and be in PHE house style. The works must comply with any appropriate ethics requirement/approval The data will be considered as Official Statistics, which is produced impartially and free from political influence. We expect the supplier to deposit the data with the UK Data Service Archive. Further information can be found here: https://www.ukdataservice.ac.uk/ |
| Equity & Equality | PHE is vigilant in its duty to reduce inequalities and to promote equity and equality. It is therefore vital that all work undertaken on behalf of PHE can demonstrate how it supports this agenda and where appropriate/required an Equality Impact Assessment (EIA) is carried out. It is also important to consider the Equalities Act 2010 and ensure compliance with this and the protected characteristics within are considered |
| Timeframe | All the deliverables must be in place by 31st March 2017. The Service Provider will provide the Authority with regular progress updates regarding delivery of the agreed deliverables by the end of the financial year. |
| Enquiries and returned bids to | The tendering process is being carried out using BravoSolution e-tendering portal: https://phe.bravosolution.co.uk Potential providers must register on the portal to be able to access the Invitation to Tender. All questions and responses must be made via the portal. Questions or responses sent directly to employees of PHE will not be answered or accepted. Stage 1; Formal Invitation to Tender. Stage 2; Evaluation and Clarification*. Stage 3; Award. *We reserve the right to interview applicants or to make decision via e-correspondence and applications only Suppliers must complete Stage 1 by the date and time specified on BravoSolution, offers submitted by any other means will not be valid for acceptance. |

1. 	Grading of Recommendations Assessment, Development and Evaluation Working Group [Internet]. [cited 2016 Jul 27]. Available from: http://www.gradeworkinggroup.org/index.html

2. 	Critical Appraisal Skills Programme; tools and checklists [Internet]. [cited 2016 Apr 15]. Available from: http://www.casp-uk.net/#!casp-tools-checklists/c18f8

3. 	Joanna Briggs Institute, SUMARI, Reviwers manuals [Internet]. [cited 2016 Jul 27]. Available from: http://joannabriggs.org/sumari.html

| Application process | You should provide information on each of the key elements outlined below There is a maximum 1,500 word limit for applications. - Background: full contact details for your organisation together with a statement of the approach that you would take in relation to the above outline, and a summary of why you wish to undertake this work. - Previous experience in the field/area: a description of your organisation/individuals expertise as it pertains to carrying out this project, in particular expertise in systematic reviewing of evidence work that demonstrate your experience and ability to provide this work to a high standard. Particular attention should be paid to demonstrating your experience of how research outputs have been used for health/public health and/or employment/labour market related policy. - Brief project plan and methodology: detailed description of the activities that would be undertaken for the production of each of the research questions and how this will be achieved within the set timeline. This should include a description of and rationale for the proposed methods/approach for each stage of development. - Risk statement: on the management and ownership of the rapid evidence assessment(s) - Project costs: Please provide a breakdown of the estimated budget necessary to deliver the service. This should also show the estimated time commitment of core team members. - Team CVs: these will not be included in the word count. |
| --- | --- |
| Submissions d deadline | Completed bids should be submitted via the BravoSolution e-tendering portal as detailed above. Deadline for submissions is Noon on Friday 13th January 2017. The successful supplier will be appointed on 20th January 2017. |
| Assessment & scoring criteria for bids | Public Health England (PHE) is looking to engage with a professional body to produce the outputs as described in the attached "Specification Document. Please note: There is a total word limit (excluding CV's) of 1,500 words per application. Question; Description; Question Type; Min. / Max. Score. Completion Date; Please confirm that you will be able to compete this piece of work in accordance with the timetable included in the Specification Document (31st March 2017); Yes/No; 0/0. Mandatory; Please detail the background of your organisation together with a statement of the approach that you would take in relation to the above outline, and a summary of why you wish to undertake this work.; Attachment; 0/20. Mandatory; Please detail your previous experience in the field/area: a description of your organisation/individuals expertise as it pertains to carrying out this project, in particular expertise in systematic reviewing of evidence work that demonstrate your experience and ability to provide this work to a high standard. Particular attention should be paid to demonstrating your experience of how research outputs have been used for health/public health and/or employment/labour market related policy.; Attachment; 0/20. Mandatory; Please attach your brief project plan and methodology: detailed description of the activities that would be undertaken for the production of each of the research questions and how this will be achieved within the set timeline. This should include a description of and rationale for the proposed methods/approach for each stage of development.; Attachment; 0/60. Mandatory; Please attach a risk statement: on the management and ownership of the rapid evidence assessment(s), using the template provided.; Attachment; 0/0. Mandatory; Please provide a breakdown of the estimated budget necessary to deliver the service. This should also show the estimated time commitment of core team members.; Attachment; 0/20. Mandatory; Please attach copies of your team CVs. N.B. These will not be included in the word count.; Attachment; 0/60. Total maximum score = 180 |