## Risk evaluation
OFFICIAL
Risk evaluation table example | [7 empty] | Document no2a
LIKELIHOOD (of risk materialising) | Suggested approximate percentage
Rating | %
Completely mitigated | 0%
Rare | up to <3%
Highly unlikely | 3% to <10%
Unlikely | 10% to < 30%
Possible | 30% to < 70%
Likely | 70% to <90%
Almost Certain | 90% to 100%
IMPACT (loss of programme benefit if the risk materialises | Suggested approximate percentage
Rating | %
Zero impact | 0%
Negligible | up to <3%
Very Low | 3% to <10%
Low | 10% to < 30%
Medium | 30% to < 70%
High | 70% to <90%
Very High | 90% to 100%
EXAMPLES
Risks that could interupt supply |  | Impact to vaccination programme / based on current mitigation measures |  | Additional supplier mitigation (reduces the likelihood) or additional concerns (increases the likelihood) | Likelihood (adjusted) |  | Exposure | Additional measures taken by the Authority to reduce exposure and associated costs
MANUFACTURING
Areas of concern that may impact scoring:
- Inspection outputs; criticals, or high number in majors findings
- High number of complaints and repeated deviations
- Frequent recalls / poor recall plan
- Weak Quality Management System
- Delays in Regulatory approvals; Marketing Authorisation variations
- Delays in manufacurer implementation and approvals on change controls
- Lack of personnel (resources) or lack of qualified personnel
- Poor training adherence
- Cross-contamination incident
- Poor environmental monitoring program
- Lack of Control Strategy
- Aging facility; shutdowns
- No capacity plan
- Poor contigency plan
- Poor maintenance programme
- Equipment breakdown; manufacturing or packaging
- Quality Control failures
- Lab investigations
- Poor self inspection program
- Poor quality KPI's
- No improvement Plans
- Poor Vendor Assurance management; raw materials, packaging
Overall estimated risk exposure, taking into account any mitigating actions |  | Rating | 0% |  | Rating | 0% | 0%
SUPPLY CHAIN
Areas of concern that may impact scoring:
- Introduction of falsified medicines in the supply chain
- Lack of security on transportation; stolen medicines / medicines diversion
- Loss of Licence to Operate
- Uncontrolled storage sonditions; no pest control, no temperature monitoring
- Breaking cold chain during transportation
Overall estimated risk exposure, taking into account any mitigating actions |  | Rating | 0% |  | Rating | 0% | 0%
EXTERNAL RISKS
Areas of concern that may impact scoring:
- Customs controls
- EU exit (legislation, movement, customs)
- Government restrictions
- Energy Restriction; Electricity
- Water or fuel restrictions
- War, Conflict
Overall estimated risk exposure, taking into account any mitigating actions |  | Rating | 0% |  | Rating | 0% | 0%
ANY OTHER RISKS |  | Rating | 0% |  | Rating | 0% | 0%
Total risk exposure score |  | Rating | 0% |  | Rating | 0% | 0%
The Authority may refer to the EMA's guidance on risk management in carrying out its evaluation (https://www.ema.europa.eu/en/documents/scientific-guideline/international-conference-harmonisation-technical-requirements-registration-pharmaceuticals-human-use_en-3.pdf)