South Tees Site Company Ltd

Teesside Management Offices

Redcar

TS10 5QW

# Decontamination Tender

Works Information

South Tees Site Company

22 October 2018

Notice

This document and its contents have been prepared by Faithful+Gould and are intended solely as information for South Tees Site Company Ltd and use in relation to Decontamination of former SSI iron and steel making assets at South Tees Project.  Faithful+Gould assumes no responsibility to any other party in respect of or arising out of or in connection with this document and/or its contents.

Document history

| Revision | Purpose description | Originated | Checked | Reviewed | Authorised | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Rev 1.0 | Draft for Review | DRR | AGB / IG |  |  | 02.10.2018 |
| Rev 2.0 | Addition of Pricing information section | IG | AGB |  |  | 22.10.2018 |

South Tees Site Company Ltd Authorisation Signoff

| Name |  |
| --- | --- |
| Project | Decontamination Project |
| Date |  |
| Signature |  |

Contents

1.	Project Background	4

2.	Performance Specification	7

3.	Early Contractor Involvement Strategy	9

4.	Pricing Information / Activity Schedule	13

5.	Approvals and Consents	15

6.	Project Management Strategy	15

7.	Compliance with STSC Procedures	15

8.	Performance Bond	15

9.	Further Information for Contractors	15

Appendices	16

Appendix 1.	South Bank Coke Ovens	16

Appendix 2.	Coke Ovens Gas Main	16

Appendix 3.	Heavy Fuel Oil	16

Appendix 4.	Redcar Coke Ovens	16

Appendix 5.	Project Management Strategy	16

Appendix 6.	Compliance with STSC Procedures	16

Appendix 7.	Performance Bond	16

# Project Background

## South Tees Site Company Ltd (STSC) is a Government-owned company set up in December 2016 to maintain the safety and security of the former SSI iron and steel making assets on Teesside pending the progressive redevelopment of the various lands identified for regeneration within the South Tees area by South Tees Development Corporation (STDC).

## Funding for the Company has been agreed for the next four financial years (starting in 2018/19). This includes funding for a major project to facilitate decontamination of certain industrial facilities and removal of the related hazardous materials from the site. By virtue of these materials, the site is presently assigned Control Of Major Accident Hazards Regulations (COMAH) Top Tier status. Successful completion of the project will remove the site from COMAH status and support the redevelopment of the site by STDC.

## The approach being mapped is to ensure adherence to current regulatory requirements and industry best practice with the aspiration being for innovation in the project delivery strategy, both contractually and physically, to realise maximum value from project outcomes.

## The site context may best be described as complex, with a number of key issues to consider including the scale of the SSI assets, other on-site operations, safety and environmental regulations, budgets and anticipated timescales.

## Prior to liquidation in October 2015, SSI (UK) Ltd operated a 4 million tonne per annum integrated iron and steelmaking facility on Teesside. Included in the complex are two coke ovens and by-products plants, a coke oven gas pipeline/main (COGM) and a heavy fuel oil pipeline/main (HFO). As well as providing coke for the iron-making process the coke ovens produced coke oven gas (COG) which was used as fuel for the coke ovens and other on-site manufacturing assets, crude Benzole and Coal Tar, which was processed and sold as a by-product.

## The coke ovens are situated approximately 8km apart and connected by the COGM. The COGM, which supplied the other non-operational manufacturing facilities and the on-site power station, is approximately 27km long. The diameter varies across the 27km, but the interconnecting main is 600mm and the by-products mains 1200mm, with c.7km of underground sections. The HFO is around 9km in length and is mostly 150mm in diameter.

## When SSI entered liquidation the production assets were shut down in a very short period and were not cleaned out. This has left material in tanks and vessels in the by-products plants and both pipelines. In addition, there is historic material from pre-liquidation days in some tanks. In some areas there is residue remaining in gullies and drainage systems.

## Project Aims and Objectives.

### The Contractor is to remove all Top Tier COMAH materials from the SSI assets listed below (primarily Coal Tar, Coal Tar composites, Benzole and Naphthalene), decontaminating all process equipment to the specified standards.

South Bank Coke Oven by-products plant (SBCO).

Coke Oven Gas Main (COGM).

Heavy Fuel Oil Main and storage tanks (HFO).

Redcar Coke Oven by-products plant (RCO).

## Current Status.

### The STSC site still operates as a Top Tier COMAH site and also needs to continue to meet its obligations within its Environmental Permit: Both are regulated by the Competent Authority.

## Some of the material in the SBCO, RCO and the COGM is pyrophoric and is currently maintained under a nitrogen blanket.

## The approximate inventory of materials is:

SBCO.

  - 4,000T including Coal Tar and distillates, such as Naphthalene, Benzole Oil, Ammonia, Creosote Oil (their liquors and emulsions together with Breeze).

  - 5400t of mixed coal tar, coal and by-product residue

COGM.

  - 5,500T of Naphthalene and other GOG components.

HFO.

  - 150T of heavy fuel oil.

RCO.

  - 6,000T including Coal Tar and distillates, such as Naphthalene, Benzole Oil, Ammonia, Creosote Oil (their liquors and emulsions together with Breeze).

- NB: Redcar Coke Oven also has a live system for the processing of rainwater prior to discharge to the River Tees that is not included in the decontamination project.

## Current risks are managed under the “Keep Safe” activities by the implementation of a range of activities including:

Site Security and Access Control.

Random Drugs and Alcohol testing.

Permit To Work systems for all work on site.

Procedures detailing Control Measures for work – including Risk Assessment and Method Statements (RAMS), Excavation, Working at Height and Electrical Isolations.

Continuous blanket of Nitrogen across the Coke Oven Gas systems (COGM, SBCO and RCO).

Routine inspections by STSC personnel, including scheduled routine inspections by STSC Shift Managers.

Scheduled structural inspections by STSC Integrity Dept. personnel based on Risk Assessed criteria.

All hazardous product storage tanks are situated within sealed areas & provided with tertiary containment.

Internals of vessels, tanks, pipework and sumps are fouled with COG by-products (including COMAH substances) and Pyrophoric material. These substances include, Coal Tar, Benzole & Naphthalene Absorbing Oil, Benzene and Ammonia

Coke Oven by-products operations involved the production, process and transfer of a number of Top Tier COMAH substances plus hazardous & non-hazardous products / substances which pose a risk to the general health of personnel and the environment.

In addition to tanks, vessels and pipelines part of this process and transfer requires the use of gullies and sumps for the collection and distribution of products including Tar, Oils and Liquors.

The abrupt cessation of coke making operations in October 2015 gave insufficient time to shut down the by-product recovery process in a prescribed timely manner.

The legacy of this has resulted in a significant amount of the by-product tanks, vessels and pipelines contents still being present.  An inventory of the substances has been compiled and is monitored by the EHS dept.

There is an ongoing requirement to monitor and maintain the site to prevent a loss of containment, prevent flooding and ensure safe and legal disposal of contaminated surface rainwater.

The solution to reducing the Safety and Environmental controls on the site is the cleaning, removal and safe disposal of all of the COMAH, hazardous and non-Hazardous substances from transfer lines, tanks, vessels, gullies, sumps and bunds.

The HFO line has pigging and electric trace heating stations along its length. However, these have either not been used for several years, or have been vandalised.  The material within the HFO is considered almost solid, or at least of very high viscosity.

Redcar Coke Ovens has some operations (rainwater treatment) which will continue during the project.

## Details of the STSC Procedures that the Contractor will need to comply with are provided in Appendix 6.

## Health & Safety and the Environment:

### Maintaining the Nitrogen Blanket:

Both SBCO and RCO by-product recovery vessels, and the COGM, are currently under a Nitrogen blanket.

The Nitrogen is provided by BOC and is introduced at Redcar Blast Furnace and then into the arterial main, with the COGM providing the distribution system for all areas of site. This distribution system is made up of sections of elevated and underground arterial mains, and branches.  The methodology used for decontamination will need to maintain the Nitrogen supply throughout the decontamination process or implement other suitable control measures.

In the past, arrangements have been made with BOC to provide additional temporary supply of Nitrogen, located at specific fixed tie–in points. There is therefore the means to use temporary supply of Nitrogen.

The COGM transits the site and includes routes that have implications for other operators on site, such as British Steel and the National Rail network.

Access to the COGM can be difficult due to the elevated and underground sections and the fact that areas of the site are remote and are covered with vegetation.

The remainder of the RCO and SBCO by-product recovery vessels are not under a Nitrogen blanket but are periodically purged with Nitrogen.

### Working with Hazardous Substances.

The composition of COGM Wash Solids varies depending on the source of the gas/deposit and also the history of the section of COGM piping in question. The SBCO by-product COG stream plant has had basic process cleaning but has NOT been through Desulphurisation treatment and will therefore have a high Sulphur content.

In all instances the COG deposits, initially coming from the SBCO by-product plant gas stream, will be high in Naphthalene with traces of other organics (Benzene, Toluene, etc.) and relatively low in the heavier compounds (Coal Tar etc.) these deposits would appear like white flakes. The sulphur content is higher and the colour can be yellow or green.

If the COGM pipework is cleaned by “steaming”, the volatile components will be vaporised and the heavier compounds (with higher vaporisation and boiling temperatures) will be left behind. This could result in deposits very low in Naphthalene but high in Sulphur and Coal Tar. Those deposits can appear like black Tar or hard black solids similar to Coal or Coke.

In all instances of working with COG by-products contractors must adhere to all instructions detailed in Material Safety Data Sheets & Control of Substances Hazardous to Health (COSHH) Assessments in the attachments below.

Control Measures, aimed at limiting personal exposure, are used prior to high Pressure Water Jetting taking place; these include a Nitrogen purge of the COGM.

To avoid skin contact the wearing of impermeable protective clothing and gloves is required. Disposable oversuits and PVC coated gloves may be suitable. Proprietary UV barrier creams may be useful as a barrier to prevent skin irritation, particularly in hot, sunny conditions.

Contractors must adhere to Current Occupational Exposure Limits.

To ensure the Occupational Exposure Limit is not exceeded when vapour is generated, adequate ventilation may need to be provided, if necessary, including local exhaust ventilation.

Alternatively, where necessary, suitable respiratory protective equipment must be provided for use by those at risk from inhalation of vapour.

Suitable Protective Clothing and Eye Protection must be worn to prevent skin and eye contact.

# Performance Specification

## Definitions:

### Contents and Arisings.  Contents and Arisings are all waste material generated by the decontamination including:

arising from processing water contaminated during decontamination.

waste material from other processes that the Project Manager instructs the Contractor to treat as Contents and Arisings.

### Process Equipment.  Process Equipment are those components of the process infrastructure that the Contractor is to decontaminate.

### Top Tier COMAH Substances.  Top Tier COMAH substances are those substances found in the Contents and Arisings and Process Equipment that make the STSC site a Top Tier site under the COMAH regulations.

## Decontamination.

### South Bank Coke Oven.  The Contractor is to decontaminate the SBCO.  The SBCO is defined in Appendix 1.  The Project Manager may instruct changes to this definition prior to issuing the Notice to Proceed to Stage Two.

### Coke Oven Gas Main.  The Contractor is to decontaminate the COGM.  The COGM is defined as in Appendix 2. The Project Manager may instruct changes to this definition prior to issuing the Notice to Proceed to Stage Two.

### Heavy Fuel Oil Main. The Contractor is to decontaminate the HFO.  The HFO is defined as in Appendix 3. The Project Manager may instruct changes to this definition prior to issuing the Notice to Proceed to Stage Two.

### Redcar Coke Oven. The Contractor is to decontaminate the RCO.  The RCO is defined as in Appendix 4. The Project Manager may instruct changes to this definition prior to issuing the Notice to Proceed to Stage Two.

### Decontamination of above ground process equipment.  The Contractor is to decontaminate all above ground process equipment removing all Top Tier COMAH substances and cleaning the process equipment to the standard set out in the United Kingdom specifications for iron and steel scrap. As detailed in: https://www.letsrecycle.com/prices/metals/ferrous-metal-prices/ferrous-grades/

### Decontamination of buried process equipment.  The Contractor is to decontaminate all buried process equipment removing all Top Tier COMAH substances and cleaning the process equipment to the standard set out in the United Kingdom specifications for iron and steel scrap unless a strategy for encapsulation of contents and arisings in situ has been instructed by the Project Manager.

### Nitrogen Blanket.  The Contractor is to maintain the integrity of the nitrogen blanket throughout the works unless the Project Manager has approved the removal of the nitrogen blanket from part or all of the works following decontamination.  Application to amend the nitrogen blanket should be made in accordance with Clause 21.

## Contractor Duties and Responsibilities.

## The Contractor will be responsible for

Duties of Principal Designer under the CDM Regulations

Duties Principal Contractor under the CDM Regulations complying with all STSC Procedures as detailed in Appendix 6.

Develop the methodology for cleaning, reprocessing and disposal of contents and arisings in the most cost-effective manor seeking to maximise the opportunity to recycle this material, generating income to offset the cost of the works.

Execute the agreed methodology for cleaning, reprocessing and disposal of contents and arisings

Develop and execute trials to inform future operations to enable innovation, improve safety, environmental management and cost-effectiveness as well as manage risks.

Develop and execute methodology to treat the buried sections of the COGM that meets all environmental and safety standards in the safest and most cost-effective manner.  This could include leaving the pipe in situ.

Carry out the task in a safe manner adhering to all Health & Safety, Environmental regulations

Carry out the task in a safe manner consistent with all STSC Health & Safety, Environmental Systems and Procedures as detailed in Appendix 6.

## Structural Surveys.  The Contractor is responsible to ensuring the structural and gas integrity of the Process Equipment is suitable for the decontamination methodology proposed.  The Contractor is responsible for undertaking any additional surveys that may be required prior to submitting the methodology to acceptance under Clause 21.

## Design of Equipment.  The Process Equipment to be decontaminated is old and in a poor state of repair.  The Contractor is to ensure, wherever possible, that all Equipment (temporary works) is free standing and places no load on the Process Equipment.  In accordance with Clause 23, the Contractor is to submit particulars of the design of all items of Equipment to the Project Manager for acceptance.

## Environmental Surveys.  The Contractor is responsible for undertaking any environmental surveys that may be required to support proposed methodologies prior to submitting the methodology to acceptance under Clause 21.

## Site Security.

### The Contractor is to comply with the STSC Security procedures in Appendix 6.

### In addition, the Contractor is responsible for ensuring the security of the works.

### Where the methodology increases the risk of trespass or theft the Contractor is to include, in the methodology, proposals to mitigate this risk.

## Third Party Agreements.  The COGM passes in close proximity to assets and on land owned by third parties.  The Contractor is responsible to all negotiations associated with the proposed methodologies with third parties and obtaining their authority or agreement to the proposed methodologies prior to submitting the methodology to acceptance under Clause 21.

# Early Contractor Involvement Strategy

## Definition of Stage One.

Stage One of the works will include:

### Coke Oven Gas Main.

#### Stage One is to include decontamination of sections 012, 013, 014, from SBV 2 to SBV 16 exclusive and associated valves and infrastructure of the COGM to the standard specified in Paragraph 2, Performance Specification, of the Works Information.

#### The Project Manager may instruct the Contractor to include or exclude sections of the COGM within Stage One.

#### Assessment of Methodology.  During Stage One the Contractor is to assess the viability and cost effectiveness of proposals to decontaminate the COGM by undertaking planned trials.  Stage One trials are to include trial of proposals to clean the buried sections of the COGM through experimentation on this above ground section.  Prior to commencing each trial, the Contractor is to submit a method statement for the trial to the Project Manager for acceptance in accordance with Clause 21.  The method statement is to include:

Risk Assessment and Method Statement compliant with STSC’s Procedures, Appendix 6, including the of design of all Equipment (temporary works) for the Project Manager’s acceptance, to be issued in accordance with Clause 21.

Fully costed estimate for the trial works priced in accordance with the Pricing Information.

### South Bank Coke Ovens.

#### Stage One is to include decontamination of the following plant items within the SBCO:

Benzol Storage Tank

Effluent Tank No 4

Tar Tanks L & M

#### The Project Manager may instruct the Contractor to include or exclude items of piocess equipment.

#### Assessment of Methodology.  During Stage One the Contractor is to assess the viability and cost effectiveness of proposals to decontaminate both the South Bank and Redcar Coke Ovens by undertaking planned trials.  Prior to commencing each trial, the Contractor is to submit a method statement for the trial to the Project Manager for acceptance in accordance with Clause 21.  The method statement is to include:

Risk Assessment and Method Statement compliant with STSC’s Procedures, Appendix 6, including the of design of all Equipment (temporary works) for the Project Manager’s acceptance, to be issued in accordance with Clause 21.

Fully costed estimate for the trial works priced in accordance with the Pricing Information.

### Heavy Fuel Oil.

#### Stage One does not include any trials on the HFO system.

#### The Project Manager may instruct the Contractor to undertake trials on the HFO system.

#### Assessment of Methodology.  During Stage One the Contractor is to submit a method statement for the decontamination of the HFO, for execution in Stage Two, to the Project Manager for acceptance in accordance with Clause 21.  The method statement is to include:

Risk Assessment and Method Statement compliant with STSC’s Procedures, Appendix 6, including the of design of all Equipment (temporary works) for the Project Manager’s acceptance, to be issued in accordance with Clause 21.

Fully costed estimate for the trial works priced in accordance with the Pricing Information.

### Reprocessing and disposal of Contents and Arisings.

#### Stage One is to include the reprocessing and disposal of all Contents and Arisings generated during this stage.

#### The Project Manager may instruct the Contractor to include waste from other sources in these trials, to stock pile Contents and Arisings on site for Stage 2 or remove the reprocessing and disposal of Contents and Arisings from the contract.

#### Assessment of Methodology.  During Stage One the Contractor is to assess the viability and cost effectiveness of proposals to reprocess and dispose of Contents and Arisings from the Stage One trials.  This may include, but is not limited to desk top studies, reprocessing trials and disposal trials.  Prior to commencing each trial, the Contractor is to submit a method statement for the trial to the Project Manager for acceptance in accordance with Clause 21.  The method statement is to include:

Risk Assessment and Method Statement compliant with STSC’s Procedures, Appendix 6, including the of design of all Equipment (temporary works) for the Project Manager’s acceptance, to be issued in accordance with Clause 21.

Fully costed estimate for the trial works priced in accordance with the Pricing Information.

### Completion of Stage One.  The Stage One Completion Date has been based on an estimate of the time required to complete the Stage One works using traditional techniques.  The Project Manager may instruct a change to this date, this would be a compensation event under Clause 60.1 (4).

### Authority of the Official Receiver. The Process Equipment to be decontaminated belongs to the Official Receiver who will be kept informed of the Decontamination Works.  Where the Contractor’s methodology could impact the Official Receiver’s asset there may be a requirement to obtain the Official Receiver’s approval for that methodology.  The Contractor is to cooperate with all reasonable requirements and allow reasonable time for the Employer is to obtain approvals for the Contractor’s methodologies from the Official Receiver.

## Definition of Stage Two.

Stage Two is the decontamination of the remainder of the works including, but not limited to:

### Coke Oven Gas Main.

#### Stage Two is to include decontamination of all sections of the COGM, as specified in Appendix 1, not decontaminated in Stage One.

#### Prior to proceeding to Stage Two, the Project Manager may instruct the Contractor to include or exclude sections of the COGM.

### South Bank and Redcar Coke Ovens.

#### Stage Two is to include decontamination of the remainder of the SBCO, as specified in Appendix 2, and the whole of the RCO, as specified in Appendix 4.

#### Prior to proceeding to Stage Two the Project Manager may instruct the Contractor to include or exclude any aspects of the SBCO or RCO.

### Heavy Fuel Oil.

#### Stage Two includes the decontamination of the HFO system, as specified in Appendix 3.

#### Prior to proceeding to Stage Two, the Project Manager may instruct the Contractor to include or exclude any parts of the HFO system.

### Reprocessing and disposal of Contents and Arisings.

#### Stage Two is to include the reprocessing and disposal of all Contents and Arisings generated during this stage.

#### Prior to proceeding to Stage Two, the Project Manager may instruct the Contractor to include Contents and Arisings from other sources or remove the reprocessing and disposal Contents and Arisings out of the contract.

## Proposals for Stage Two.

### During Stage Two the Contractor is to decontaminate the remainder of the Process Equipment, as defined in Appendices 1 to 4, to the standard specified in Performance Specification, of the Works Information.  The Contractor’s design proposals for Stage Two are to follow the methodologies trialled in Stage One and accepted by the Project Manager.

### The Contractor’s design proposals are to include a fully resourced programme that supports the Contractor’s forecast of the total Defined Cost.  This programme is to comply with the definition of the programme specified in Appendix 5 and is to be submitted under Clause 31.

### The Contractor’s design proposals are to be issued to the Project Manager no later than twice the period for reply prior to Completion Date for Stage One.

### Should the Project Manager or the Contractor propose a revised methodology aimed at further improving Value for Money the Contractor is to submit a method statement for a trial of the revised methodology to the Project Manager for acceptance in accordance with Clause 21.  The method statement is to include:

Risk Assessment and Method Statement compliant with STSC’s Procedures, Appendix 6, including the of design of all Equipment (temporary works) for the Project Manager’s acceptance, to be issued in accordance with Clause 21.

Fully costed estimate for the trial works priced in accordance with the Pricing Information.

## Performance Requirements.

### Through the Stage One trials; the Contractor is to demonstrate to the Project Manager’s satisfaction that the methodologies proposed for Stage Two will achieve the standards for decontamination defined in the Works Information.

### Through the Stage One trials; the Contractor is to demonstrate to the Project Manager’s satisfaction that the methodologies proposed for Stage Two will optimise the value of all contents and arisings.

### The Contractor’s design proposals are to be issued to the Project Manager no later than twice the period for reply prior to the Completion Date for Stage One.

# Pricing Information / Activity Schedule

## STSC SSI Asset Value

### It should be noted that ideally, the chosen method of decontamination should not affect the value of the Assets – neither reducing or enhancing this value.  If however, the methods proposed will likely result in such a change, for example to reduce overall risk or cost, then this should be made clear at the return of Bids stage as approval will need to be sought from the Official Receiver.

## The Pricing Information

### The elements pre-populated in the Pricing Information, are indicative only. Tenderers may amend the information to suit his business model. The Tenderer may insert new elements / rows but may not otherwise amend the format without approval from the Employer.

### Tenderers are to complete the Pricing Information by entering information in the yellow highlighted cells.

### Tenderers shall complete the Pricing Information with all of the pricing information required to carry out and complete the Decontamination Project.

### However, Tenderers shall note that the Pricing Scenarios, which will be the basis of the comparison of the prices submitted at Tender stage, must be populated with the prices provided in the Pricing Information and must be returned full and complete.

### Tenderers shall use the Pricing Information to calculate the prices shown in the activity schedules for Stage One and Stage Two.

## Stage One

### Tenderers are to submit an activity schedule for Stage One with their tenders. This will be a document headed ‘activity schedule’ and will comprise a list of activities with an amount entered against each activity.  The activities may be of the Tenderers own choosing but activity descriptions must be clear and complete so that the work included in each can be identiﬁed and the completion of each activity easily recognised.

### The Tenderer shall use the Pricing Information to calculate the Prices.

### The format required for the activity schedule shall be as sheets, “activity schedule – summary” and “activity schedule – detail” in the Pricing Information. The pre-populated information shown in these sheets is indicative of the works to be carried out in Stage One. The Tenderer shall add, omit or amend any items as the Tenderer deems appropriate.

### The Tenderer can insert new rows against the items in sheet; activity schedule – detail in order that the item sub-totals are whole and complete. The completed activity schedule shall include all of the works required to complete Stage One.

## Stage Two

### The Contractor will be required to provide the Assessment of the Prices for Stage Two by the dates for submission stated in the contract.

### The format required for the activity schedule shall be as sheets, “activity schedule – summary” and “activity schedule – detail” in the Pricing Information.

### The activities may be of the Contractor’s own choosing, but activity descriptions must be clear and complete so that the work included in each can be identiﬁed and the completion of each activity easily recognised.

### The Contractor shall use the Pricing Information to calculate the Prices.

### The Contractor will be required to provide a detailed build up to all of the activities in the activity schedule for Stage Two using the “activity schedule – detail” in the Pricing Information. This information is carried forward to and summarised in the sheet activity schedule – summary”.

## Treatment of Discrepancies

### The tenderer is responsible for ensuring that extension, sub-totals and totals are correct, arithmetically or otherwise. Errors, or discrepancies, identified in the Pricing Information, Activity Schedule or Pricing Scenarios cannot be amended once the Tender has been submitted.

## Contract Programme

### The Tenderer shall note also the requirement of clause 31.4 of the conditions of contract about the relationship between the activity schedule and the programme.

# Approvals and Consents

## The Contractor is to obtain all permits, statuary approvals and consents for his works.

## The Employer is to obtain approvals for the Contractor’s methodologies from the Official Receiver.

# Project Management Strategy

## The Contractor is to follow the Project Management Strategy in Appendix 5.

# Compliance with STSC Procedures

## The Contractor is to comply with all STSC Procedures as detailed in Appendix 6.

## Where the Contractor’s methodology requires a departure from the STSC Procedures the Contractor is to apply for that departure in accordance with the STSC Procedures and obtain the relevant approvals prior to issuing the methodology to the Project Manager for acceptance under Clause 21.

# Performance Bond

## The Contractor is to provide a Performance Bond in the sum set out in the Contract Data and in the form set out in Appendix 7.

# Further Information for Contractors

## Grangetown Training and Employment Hub.  Redcar and Cleveland Grangetown Training and Employment Hub model is delivered through a partnership of Jobcentre Plus, Redcar and Cleveland Borough Council, Coast and Country Housing, Work Programme providers, training providers and individual projects such as the Youth Engagement Initiative and the Tees Valley Routes to Work Project.  Many employers involved in local activity engage with the centre as it helps them deliver any commitments or agreed targets they have to employ local labour as well as supporting them to fill vacancies with appropriately skilled workers.  Further information can be found at: https://www.facebook.com/.../Grangetown-Training-and-Employment-Hub-175384974

## Inspiring Our Future.  The Tees Valley Combined Authority (TVCA) strategy “Inspiring Our Future”, outlines the key issues and priorities within Education, Employment and Skills. It will look to raise skills levels to help attract new businesses to the area and provide support to local people to access these jobs.  Further information can be found at: https://teesvalley-ca.gov.uk/inspiring-future-ambitious-vision-launched-transform-education-employment-skills/

# Appendices

South Bank Coke Ovens

Coke Ovens Gas Main

Heavy Fuel Oil

Redcar Coke Ovens

Project Management Strategy

Compliance with STSC Procedures

Performance Bond