# Appendix 5 – Project Management Strategy

## Introduction.

### This appendix provides details of how the contract will be managed and administered.

### The STSC Decontamination Project is to be delivered under an NEC3 ECC Option C contract.  The contract defines the outline processes for contract management and takes precedence over the procedures described in this Project Management Strategy.

## Project Communications.

### Communication Types. Open and free communication is key to successful collaborative relationships.  Project participants are to seek and utilise the most appropriate means of communication to achieve a shared understanding.  Communications fall into 3 general categories:

Unrecorded Communications.  Unrecorded communications are anything from a telephone call to an email and will include conversations within meetings that are not recorded in the minutes.  (For the purpose of this project, MS Outlook email is considered as an unrecorded communication as it is not published on or auditable through the Internet Based Collaborative (IBC) system, see Paragraph 3, below.)

Recorded Communications.  Recorded communications are communications for which a record is produced.  These include minutes of meetings and all formal contract communications.

Contract Communications.  Contract communications are communications required under the terms of the contract.  All contract communication is to be through the IBC system.  Any contract communication recorded via other media will not be contractually recognised.

## Internet Based Collaborative (IBC) system.

### The Contractor shall propose an Internet Based Collaborative (IBC) system for approval by the Project Manager.

### The Contractor will provide an IBC system that will meet, but not be limited to, the individual requirements given below:

The IBC is to be accessible via an internet log-in function without the requirement to install additional addins etc.

The IBC is to provide a document management system that ensures all parties have a shared view of the latest version of all documents, and an audit trail of previous versions.

The IBC document management system is to include the ability to download documents, mark-up/ edit and upload amended documents with auditable tracked changes.

The IBC is to enable the collation of the Health and Safety File documentation

The IBC is to provide a conversation management system that allows all parties to have a shared understanding of the current state of all issues, where this conversation sits with regard to contract processes and an audit trail of the conversation.

The IBC is to provide a contract management system that reflects all processes set out in this contract, NEC3 ECC Option C with Z clauses, including the management of risk through early warnings and risk reduction meetings.

The IBC is to provide each user with a dashboard detailing all outstanding actions and their timeframe for Completion.

The IBC is to provide a reporting capability to allow the user to report an any aspects of the above.

The IBC is to include a comprehensive search facility

The IBC is to be GDPR compliant and secure all data in the accordance with UK Government Policies.

The IBC is to have unlimited storage.

The IBC is to provide unlimited users/organisation access.

The Contractor is to provide the Employer with a fully searchable and auditable record of all communications from the IBC in a format that can be installed on the Employer’s network without proprietary software or legacy fees to maintain access to the data.

### The Contractor shall provide on-site training prior to the IBC system going live. Provision should also be made for a hard copy user manual, on-line training and refresher/ new starter training.

### The Contractor is to provide a business continuity strategy for the IBC System that includes, 24 hour help desk support.  In the event that any issues cause the system to be inoperable, these should be resolved within 24 hours and alternative access to stored data should be made available immediately.

## Programme.

### The following paragraphs define the programme, as included in the Contract Data or submitted for acceptance by the Project Manager under Clause 31 or Clause 32.  Failure to meet these requirements shall be grounds for not accepting the programme in that it does not comply with the Works Information (Clause 31.3 bullet 4).

### Programme – General.

#### The programme is to demonstrate that the Contractor can deliver the works in an economic, realistic & practical way within the constraints of the contract.

#### The Contractor shall upon request from the Project Manager provide any additional information as may be reasonably required to enable him to interpret, evaluate and accept the programme as being realistic and practical.

#### If the Contractor is unclear or unsure as to the practical fulfilment of any of the requirements within this section, then the Contractor shall discuss these with the Project Manager prior to the submission of the programme for acceptance.

#### The programme shall be produced using Primavera P6 software, unless otherwise agreed with the Project Manager.

#### The programme is required to be fully resourced in and reflect the Activity Schedule.

#### The programme shall be fully logic linked and be capable of critical path analysis. Each activity shall have sufficient & appropriate logic links so as to describe the dependencies between each work activities. Every activity (excluding the last) shall have at least one appropriate successor logic link.

#### The programme is to include a month by month cashflow that is tied to the Activity Schedule.

#### The programme includes the Quality Plan, see Paragraph 7, below.

#### A revised programme is to be submitted with each revised forecast of total Defined Cost.

#### Programme – Structure.

#### The Work Breakdown Structure, WBS, activity IDs, activity codes & values, calendars and such like shall be developed, named and organised in a logical and concise fashion.

#### Each activity in the programme (including milestones) shall bear a single description, which relates to a unique Activity ID.

#### Each activity description shall be concise and clear as to its meaning and work scope. The Contractor shall avoid the use of activity descriptions that are general or ambiguous in nature. If it is not possible to sufficiently describe an activity within the space provided within the description field of the programme, then further explanation shall be made within the notes section of the software.

#### Within the scheduling software, the correct logic link type shall be used between the various activity types.

#### The use of activity constraints shall be avoided. Where any type of activity constraint is used, details as to the nature and reason for it shall be given.

#### The programme shall be prepared using a planning unit of days.

#### All activities that describe work shall have the following attributes, unless otherwise agreed with the Project Manager:

Activity Type: Task Dependant

Duration Type: Fixed duration & units

% complete Type: Physical

#### Prior to the submission of any programme for acceptance, the Contractor shall conduct a scheduling review to ensure that none of the following exist:

Out-of-sequence activities

Activities with Actual Dates > Data Date

Milestone Activities with invalid relationships

Activities with unsatisfied constraints

Activities with unsatisfied relationships

Activities with external dates

### The Programme – Content.

#### The programme shall include sufficient activities so as to fully describe the operations & processes to be undertaken to Provide the Works.

#### In addition to the requirements of clause 31.2 of the conditions of contract, the programme shall include as a minimum, but not limited to, activities, as and if they relate to the Contractor’s work, to describe the following:

The preparation, submission and acceptance of design information (including temporary works design)

The preparation, submission and acceptance of designs

The preparation and award of supplier contracts

Submission of samples and allowance for consideration

Ordering, manufacturing & supply of key Materials and items of equipment

Preparation, submission and processing of documents requiring approval before construction can proceed.

Site mobilisation

Construction & installation, including temporary works of a material nature

Contractor & Statutory inspections, witness testing, acceptances and sign offs

#### Each appropriate activity shall be loaded with resources (Plant, labour and key quantities). The Contractor shall propose, discuss and agree with the Project Manager the approach to resourcing and costing the programme before the submission of the first programme.

#### Activities describing the work/ operation to be undertaken by the Project Manager, or Others, shall be clearly identified by way of the activity description and the use of appropriate coding. Each submitted programme shall include a separate PDF copy extract of all such activities.

#### The programme shall clearly identify milestones representing significant dates at the start of the programme and organised in a clear and logical way so as to assist the reader’s understanding.

#### Significant dates may include:

Starting date, access dates, Key Dates, Completion Date

Dates of planned Completion of Key and Completion Dates

Dates that are significant to the monitoring of the progress of a group of activities/ section of works

Significant dates the Contractor believes the Project Manager should be aware of

Other dates as later requested by the Project Manager

Dates of any isolations or STSC permits to work required

### Submission & Presentation of the Programme.

#### The programme shall be submitted in electronic format.  The electronic copy of the programme shall be taken to mean the programme files associated with the planning software package used.

#### The programme shall be submitted to the Project Manager via the IBC system.

#### The Contractor shall upon request establish any layouts and filters within the electronic programme that the Project Manager requires.

### Revising the Programme.

#### Prior to issuing a revised programme the Contractor and Supervisor are to undertake a joint review of the works to agree:

The % complete for each activity as be a reflection of the actual quantity of work scope/ deliverable complete against the current forecast of quantity of work scope/ deliverable for the activity.

The remaining duration for each activity shall be a reflection of the estimated duration required at the time of the revision to complete the activity, taking account of past performance.

#### Where the rate of progress of activities has affected the timing of the remaining works such that it will prevent the achievement of one or more of the significant date milestones, then the Contractor shall, within the programme, provide details how it intends to recover the delay.

#### Where planned activities have started in an order or sequence different from that planned, the logic contained within the programme shall be corrected to illustrate the sequence actually followed.

#### If an activity is no longer required, it shall be retired within the programme but not deleted. Its unique ID number shall not be used again to identify another activity in any future. Retired activities shall have logic removed, duration set to zero and appropriately coded.

#### The revised programme is to include a revision report in which the Contractor is to clearly identify any changes and the reasons including, but not limited to, the:

Addition / retirement of activities

Alteration of activity descriptions

Alteration of activity durations

Alteration to the planned logic and sequence of remaining works.

### Where additional activities are included in the programme as a result of compensation events, these shall be suitably identified within the programme and described in the revision report.  The programme is to distinguish between notified and implemented compensation events.

## Meeting Schedule.

### The Contractor is to agree a meeting schedule with the Project Manager this is to include, but is not limited to:

| Meeting Title | Items for Discussion | Frequency | Attendance |
| --- | --- | --- | --- |
| Principals’ Meeting | General Project Progress Health & Safety Collaborative relationships | Quarterly | Chair Project Board Project Director* Contractor’s Board Director Contractor’s PM Project Manager (Subcontractor Director) |
| Risk Review Meetings | Review of the Risk Register Other contract administration issues | Monthly | Project Manager* Project Manager’s commercial lead Contractor’s PM Contractor’s commercial lead (Planners) |
| Progress | Monthly progress meeting to cover all aspects of the project | Monthly | Employer’s representatives Project Manager* Supervisor (Project Manager’s team) Contractor’s PM (Contractor’s team) |
| Health and Safety Review | Monthly review of Health and Safety | Monthly | Project Manager* Employer’s H&S Lead Supervisor Contractor’s PM Contractor’s H&S Lead |
| Health and Safety Update | Weekly communication of changing Health and Safety risks | Weekly | Contractor’s H&S Lead* Supervisor All Subcontractors (Employer’s H&S Lead) |
| 3 Month Look Ahead | Planning meeting to coordinate the level of planning information required by all parties to ensure effective preparation for new activities | Monthly | Contractor’s PM* Project Manager Supervisor Planners |
| 3 Week Look Ahead | Coordination of all impending works. | Weekly | Contractor’s Site Manager* Supervisor Contractor’s Section Engineers (Subcontractors) |
| Contractor’s Design | Review of all outstanding Contractor’s design issues | Weekly in Stage One | Contractor’s PM* Project Manager Supervisor Planners |

*Meeting Chair	(Optional)

## Progress reporting.

### The Contractor shall submit a progress report a minimum of 24 and maximum of 48 hours prior to each Progress Meeting. The Contractor is to agree the format of the progress report with the Project Manager.

### The progress report should record the current status of the project at the date of the report against what the position should have been.

### It should highlight any issues, decisions required or taken and predict the final outcome of the project.

## Quality management.

### The Contractor shall institute and operate a quality management system complying with BS EN ISO 9001. The quality management system shall be described in a contract specific Quality Management Plan that shall be submitted to the Project Manager for its acceptance in accordance with Clause 21 and constitutes a part of the initial programme to be submitted under Clause 31.

### The Quality Management Plan should detail the procedures, tools and techniques which will be put into place by the Contractor to ensure:

Quality assurance

Quality control

Continual improvement

### The Quality Management Plan shall cover the following items:

The Contractor’s organisation and management including a quality statement.

The Contractor’s method statements and construction procedures.

The Contractor’s construction quality control.

Subcontractors and suppliers Quality Plans.

## Services and other things to be provided.

### Site meeting room.

#### The Contractor is required to provide a site establishment which includes a meeting room for use during project meetings and by the Project Manager, equipped with the following items:

Conference table of a suitable size to accommodate 12 people

12 nr. Chairs

Whiteboard with assorted colour markers

A minimum of 6 Power sockets

### Consumables.

#### The Contractor shall provide a continuous supply of the following consumable items:

protective goggles

ear plugs

disposable dust masks

cotton overalls

disposable latex gloves

general purpose cotton gloves

## Completion.

### Completion is when the Contractor has completed all of the work specified in the following Appendices of the Works Information:

- Appendix 1. South Bank Coke Ovens

- Appendix 2. Coke Ovens Gas Main

- Appendix 3. Heavy Fuel Oil

- Appendix 4. Redcar Coke Ovens