# KEY PERFORMANCE INDICATORS (KPI’s)

1.	The following Key Performance Indicators 1-3 (KPIs) shall be applied to all work undertaken against this Contract in order to determine the performance of the Contractor during each Quarter report.  Each KPI consists of a number of individual Performance Indicators (PIs) which are measured quarterly.

2.	The PIs are marked Red, Amber or Green against relevant criteria, listed at annex B, which then informs the overall KPI score.

3.	For each KPI defined, the Contractor shall be expected to achieve a ‘Green’ level of performance. The level of performance required to achieve a ‘Green’ level varies for each KPI and is detailed at Annex B.

4.	The minimum acceptable level of performance is ‘Amber’ on each KPI. Should any KPI performance level fall below ‘Amber’ and achieve a ‘Red’ level of performance, the 6% performance element of the milestone payment shall be retained by the authority.  If three Performance Indicators under KPI 1 or two PIs within KPIs 2 and 3 separately are “Amber”, this KPI shall be deemed Red. In these circumstances, the Contractor shall be eligible to claim payment for the core element of the milestone payment only.

5.	The performance element will be retained by the Authority until the next Quarterly Progress Report/Meeting. Should performance levels have reached an acceptable level on each KPI at the following quarter; the performance element will be released to the contractor along with the quarterly milestone for that period. 

6.	In the event that the level of performance has not been acceptable on each KPI (i.e. ‘Red’ levels of performance appear in subsequent quarters), the contractor will forfeit any right to the performance element retained in the earlier quarter. The 6% performance element will also be retained from the milestone payment for the current quarter, pending review at the subsequent Quarterly Progress Report/Meeting.

The Contractor shall provide a Quarterly Report detailing performance against the KPIs and including any supporting information, mitigating circumstances and a calculation of any retailed elements.  The report shall be submitted to the Authority for validation a minimum of ten working days before each quarterly progress review meeting. The performance level will then be discussed and agreed at the progress meeting should there be any dispute on the level achieved.

7.	The performance element retained will be calculated based on the greater of 6% of the relevant quarterly milestone payment or 6% of the pro-rated milestone payment instalments, assuming an even distribution over each quarter.

8.	The Contractor shall produce and supply to the Authority quarterly Performance and Progress Reports giving details of progress of Core and Non-Core activities.

9.	The Contractor shall maintain project data.  The Contractor shall issue Progress Reports to the Authority quarterly and ten working days prior to each Progress Meeting.  The APM and their project team will review the report and respond within five working days.  A final version of the report is to be provided to the Authority no later than two working days before the Progress Meeting. The Contractor shall maintain a log to include all communications (such as telephone calls and emails) and have the log available for review in the Progress Meetings and reports.

10.	The Contractor shall ensure that all Project meetings, Progress Report and Project Management Plans are conducted in accordance with the Contract.  If the Contractor fails to perform in his responsibility the Authority reserves, the right to withhold any payment for delivery against any item until satisfactory performance resumes

| Key Performance Indicator |  |  |  |
| --- | --- | --- | --- |
| KPI Number |  | 1 |  |
| Service Area |  | Delivery of the Core Service |  |
| Measurement Criteria |  | PI 1.1 Quarterly Progress Documentation PI 1.2 Technical Responsiveness PI 1.3 Safety PI 1.4 Security |  |
| Who Reports? |  | The Contractor |  |
| Reporting Frequency |  | Quarterly |  |
| Performance Bands |  |  |  |
| Band | Performance Levels |  | % Retention |
| GREEN | 3 or above PIs are marked Green |  | NIL |
| AMBER | 2 or below are marked Amber |  | NIL |
| RED | Red scored against any PI or 3 or above are Amber |  | 6% |

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 1.1 |
| PI Descriptor |  | Delivery of Quarterly Performance Documentation |
| Service Area |  | Delivery of Core Service |
| Description |  | Delivery of full Quarterly Performance Documentation in accordance with the timescales and standards described in Annex A – Section 2.1(k) |
| Rationale |  | As in SOW |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Quarterly |
| Reporting Frequency |  | Quarterly |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | Documents delivered in accordance with Requirement 5k |  |
| RED | Documents not delivered in accordance with Requirement 5k |  |

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 1.2 |
| PI Descriptor |  | Technical Responsiveness |
| Service Area |  | Core Support |
| Description |  | Contractor report of responsiveness to Technical Queries and S2022s. MOD assessment of responsiveness. In accordance with the timescales and standards described in Annex A – Section 2.1(b) |
| Rationale |  | As in SOW |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Quarterly |
| Reporting Frequency |  | Quarterly |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | =>98% of responses acknowledged and closed within four working days |  |
| AMBER | 95 to 97% of responses acknowledged and closed within four working days |  |
| RED | <95% of responses acknowledged and closed within four working days |  |

Example:

- A call arrive at 10:00 Monday. It is to be acknowledge within 24 hours (by Tuesday 10:00).

- The call is acknowledged at 14:00 Monday.  The contractor now has three working days to respond therefore a final response is required by 14:00 Thursday.

Calculation example:

- 38 calls in a quarter

- 36 calls are acknowledged and responded to within the required timeframe

- 2 are not

Percentage calculation is: 36/38 x 100 = 94.7% rounded up to 95% = AMBER

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 1.3 |
| PI Descriptor |  | Safety |
| Service Area |  | Core Support |
| Description |  | Completion of activities as described in Annex A – Section 2.1(c) |
| Rationale |  | As in SOW |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Annual |
| Reporting Frequency |  | Annual |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | Activities against requirement rationale satisfactory. |  |
| RED | Activities against requirement rationale unsatisfactory. |  |

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 1.4 |
| PI Descriptor |  | Security |
| Service Area |  | Core Support |
| Description |  | Completion of activities as described in Annex A – Section 2.1 (d) |
| Rationale |  | As in SOW |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Quarterly (Annual for SWG) |
| Reporting Frequency |  | Quarterly |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | Activities against requirement rationale satisfactory. |  |
| RED | Activities against requirement rationale unsatisfactory. |  |

| Key Performance Indicator |  |  |  |
| --- | --- | --- | --- |
| KPI Number |  | 2 |  |
| Service Area |  | Non-Core Tasking |  |
| Measurement Criteria |  | PI 2.1 Proposed TAF PI 2.2 Performance against Plan |  |
| Who Reports? |  | The Contractor |  |
| Reporting Frequency |  | Quarterly |  |
| Performance Bands |  |  |  |
| Band | Performance Levels |  | % Retention |
| GREEN | All PI’s are marked Green |  | NIL |
| AMBER | Amber scored against any one PI |  | 0% |
| RED | Red scored against any one PI, or Amber scored against both PI’s (see Reporting and KPI section of SOR) |  | 6% |

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 2.1 |
| PI Descriptor |  | Proposed TAF |
| Service Area |  | Non-Core Tasking |
| Description |  | Completion of activities as described under Condition 13.9 of the Contract. |
| Rationale |  | See Condition 13 |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Quarterly |
| Reporting Frequency |  | Quarterly |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | ≥95% of TAF Part B delivered on time |  |
| AMBER | 90% to 94% of TAF Part B delivered on time |  |
| RED | ≤90% of TAF Part B delivered on time |  |

Example:

- Over the quarter the APM sends out 30 TAF part A’s to the contractor.  The contractor receives these and sends back costed proposals (completed TAF Part B’s) within ten working days.  Within the quarter 29 costed proposals are received in time and to the requred standards.  The calculation is:

    - 29/30 x 100 = 96.6%, rounded up to 97% which equals GREEN

Example:

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 2.2 |
| PI Descriptor |  | Performance against Plan |
| Service Area |  | Non-Core Tasking |
| Description |  | Completion of activities as described under Condition 13 of the Contract. This shall exclude the provision of spares and repaired items. |
| Rationale |  | See Condition 13 |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Quarterly |
| Reporting Frequency |  | Quarterly |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | 100% of tasks completed on time and within scope |  |
| AMBER | 90% to 99% of tasks completed on time and within scope |  |
| RED | ≤90% of tasks completed on time and within scope |  |

- 83 tasks are rased within the quarter.  Each task has Price, Time and Performance targets agreed with the APM.

- 72 are completed within the required parameters, 11 fail to meet the required targets, the calculation is:

72/83 x 100 = 86.7%, rounded up to 87 which equals RED

| Key Performance Indicator |  |  |  |
| --- | --- | --- | --- |
| KPI Number |  | 3 |  |
| KPI Descriptor |  | Management of Inventory |  |
| Measurement Criteria |  | PI 3.1 Provision of Repair Quotations PI 3.2 Delivery of Spares and Repaired items |  |
| Who Reports? |  | The Contractor |  |
| Reporting Frequency |  | Quarterly |  |
| Performance Bands |  |  |  |
| Band | Performance Levels |  | % Retention |
| GREEN | All PIs are marked Green |  | NIL |
| AMBER | Amber scored against any PI |  | NIL |
| RED | Red scored against any PI, or Amber scored against both PI’s |  | 6% |

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 3.1 |
| PI Descriptor |  | Provision of Repair Quotations |
| Service Area |  | Management of Inventory |
| Description |  | Performance for Provision of Repaired items. |
| Rationale |  | As directed under Condition 13 (Tasking) |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Quarterly |
| Reporting Frequency |  | Quarterly |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | ≥ 95% of Quotes received on time |  |
| AMBER | 90% to 94% of Quotes received on time |  |
| RED | <90% of Quotes received on time |  |

| Performance Indicator |  |  |
| --- | --- | --- |
| PI Number |  | 3.2 |
| PI Descriptor |  | Delivery of Spares and Repaired Items |
| Service Area |  | Management of Inventory |
| Description |  | Performance for Provision of Spares and Items Repaired by the Contractor. |
| Rationale |  | As directed under Condition 13 (Tasking) |
| Who Reports? |  | The Contractor |
| Monitoring Frequency |  | Quarterly |
| Reporting Frequency |  | Quarterly |
| Performance Bands |  |  |
| Band | Performance Level |  |
| GREEN | ≥95% of Spares and Repairs delivered on time |  |
| AMBER | 90% to 94% of Spares and Repairs delivered on time |  |
| RED | < 90% of Spares and Repairs delivered on time |  |