## Title Sheet
Car Park, Reliance House, Dursley
New Car Park
2018-06-12

## Summary
| Car Park, Reliance House, Dursley |  |  | Date
| Dursley Town Council |  |  | Valuation | No.
| New Car Park |  |  | P Ending | Date
|  |  | Total | % Complete | Total Claimed | Client Comments | Contractor Comments
1 | Car Park and Drainage Works |  | 3500 | 0% | 0
X. | Preliminaries |  | 0 | 0% | 0
|  | Sub Total | 3500 | 0% | 0
|  | OH & P | 0% | - | 0%
|  | Total | 3500 | 0% | 0
All prices are excluding VAT
Less Previously Paid
0
Total Due this Valuation
0
CONTRACTOR LOGO/HEADER

## 1. Works
Car Park, Reliance House, Dursley | [5 empty] | Valuation | No.
Dursley Town Council | [5 empty] | P Ending | Date
|  | Qty | Unit | Rate | Total | % Comp | Total Claimed | Client Comments | ADCMS Comments
Section 1
All tendering contractors should take the opportunity to view the site and any access restrictions
Contractors should be aware of the existing services running through the site (see tender drawings) during excavations
Contract is to maintain the existing storm water drainage from SW01
Drainage Works
S1/1/A | Allow to break out and remove existing storm and foul drainage + associated manholes and gullies as detailed, seal ends as required including excavation and backfill with well compacted material | 97 | m | 0 | 0
| 300mm Dia HDPE pipe with granular surround class S including excavation not exceeding 2.0m deep, backfill and cart away | 1 | m | 0 | 0
| 300mm Dia HDPE pipe with granular surround class S including excavation not exceeding 1.5m deep, backfill and cart away | 11 | m | 0 | 0
| 150mm Dia HDPE pipe with granular surround class S including excavation not exceeding 1.25m deep, backfill and cart away | 17 | m | 0 | 0
| 150mm Dia HDPE pipe with granular surround class S including excavation not exceeding 1.0m deep, backfill and cart away | 30 | m | 0 | 0
| Extra over excavations for working around, adjacent or across existing services, encountered during excavations; HAND DIG any depth - APPROXIMATE QUANTITY | 59 | m | 0 | 0
Extra over breaking out obstructions encountered during excavations at any depth - APPROXIMATE QUANTITY
| Brickwork | 10 | m3 | 0 | 0
| Plain Concrete | 10 | m3 | 0 | 0
| Reinforced Concrete | 10 | m3 | 0 | 0
| Rock | 10 | m3 | 0 | 0
| Allowance for dealing with surface or ground water encountered during excavation works - PROVISIONAL | 1 | item | 2000 | 2000
| Precast trapped road gully with grating and frame with reinforcement concrete base, concrete surround including excavation and cart away | 3 | nr | 0 | 0
| Aco multidrain monoblock channel section with tarmac circulation areas with 200mm thick concrete base and surround including excavation and cart away | 12 | m | 0 | 0
| Trapped outlet from aco drain as required | 1 | nr | 0 | 0
| Allow for general works in protection of existing services and drains as detailed on drawings | 1 | item | 0 | 0
| 1200mm Dia Precast concrete ring manhole chamber with 225mm concrete base, 150mm concrete surround, precast concrete top with 600 x 600 opening with 3 No courses class B engineered brickwork to receive D400 grade manhole cover and frame including excavation not exceeding 2.0m deep, cart away as required and backfill (S1) | 1 | nr | 0 | 0
| 1200mm Dia Precast concrete ring manhole chamber with 225mm concrete base, 150mm concrete surround, precast concrete top with 600 x 600 opening with 3 No courses class B engineered brickwork to receive D400 grade manhole cover and frame including excavation not exceeding 1.5m deep, cart away as required and backfill (S2) | 1 | nr | 0 | 0
| 1200mm Dia concrete manhole formed with concrete grade 3150mm surround and 225mm base mounting blocks including hydrobrake system concrete cover with 600 x 600 opening brickwork support to D400 cover and frame including excavation not exceeding 1.25m deep, cart away as required and backfill (S3) | 1 | nr | 0 | 0
| 1200 Dia concrete manhole formed in grade 3 concrete, base 225mm thick concrete surround 150mm thick with concrete cover with 600 x 600 opening, brickwork to support D400 cover and frame including excavation not exceeding 1.25m deep, cart away as required (S4) & (S6) | 2 | nr | 0 | 0
| Extra over to install a nonreturn valve to prevent foul flowsbacking up into proposed on-site storm drain network (S4) | 1 | nr | 0 | 0
| Allow to connect new drainage to existing 225m dia to combined water system as required (S5) | 1 | item | 0 | 0
| Allow to remove existing manhole cover SW01, SW02 and FW02 and replace with new D400 class cover and frame | 1 | nr | 0 | 0
| Allow to supply and install attenuation tank 10.0m x 8.5m x 0.5m deep with 300mm perforated ppe pipe in 1m wide gravel strip, including excavation not exceeding 1.5m deep and cart away; wrapped in geotextile membrane in accordance with manufacturers recommendations | 1 | item | 0 | 0
New Car Park Works
| Allow to remove all remaining vegetation around the existing building; dispose off site | 1 | item | 0 | 0
| Allow to break out and remove existing low level walls and planters including any associated foundations following demolition of existing building | 1 | item | 0 | 0
| Allow to break out and remove remaining pcc kerbs and associated foundations | 1 | item | 0 | 0
| Excavate to reduce levels; not exceeding 250mm thickness | 11 | m3 | 0 | 0
| Cart away spoil arising off site | 11 | m3 | 0 | 0
| Level and compact base of excavations | 49 | m2 | 0 | 0
| Tarmac surface course 20mm thick; to footpaths | 49 | m2 | 0 | 0
| Binder course of tarmac 45mm thick; to footpaths | 49 | m2 | 0 | 0
| Excavate to reduce levels as required; not exceeding 500mm average depth | 290 | m3 | 0 | 0
| Cart away spoil arising off site | 290 | m3 | 0 | 0
| Level and compact base of excavations | 839 | m2 | 0 | 0
| Tarmac surface course 30mm thick | 839 | m2 | 0 | 0
| Tarmac binder course 80mm thick | 839 | m2 | 0 | 0
| Imported granular material; type 1; 150mm thickness well compacted | 8 | m3 | 0 | 0
| Imported granular material; type 1; 250mm thickness well compacted | 210 | m3 | 0 | 0
| Allow to excavate crushed material (6F2) from stockpiles on site use to back fill softspots and make up levels; all material to be well compacted in layers not exceeding 150mm thickness | 525 | m3 | 0 | 0
| Remove remaining un-used crushed stone (6F2) from site - APPROXIMATE QUANTITY | 50 | m3 | 0 | 0
| Allow for general preparation work to existing car park areas including any repairs ready to receive new tarmac surfacing | 645 | m2 | 0 | 0
| Apply bitumen tack coat to existing surface | 645 | m2 | 0 | 0
| Tarmac surfacing to be 30mm surface course with minimum 50mm thick binder course | 645 | m2 | 0 | 0
| Allow for staggered 300mm wide joint between new and existing car park construction with existing bituminous material cut back and painted with hot bitumen | 42 | m | 0 | 0
| Careful excavation into existing bank, raking back; making good grass on completion | 1 | item | 0 | 0
| 125 x 255 precast concrete kerb with concrete 150 x 275mm base and concrete haunching including excavation and cart away | 243 | m | 0 | 0
| Extra over 125 x 255 kerb for drop kerb as required | 3 | m | 0 | 0
| Extra over above; curved | 30 | m | 0 | 0
| 125 x 150 precast concrete kerb type BN with 150 thick x 275m wide concrete base, concrete haunching including excavation and cart away | 6 | m | 0 | 0
| Allow to remove existing barrier and site hoarding; dispose off site | 1 | item | 0 | 0
| Repairs and making good to existing brickwork wall - PROVISIONAL | 1 | item | 1500 | 1500
| 8m span double leak hinged car park height restrictor with a 2.1m max height barrier fitted with a 6m nudge bar stating max vehicle height by stopem or similar | 1 | nr | 0 | 0
| Allow to supply and install stainless steel bollards with relecting banding and a length above ground of 1m; including concrete foundation | 5 | nr | 0 | 0
| Allow to supply and install street lighting columns (PC Sum £500 for Supply); including forming necessary concrete bases | 11 | nr | 0 | 0
| Locate existing mains power supply (located outside existing substation); provide power to lighting columns and pay kiosks; as required | 1 | item | 0 | 0
| Excavate trenches and provide ducting for power cables; including warning tape; all backfilled with well compacted type 1 material - APPROIMATE QUANTITY | 250 | m | 0 | 0
| Provision of permanent water stand pipe | 1 | item | 0 | 0
| Allow for provisional for future car parking pay and display machine to be provided | 2 | nr | 0 | 0
| Provision of all road markings including parking bay; hatched areas; wheelchair symbol; give way markings and directional arrows - all as shown on drawing P18-135-102 | 1 | item | 0 | 0
| GIVE WAY signage including concrete base | 2 | nr | 0 | 0
|  | Sub-Total |  |  | 3500 | 0% | 0

## X. Prelims
Car Park, Reliance House, Dursley | [5 empty] | Valuation | 0 |  | No.
Dursley Town Council | [5 empty] | P Ending | Date |  | Date
|  | Qty | Unit | Rate | Total | % Comp | Total Claimed | Client Comments | ADCMS Comments
Section X
Preliminaries
| Site Overheads - Based on | 0 | weeks
|  | 0 | months
A | Supervision
| Site Agent | 0 | week | 1000 | 0
| H & S Adviser |  | visit | 250 | 0
| Mileage Allowance |  | week | 0 | 0
| Contracts/Project Manager (two day per week) | 0 | week | 440 | 0
| QS (one day per month) | 0 | month | 360 | 0
B | Temporary Buildings
| Clients Office |  | week | 0 | 0
| Managers Office |  | week | 225 | 0
| Canteen/Drying Room |  | week | 0 | 0
| Storage Huts |  | week | 0 | 0
| Toilet |  | week | 45 | 0
| Site Setup Electricity Connection |  | each | 800 | 0
| Site Setup Water Connection |  | each | 800 | 0
| Site Set Up/Compound within grounds |  | week | 5500 | 0
| Transport |  | each | 85 | 0
| Office Equipment |  | £ | 12.5 | 0
C | Telephone & Fax
| Line Installation |  | each | 99 | 0
| Rental |  | qtrs | 85 | 0
| Call |  | week | 35 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
D | Temporary Electricity
| Electricity Connection Charge (temporary generator) |  | each | 10500 | 0
| Mains Cable |  | m | 0 | 0
| Temporary Lighting |  | item | 1500 | 0
| Power Transformers |  | week | 500 | 0
| Consumption - Construction Phase |  | week | 100 | 0
| Consumption - Completion Phase |  | week | 0 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
E | Building Water
| Water Connection Charge (Bowsers) |  | each | 5500 | 0
| Consumption - FOC |  | wks | 60 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
F | Temporary Siteworks
| Temporary Road for Site Access |  | each | 0 | 0
| Hears Fencing |  | Item | 3000 | 0
| Erect Heras and clear on completion |  | Item | 0 | 0
| Information signage |  | item | 450 | 0
| Directional Signage |  | item | 200 | 0
| Protection of existing trees |  | £ | 750 | 0
G | Cleaning
| Skips |  | each | 220 | 0
| Final Clean Internal |  | m2 | 7 | 0
| Final Clean External |  | days | 0 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
H | Scaffolding
| Labour & Hire - External inc sheeting |  | m2 | 18 | 0
| Inspections |  | week | 75 | 0
| Loading Towers |  | each | 0 | 0
| Internal crash deck |  | item | 0 | 0
| Chmneys |  | week | 0 | 0
| Fire Escape, foundations, pathway |  | each | 0 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
I | Distribution of Materials
| Tower Crane (base/erect/dismantle/power) |  | item | 0 | 0
| Concrete Pump |  | week | 0 | 0
| Telescopic Handler and Driver |  | week | 650 | 0
| Fuel |  | week | 0 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
J | General Items
| Site Security/general protection |  | item | 400 | 0
| Maintenance of Roads |  | vist | 0 | 0
| Drying Out Works |  | week | 0 | 0
| Test Cubes |  | each | 0 | 0
| Sample Panels |  | item | 0 | 0
| SmallPlant & Tools/Consumables/PPEquipment |  | week | 50 | 0
| Attendant Labourer - part only |  | week | 200 | 0
| Fall arrest netting |  | m2 | 0 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
K | Bond
| Bond |  | item | 0 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
L | Insurances
| Emplrs/PblcLiability/All Risks Insurance |  | item | 2500 | 0
| Temporary Works Engineer |  | £ | 0 | 0
M | Firm Price
| Labour |  | item | 0 | 0
| Materials |  | item | 0 | 0
| Item for clothing (Preliminaries) |  | £ | 0 | 0
|  | Sub-Total |  |  | 0 | 0% | 0