# External Assessment Group

# Service Level Agreement

This Service Level Agreement applies to all work commissioned by The Centre for Guidelines (CfG), The Medicines programme, The HealthTech programme, NICE advice, The Science, Evidence and Analytics (SEA) directorate, including: The Methods and Economics team, The Data and Analytics (D&A) team, Science Policy and Research (SP&R) programme.

- Work may be commissioned from time to time on behalf of other NICE Programmes.

- The following SLA table works in conjunction with the KPI excel spreadsheet. Abbreviations in the measurement column below are defined in the corresponding KPI in the excel spreadsheet.

- Excel Spreadsheet - Annex 2 of Sch 6 KPIs and Reporting

| - KPI number | - Name of KPI | - Detail | - Frequency measured | - Measurement | - Service credit |
| --- | --- | --- | --- | --- | --- |
| - 001 | - Percentage of work packages delivered | - The supplier shall deliver 100% of work packages commissioned by NICE. | - Annually | Failure levels - < 80% then service credit shall be 2% of annual service charge - < 90% and > 80% then service credit shall be 1.5% of annual service charge - <100 and > 90% then service credit shall be 1% of annual service charge | - Service credits apply |
| - 002 | - Key Milestone delivery of Work package | - The supplier shall deliver 100% of the milestones (to be defined with the work package documentation for each work package), and shall be measured against the status report traffic light system | - Each work package and quarterly | - GREEN - AMBER Failure levels - > 0 and < 30% then service credit shall be 1% of quarterly service charge - > 30 and < 60% then service credit shall be 2% of quarterly service charge - > 60 then service credit shall be 3% of quarterly service charge - RED Failure levels - > 0 and < 50% then service credit shall be 5% of quarterly service charge - > 50 then service credit shall be 10% of quarterly service charge | - No service credits - Service credits apply - Service credit applies to quarterly measurement - Service credits apply - Service credit applies to quarterly measurement |
| - 003 | - Status reporting and progress reporting | - The supplier will provide status reports that accurately reflect the work package progress to the frequency as detailed in the work package commissioning documents. - The supplier shall provide progress reports in accordance with the requirements of the current performance management and progress reporting framework to the frequency as detailed in the work package commissioning documents. | - Each work package and quarterly | - Reporting only Frequency as stated in the Instruction to Proceed Total number of weeks in work package from start date to completion - Number of Status/Progress reports delivered - Number of missed reports | - No service credit applied |
| - 004 | - Expressions of Interest (EoI) | - The supplier shall respond to all Calls for Expression of Interest within the specified number of days detailed on the EoI. Where the EAG is unable to provide an EoI, the supplier shall provide a statement of non-interest within 5 working days. Guidance work packages are not subject to the EoI process. | - Each work package and quarterly | - Reporting only - Number of EoIs received from NICE Number of EoIs responded to where EAG is interested in the work package Number of EoIs responded to where EAG did not submit bid for the work package - Number of EoIs not responded to | - No service credit applied |
| - 005 | - NICE informed of project team | - The supplier shall provide the details of the appointed persons including project lead and associated team responsible for the work package, within 10 working days of each work package commencement date. | - Each work package and quarterly | - Reporting only Date the EAG to inform NICE of the Project team was due Date the EAG informed NICE of the Project team - Number of days late | - No Service Credit Apply |
| - 006 | - Attendance at NICE Committee meetings (when required) | - An appropriate representative with permission and authority to speak on behalf of the supplier shall attend Committee meetings as required by NICE. | - Each work package and quarterly | - Reporting only Notification of name and role of the person attending to be sent 10 working days prior to the meeting - Actual attendance | - No Service Credit Apply |