## Sheet1
CLARIFICATION LOG
Tender: | Gerry Park, Camborne
Tender Reference: | 04/21
Clarification deadline:
Published Date: | 2021-11-05
Version number: | 0.1
Number | Clarification | Response | Reply date
1 | The documents state a high level of PII required; would you consider a lower level of PII considering the contract value of the project? | Ideally we would be seeking the level of cover as quoted, but could be discussed if it was a block for a supplier. If it were a close call in the scoring then this may have an impact on the final decision though. | 2021-11-05
2 | The specification within volume 2 (section 3.2) includes the following additional items after the main bullet points (with no indicative sum allowance): “Plus, reinstatement of the football pitch (landscaping / posts), creation of a sensory/ memorial garden, wildflower meadows, signage and extending the existing car parking.” Is the intention that all of these works would be included in the works to be tendered/ delivered, or might some elements just be included within the master planning process? | The extended car parking will be included in the wider groundworks tender. We envisage that the goal posts will be included in the outdoor gym, MUGA and any Play it Tender. There will likely be landscaping to be carried out in association with the delivery of the sensory garden so we would hope that the ground levelling around football pitch goals will be carried out by this contractor. Once plans for the sensory garden completed, we can plan the works with the ground workers that will be carrying out the excavations for the skate park. There will be a large amount of excess soil from this which we intend to use across the site to carry out remedial works and outstanding issues in the park. These will be developed through the masterplanning and negotiated after tendering with the preferred supplier. Signage will form part of a separate quoted works and the wildflower meadows plus soft landscaping for the sensory gardens will all be carried out in house. Assistance with the design work for the sensory garden will be expected from the Principal Designer that is selected through this tender. | 2021-11-05
3 | The pricing schedule 1 refers to an “architect led team” and specifically includes the architect role under the consultancy categories for pricing. Does this require that an registered architectural practice/ charter architect is included in the team, or could preparation of the D&B contracts for architectural elements potentially be prepared by other professionals? | As long as we have the necessary level of detail for the D&B tenders to achieve the desired results, then we are happy for this to be carried out by suitably qualified and experienced professionals. | 2021-11-05
| Within pricing schedule 1, under the “Fixed Fee” heading is included “Based on the estimate of £400k construction cost an indicative Percentage-based Fee Proposal should also be submitted to cover the cost of developing and delivering the project over RIBA Stages.”. Is this text applicable to this project – my understanding from the other documents is that consultancy costs should be fixed (not indicative percentage based), and the construction cost estimate is well over £400k | Thank you for highlighting this. Yes, we are looking for a fixed, so this text should not have included this wording. Apologies for our oversight. | 2021-11-05
| Within pricing schedule 1, the notes require that consultancy costs be included for design proposals in sufficient detail for submission of consent applications. Please confirm that this may not be applicable to some key elements to be heavily led by the D&B contractor’s design (e.g. skatepark design) where the contractors design may be required to support the planning application. | We will expect our Principal Designer/ Contract Administrator (selected through this tender) to ensure that our tender documents for the D&B contractors are sufficiently robust that they include all of the necessary design work to be submitted for us to achieve consent for the project | 2021-11-05
In the event of queries please contact: amenities@camborne-tc.gov.uk