Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Order Contract

Attachment 3 – Statement of Requirements

Contract Reference: CCZP22A01 - Inspire Academic Programme

CONTENTS

1.	PURPOSE	3

2.	BACKGROUND TO THE CONTRACTING AUTHORITY	4

3.	Background to requirement/OVERVIEW of requirement	4

4.	definitions	5

5.	scope of requirement:	6

6.	The requirement	6

7.	key milestones and Deliverables	9

8.	MANAGEMENT INFORMATION/reporting	12

9.	volumes	12

10.	continuous improvement	12

11.	Sustainability	12

12.	quality	13

13.	PRICE	13

14.	STAFF AND CUSTOMER SERVICE	14

15.	service levels and performance	14

16.	Security and CONFIDENTIALITY requirements	16

17.	payment AND INVOICING	16

18.	CONTRACT MANAGEMENT	17

19.	Location	17

# PURPOSE

  - The Cabinet Office (henceforth referred to as the Authority) is seeking to establish a contract for the provision of the academic element of the Government Communication Service’s (GCS) Inspire programme.  The Authority has a requirement for a 30 strong cohort of high potential G6s/G7s drawn from across government and our Arm’s Length Bodies (ALBs).

  - The delivery should commence no later than September 2022 and academic content should be accredited to a postgraduate Diploma level, with an option for up to 15 to continue to an MSc.  Content should focus on the communications leadership challenges faced at a senior level in government communications.

  - Our people are central to achieving the Government Communication Service’s (GCS) mission to deliver exceptional public service communication that makes a difference.

  - To continue to deliver for the public we need to raise professional standards, attract and retain talent, improve leadership, and create a more diverse and inclusive GCS located throughout the UK.

  - Our accelerated development programmes are a key part of GCS’s priorities as set out in the GCS Strategy of attracting, developing and retaining talent; developing our people and raising professional standards; building brilliant leaders and creating a more diverse and inclusive GCS.

  - The Inspire Programme for our internal G6s/G7s, aims to:

- Develop exceptional communications leaders and practitioners

- Build a strong talent pipeline for future senior communications roles

  - The learning objective is to provide an academic programme to accelerate the development of high potential G6s and G7s, building excellence in both leadership and communications skills.

  - The academic programme sits within other elements of the overall Inspire programme provided by the GCS, which include masterclasses, networking opportunities, career support, and senior mentoring.

# BACKGROUND TO THE CONTRACTING AUTHORITY

  - Government Communication Services (GCS)  (hereafter referred to as ‘the Client’) within the Cabinet Office (CO), which is the Contracting Authority, is the professional body for public service communication professionals working in central government departments, agencies and Arm’s Length Bodies. The contract will be with the Cabinet Office for this requirement.

  - The Government Communication Services (GCS) will be the lead Client, and will coordinate access to the Cabinet Office as and when required.

# BACKGROUND TO REQIREMENT/OVERVIEW OF REQUIREMENT

  - The Government Communication Service (GCS) is the professional body for more than 7,000 public service communicators working in government departments, agencies and arm’s length bodies. The GCS works across 25 ministerial departments, 21 non-ministerial departments and more than 300 agencies and other public bodies.

  - Our mission is to deliver exceptional public service communication that makes a difference.

  - Exponential growth of data, rapid transformations in media consumption, fragile public trust and false content, new technology, the need for greater efficiency, and changing societal expectations are creating new opportunities, challenges and ethical questions for GCS.

  - In response to those challenges, GCS has created a new GCS Strategy. Its goals are to help government speak with one voice; harness rapid technological changes for the public good; deliver a more efficient and effective GCS; build public trust in government communications; and retain, attract and develop the best talent.

  - Government Communications exists in an environment that is increasingly complex with a constantly developing, and more demanding, communication landscape. This means that Government has to respond and pro-actively engage not only with an expanding and fragmenting media, but with a multi-channel environment. Internally, there are also powerful drivers including the need for value for money services delivered at minimal cost, but with maximum impact.

  - A critical group to the delivery of exceptional government communications is our Grade 6s and 7s (G6s/7s) - our future senior talent. By virtue of their current role, many people in this group are already in leadership positions, but potentially are the leaders of large Government communication functions and directorates in the future, and could be leaders in more broadly-based roles.

  - To develop this group, the GCS initiated a development programme called Inspire, integral to which is a structured programme of academically accredited formal learning. That programme has run since 2014, with a full re-tender carried out in 2017 for a contract running 2018-2021.

  - The talent scheme operates as a cross-Government accelerated learning programme.

  - The potential supplier for this programme will need to be an academic body as the programme covers delivery of a Diploma and Masters offer.

# DEFINITIONS

| Expression or Acronym | Definition |
| --- | --- |
| GCS | Government Communication Service / ‘the Client’ |
| CO | Cabinet Office or the Contracting Authority |
| G6/G7 | Grade 6/ Grade 7 |
| PST | Professional Standards Team |

# SCOPE OF REQUIREMENT

  - We are seeking a supplier to deliver the academic core of an accelerated development programme to GCS’s G6s/7s for one cohort from September 2022.

The Inspire Programme aims to:

- Accelerate the development of the profession’s high potential G6s and G7s, building excellence in both leadership and communications skills.

- Build a strong talent pipeline for future senior communications roles

The supplier is required to provide a rigorous academic core of the programme, which is supplemented by masterclasses, senior mentoring and career conversations provided by the GCS profession.

The course must start by September 2022 and be tailored to align with the GCS Leadership Framework and the profession’s cannon of practice.

  - Learning from the programme needs to demonstrate its effectiveness in developing the leadership skills of its participants and building the senior talent pipeline – this is evidenced by the programme’s effectiveness in accelerating the promotion of its participants within two years of starting the programme, and evaluation of participants’ improved leadership and communications skills.

  - Content should exist within an accredited framework within which candidates can ultimately progress to a Masters level qualification in communication leadership, via a Diploma.

# THE REQUIREMENT

  - The supplier is to deliver a postgraduate Diploma programme in communication leadership, with the option for up 15 to continue to an MSc qualification to a cohort of 30 G6s/G7s.

  - The programme must be designed to improve the participants’ understanding of the specific challenges and opportunities of leading within a communications function, and equip them with theoretical models and practical examples to strengthen their communication leadership skills.

  - Key themes must reflect the five dimensions of the GCS Leadership Framework - Strategic, Collaborative, Creative, Connected, Trusted - and the profession’s Canon of professional practice.

  - Content must support and equip participants to think critically and strategically about their leadership role within the communications profession, including:

    - navigating “Wicked problems”

    - understanding their role as a trusted adviser and how to be effective in this role

    - maximising team performance

    - understanding the impact of current trends in the communications field, and their relationship to wider societal trends

    - leading change and maintaining resilience

    - reflective learning to improve their leadership effectiveness

  - The programme must highlight the latest research, thinking and best practice in communications leadership in complex environments.

  - As part of the Diploma, the supplier is required to set marked assignments throughout the modular programme, with a variety of individual and group-based assignments.

  - The programme must include reflective learning journals, leading to an assessed summative reflective journal included in the Diploma accreditation.

  - In terms of the academic elements, its effectiveness is evidenced by the cohort’s performance in the assessed elements leading to an academic qualification and evaluation of:

- the modular programme

- the quality of academic support

- the effectiveness of the learning in improving participants’ performance in their government communications roles (personal, line manager and DoC feedback).

  - The programme needs to ensure it carries professional academic credibility.

  - Potential suppliers would be expected to propose, agree and implement improvements or approaches to deliver the programme’s aim of developing exceptional communications leaders and practitioners, who are Confident, Strategic and Empowering, providing a strong talent pipeline for future senior communications roles within the GCS.

  - The current programme is highly regarded throughout GCS and is providing a pipeline of future talent across government in the field of communications. All government organisations are eligible to submit nominations. Participants are nominated to the programme by Directors of Communication.

  - To date, over 200 places have been filled and the average rate of promotion for individuals on the programme is approximately 40%.

  - Target Audience

    - GCS G6s and G7s.

    - This a critical group of people within the GCS and would be regarded as Senior Account Directors in a consultancy, or as head of a communication specialism in-house, just below Executive Board or main Board level.

    - They are a vitally important cadre, usually in charge of a team and at the point where policy and operations come together. They have to be fully competent as functional practitioners, but also demonstrate a high level of general leadership and management capability.

    - The programme is targeted at those GCS Grade 6s and 7s, identified and nominated by Directors of Communication, as high potential individuals who aspire to work at the most senior level leadership roles in the profession.

  - Delivery Criteria for Trainers/Facilitators

    - Academic leads in their respective institutions with prior experience of delivering this type of training.

  - Logistics

| Format | Four two day face to face group modules plus modules focussed on supported individual work on reflection assignments and a Diploma level dissertation An option to continue to an MSc with individual support provided. In light of the pandemic, there remains potential to revert to remoted delivery. |
| --- | --- |
| Numbers of delegates | 30 for the post graduate Diploma, with potential for up 15 to continue to an MSc for those that choose this option |
| Number of facilitators / trainers | Supplier to recommend |
| Length of event | As outlined above over 15 months, plus option five months for the MSc |
| Location | Supplier to propose based on information provided above |
| Key Dates & Timing | Contract to commence September 2022 for 15 months (Dec 2023), plus optional five months (MSc) to early June 2024 |
| Materials | Supplier to provide |

# KEY MILESTONES AND DELIVERABLES

  - Within five working days of the contract award, the supplier will meet with the Client to begin the implementation period and discuss the Client’s requirements in detail.

  - Diploma Programme: Key academic modules to be delivered over 15 months from September 2022 - December 2023.

  - Optional MSc support over five months from end of Diploma course - to early June.

  - Face to face modules to be delivered in London with one module as a residential with an overnight stay.

  - The supplier to work with participants, running a group introductory session and supporting participants in achieving their Diploma in a selected research project with a dedicated supervisor per individual. It provides a Diploma to successful participants including the certificate and graduation.

  - Participants can choose to continue to a Masters Degree level qualification. The supplier to host two days of research training for participants at a University site. It will assign a supervisor per individual and assist the participant through the degree process. A certificate confirming the Masters qualification and graduation will be arranged by the supplier.

  - Members of the GCS team will work with the supplier to review and agree the proposed content and planned delivery of the modules.

  - The supplier assesses the assignments, moderates and provides academic marks for work submitted by individuals and groups. These marks are shared with GCS.

  - The supplier has responsibility for onboarding cohort participants onto the academic organisation.

  - In addition to the academic element of the programme, there is a broader Inspire offer run by GCS which includes career conversations and mentoring or coaching. The supplier signposts these with students to ensure a joined-up one programme offer but does not run these elements of the curriculum.

  - The supplier is required to source guest speakers for each of the modules, with agreement from the GCS’s PST.

  - The contract involves regular meetings with GCS and regular interaction with the participants throughout the programme as the supplier will deal with all academic qualification-related queries.

  - The supplier carries the costs of the residential stays for its academic tutors and any other speakers or trainers it has sourced for modules.

  - The supplier carries the costs in its contract of any other trainers or speakers it sources for the modules.

  - Currently there are four group face-to-face modules each lasting two days, with one of these a residential with an overnight stay, enhancing the group's networking/support system, which is a valuable part of the talent programme.

  - For the 2022/3 delivery, training may need to be provided in a variety of formats.  GCS is hopeful that the programme will be predominantly face to face, with options for webinars where relevant.  However, in light of the pandemic, the supplier would need to be flexible on the potential for remote delivery of the programme.

  - Face to face modules will be held on the government estate.  Cohort costs for the overnight module will be funded by the client. The supplier will be liable for accommodation costs incurred by the supplier’s staff, or any module speakers sourced by the supplier for the residential module.

  - Rooms for all sessions of the quarterly modules should be set up to facilitate exercises and activities across the cohort, and encourage networking across the group.

  - Potential suppliers are expected to propose improvements/approaches to the delivery of the academic programme.

  - The following Contract milestones/deliverables shall apply:

| ### Milestone/ Deliverable | ### Description | ### Timeframe or Delivery Date |
| --- | --- | --- |
| ### Core programme: Delivery of Postgraduate Diploma | ### Deliver the key academic modules including assignments. Face to face two day modules delivered in London and one module (two days) as a residential with an overnight stay. Support and work with participants for the Diploma level qualification in a selected research project. Provide a dedicated supervisor per individual to support the research project. | ### 15 months from September 2022 to December 2023 |
| ### Optional for up to 15 participants: MSc | ### Host two days of research training at a University site for participants participating in the Masters Degree level qualification. Assign a supervisor per individual and assist the participant through the degree process | ### Over five months: Jan 2023 - early June 2023 |

# MANAGEMENT INFORMATION/REPORTING

  - The Authority will require the supplier to provide appointed liaison points for both the academic programme, financial control and contract management.

  - The Authority expects the following management information and reporting:

    - High level reporting on the delivery of milestones at regular scheduled catch ups with GCS throughout the programme.

    - Quarterly contract management meetings including detailed progress report against milestones and forecast cost (exact format to be agreed through the mobilisation period)

    - Reporting of academic marks for each member of the cohort following each assignment.

    - Regular feedback on individuals, including any issues raised in relation to the academic programme - e.g. requests to defer deadlines, or non-attendance at modules.

# VOLUMES

  - The cohort for this programme is approx. 30 participants with up to 15 participants having the possibility to continue with MSc.

# CONTINUOUS IMPROVEMENT

  - The supplier will be expected to continually improve the way in which the required services are to be delivered throughout the work package duration.

  - Where appropriate and beneficial, the supplier should present new ways of working to the Client during catch up meetings.

  - Changes to the way in which the services are to be delivered must be brought to the Authority’s attention and agreed prior to any changes being implemented.

# SUSTAINABILITY

The supplier must consider social sustainability, including diversity, when creating and delivering its content and its communications to the cohort.

# QUALITY

  - The supplier will ensure that there is a technically qualified, dedicated delivery team providing consistent quality assured outputs and outcomes.

  - The programme needs to ensure it carries professional academic credibility and any potential supplier will need to demonstrate its accreditation to deliver an academic programme and subsequent qualifications for participants.

# PRICE

  - The supplier's pricing must incorporate the costs associated with the course, course materials, evaluation, catering during the event, overnight accommodation, and any required transport between the venue and the accommodation for that night's stay.

  - The supplier carries the costs of the residential stays for its staff and course facilitators, and any other speakers or trainers it has sourced for the course.

  - The supplier carries the costs in its contract of any other trainers or speakers it sources for the modules.

  - The supplier is required to source guest speakers for each of the modules, with agreement from the GCS Professional Standards Team.

  - Should a  Potential Bidder be successful in proceeding to Stage Two, they will be required to submit Attachment 4b - Pricing Schedule, this must include costs relating to delivering the provided scenario at Stage Two. Rates submitted at Stage One must be used to calculate the costs associated with the tasks stipulated at Stage Two.

  - The supplier will need to adhere to best practice for utilising budget and optimising the use of public money to achieve results and/or deliver a quality service.

  - Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

# STAFF AND CUSTOMER SERVICE

  - The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

  - The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

  - The Supplier shall ensure that staff understand the Authority’s vision and objectives and will provide excellent customer service to the Authority throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

  - Learning from the programme needs to demonstrate its effectiveness in developing the leadership skills of its participants and building the senior talent pipeline.  This will be evidenced by the programme’s effectiveness in accelerating the promotion of its participants, evaluation of participants’ improved leadership and communications skills, academic performance, and the Supplier’s compliance with the management reporting schedule.

## The Authority will measure the quality of the Supplier’s delivery by:

| KPI/SLA | Service Area | KPI/SLA description | Target | How measured |
| --- | --- | --- | --- | --- |
| 1 | Delivery timescales | The rate of promotion would be expected to be approximately 35% of the cohort within the first two years of the programme. | Minimum 35% | Measured by the Client’s delivery manager and through management reporting. |
| 2. | Delivery timescales | Assessment of the cohorts performance and effectiveness. | Positive feedback of > 80% Pass rate of > 80% | Measured by the evaluation of: - the modular programme - the effectiveness of the learning in improving participants’ performance in their government communications roles (personal, line manager and DoC feedback). - Academic qualification obtained |
| 5 | Management reporting | Attendance and high level reporting on the delivery of milestones at catch-ups with GCS | 100% | Measured by the Client’s delivery manager |
| 6 | Management reporting | Quarterly contract management meetings including detailed progress report against milestones and KPIs | 100% | Measured by the Client’s delivery manager |
| 8 | Financial | Invoicing on completion of each module and completion of the Diploma and MSc (optional) | 100% | Measured by the Client’s delivery manager |

  - The Client  reserves the right to refine or include further KPIs or SLAs at the outset of each delivery milestone.

  - The Client  will maintain a record of Supplier’s adherence to the agreed service level and performance timelines. Any non-adherence will result in performance review meetings between the Client and the Supplier, to provide an explanation as to why the service level agreement was not met. Improvement plans will also be established here.

  - Where the Supplier fails to provide a Service Improvement Plan or fails to deliver the agreed Service Improvement Plan to the required standard, the Client reserves the right to seek early termination of the contract in accordance with the procedures set out in the Terms and Conditions.

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

  - Any IT systems used by the Supplier to meet the Authority’s requirement shall have a Cyber Essential Scheme Casic Certificate or equivalent at the commencement date of the contract, and maintain that certification throughout the life of the contact. Cyber Essential Scheme requirements can be located at https://www.cyberstreetwise.com/cyberessentials/files/requirements.pdf

  - The Supplier shall comply with all relevant legislation, organisational and cross Government policy and guidelines in relation to Data and asset security.

  - The Supplier shall ensure that Contracting Authority’s information and Data (electronic and physical) shall be collected, held and maintained in a secure and confidential manner and in accordance with the Terms of this Contract.

  - The Supplier shall take all measures reasonably necessary to ensure that all Supplier Personnel involved in the performance of the Contract are aware of all ongoing Data security and confidentiality requirements.

  - All programme activity undertaken by the Supplier to deliver this work package must comply with the Data Protection Act, in particular with regard to the collection and storage of personal data.

  - The IPR clause within the framework terms for RM6219 (Learning and Training Services DPS)  will apply for the entire contract term.

# PAYMENT AND INVOICING

  - Payment can only be made following satisfactory delivery of pre-agreed products and deliverables. The Supplier will send invoices for payment to the Client quoting the appropriate purchase order number following each module.

  - Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

  - Invoices should be submitted to: REDACTED TEXT under FOIA Section 43 Commercial Interests.

# CONTRACT MANAGEMENT

  - As per section 8 above, communication will be maintained with the supplier through regular meetings and email correspondence.

  - Attendance at regular review meetings shall be at the supplier’s own expense, and at a venue specified at commencement of the contract.

  - Attendance at Contract Review meetings shall be at the Supplier’s own expense.

# LOCATION

  - The location of the Services will be carried out at Cabinet Office, REDACTED TEXT under FOIA Section 40, Personal Information, other parts of the Government estate or working from home.