# Annex A

| Title of project: | 0723S Survey Particle Size Sample Analysis |
| --- | --- |
| Project summary | JNCC and the Scottish Marine Directorate (formally Marine Scotland Science (MSS)) carried out an offshore seabed survey to the Central Fladen MPA (CFL hereafter) onboard the Marine Research Vessel (MRV) Scotia (survey code 0723S). Sampling at CFL was focussed on the designated Burrowed Mud feature. Benthic Samples were collected from stations within the MPA from water depths of 100-280m JNCC wishes to commission a contract to undertake the Particle Size analysis of samples collected on the 0723S cruise. 139 samples were collected on this survey.Up to a further 80 stations to be collected from the same area on a survey currently in progress which will also be included in this analysis forming a combined 219 samples maximum. |
| Date and time for return of tenders: | Thursday 7th September 2023 at 09:00 |
| Contract Reference No: | C23-0400-1794 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO TOM TANGYE OR SHARON JOYCE VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Joint Nature Conservation Committee Name: Josh Tate Email: josh.tate@jncc.gov.uk Telephone:01733 866906 OR Joint Nature Conservation Committee Name: David Reynolds Email: david.reynolds@jncc.gov.uk Telephone: +44 (0)1733 943167 |
| Contact for any queries regarding the tendering procedure: | Sharon Joyce Finance Team Joint Nature Conservation Committee Email: Sharon.Joyce@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | September 2023 |
| Proposed end-date: | February 29th 2024 |

## Project Aims

JNCC wishes to commission a contract to undertake the Particle Size Analysis (PSA), of samples collected on the 0723S offshore survey to CFL as well as further samples collected from CFL on a survey currently in progress. There were 139 PSA samples collected on the 0723S survey, with up to an additional 80 samples to be collected on the current survey.

Bidders are invited to provide a description of how the requirements set out below will be met and a per sample quote.

The sample residues will be stored by the contractor until completion of the contract (i.e. after any remedial action identified through quality checks has been actioned).

Option 1

Please provide quote for complete analysis of up to 219 PSA samples and draft report by w/c Feb 26th 2024, any remedial action to be completed by 11th March 2024.

## Project Summary

JNCC and Scottish Marine Directorate (formerly Marine Scotland Science (MSS) undertook an offshore seabed survey to the Central Fladen MPA (CFL hereafter) onboard the Marine Research Vessel (MRV) Scotia (survey code 0723S).

The 0723S survey departed from Aberdeen on 18th June 2023 and returned to Aberdeen on 26th June 2023.

CFL lies in offshore waters to the north east of Scotland. For more information regarding CFL please see https://jncc.gov.uk/our-work/central-fladen-mpa/

Sampling at CFL was focused on the designated Burrowed Mud feature. The depth range within CFL is from approximately 100 to 280m (Figure 1).

Sampling was conducted using a 0.1 m2 Day Grab.

Particle Size (PS) sediment sub-samples were extracted from each sample and frozen with the remaining sample sieved using a 1 mm mesh diameter sieve.

For more information regarding the survey design and methodology, please contact JNCC

Please note the following documents will be supplied to the successful contractor:

Survey programme

Associated metadata

Draft Cruise Report

MEDIN compliant MS Excel proforma spreadsheets

Figure 1. Summary map showing all stations visited with the 0.1m2 Day grab during the 0723S survey of Central Fladen MPA

## Project Objectives

JNCC wishes to commission a contract to undertake the Particle Size Analysis (PSA), of samples collected on the 0723S offshore survey. There were 139 PSA samples collected on this survey to the Central Fladen MPA, and up to a further 80 samples are due to be collected from the same area on a survey currently in progress.

Particle Size analysis

Particle Size analysis must comply with NMBAQC guidelines for completing analysis for biological reasons1. This analysis is inclusive of the ‘greater than 1 mm’ fraction, which will be enumerated by dry sieving.

The ‘smaller than 2mm’ fraction will be analysed using laser diffraction. Each sample will be run for 1 minute, and all laser settings should be provided alongside the final dataset, such as what dispersants are used (if any), which type of correction (if any) are used and the replicate number per run.

Quality Assurance

JNCC requires that the successful contractor complies with our EQA Policy. The policy can be found here: http://jncc.defra.gov.uk/default.aspx?page=6675.

Work under this contract will be subject to the provisions within the EQA policy.

Tenderers are required to provide details of internal Quality Assurance and Quality Check procedures, including details of present and past participation in relevant NMBAQC Scheme Components.

External Quality Assurance

Following award of the contract, and dependent on the evaluation scores they achieved, unsuccessful bidders may be invited to undertake the Particle Size Analysis independent external QA aspects of this project. Please indicate in your tender if you do not wish to be considered for this work.

Award of the external QA aspects of this work will be made following main award of the contract.

5% of Particle Size samples processed are to be subject to an independent external QA process.

Comparison between external QA and original analysis will be undertaken as described below.

Prospective contractors should note the following:

- Adherence with the NMBAQC guidelines is not an end in and of itself, but contractors Standard Operating Procedure must be sufficiently rigorous in practise to achieve the required QA standards.

- The Remedial Action process may be iterative until the QA standards are achieved.

- Samples may be withdrawn, and refunds requested if samples fail to achieve satisfactory QA within a set number of rounds or within a specified time schedule.

- Contractors should alert the project manager if any samples they receive are deemed to be atypical, such that they require, or would benefit from, some method variation of their Standard Operating Procedure.

External Quality Assurance process for Particle Size Analysis

External QA Particle Size analysis will comply with NMBAQC guidelines for completing analysis for biological reasons.

The Particle Size analysis QA will consist of a 5% reanalysis of the processed samples, in line with the NMBAQC Own Sample scheme.

Where remedial actions are required, these are to be completed following discussions between the appointed contractor and JNCC at no additional cost.

## Outputs

Any products or outputs submitted to JNCC [for publication] should adhere to JNCC’s house-style and should be produced in an accessible format (see product specification for more information).

| Output/Deliverable | Format |
| --- | --- |
| Particle Size Analysis of Particle Size samples as per NMBAQC Standards (http://www.nmbaqcs.org/media/1255/psa-guidance_update18012016.pdf) | MS Excel spreadsheet (proforma spreadsheet will be provided by JNCC) |
| GIS point shapefiles for area surveyed including PSA summary per station (Folk classification and corresponding EUNIS broadscale habitat) Shapefile should be imbedded with INSPIRE compliant metadata (INSPIRE metadata template available in GIS) and fully georeferenced in a defined coordinate system | ArcGIS point shapefiles |
| Final report | MS Word DOC |

Please note the Final Report must adhere to the JNCC report template and house style guidance an example table of contents is given in Appendix C The report should be no longer than 14,000 words including all tables and appendices.

The report should be provided electronically via email as a Microsoft Word document, and will include the following sections:

- Methodology

- Results

- Details of all QA work undertaken and any remedial action deemed necessary.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting | ~16/08/23 |
| Collection of samples from Marine Scotland Science / MRV Scotia, Aberdeen | ~18/08/23 |
| Completion of analysis and reporting, provision of draft deliverables to JNCC and external QA samples to external QA laboratory | 26/02/2024 |
| Completion external QA and remedial action (if necessary) | 11/03/2024 |

## Contract management and communication

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points: Josh Tate

Email: josh.tate@jncc.gov.uk

Tel: 01733 866944

And

Dave Reynolds

Email: David.Reynolds@jncc.gov.uk

Tel: 01733 943167

The contract will begin following a start-up meeting to be arranged between the successful contractor and JNCC upon contract award.

Contractors are to provide weekly progress updates the format of which will be agreed at the start up meeting.

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor)

Any incidents occurring within the contract should be immediately reported to JNCC.

## Available Budget

Please provide a quote for the above work.

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## Evaluation table for Mini-Competition

## Project Manager to decide category and maximum score for each.

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (80% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) |  |  |
|  | Understanding of, and relevance to, the requirements |  |  |
|  | Soundness and logicality of methods |  |  |
|  | Realism and measurability of milestones |  |  |
|  | Identification and proposed solutions to potential problems/risks |  |  |
|  | Probability of success |  |  |
|  | Sub Totals | 80 |  |
| 3. Cost (20% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation |  |  |
|  | Fairness/reasonableness for the level of work and expertise required |  |  |
|  | Clarity of each team member’s contribution and value added |  |  |
|  | Sub Totals | 20 |  |
| Total score |  | 100 |  |

## Appendix A: Summary Metadata will be provided prior to start up meeting

## Appendix C: Example Table of Contents for Report

1	Introduction										1

2	Aims and objectives									2

2.1	Aim										2

2.2	Objectives									2

3	Methods										3

3.1	Survey										3

3.2	Particle Size Analysis – Laboratory methods					6

3.2.1 Particle size analysis (PSA) samples					6

3.2.2 Quality assurance (internal)						6

3.3	Quality control (external)							8

4	Results										9

4.1	Sediment composition							9

4.3	External Quality Control							10

4.3.1 Particle size analysis							10

5	Discussion										12

6	References										13

Appendix 1: Particle Size data for survey							14

Appendix 2: Particle size analysis external AQC Report 					15

Note a Teams video meeting will suffice for the start-up meeting