# Expression of Interest

# Title: Qualitative Research – What motivates employers to improve their Shared Parental Leave and Pay offer?

Project reference: 2018059

Deadline for expressions of interest: 17th September 2018

## Summary

The Government Equalities Office (GEO) is seeking a contractor to deliver qualitative research that will help us understand more about what motivates employers to improve their Shared Parental Leave offer to employees beyond the statutory minimum.

## Background

Since April 2015, UK employers have been required to offer Shared Parental Leave (SPL) and Shared Parental Pay (ShPP). The policies are designed to enable both parents to take time out of work to care for their children, where previously only mothers were entitled to a longer period of leave. This is crucial in tackling the gender pay gap, the largest cause of which is the reduction in women’s labour market participation, which in itself is primarily due to time spent caring for children. However, take-up of SPL remains low (estimated between 2-8% of those eligible). There are a number of reasons for this, including a lack of awareness of the policies, and that employers may not enhance ShPP as they often do maternity pay.

This research seeks to understand more about what leads some employers to offer an improved SPL and ShPP offer, with the final objective of leveraging these findings to support other employers to do the same.

This work is being commissioned under GEO’s Workplace and Gender Equality (WAGE) Research Programme. Over the next two years, GEO plans to build the evidence base, focusing on key themes around what works to close the gender pay gap. This project is commissioned in response to the Family-Friendly Policies theme.

.

## Project aims

For the purposes of this project, we define an improved SPL or ShPP offer broadly – it is likely to include enhancing ShPP, but could also include promotion of SPL to employees, e.g., via a marketing campaign, or use of role models within the organisation.

The project should respond to the following research questions:

- What examples of good practice exist in improvement of SPL/ShPP offer, and what lessons can be taken from these by:

  - Employers?

  - Government?

  - Other stakeholders?

- What motivates some employers to improve their SPL/ShPP offer?

  - What forms can this improvement take?

  - What does the employer journey to an improved offer look like?

  - How do company characteristics affect this, e.g., size, sector, composition (e.g., women in senior positions)?

  - What are the impacts of improving the SPL/ShPP offer, e.g., in terms of take-up?

As one objective of this project is to encourage employers to enhance their own SPL and ShPP offers, we will ask bidders at the ITT stage to offer a proposal as to how they would ensure effective dissemination of the work (note that full details of proposed approach are not required at the EOI stage). The successful contractor will be required to present findings both internally and externally. Along with a traditional research report, contractors will be required to produce summaries of outputs suitable for employers and other stakeholders. To fulfil GEO’s objective of ensuring work is effectively disseminated, we encourage bids from contractors who would intend to publish findings in academic journals.

## Methodology

Submitted EOIs should include a proposal of a high-level methodology for the work. We require that the identified research questions be answered via qualitative research, but leave it open to bidders as to the specific form this should take (e.g., in terms of precise approach, sample size). Details of the sampling and recruitment should be addressed at the ItT stage.

Please note that GEO are currently funding a literature review on the motivations for employers offering family-friendly policies more broadly. The successful bidder would be required to engage with the contractors producing the literature review, enabling early findings to influence the research design (e.g., topic guides).

Bidders should also offer high-level proposals as to how they would engage with GEO throughout the project, e.g., in consulting on search strategies, handling of emergent themes, ensuring final products are fit-for-purpose.

## Timing

| EoI Issue | 3rd September 2018 |
| --- | --- |
| EoI Deadline | 17th September 2018 |
| EoI Assessment | 18th-21st September 2018 |
| ITT Issue | 24th September 2018 |
| ITT Deadline | 22nd October 2018 |
| ITT Assessment | w/c 22nd October 2018 |
| Contract Award | w/c 29th October 2018 |
| Delivery of Draft Report | March 2019 |
| Delivery of Final Report | April 2019 |
| Dissemination | April – May 2019 |

## Assessment criteria

| Criterion | Description | Weighting |
| --- | --- | --- |
| Evidence of relevant experience | Experience of having delivered high-quality qualitative research, preferably on similar topics. We are particularly keen to see evidence of bidders having delivered academic research where findings have been successfully translated into outputs that suitable for use by other stakeholders (e.g., employers). | 40% |
| Understanding of subject matter | Demonstration of outstanding expertise in the subject matter, including a track record of producing high-quality research in this field and familiarity with the existing evidence base. Ideally, this will be demonstrated at both an institutional and individual level. | 40% |
| Value for money | Evidence of ability to deliver in a manner that is efficient, effective and economical. | 10% |
| Capacity to carry out work | Demonstrable ability to complete the required work, i.e., in employing or intending to recruit appropriately skilled staff. | 10% |

Submitted EoIs should be no more than 1,500 words in length. Only the top three scoring EOIs will be invited to tender for the work.

Closing date for EOIs: 17th September 2018 Send your EOI form to: GEO.researchprogramme@geo.gov.uk

## How to submit an expression of interest

You must submit an expression of interest (EOI) in order to be considered to be invited to tender. To do so, please complete the NEW EOI Form which can be found under attachments. A submission of an EOI does not guarantee an invitation to tender and the Department does not routinely advise organisations that they have not been successful in being invited to tender. Feedback is however available on request.

All contracts are let on the basis of the Department’s Terms and Conditions. You are encouraged to check these before submitting your expression of interest, as these form part of your contractual obligations.

© Crown copyright 2018