Invitation to Quote – Call-Off 8

Trialling and Sampling Framework

Contract STA-0166

2020 Key Stage 2 National Curriculum

Science Sampling Test and Technical Pre-Test Administration

| Tenderer: |  |
| --- | --- |
| Single Point of Contact: |  |
| E-mail: |  |
| Phone: |  |

Contents

- Specification of Requirements

1.a. Context								           03

1.b. Deliverables and Outputs						09

1.c. Functional Requirements						22

1.d. Performance Requirements						62

1.e. Payment Milestones						           66

1.f. Instructions to Tenderers						68

1.g. Procurement Timescales						71

1.h. Tender Evaluation Methodology					72

- Annexe A: Supplier’s Proposal

Q1) Method Statement							73

Q2) On-screen Coding / Coder Recruitment				74

Q3) Administrator Training						           75

Q4) Data Integrity							           76

Q5) Security								           77

Q6) Resource Strategy							78

Q7) Sub-contractors							79

- Pricing Schedule								80

- Appendices

Appendix 1 – Cost Breakdown						81

Appendix 2 – Data Templates						81

Appendix 3 – Reporting Templates					81

Appendix 4 – Supplementary Information				82

- Annexe B – Departmental Security Assurance Model process		83

- Declaration by Tenderer							85

1. Specification of Requirements 1.a. Context

Introduction - This Invitation to Quote (ITQ) is for a call-off under the Standard and Testing Agency (STA)’s Trialling and Sampling Framework (STA contract reference: STA-0166). Please note, this ITQ outlines the requirements of this call-off, whilst the Trialling and Sampling Framework details the specifications (see Appendix 4). Suppliers will need to refer to both documents when completing their bid. - The scope of this ITQ is for the manufacture, administration and coding of the 2020 key stage 2 (KS2) national curriculum science sampling test (SST) and science technical pre-test (TPT). Background to Requirement - STA is responsible for developing and delivering national curriculum tests on behalf of the Department for Education (DfE). It must ensure that all contracted agencies and consultants are aware of, and comply with, the relevant sections of the Ofqual Regulatory framework for national assessments - The purpose of the SST is to estimate national performance in science at the end of KS2, with respect to the KS2 programme of study for science. The purpose of the TPT is to provide data on the performance of all items included in the trial test papers, in order to inform future SST construction. - The SST takes place biennially. Administration of SST using the current sampling model first took place in June 2014, involving approximately 9,500 pupils in 1,900 schools. In 2016, TPT administration was delivered alongside SST for the first time, in order to improve data reliability. In 2018, no TPT took place. In 2020, the 2016 model will be repeated, that is, a simultaneous, combined SST and TPT administration. The 15 test booklets used in the 2018 SST will all be re-used in 2020. - The 2020 model will involve approximately 14,000 pupils in 1,900 schools. The selected 1,900 schools will participate in the SST and 900 of those schools will also participate in the TPT. Of the 14,000 pupils, 9,500 will take the SST and 4,500 will take the TPT. 5 pupils per school will take the SST, with an additional 5 pupils taking the TPT at the 900 selected schools. School and pupil samples will be selected by STA. - The SST-TPT contract will be project managed by the STA Assessment Delivery Team. The Supplier will need to work proactively with the STA SST-TPT Project Manager, who is supported by the SST-TPT Project Team, which is made up of representatives from STA’s Assessment Delivery, Development and Services divisions. Freedom of Information and Transparency - As an executive agency of the Department for Education, STA is committed to open government and to meeting its legal responsibilities under the Freedom of Information Act 2000 (‘FOIA’). Accordingly, Tenderers should be aware that all information submitted to STA may need to be disclosed by the Agency in response to a request under the FOIA, and that STA may also decide to include certain information in its publication scheme, which it maintains under FOIA. - STA participates fully in the Government’s transparency arrangements. As such, Tenderers should be aware that: - any contracts or agreements resulting from its procurement exercises may be published in full, subject to limited redactions in line with FOIA exemptions - financial transactions in relation to any contracted goods or services will be published and so cannot be deemed commercially sensitive (see over) - If a Tenderer considers that any of the information included in its Tender is commercially sensitive, it should identify this information in the table below and explain a) what harm may result from disclosure if a request is received, and b) the time period applicable to that sensitivity. Tenderers should be aware that, even where they have indicated that information is commercially sensitive, STA may be required to disclose in response to a request under FOIA or as part of the Government's transparency arrangements. For example, the value of a contract must be made publicly available so this information cannot be deemed commercially sensitive. Section; Commercial Sensitivity; Time Period. - The table below shows an example of the level of information disclosed to all bidders following evaluation: Technical threshold result; Relative Quality Score; Relative Price Score; Weighted Combined Score; Rank for Compliant Bidders. 70%; 30%. Tenderer A; PASS; 0.73; 0.12; 0.55; 2. Tenderer B (WINNER 1); PASS; 1.00; 1.00; 1.00; 1. Scope of Services Required - This document sets out the Specification of Requirements (SOR) for delivering a Science Sampling Test (SST) and Technical Pre-Test (TPT). The administration of both tests must take place between 8 and 19 June 2020 inclusive. - Participation in SST and TPT is mandatory, with STA selecting the schools to participate for both SST and TPT administrations. STA will provide the Supplier with participating school and pupil level data detailing the test combinations that each pupil should be given. Following selection of the school sample and informing of schools by STA, the Supplier is responsible for contacting schools to confirm their selection and securing their acknowledgement of their statutory obligation to participate. - The Supplier is responsible for the printing, collation and distribution of all test materials and other documents specified in this ITQ. - The Supplier is responsible for the end-to-end process of the recruitment and management of coders, including the senior coding team. - STA is responsible for the content and specification of the tests used in both SST and TPT so this is not in scope for the supplier. - The table below provides the high-level requirements with respect to this specification. It outlines what aspects of the Framework Agreement will be required in this Call Off.

High Level Requirements

| Core | SST | TPT |
| --- | --- | --- |
| Drawing the sample | N | N |
| Recruiting schools | N | N |
| Informing schools | Y | Y |
| Recruit and train administrators | Y | Y |
| Collation and distribution | Y | Y |
| Administration of assessments | Y | Y |
| Handling pupil data | Y | Y |
| Recruitment, management and payment of coders | Y | Y |
| Coding (on-screen) | Y | Y |
| Script management during coding | Y | Y |
| Data capture of test scripts | Y | Y |
| Data capture and analysis of questionnaires | Y | Y |
| Sample & Trial administration report | Y | Y |
| Printing | Y | Y |
| Helpline | Y | Y |
| Systems management | Y | Y |
| Return of results to schools | N | N |
| Incentives | N | N |
| Recruiting schools | N | N |

Key

| Included in call-off | Y |
| --- | --- |
| Not included in call-off | N |

- The project deliverables and outputs (milestones) are provided in section 1.b. Timelines and project plans will need to be presented and discussed at the start-up meeting. - The dates in section 1.b are indicative dates and the Supplier can propose alternative dates. The exceptions to this are the project fixed dates, which are non-negotiable and are listed in the table below. Project Fixed Dates - Further detail on the requirements listed in this table can be found in sections 1.b and 1.c. No.; Milestone; Fixed date. 13; Test booklet scanning specification; 23 October 2019. 14; Print reassurance and end-to-end testing report; 5 February 2020. 8; Confirmation of school participation; 15 May 2020. 8; Confirmation of pupil participation; 22 May – 12 June 2020. 17; Test administration; 8 June – 19 June 2020. 38; Provision of administrator questionnaire data and analysis; 30 July 2020. 41; Data feed item level (SST); 14 August 2020. 43; Data feed item level (TPT); 19 October 2020.

Dependencies - Delivery will be dependent on STA providing the Supplier with various information or having completed certain activities; these are detailed in the Dependencies table below. STA Activity / Information to be handed over; Anticipated date. Communications strategy; 25 September 2019. Ways of working document; 25 September 2019. Information to inform the test administration guidance; 25 September 2019. Administrator questionnaire template; 25 September 2019. Test specifications (including dimensions, colours and finishing) and quantity estimates; 25 September 2019. Finalised test materials SST (Standard and Modified); 31 January 2020. Draft test materials for generation of TPT coder training materials; 28 February 2020. 2018 finalised coding frames and coder training and practice materials for familiarisation; 6 March 2020. 2018 responses for generation of SST standardisation materials; 6 March 2020. Final Combination tables for SST and TPT; 6 March 2020. Draft SST data specifications; 3 April 2020. Draft TPT data specifications; 3 April 2020. Finalised test materials TPT; 6 April 2020. Sample data – school and pupil level including modified flags – provided to supplier; 24 April 2020. Schools informed of selection by STA; 27 April 2020. Draft coding frames for generation of TPT coder training materials; 29 May 2020. Final SST data specifications; 31 July 2020. Final TPT data specifications; 31 July 2020.

| 1. Specification of Requirements 1.b. Deliverables and Outputs |  |  |  |
| --- | --- | --- | --- |
| No. | Milestones |  | Due Date |
| 1 | Project Management |  |  |
| 1.1 | Start-up meeting | The Supplier must attend a face-to-face start-up meeting with STA. The purpose of this meeting will be to ensure clear understanding of requirements on both sides. The agenda for the meeting may include, but is not limited to: - introductions and roles and responsibilities - Supplier clarification of STA’s requirements - STA clarification of Supplier’s approach - agreement on governance and reporting arrangements - other key feedback on submitted documentation The following Supplier documents will inform discussion at the start-up meeting. The Supplier must provide these documents at least 10 working days before the start-up meeting: - detailed project risk and issue log for review - detailed project timeline - draft exit and transition plan (see template and guidance at Appendix 3) - draft coding management strategy (to include the end-to-end approach to coding) - draft administrator recruitment, training and management strategy - proposed highlight report template - draft security plan and completed HM Government Supplier Assurance Questionnaire - draft product breakdown structure - document review and sign-off tracker (to include product descriptions) - product description drafts for early deliverables - details of sub-contracting arrangements, including, but not limited to: contractual status and milestones, security status, management and escalation arrangements - example of the scanning elements required to amend the test paper templates that have been provided at Appendix 4, in order to assure test administration and script management procedures that the Supplier proposes to use. Scanning elements must fit within the denoted customisable areas of the template STA will provide a draft ways of working document and overarching communications strategy for review 10 working days before the start-up meeting. | 9 October 2019 |
| 1.2 | Process walk-through meeting(s) | The Supplier must provide STA with a complete end-to-end process walk-through including, but not limited to: - administrator and coder recruitment, management and training - printing, collating and distribution of hard copy test materials (including modified materials) - scanning - processes for auditing and monitoring scripts: reconciliation of scripts sent, scripts received and scripts unused - security and incident management - tracking physical movement of materials - data capture and quality assurance - data reporting / exporting / QA - helpline - systems to be used as part of project delivery including assurances on use of data, testing, customisation, file-transfer protocol and hosting environment - secure means of data transfer - on-screen coding (OSC) processes and an end-to-end demonstration of the OSC system, along with OSC guidance documents for coders - monitoring of coding progress and steps to ensure progress is maintained, including accurate MI - data capture and management of access arrangements for pupils - working with modified materials - creation of script archive and secure transfer to STA The process walk-through should take place over a full day at the Supplier’s main site, that is, from where the project will be delivered. Where elements of delivery are to be conducted by a sub-contractor, site walk-throughs may also be required at sub-contractor premises. All walk-throughs should describe hand-offs between parties and the Supplier must provide a written summary of arrangements confirming their assurance that any sub-contractors are ready to deliver. STA will provide feedback on the process and make recommendations for improvements and changes. The Supplier must provide evidence of steps taken to address areas for improvement, weaknesses or security concerns. STA will sign off the end-to-end process, once agreed. | w/c 13 January 2020 |
| 1.3 | Project meetings | The Supplier to attend checkpoint meetings to review the progress of the project against the agreed schedule, highlight any risks and issues and assign and track actions. Supplier to provide the following documentation 24 hours before the weekly checkpoint meeting: - project status and highlight reports - updated risk and issue logs. Full risk logs will not be required on a weekly basis – but risks of high severity rating, risks that have changed significantly, or those in close proximity should be included in the weekly report. STA may request an updated version of the full risk log periodically - management information as agreed in signed off product descriptions The table below indicates required meeting frequency: Phase; Dates; Frequency. Mobilisation; September 2019 – May 2020; Weekly. Delivery; June 2020 – October 2020; Weekly / daily by exception. The Supplier should not wait for the checkpoint meeting in order to inform STA of any issues. Issues should be brought to the attention of the STA project manager as soon as possible on the working day that the issue has arisen. The Supplier’s approach to dealing with problems and incidents will be recorded in the approach to incident and problem management document (Requirement 6). | Ongoing |
| 1.4 | Lessons learnt meetings | The Supplier must record lessons learnt throughout the duration of the project and will be required to: - attend lessons learnt meetings, - contribute to a constructive evaluation of the project - identify areas for further improvement and innovation in future sampling tests and trials. 2 lessons learnt meetings will take place: 1 following test administration and another at project closure. If an early lesson is identified that may have an impact on the remainder of the project, a change request may be raised – in accordance with guidance in the Trialling and Sampling Framework Schedule 5 – in order to alter planned approaches. | w/c 29 June 2020 w/c 2 November 2020 |
| 1.5 | Sub-contracting arrangements | The Supplier must provide confirmation that all sub-contracts are in place and provide details of all sub-contractors for STA’s approval. | w/c 1 October 2019 |
| 2 | Equalities | An equalities plan must be submitted in accordance with section G4 of the Trialling and Sampling Framework at regular intervals during the project: - first report within 15 working days following the start-up meeting. - equalities report at midway point. - final equalities report at end of project. | 30 October 2020 27 April 2020 2 November 2020 |
| 3 | Exit and Transition | Supplier to submit exit and transition plans for review and sign-off to cover the following scenarios: - routine exit - emergency exit after completion of test administrator training events - emergency exit after completion of scanning | 25 September 2019 |
| 4 | Security plan and Departmental Security Assurance Model (DSAM) | Supplier’s security plan agreed and signed off. The Supplier must undergo a Security Assurance Assessment using the DSAM. The process will begin at start-up and must be completed by 30 March 2018. Any sub-contractors must complete the HM Government Supplier Assurance Questionnaire as part of the DSAM process. Further information on the DSAM process is provided at Annexe B. | 12 November 2019 27 March 2020 |
| 5 | Systems test strategy and plan | The Supplier must document a systems test strategy and plan and submit to STA for review. | 16 October 2019 |
| 6 | Approach to incident and problem management | The Supplier must document an approach to incident and problem management and submit to STA for review. | 16 October 2019 |
| 7 | Helplines | The Supplier must submit a helpline forecast, resource management plan and training schedule to STA for approval. | 17 March 2020 |
| 8 | Inform schools of statutory participation | Confirmation of school participation STA will inform schools on 27 April 2020 that they have been selected to participate in the science tests. STA will also contact LAs and controlling academy trusts to inform them of schools that will be required to participate before schools are informed. The Supplier must confirm that schools are aware of selection, work with them to agree suitable test dates (within the 8–19 June window) and provide the final timetable for administration of the tests to STA by 5pm on 15 May 2020. Confirmation of pupil participation The Supplier must inform each school 5 working days before scheduled test administration, which of their pupils (5 or 10 depending on TPT participation) have been selected to sit the tests, taking account of school national and religious holidays, in accordance with the agreed test administration timetable. | 15 May 2020 (fixed date) 22 May – 12 June 2020 (fixed date) |
| 9 | Guidance documentation | The Supplier must work with STA in order to update the test administration guidance, administrator questionnaire, administrator training materials and attendance register. The Supplier must contribute to and jointly sign off guidance for participating schools that will be drafted by STA, and published on GOV.UK | 28 February 2020 6 April 2020 |
| 10 | Recruitment of administrators | The Supplier must recruit administrators according to the capacity model that will be agreed as part of the administrator recruitment, training and management strategy. | 27 March 2020 |
| 11 | Allocation of administrators | The Supplier must provide an assurance statement detailing the allocation of administrators to schools. | 12 May 2020 |
| 12 | Training of administrators | The Supplier must train administrators specifically for the administration of these tests. All materials will need to be printed and collated in advance. STA will attend training events and deliver parts of the training as agreed by both parties. The supplier must propose an efficient and cost effective method by which to deliver training as detailed in the Administrator Recruitment and Training strategy. Training venues must be made available in London, Birmingham and Manchester, to ensure regional spread, and should be accessible using public transport. | 4 May 2020 |
| 13 | Test booklet scanning specification | The Supplier must work with STA to agree a final test booklet scanning specification. STA will provide the supplier with specifications (including dimensions, colours and finishing) and pagination and quantity estimates for the test materials by 25 September 2019. Estimates are provided in Section 1.c. The Supplier must provide the scanning elements specification to STA by 23 October 2019 so that STA can apply them to the test materials artwork. The Supplier must propose a quality assurance regime by 23 October 2019, that ensures the printed test materials match the STA specifications and the signed-off production proofs are free from defects that would prevent pupils accessing the tests as intended, and are compatible with the scanning and image capture process. | 23 October 2019 (fixed date) |
| 14 | Print reassurance and end-to-end testing report | The Supplier must provide confirmation and proof that print quality can be achieved, scanning processes work and sample data and data elements that are used to drive the process can be used as planned. | 5 February 2020 (fixed date) |
| 15 | Production | STA will hand over test booklets to the Supplier for printing for SST on 31 January 2020 and TPT on 6 April 2020. The Supplier must produce sufficient quantities of materials (standard and modified) to the required quality standards. | To be agreed |
| 16 | Collation and distribution of materials to administrators | The Supplier must create school batches, create administrator consignments and distribute to administrators. | 3 June 2020 |
| 17 | Test administration | The Supplier must ensure the administration period is managed securely, with the correct pupils sitting the correct test booklet combinations and administration documentation being completed fully and accurately. | 8 – 19 June 2020 (fixed date) |
| 18 | Validation of returned scripts and reporting of any missing or lost scripts | The Supplier must provide evidence that all materials have been returned and are accounted for within the agreed timescales. The Supplier must validate returned scripts and provide a written report to STA on any scripts that are missing or lost or have been removed for any reason. | 9 July 2020 |
| 19 | Scanning and matching | The Supplier must provide confirmation that all scripts have been successfully scanned (or dealt with as unscannables) and that pupil-script matching is complete and accurate. | To be agreed |
| 20 | Coding capacity model | The Supplier must submit a coding capacity model (see section 1.c for details) for both SST and TPT to STA for approval by 29 October 2019. STA will approve the coding capacity model by 12 November 2019. | 29 October 2019 |
| 21 | Approach to management of coding windows | The Supplier must submit an approach to management of coding windows document to STA for approval. This document must include: - a coding plan which sets out how coding will be managed and must include a decision log - an escalation process - a coder communications plan - standardisation rules - deadlines for all activities | 29 October 2019 |
| 22 | Coder training plan | The training plan (see section 1.c for details) must be submitted to STA for approval. | 19 November 2019 |
| 23 | Senior Coder recruitment (SST) | The Supplier must recruit and contract the SST senior coding team according to the hierarchy agreed in the coding capacity model, to be completed by the date opposite. | 6 January 2020 |
| 24 | Senior Coder recruitment (TPT) | The Supplier must recruit and contract the TPT senior coding team according to the hierarchy agreed in the coding capacity model, to be completed by the date opposite. | 14 February 2020 |
| 25 | Coder recruitment (SST) | The Supplier must recruit SST coders according to the agreed coding capacity model (see section 1.c for details) to be completed by the date opposite. | 27 March 2020 |
| 26 | Coder recruitment (TPT) | The Supplier must recruit TPT coders according to the agreed coding capacity model (see section 1.c for details) to be completed by the date opposite. | 2 July 2020 |
| 27 | Initial sample of scripts (SST) | Initial sample of scripts (at least 100 scripts per test version) for SST must be available on screen for the selection of items for ongoing quality assurance. | To be agreed |
| 28 | Initial sample of scripts (TPT) | Initial sample of scripts (at least 100 scripts per test version) for TPT must be available on screen for coding frame development, selection of standardisation scripts and items for ongoing quality assurance and preparation of coder training materials. | To be agreed |
| 29 | Coders trained (SST) | The Supplier must train coders for SST to the specification agreed with STA. | 3 July 2020 |
| 30 | Coders trained (TPT) | The Supplier must train coders for TPT to the specification agreed with STA. | 7 September 2020 |
| 31 | Coders standardised (SST) | The Supplier must confirm that sufficient numbers of coders have successfully passed standardisation to code SSTs. Two standardisation sets must be conducted. | To be agreed |
| 32 | Coders standardised (TPT) | The Supplier must confirm that sufficient numbers of coders have successfully passed standardisation to code TPTs. Two standardisation sets must be conducted. | To be agreed |
| 33 | SST and Anchor tests Coding | The Supplier must ensure that all coding for SST and TPT anchor tests is completed and that the procedures and quality checks documented in the relevant product descriptions have been completed. | To be agreed |
| 34 | TPT Coding | The Supplier must ensure that all coding for TPT is completed and that the procedures and quality checks documented in the relevant product descriptions have been completed. | To be agreed |
| 35 | Coder coding quality assurance data (SST) | The Supplier must accurately capture coder coding quality assurance (QA) data for standardisation and ongoing coding QA for all coders and provide the data to STA in an electronic file format to be agreed with STA. The Supplier must conduct a coder grading process as part of performance management. The Supplier must also hand over a file of all coders’ queries, the names of the coder and supervisor, the children’s responses and how each was coded. | To be agreed |
| 36 | Coder coding quality assurance data (TPT) | The Supplier must accurately capture coder coding quality assurance (QA) data for standardisation and ongoing coding QA for all coders and provide the data to STA in an electronic file format to be agreed with STA. The Supplier must conduct a coder grading process as part of performance management. The Supplier must also hand over to STA a file of all coders’ queries, the names of the coder and supervisor, the children’s responses and how each was coded. | To be agreed |
| 37 | Coder register | The Supplier must maintain a register of coders’ details (owned by STA) and provide to STA on the following basis: - Upon the Supplier contracting sufficient coders required to reach the agreed coding capacity for SST and TPT. - On a monthly basis to take account of any changes to the coding hierarchy and inform STA of initial coder grades. - At the end of the test cycle to inform STA of final coder grades. A complete copy of the final Coder Register must be provided to STA (who may use it as required), within three weeks following the coding completion deadline for TPT. Coder Register requirements are outlined at Appendix 2. | Ongoing from the start of coder recruitment 23 October 2020 |
| 38 | Data capture of questionnaires | The Supplier must capture all responses from the administrator questionnaires and provide the data to STA in an electronic file in a format to be agreed with STA. Further, the outcomes from the analysis of the questionnaires must be provided in the report template at Appendix 2. | 30 July 2020 (fixed date) |
| 39 | Data capture of attendance codes | The Supplier must accurately capture all data from attendance registers and provide this to STA. | 24 July 2020 |
| 40 | Preliminary data feed - item level (SST) | The Supplier must securely provide a data feed of item level data – at the lowest code capture level – (minimum 10% of data for each paper) to STA in an electronic file format to be agreed with STA. The Supplier must confirm that all checks documented in the Data capture and quality of data and On-screen coding and coding quality assurance measures product descriptions have been completed. | 24 July 2020 |
| 41 | Data feed - item level (SST) | The Supplier must securely provide 100% data feed of item level data at the lowest code capture level - to STA in an electronic file format to be agreed with STA. The Supplier must confirm that all checks documented in the Data capture and quality of data and On-screen coding and coding quality assurance measures product descriptions have been completed. | 14 August 2020 (fixed date) |
| 42 | Preliminary data feed - item level (TPT) | The Supplier must securely provide data feed of item level data at the lowest code capture level (minimum 10% of data for each paper) to STA in an electronic file format to be agreed with STA. The Supplier must confirm that all checks documented in the Data capture and quality of data and On-screen coding and coding quality assurance measures product descriptions have been completed. | 25 September 2020 |
| 43 | Data feed - item level (TPT) | The Supplier must securely provide 100% data feed of item level data at the lowest code capture level - to STA in an electronic file format to be agreed with STA. The Supplier must confirm that all checks documented in the Data capture and quality of data and On-screen coding and coding quality assurance measures product descriptions have been completed. | 19 October 2020 (fixed date) |
| 44 | Final administration report | The Supplier must produce a test administration report with the level of detail and in the format set out in the Functional Requirements (section 1.c.). The trial administration report should be split into three parts: A, B and C. - part A – administration report - part B – analysis of questionnaire data - part C – reporting on the test papers | 10 August 2020 |
| 45 | Handover electronic archive | The Supplier must hand over electronic archives of test scripts and administrator questionnaires to STA as described in section 1.c. | 28 August 2020 (SST & TPT anchor tests) 30 October 2020 (TPT) |
| 46 | Handover of coder training materials and coding frames | All training materials and finalised coding frames must be handed over to STA in the format agreed with STA. | 28 August 2020 (SST) 30 October 2020 (TPT) |
| 47 | Exit | Routine exit plan successfully completed. | 30 October 2020 |
| 48 | Apprentices | The Supplier is required to support the DfE apprenticeship policy and shall employ apprentices and report the numbers of apprentices employed during the delivery of the contract for STA. | 30 October 2020 |

| 1. Specification of Requirements 1.c. Functional Requirements |  |  |  |
| --- | --- | --- | --- |
| Subjects | 2020 key stage 2 (KS2) national curriculum science sampling test (SST) and KS2 science technical pre-test (TPT) |  |  |
| Sub-Contractors | The Supplier shall ensure that every proposed sub-contractor, consortium member and adviser abides by the requirements of the Framework Agreement and this ITQ. |  |  |
| Project Management | - The Supplier must use a product breakdown structure to illustrate the products required in delivery of the project. - Product descriptions (PDs) must be provided for, but not limited to, the following deliverables and agreed with STA. PDs should consider the quality criteria, quality tolerances and quality method in line with PRINCE2 methodologies: - trial administration and test administration guidance - recruitment and contracting of coders - recruitment, management and training of administrators - training of coders and coder training plan - coder training, practice and standardisation materials - end-to-end testing - tests and administrative materials produced - school, coder and administrator consignments fulfilled - scripts collected and scanned for onscreen coding - on-screen coding and coding quality assurance measures - data capture and quality of data - school facing systems - school communications - helplines - security - STA will sign off all PDs and these must be referred to by the Supplier when creating deliverables during delivery. - PDs must be used at the handover of each deliverable to check that the quality criteria detailed by the Supplier have been achieved before consideration for sign-off by STA. The template provided at Appendix 3 should be used. Full risk and issue logs must be submitted for review by STA in advance of the start-up meeting. Key risks will be monitored through senior supplier meetings during the course of the project. Risks should have clear management and contingency plans. Where sub-contractors are involved, the Supplier must define the sub-contractors and their credentials, to provide assurance that they are equipped to deliver the planned work. Logs should be maintained and used at project meetings to highlight the risks that have changed RAG status, are of high severity or in close proximity or to highlight issues. The full risk log must be available for STA to review upon request throughout the course of the project. - A product-based project schedule must be maintained and shared with STA fortnightly. The preferred format for this is MS Project; however, an Excel workbook will be accepted. The schedule must be detailed and kept up to date and all changes must be discussed and agreed between the Supplier and STA at checkpoint meetings. - A highlight report must be created and used to present project progress at checkpoint meetings. - A document tracker must be created, listing all documents, their ownership and timescales for when they are due for delivery, review and sign-off. |  |  |
| - Change control | - A change request must be completed for all proposed variations to the contract or key changes to approach that might introduce risk or have security implications. This applies whether or not there is any reduction or increase in costs. A change request template has been provided at Appendix 3. In order to be able to authorise changes, STA will require a detailed, transparent breakdown of: - the rationale for the change - the intended approach to implementation - the operational, financial, security and reputational implications of the intended approach |  |  |
| Management Information (MI) | MI will be required at various points throughout the project. The precise content, timing and frequency of MI will be agreed through signed off PDs. MI must include, but is not limited to: Informing schools: - school confirmation of participation - school withdrawals on the basis that all pupils nominated are working below the standard - agreement of test dates - agreement to participate in teacher questionnaires - confirmation of pupil selection - access arrangements - requirements for modified test versions Helpline: - helpline call volumes and types (including complaints) - abandoned calls Print: - print progress against forecast for: - test materials (standard and modified) - coder training materials - administrator training materials and guidance - evidence of the application of the quality criteria documented in the PD - reported issues by administrators and coders Fulfilment: - progress against forecast for the collation of: - school batches - administrator packs - coder and administrator training materials - evidence of application of the quality criteria documented in the PD - reported issues by administrators and coders Logistics: - progress with deliveries against forecast to and from administrators and coders shown as both number of packages and number of recipients - details of delivery exceptions for each despatch - parcel tracking (ongoing at points when scripts are in transit) – to and from administrators Administration: - administrator recruitment against target and forecast - allocation of administrators to schools against forecast - administration progress Scanning: - scanning progress against forecast - script matching progress against forecast - the number of non-scannable scripts received and a reason for each Missing and lost scripts: - details of all unaccounted for scripts and their status in the missing and lost pipeline Coding: - Coder recruitment and contracting progress against forecast - Provision of UAT data (for Standardisation scripts) 2 working days after UAT coder standardisation - coding progress against forecast - precise requirement to be defined in the On-screen coding and coding quality assurance measures product description once coding model is defined - unscannable scripts coding progress - coding capacity against stated requirement - coder status: number of approved, suspended, stopped, withdrawn - coding at risk of being reallocated due to coders being stopped - monthly reporting on coder register and coding capacity - coding quality assurance data – including information on number of seeds failed and where changes have been made to coders’ marks by supervisors - destruction of training materials Data capture: - progress of attendance register data capture - capture progress in relation to administrator questionnaires Service management: - monthly service management report |  |  |
| Equalities | For details, please refer to Section G4 of the Trialling and Sampling Framework. An equality plan must be submitted at regular intervals during the project: - following the start-up meeting - at midway point - final equalities report at end of project Refer to 1.b deliverables and outputs section for dates. |  |  |
| Exit and Transition | The Supplier must submit draft routine and emergency exit and transition plans in advance of the project start-up meeting with sign-off being no later than one month following this. The routine exit plan should describe what activity would happen as a result of exit of the call-off at the natural end of the work. A template is provided at Appendix 3. The Supplier will also be required to submit emergency exit and transition plans. These are scenario-based plans to describe what activity will happen as a result of exit at various stages of contractual delivery. Scenarios will be provided at project start-up. |  |  |
| Test Type and Administration | The test administration window will be 08 – 19 June 2020. |  |  |
|  | Item Validation Trial (IVT) | Technical Pre-Test (TPT) | Science Sampling Test (SST) |
|  | N | Y | Y |
|  | Requirement for each pupil: 1,900 schools will participate in the live science sampling test, with 5 pupils per school sitting the test. 900 of the 1,900 schools will also participate in the technical pre-test, with an additional 5 pupils per school sitting the TPT. Each pupil will sit one complete test comprising 3 test booklets – known as a combination – for either the SST or the TPT. Each booklet (for both SST and TPT) will take 25 minutes. There can be a break between each booklet. The booklets must be administered in the order specified in the combination tables provided by STA. Example tables are included below. Final combination tables for SST and TPT will be provided by STA on 6 March 2020. All tests must be administered securely by trained administrators. Each pupil must complete their 3 tests on the same day. |  |  |
| Versions for Sampling and Trialling | Science Sampling Test (SST) 15 test booklets to be administered in different combinations. The 15 test booklets used in the 2018 SST will all be re-used in 2020. One SST combination will be required to be manufactured in standard format, modified large print format and UEB Braille format. Another SST combination will be required to be manufactured in standard format and enlarged print format. See table below. Technical Pre-test (TPT) 12 test booklets – including 3 anchor booklets – to be administered in different combinations. One TPT combination will be required to be manufactured in enlarged print format. SST and TPT The test combination and order in which tests should be administered to each pupil, along with associated timings, will be detailed in the attendance register. The Supplier must ensure that the correct pupil sits the correct combination of tests, in the correct order. Any pupil absences must be recorded in the attendance register. There must be no substitutions, with the exception being the requirement to substitute a modified test combination for those pupils who require it, and to inform STA of this change. Test booklets contain an average of 34 coding requirements, so there will be an average of 34 coding boxes per test booklet in 2020. |  |  |
| Target Group and Delivery Mode | The combination tables provided below are examples only; final combinations will be provided by STA as detailed in the dependencies table. The ‘Number of pupils’ column specifies the number of pupils that STA will assign to each combination, with the exception of the modified combinations, which specify the number of pupils who required those combinations in 2018 (or 2016 for enlarged print in the TPT or braille in the SST). The number of pupils for modified combinations are indicative and cannot be confirmed until schools confirm their pupils’ requirements in 2020. SST. Combination; Position; Number of pupils. 1st; 2nd; 3rd. 1; SS001B; SS010C; SS011P; 633-634. 1b (Braille UEB); SS001B; SS010C; SS011P; 2. 1m (modified large print); SS001B; SS010C; SS011P; 7. 2; SS002B; SS008C; SS012P; 633-634. 3; SS003B; SS007C; SS013P; 633-634. 3m (enlarged print); SS003B; SS007C; SS013P; 22. 4; SS004B; SS006C; SS015P; 633-634. 5; SS005B; SS009C; SS014P; 633-634. 6; SS010C; SS013P; SS002B; 633-634. 7; SS008C; SS015P; SS003B; 633-634. 8; SS007C; SS014P; SS004B; 633-634. 9; SS006C; SS011P; SS005B; 633-634. 10; SS009C; SS012P; SS001B; 633-634. 11; SS011P; SS003B; SS009C; 633-634. 12; SS012P; SS004B; SS010C; 633-634. 13; SS013P; SS005B; SS008C; 633-634. 14; SS015P; SS001B; SS007C; 633-634. 15; SS014P; SS002B; SS006C; 633-634. TPT (including 3 anchor booklets). Combination; Position; Number of pupils. 1st; 2nd; 3rd. 1; STPT01; STPT06; STPT11; 375. 1m (enlarged print); STPT01; STPT06; STPT11; 35. 2; STPT02; STPT07; STPT12; 375. 3; STPT03; STPT08; STPT13; 375. 4; SS005B; SS010C; SS015P; 375. 5; STPT06; STPT12; SS005B; 375. 6; STPT07; STPT13; STPT01; 375. 7; STPT08; SS015P; STPT02; 375. 8; SS010C; STPT11; STPT03; 375. 9; STPT11; SS005B; STPT07; 375. 10; STPT12; STPT01; STPT08; 375. 11; STPT13; STPT02; SS010C; 375. 12; SS015P; STPT03; STPT06; 375. |
| Informing schools of participation | General requirements All communications to schools must be STA branded and shall not refer to the Supplier unless necessary and agreed with STA. STA will sign off all communications to schools for style and content, including scripts for telephone communications. The Supplier must sign off all communications in terms of accuracy of facts and procedures relating to Supplier systems and processes. A product description outlining the Supplier’s school communications approach will be required. This should be drafted following consideration of STA’s over-arching communications strategy, which will be provided for review 10 working days before the start-up meeting. Specific arrangements Confirming school participation The Supplier must ensure that all selected schools have: - either acknowledged their participation, or confirmed that all of their pupils are working below the expected standard of the tests - provided a contact name and details for future correspondence - agreed a time and date, within the agreed test administration period of 8 to 19 June 2020, when tests will be administered. All testing must take place in a school on the same day and at the same time, unless permission has been granted due to a specific, access arrangements related exception - confirmed whether a year 6 teacher will be available to discuss the TPT tests with an STA representative and if so, are advised that STA will be in touch with schools to arrange this If a school asks to be withdrawn from the tests for any other reason than that all of their pupils are working below the expected standard of the tests, the Supplier must refer the request to STA. In confirming this information, the Supplier must ascertain if the school has pupils that, if selected, would require access arrangements and what those might be. Confirming pupil participation The Supplier must inform schools of the pupils who have been selected to sit tests 5 working days before the tests are to be administered. Further, they must obtain from the school the necessary information about individual pupils that will impact on the administration of the test and agree appropriate arrangements such as: - any access arrangements that need to be made for a pupil - requests for additional time - requirements for modified materials. Pupils who have been selected to participate in the TPT and require modified large print or Braille materials will be given the live modified materials and will participate in the SST. Braille materials will be offered in Unified English Braille (UEB). If schools require specialist advice about requirements for modified materials, STA will provide contact details for its contracted modified test agency who will be able to help - availability of school staff to act as readers, scribes, translators or provide other forms of support. If necessary, a separate session may be arranged for pupils using access arrangements on the same day but at a different time - support for pupils with challenging behaviour in line with normal classroom practice - pupils who should be excused from participating on the basis that they are working below the expected standard of the test - pupils who should be excused from participating on the basis that they are working at the expected standard but are unable to access the tests, even with appropriate access arrangements - If the school believes that there is another reason why a pupil should not take the test, they must seek guidance from the supplier who must refer to STA for a decision on a case by case basis - pupils who have left the school (in which case, there must be no substitution) Wherever possible this activity should be completed on day 1 of the 5-day window prior to test administration. STA will work with the Supplier to help to verify requests and agree appropriate access arrangements with schools. Where necessary, administrators may be required to contact schools in advance of the test day to discuss specific modifications or requirements for access arrangements. Estimated access arrangements volumes, based on previous sample testing, are documented at Appendix 4. Detailed information about the use of access arrangements and what may be allowed will be provided in the Test Administration Guidance and further guidance may be provided in the administrator training sessions. No substitution of pupils is allowed under any circumstances; only those pupils selected by STA must sit the tests. The only exception is when a pupil selected for the TPT requires modified large print or Braille materials, in which case the pupil will participate in the SST. Timetable variations, early opening (other than arrangements that have been agreed with and managed by the administrator), special consideration and compensatory marks are not applicable to science sampling. |  |  |
| Updating trialling documentation | The Supplier will draft the test administration guidance, having been provided with key information on administration and access arrangements by STA. The guide and associated quality criteria will be described in the Trial administration and test administration guidance product description, but must comply with the following general requirements: - logical structure, for example, chronological - concise and free from repetition - clear key messages - factually correct - free from jargon - easy to read, for example, avoiding large paragraphs of text, favouring bullet points STA will provide information to inform this document before the start-up meeting. An early draft of the test administration guidance should be provided to STA for review by 6 January 2020. The Supplier will provide an attendance register for administrators to complete at the end of the testing period. The register must include the attendance codes required for capture by STA and the data outlined in the attendance register section below. STA will sign off the attendance register prior to and following production. Administrator questionnaires will be updated by STA. The Supplier will have the opportunity to contribute to questionnaire design and should include in the timeline the opportunity to test questionnaire design prior to data capture. The Supplier must draft administrator training materials. STA will contribute to the materials prior to joint sign-off by the Supplier and STA. |  |  |
| Administrator recruitment | The Supplier will be responsible for determining the number of administrators required to administer the tests. The Supplier must ensure that there is adequate geographical coverage and that appropriate individuals are recruited – see section SA2.3 of the Trialling and Sampling Framework. Although schools will be asked to provide assistance in line with normal classroom practice, consideration should be given to the approach to administration of modified tests and access arrangements. The Supplier must ensure that where pupils are using modified materials, the administrator has the appropriate skills and knowledge to administer the tests correctly. Once the school sample has been selected, the Supplier must allocate administrators to schools, ensuring full coverage. Should there be a school with a high number of pupils requiring access arrangements or modified test versions, such that administration may be complicated or needs to take place in more than one sitting, the Supplier may consider allocating more than one administrator. The Supplier must ensure that recruitment is in line with the agreed administrator capacity model (which should be documented as part of the administrator recruitment, training and management strategy) and that it remains so, managing withdrawals, and other issues, up to the end of the testing period. All administrators must complete a declaration of interest to confirm if they have any close relatives sitting the tests in 2020. |  |  |
| Administrator Training | The Supplier must determine the most appropriate means by which to train administrators and agree the approach with STA. The finalised test administration guidance must be provided to administrators prior to any training to allow any questions to be raised and answered. The Supplier must ensure that all administrators attend specific face-to-face training for this test administration. STA will attend and provide aspects of the training, as agreed between STA and the Supplier. Training must ensure that administrators work according to requirements in the areas of: - setting expectations of behaviour as a representative of STA - confidentiality - the context of live sampling and technical pre-testing - receiving materials and confirming receipt - storage at home, including the requirement for materials to be locked in a secure cabinet at all times when not in use by the administrator - security procedures to be followed to ensure the integrity of the materials. This includes information about confidentiality and security, particularly in relation to the use of social media and electronic communication - working with schools, including making arrangements for pupils with specific educational needs - secure transportation of materials - security procedures within schools, including the requirement that all materials are accounted for and collected at the end of test administration - administration of the tests, including ensuring that appropriate access arrangements are in place and operating effectively - completing administration documentation, such as attendance registers - escalation procedures in the event of security incidents - what to do in the event of emergency during test administration Where the administrator will be required to interact with systems in order to fulfil their responsibilities, the Supplier must ensure that system familiarisation training is included in the training. It is the Supplier’s responsibility to determine the level of support required for administrators following their training. Some aspects of the training may be reinforced in an online version. It is recommended that training takes place no more than 6 weeks prior to test administration. However, where this cannot be accommodated due to training requirements for other trials, the Supplier is advised to consider refresher training on particular aspects of training. This may also be targeted to specific individuals, such as administrators who will be required to administer modified tests or complex access arrangements. The Supplier will source suitable venues and ensure that adequate refreshments and catering are provided. A venue checklist is provided at Appendix 3. Training venues must be available in London, Birmingham and Manchester, and should be accessible using public transport. STA will review and contribute to training materials and work collaboratively with the Supplier to set agendas to ensure that training is fully effective. The Supplier must ensure that only appropriate individuals are allowed to administer tests in schools and should take action to withdraw contracts from administrators who do not perform or behave appropriately during administrator training or subsequently. |  |  |
| Attendance register | The Supplier must design and implement an attendance register solution – to be agreed with STA – that will enable the accurate recording of the attendance status of each pupil (per booklet) by the administrator and the reconciliation of scripts received and not received for coding. As a minimum, the attendance register must record: School level - school name - school DfE number Pupil level - unique pupil identifier (provided by STA) - full name - date of birth - attendance status per booklet (required status codes – and their meaning – will be provided by STA) An example attendance register is provided at Appendix 2. In advance of handover, the Supplier must provide STA with assurance that the solution is set up to produce the data in the format specified by STA by generating data feeds for user acceptance testing. Attendance data must be captured and provided to STA on or before the date of the preliminary data feed. |  |  |
| Scanning and matching | Prior to scanning, the Supplier must devise a process which enables the Supplier to: - Confirm that all expected components of a pupil’s test script are present, when compared to the pupil’s attendance status on the register. - Record at component level, where a test script is missing, partly missing or defaced. - Make corrections where the test script and attendance register do not exactly match. - Resolve either of the situations in 2 or 3 above with schools and administrators before making corrections, being mindful of minimising burden on schools. The process must record an audit trail of all changes to the attendance register. M1.32 of the Trialling and Sampling Framework applies. Scanning and matching progress profiles must be agreed with STA before scanning and matching commences. Profiles must clearly indicate tolerance in relation to the anticipated and required rates of coding in order to ensure a continual supply of work for coders until coding is complete. The critical point at which coding completion would be affected by failure to scan efficiently must be clear. Available contingency options to recover – should scanning fall behind schedule – must also be defined in the risk log. Sections M1.33, M1.37, M1.39 and M1.40 of the Trialling and Sampling Framework also apply. The Supplier must identify scripts that cannot be scanned and make arrangements to have them coded manually, for example, modified tests and scripts that are slightly damaged. |  |  |
| Collation of test materials | The Supplier must collate materials for administrators in accordance with the requirements in sections PL3.1 and SA1 of the Trialling and Sampling Framework. The Supplier must create batches for each school, containing the designated papers for each school’s selected pupils. Materials for each school must be double wrapped separately in tamper evident packaging, including those schools that have a common administrator, in order to prevent errors in administration. The Supplier must create consignments for each administrator, containing only the school batches allocated to that administrator and any supplementary documentation, stationery and packaging for script return. Each layer must be addressed to the recipient and should also confirm the return address of the sender. Consignment packaging must be robust enough to remain intact under normal handling conditions within the distribution process. The Supplier must carry out assurance tests (as agreed with STA) and demonstrate to STA, at the process walk-through, that the chosen packaging is fit for purpose. The Supplier must provide STA with details of its collation quality assurance processes and must provide 3 collation approval packs using dummy data (as provided by STA). The collation approach must fully consider the requirement to provide modified materials for administration and that modified requirements will not be confirmed until a maximum of 5 days before test administration. |  |  |
| Secure Deliveries of Test Materials | The Supplier must provide a logistics service to deliver consignments to administrators and to collect completed scripts from administrators for delivery to the scanning point. The Supplier must balance the risk of ensuring that materials are with administrators in good time with the risk of breach of security. The Supplier should avoid including too many different test booklet versions within a single package, where possible. If an external or sub-contracted coding/scanning agency is used, deliveries to the coding/scanning agency must be collated and packaged in accordance with the requirements specified in section PL3 of the Trialling and Sampling Framework. A delivery manifest and handover form must be included with all deliveries. The logistics service must enable packages to be tracked from collection to delivery and the Supplier must be able to account for materials at all times. Packages must: - be delivered only to the intended recipient - not be damaged in transit - not be lost in transit STA considers any deliveries that do not meet the criteria above to be critical exceptions that heighten the risk of early public disclosure of confidential test materials, which could invalidate the tests and cause considerable reputational damage to STA. Any missing or lost packages must be treated as a major incident and STA informed immediately. For critical exceptions, the Supplier must: - Notify STA of the incident immediately upon discovery and provide a detailed report and approach for resolution within 2 hours - Implement resolution measures and provide updates twice daily, or as otherwise agreed with STA, until the issue is resolved For administrator consignments, the Supplier must despatch replacements where the original consignment cannot be quickly located or is damaged beyond further use. The original consignment must be returned to the Supplier if retrieved at a later date, although damaged consignments must be made secure before return. Any replacement materials must be tracked and the same procedures followed as in the original delivery. After resolution, the Supplier must provide a report to STA that describes the incident, timelines and steps taken to resolve the issue and to prevent it happening in future. The Supplier must propose an incident management plan to describe their approach to handling both critical exceptions and other typical exceptions that could prevent first-time delivery, for example, recipient not available to take receipt of the delivery. Non-critical exceptions must be notified to STA within 24 hours and updates provided daily. A security incident reporting template is provided at Appendix 3. Daily management information (MI) must be provided to STA throughout the delivery period at 09:00hrs and 17:00hrs. |  |  |
| Test Administration | Detailed test administration guidance will be drafted by the Supplier, with contributions from STA. This document will be jointly signed off. The requirements of test administrators may include, but are not limited to, the following activities. Prior to test administration, the administrator must: - securely transport test materials to the school and ensure that all materials are present - ensure that they have details of any specific arrangements made for the pupils sitting the tests, such as access arrangements - attend the school on time, show photographic ID and introduce themselves - ensure that a suitable venue and layout for testing has been allocated and that school representatives are available as required and agreed - accommodate STA observers - ensure that confidentiality forms are signed by all individuals, other than pupils, who have access to test materials or are present during testing The administrator must ensure that test materials remain secure at all times. All requirements for modification must be discussed with the school and completed by the Supplier. Materials must not be photocopied by schools under any circumstances. The Supplier must photocopy tests onto coloured paper at the request of schools. This might apply to requests for test papers on pink, blue, yellow, green, lilac or cream paper. All test combinations must be photocopied onto coloured paper on request, because pupils must sit the test combination they were allocated. The Supplier must inform STA of all such arrangements. Immediately after test administration, the administrator must complete the attendance register. They may need to ask for assistance in this from the school representatives who are present. During test administration, the administrator must: - adhere to the instructions within the test administration guidance and follow the prepared scripts when introducing the tests to pupils - ensure that the correct pupils receive the correct test booklets, in the correct order. In 2014, 2016 and 2018, papers were personalised to facilitate this. The Supplier must ensure that their approach to this minimises risk - confirm that agreed access arrangements are in place, referring to data collected prior to administration, and that no unauthorised arrangements occur - ensure that pupils are given the correct amount of time to complete the tests. Given potential complexities with timing as a result of access arrangements, the Supplier should consider how it will ensure that the correct timings are adhered to by administrators, for example, the use of a timings grid for completion by administrators. Following administration, the administrator must complete the administrator’s questionnaire. This will ensure that they can recall all relevant information and that materials can be sealed and not re-opened once the administrator has left the test room. Completion of the questionnaire should take approximately 10 minutes. The administrator must ensure that all test materials, including unused materials, are collected and accounted for at the end of the test period, securely packaged for transportation and securely stored. Under no circumstances must test materials be left in schools. If any issues arise, that require assistance, whilst the administrator is in the school, they should contact the Supplier for advice. The Supplier must ensure there are qualified and informed individuals available to take calls from administrators throughout the administration window. The administrator will be expected to be in the school for c.2.5 hours. |  |  |
| Test Observations | STA staff may wish to observe test administration at a number of schools. STA staff may also wish to discuss the tests with approximately 30 year 6 teachers whose pupils participated in the TPT, in order to gain feedback on the performance of items and to inform the test development process. The Supplier must provide details (dates, schools, locations) to allow STA staff to select the most appropriate schools to visit. Visits will be negotiated and agreed between STA and the Supplier. |  |  |
| Return of scripts to Supplier | The Supplier must ensure the secure return of all test materials – used and unused – from each school in accordance with Trialling and Sampling Framework requirement G3 by 23 June 2020. This includes test scripts, attendance registers, administrator questionnaires and supporting documentation. The Supplier must provide a courier service for administrators to return the materials. The Supplier can provide alternative arrangements, such as administrators delivering in person, but must describe these in the Scripts collected and scanned for onscreen coding product description. The incident management and exception process described in Secure Deliveries of Test Materials above applies to the return of scripts to the Supplier. Administrators must securely return materials to the Supplier as soon as possible following administration but at least once a week. The administrators must not book collections with the carrier for Fridays to reduce the risk of packages becoming lost in the courier’s network over the weekend. Administrators must list the package contents on a manifest. On receipt, the Supplier must check the contents of all packages against the manifest. Any discrepancies must be reported to STA immediately, and within 24 hours of receipt of materials. The Supplier must provide details of the process in place to investigate and recover lost and missing materials by providing a security incident report in a timely manner. STA may request access to hard copies of individual test papers for maladministration script interrogation. |  |  |
| Recruiting and contracting coders | The Supplier must recruit and contract all coders, including senior coding teams, for both SST and TPT. The Supplier will be responsible for the recruitment, contracting and management of a sufficient number of coders in order to complete all coding within the agreed milestone dates and to agreed quality standards. If required, the Supplier will recruit additional and new coders via GOV.UK The Supplier must ensure that they recruit coders with the skills to code UEB Braille test scripts. Section M1.5 of the Trialling and Sampling Framework also applies. References to marking in the framework apply equally to coding. The Supplier is responsible for everyone they recruit. A breach in any aspect of test and/or trial security should be treated as severe, and STA would expect a full incident report to be completed, and information on the supplier’s next steps to be provided, at the earliest opportunity, regardless of where and when the breach was identified. The detailed roles and responsibilities of the members of the senior coding team will be agreed between STA and the Supplier as part of sign-off of the coding capacity model. The Supplier must provide a list of proposed senior coders in their proposal, on the understanding that the list is provisional and likely to change, once dates, responsibilities and team structures are confirmed. The Supplier may offer contracts for either SST or TPT or for both to a coder or senior coder and must confirm their approach in the coding strategy. Applicants who are not selected to be senior coders but meet the criteria to be coders and wish to participate, should be added to the coder pool. The Supplier must submit draft contracts for each unique role to STA for comment. Contracts must include provision for coders to agree to their information being used by STA and its authorised third party organisations in future exercises. It is desirable for coders of all ranks to have completed coding – to the required quality standards – in the 2018 science coding cycle or in previous trialling since 2012. Where this is not the case, coders must have qualified teacher status (QTS) and at least one year’s qualified teaching experience in science and key stage 2 or have equivalent experience in teaching science or other suitable experience in a scientific or educational field. It is desirable that lead and deputy lead coders have held senior roles in previous trials or live tests in science. STA will facilitate the distribution of invitations to coders by providing the current national curriculum register of coders to the Supplier. However, the Supplier must consider recruiting individuals who are not on this list and must develop criteria for selection, in agreement with STA. It is expected that a relevant, science-based task would be developed by the Supplier and undertaken by all applicants, including senior coder applicants. The high-level approach to recruitment and selection must be documented in the coding strategy. The Supplier must provide a coding capacity model to STA that illustrates that they will recruit sufficient coders to code the test scripts in the given timeframe and aligns with the coding hierarchy that is provided by STA. The total recruited coding capacity should ensure an adequate level of coding and include additional capacity for any areas of risk identified by the supplier. The model should include, but not be limited to, the following information: - roles and responsibilities of each member of the coding hierarchy – see Appendix 4 - required coder numbers: the number of coders (including senior coders) to complete all coding within the timeframe, including a coding forecast. In calculating this, the Supplier must consider the requirement to recode any items, code seeds, item groups or scripts from coders who have been stopped. The Supplier must also consider the way in which test scripts are split up to code (by item, item group or test booklet) which would contribute to determining the level of flexibility that may be present in the coding pool - allocations: the minimum number of test items or item groups (whichever is relevant to the solution) coders and members of the senior coding team will be required to code - amount of contracted spare coding capacity: the volume of unused coding capacity available as a contingency against unforeseen delays to coding progress due to coders withdrawing or not meeting the coding QA criteria - a plan to describe how coders will be managed throughout the coding window to ensure that all coding will be completed within the agreed timeframe As anchor tests will be consistent for SST and TPT, all anchor test scripts must be coded during the live coding window. The coding capacity model must reflect this requirement. The coding capacity model must be agreed with STA 2 weeks following the start-up meeting. STA will provide 2018 test materials to the Supplier upon contract award in order to facilitate this. As some of these materials will be re-used in 2022 delivery, the Supplier must ensure that these materials remain secure and are deleted once no longer required. A complete list of allocations including, but not exclusive of, allocation by item group, coder to coding teams and coders to items must be provided to STA, prior to the coding event. The Supplier must ensure that they assign responsibility for acting as points of contact for escalation to the STA test development researchers (TDR) and that they minimise the number of individuals assigned to this role. |  |  |
| Recruiting and contracting the senior coding team (SST and TPT anchor tests) | Coding frame finalisation will be managed by STA. The Supplier will not recruit and contract coders for this exercise. The Supplier will be responsible for the recruitment, contracting and management of the senior coding team, who will: - familiarise themselves with the coding frames for the test booklets and existing training and practice materials, in preparation for training coders - Select standardisation materials using items from 2018, providing 2 sets of standardisation materials - Carry out UAT on standardisation materials - select ongoing quality assurance materials using live test scripts - train coders - manage and support coders throughout practice, standardisation and coding, provide appropriate feedback and report on their performance to the Supplier The Supplier must ensure that lead coders meet the standard by asking them to complete an assessment task. |  |  |
| Recruiting and contracting the senior coding team (TPT) | The Supplier will be responsible for the recruitment, contracting and management of the senior coding team, who will: - work with STA TDRs to refine coding frames - work with STA TDRs to produce training, practice, standardisation and ongoing quality assurance materials, providing 2 sets of standardisation materials - train coders - manage and support coders throughout practice, standardisation and coding, provide appropriate feedback and report on their performance to the Supplier The supplier must ensure that lead coders meet the standard by asking them to complete an assessment task. |  |  |
| Coder Payment | The Supplier must utilise an appropriate mechanism for paying coders throughout the coding hierarchy the correct amount for all work undertaken and completed, based on accurate data. This is likely to include analysis of information regarding the quantity of test script codes submitted or the time spent coding, supervisory duties undertaken and attendance at meetings. The total payment expected for each role should be calculated to ensure that it accurately reflects status in the coding hierarchy. The Supplier must ensure compliance with employment law in payment of contractors. STA has provided the Supplier with a coder payment model at Appendix 4. The Supplier must administer payments to coders and reimburse associated expenses. The Supplier must ensure that all expense claims are verified in order to mitigate fraud and may be required to provide evidence of this to STA. The Supplier must provide a mechanism to ensure that coders are paid without delay and in any case no later than 30 days after the completion of services. Expenses structures are to be agreed with STA. Once approved, the Supplier shall not amend the terms on which coders are engaged without STA’s prior written consent. The proposal must contain details of fixed and variable costs for coder recruitment. Costs must be transparent and presented in such a way as to allow STA to estimate the cost of call-off orders. |  |  |
| Coder communications | Section M1.2 of the Trialling and Sampling framework applies. Coder communications must be covered in the coding management strategy, coder training plan and approach to management of coding windows documents. |  |  |
| Coder register | The Supplier must provide a valid record in the coder register for all data fields required by STA. The Supplier must ensure that data from the coder register is accessible, up-to-date, 100% accurate and made available, in a format to be agreed by STA. See coder register requirements at Appendix 2. The Supplier must ensure that all contracts with coders state that STA shall be the data controller (as defined in the data protection legislation) of any personal data that relates to the coders and that is processed in connection with national testing. The Supplier must also ensure that the contracts include notices stating the purposes for which personal data will be processed by STA and its Suppliers (one of which will be to audit the quality of the coding). The coder register must clearly identify which coders have given their permission for their details to be used in future recruitment exercises. The coder register will be supplied as an Excel or equivalent file, with a minimum of a column per field and row per coder per test and will be encrypted to HM Government Security Policy Framework requirements and transferred via a secure portal or other secure transfer mechanism. Any passwords for encrypted files must be supplied via an ‘out of band’ transmission, that is, by telephone if transferred by email, or by email if transferred over an SFTP site. The Supplier shall ensure that the storage and security of data relating to coders, including during its transfer to STA, complies with current data protection legislation. |  |  |
| Coder training plan | The Supplier must develop a coder training plan which outlines who the Supplier will contract to deliver coding and how they will be trained. The plan must include: - how and when the supplier will develop, print and distribute training materials - what meetings will be held and their duration - what will be the inputs, outputs and outcomes of each meeting - what is the rationale for the selected approach - venue details and staffing requirements for all planned activities requiring a venue - plans for test script logistics - plans for test script security during training - plans for training coders on use of the onscreen coding system - the training materials that will be developed The coder training plan must be submitted to STA for approval by the date specified in section 1.b. |  |  |
| Coder training | Coders should be trained separately for SST and TPT, regardless of whether the same individuals are involved, due to the difference in timing of the coding windows. SST coding includes the anchor tests, which will be the same for SST and TPT. The Supplier must ensure that coders attend face-to-face training events as required according to their role(s). All coders must attend training. Training events must include, but not be limited to: - training for all coders (including seniors) on the use of the onscreen coding (OSC) system. It is highly desirable that this be face-to-face, hands on and using science, rather than another subject, to demonstrate the system. The Supplier must ensure that the OSC system has a practice area which allows coders to familiarise themselves with the functionality of the system away from the area containing live papers. Practice scripts must be science scripts. The Supplier must also produce step by step guides on the use of the OSC system for both senior and non-senior coders and where to go for support - discussion and explanation of any administrative requirements - explanation of the requirements of standardisation - explanation of what will happen to the data generated by testing - explanation of how comments made or responses flagged by coders will be dealt with - the process of escalating coding queries - communication with the supervising coder and other coders - security and confidentiality - coder payments - discussion of and training on the coding frames, delivered by the senior coders to their allocated teams - the process and mechanism for monitoring coding performance and accuracy, including ongoing quality assurance checks The Supplier must ensure that any specific training for coders that are coding modified test scripts is provided. The Supplier must also ensure that STA and its nominated representatives (regulatory or stakeholder) are invited to attend all meetings and training events sufficiently in advance to allow travel and other arrangements to be made. It must also provide an agenda, details of the venue and relevant materials. Training materials Training materials from the 2018 SST will be re-used in the 2020 SST. SST training materials The Supplier must manage the senior coders to: - select items for ongoing quality assurance checks using live responses (from an early sample of at least 100 scripts per test version) TPT training materials Training, practice and standardisation materials must be produced in the format agreed with STA in order to ensure that they may be re-used in future test cycles. All materials used during the generation of coder training, practice and standardisation materials must be clearly identifiable as being draft. The Supplier must plan meetings with consideration to allowing enough time for work to be completed outside meetings and for updated materials to be printed for use at subsequent meetings. The Supplier must record and circulate actions from all meetings to ensure that agreed changes are monitored and implemented. All individuals at each rank of the senior hierarchy should have equal input into this process. The Supplier must manage the senior coders to: - work with STA TDRs to apply the draft coding frames (provided by STA) to live examples (from an early sample of at least 100 scripts per test version) - complete coding frame development - select standardisation scripts and items for ongoing quality assurance - prepare coder training materials Pre-coding It is STA’s preference that all pre-coding will be coded on-screen. The Supplier must propose the most effective attendance pattern by senior markers at all pre-coding events. The supplier must ensure that senior markers are sufficiently familiar with the coding materials, to ensure an acceptable standard of coding and supervision. As a minimum, STA would expect all lead coders to attend all events, and deputy leads to attend events as deemed necessary by the Supplier. STA require sight of the selection of training, standardisation and seeding processes so such activities must take place face-to-face. A certain amount of preparatory work may be completed remotely by senior markers in advance of face-to-face meetings. However, in order to understand the proposed scope of the remote activity, STA would expect the Supplier to outline such activity in their proposal. TPTs For all standardisation and quality assurance item selection exercises, there must be a system in place that allows at least 2 members of the senior coding team to independently code scripts and then compare outcomes in order to ensure accuracy. The system must automatically flag discrepancies and confirm to senior coders when this work has been completed. The OSC system must allow codes generated at this stage to be saved. The OSC system must allow for codes to be cleansed following these exercises and returned to the pool for live coding. All tests The Supplier must print sufficient copies of materials for these exercises to be completed and organise venues. The Supplier must print training materials according to coder numbers. The Supplier must ensure that practice, standardisation and quality assurance scripts are available in the OSC system. Quality assurance items must appear no differently to live test items. The Supplier must produce guidance (agreed with STA) for members of the senior coding team to enable them to deliver training, support and manage the coder pool. The Supplier will be required to manage the collation and distribution of coder training materials that they have printed. Handover dates for archives and pre-existing training and practice materials and draft test materials and coding frames are set out in the dependencies table in section 1. Following coding, the Supplier must ensure that: - all materials held by the senior coding team are logged and handed over to STA - all coder materials (other than those of the senior coding team) are securely destroyed and evidence of this is provided to STA upon request. Where responsibility for this lies with coders, each coder must complete a declaration form confirming secure destruction. STA will require MI to track progress of destruction of materials |  |  |
| Coder training - event management | The Supplier must source and book a regional spread of venues, which are suitable for hosting coder training events. Ideally, STA would like to see at least two regional venues each for SST and TPT coder training (one in the North and the other in the South). However, one venue each for SST and TPT coder training may be acceptable, provided the venue is within the Midlands area or in London. The venue(s) must be easily accessible by public transport. Following contract award, STA recommends that the supplier conducts postcode analysis to determine the most suitable venue location(s). Venue security checklists must be completed (see Appendix 3) and sent to STA before a venue is approved. Training events for the senior coding team may be held on the Supplier’s premises. In addition to the services detailed in section M1.15 of the Trialling and Sampling Framework, STA staff will require access to a dedicated and secure photocopier, secure network points (for a wired connection), and secure Wi-Fi availability. Space requirements per coder (for coder training) For the duration of the training event, each coder should have enough space to open 2 A4 booklets side by side and have two closed A4 booklets in front of them. STA recommends that the minimum table space, per coder, should be 70cm (depth) by 100cm (width), but the Supplier should not be restricted to these measurements. Groups should not be distracted by others having breaks or lunch if all break times do not coincide. |  |  |
| Coding | The coding model to be used is onscreen coding at home or at a centralised location. The Supplier must ensure that the method of delivery is appropriate to the subject and scale of the requirement. The coding model will be subject to approval by STA. The Supplier must develop an approach to manage the coding window which outlines: - roles and responsibilities, including standardisation - management of coders throughout standardisation, including rules for stopping or providing feedback to coders - management of script availability and allocation of coding throughout the coding window, including reallocation arrangements - how the OSC system will support the coding hierarchy - the mechanism that will be employed to ensure the security of all test scripts and to ensure they are accounted for both before and after coding is completed - the coding timeline, including projected coding completion profiles and deadlines to be issued to coders - the decision making and escalation routes during the coding window - the mechanism that will be employed to allow coders to escalate coding frame queries or clarifications during the coding period - the mechanism that will be employed to capture feedback from coders on the draft coding frames during or following the coding period (TPT only) - how agreed quality assurance processes will be implemented - the mechanism that will be employed to allow supervising coders to view and re-code items or item groups of their allocated coders - reporting contents and arrangements from senior coders to the Supplier and from the Supplier to STA The approach to management of the coding window must be submitted to STA for approval by the date specified in section 1.b. The Supplier must provide an OSC system that will be used to capture all coding data, including item level data for scripts marked on paper. The solution must also enable the capture of a valid attendance code for a pupil where no test script has been presented for coding, by either the coder or Supplier. STA TDRs will work with the senior coding teams during the development of training, practice, standardisation and ongoing quality assurance materials. They will accordingly require access to the Supplier’s OSC system. The OSC system requirements are clearly detailed in section M1 of the Trialling and Sampling Framework (OSC system requirements are emboldened. Each states whether it is essential (coloured red) or desirable (coloured blue). Suppliers will either need to demonstrate that they can meet the essential requirements, or have a viable workaround that will allow STA’s requirements to be met. The Supplier must provide STA with a full, end-to-end demonstration of their OSC solution and be prepared to provide evidence of system functionality relating to various scenarios that could occur within the coding window. Script management during coding The Supplier must ensure that the allocation of work is approximately equivalent across all coders of equal rank in the coding hierarchy. Coders who have completed their initial allocation (and have a good quality record) may be allocated additional scripts if they confirm that they have capacity to code more. The Supplier must ensure that there is a full audit trail of all test scripts (including re-allocated test scripts) that is maintained at all times. Coders should be able to track progress against their initial allocation and any additional allocations throughout the coding window. Coding quality assurance All coding quality assurance mechanisms must be fully documented in the On-screen coding and coding quality assurance measures product description and the implementation documented in the management of the coding window document. (Please refer to sections M1.21 – M1.31 (Code quality assurance) of the Trialling and Sampling Framework. The Supplier must ensure that there is a mechanism to verify that each coder is consistently and accurately applying the coding frame to test items to the agreed standard prior to the coding period. This mechanism is to be known as ‘standardisation’. Those coders who fail to apply the coding frame accurately during standardisation to the agreed standard will not be permitted to code that item or item group. The Supplier must ensure that there are 2 sets of standardisation items to allow coders to demonstrate that they have understood and can apply feedback upon failure of the first set. Where a coder fails set 1 on a particular item, then they must pass set 2 in order continue to code that item. If a set 2 fail occurs a coder is stopped from coding that item entirely. Ongoing coder quality assurance The Supplier must ensure that there is a mechanism to verify that each coder is consistently and accurately applying the item coding frame to the agreed standard throughout the coding period. This must be agreed with STA prior to implementation. The ongoing coder quality assurance process/mechanism must consider the following: - regularly checking coders’ coding accuracy, for example, 1 in 5 item groups coded (20%) - applying the same standard against each coder for each test - providing consistent feedback to all coders, regardless of whether they pass or fail - suspending or permanently stopping coders from coding where their coding quality falls below the agreed standard for that test - efficiently allowing supervisors to monitor all coders’ coding, including coding quality assurance items or item groups and live items or item groups - allowing supervisors to view and re-code their coders’ work - allowing the manual approval and suspension of coders - having a mechanism or process which calculates the error rate for each item group coded by each coder, as specified by STA The Supplier must allow the use of live scripts for coding quality assurance. All coders should be aware of the agreed process if they fail standardisation or ongoing quality assurance. All coding completed by a stopped coder must be cleansed, re-allocated and re-coded by coders who are coding to the standard. The Supplier’s approach to data cleansing should be agreed with STA as part of the agreement of the coding capacity model. The Supplier must agree coding forecasts with STA, and ensure that expectation is set with coders accordingly regarding deadlines and progress milestones. During the coding window, the Supplier must manage coders to ensure that appropriate progress is being made. Where this is not the case, the Supplier must take action to remedy this by, for example, chasing coders, or retrieving and re-allocating uncoded test scripts. The Supplier must discuss any emerging issues with STA and agree planned interventions if coding capacity is significantly reduced. Contingencies for coding not meeting the forecast schedule must have been identified and logged on the risk register. At the end of the coding process, any queries raised by coders throughout the process, that could not be resolved by supervisors and had to be referred to STA test development researchers, should be reported to STA. The report must include a copy or transcript of the pupil response. |  |  |
| Coder feedback | The supplier must ensure that there is a reliable mechanism for gathering feedback and lessons learnt from: - senior coders following completion of the SST and TPT coding window - coders following the completion of the TPT coding window STA may wish to contact senior coders at the end of coding. |  |  |
| Administrator questionnaire data capture and analysis | The Supplier must provide full data capture of all responses from the administrator questionnaires and provide the data to STA in an electronic file format to be agreed with STA. The outcome from the analysis of the questionnaires must be provided in a spreadsheet formatted as per STA instructions. An example of a questionnaire reporting template is provided at Appendix 2. Where there are similarities in responses to a particular question from a number of different sources, those responses should be grouped together in the spreadsheet. An example of an SST questionnaire template is provided at Appendix 3. Item level feedback will be required for the TPT and therefore a template for the TPT questionnaire will be provided following project start-up. The format of the data for the questionnaires will be agreed with STA in advance of data collection in the Data capture and quality of data product description. |  |  |
| Data | STA will provide a draft data specification to the Supplier for the sample data. This will inform the Supplier of the data that they will receive from STA once schools, pupils and combinations have been confirmed (date to be agreed between parties). An example draft specification is provided at Appendix 2. STA will provide draft item level data specifications (for SST and for TPT) to the Supplier. STA and the Supplier will then jointly agree a schedule for update and sign-off. The Supplier will securely return data to STA in accordance with the format and dates and mechanisms for transfer (likely to be STA’s secure portal) detailed in the specification. In the data capture and quality of data product description, the Supplier must provide details of the: - data capture process - data capture quality assurance process - processes for dealing with exceptions efficiently - mechanisms that they will use in order to provide assurance to STA that data capture and QA processes will work effectively and that the data will be in the format specified by STA - schedule for update and sign-off of the data specification - schedule and mechanisms for data provision An example draft results file format (for TPT) is provided at Appendix 2 for reference. Section DM2.8 of the Trialling and Sampling Framework applies. There will be a requirement to update information as a consequence of schools merging with other schools or migrating to a new school. STA will provide the Supplier with weekly updates in order to ensure that the most up to date information for the school is held. The Supplier must demonstrate the end-to-end data flow to STA in order to provide assurance. Where applicable, sub-contracting suppliers should be involved in this. The Supplier must suggest and agree with STA a means by which to achieve successful data capture, in the format specified, well in advance of operational delivery in order to ensure that any changes to processes may be incorporated. The General Data Protection Regulation (GDPR) applies from 25 May 2018, when it superseded the UK Data Protection Act 1998. This places a range of new obligations on organisations to be more accountable for data protection. The Supplier must ensure they familiarise themselves with the new legislation and refer to the Department on any matters with a potential implication. Further details are provided in the Trialling and Sampling Framework Agreement. At contract award, the Supplier will be required to complete GDPR Schedule 7: Processing, Personal Data and Data Subjects at Appendix 4. |  |  |
| Administration report | The sampling test and trial administration report must be handed over in 3 parts: A, B and C. - Administration report – this part will comprise of a summary of the administration itself, including information on administrator recruitment and training. - Data analysis of information for individual questions – this part will comprise of the analysis of administrator questionnaires. An analysis of the qualitative and quantitative information collected from the questionnaires. In the report, the Supplier must highlight themes or issues that were picked up by a number of administrators or schools. See sample questionnaires and questionnaire reports at appendices C and B respectively. The qualitative and quantitative elements of the report must be provided in a format compatible with Microsoft Excel. - Reporting on the testing and test papers as a whole – this report must include information about the number of questionnaires received, any overarching comments, details from the administrators regarding any difficulties experienced when administering the tests, such as, timing issues, accessibility issues or administration issues and any external factors that could have had an influence on the pupils’ ability to complete the test, such as excessive noise or illness. |  |  |
| Handover electronic archive | The Supplier must hand over all scanned questionnaires and script files to STA within the agreed timescales. Format for questionnaire files will be confirmed by STA at the start-up meeting. All scanned script files should follow the naming convention: 2020KS2LIVE_subject_componentcode_pupilID_pg01 [yeartest]_[subject]_[componentcode]_[pupilID]_[pagenumber] [yeartest]: a test/trial identifier comprising the year, 3 character code for key stage and 3 to 4 character code for, TPT or live. [subject]: 3 character code for subject – for example, science = sci [component code]: character code determined elsewhere in spec – booklet identifier. [pupil id]: unique to pupil ID determined elsewhere in spec – pupil identifier [page number]: a 2 character code identifying each page of the booklet – 01, 02, 03 etc. The purpose of this requirement is to allow reviewers to review question responses from multiple pupils. Separate page PDFs allow reviewers to find questions via their page locations. This significantly increases the volume of material an expert can review and allows them to scroll through responses from a single PDF created by STA. The Supplier must provide secure transfer of item level data to STA in compliance with the Data Protection Act and the requirements set out in the Trialling and Sampling Framework Agreement. |  |  |
| Test Security | The Supplier must submit a security plan, which must detail the approach to ensuring that all data and test materials remain secure throughout delivery of this call-off. This should include sub-contractor arrangements, for example, print, scanning or helpdesk suppliers. The draft plan must be submitted at the start-up meeting and the Supplier must then work with STA to achieve sign-off by 12 November 2019. It is DfE policy that all systems, applications and networks that store or process departmental information must undergo a security assurance assessment using the DSU Security Assurance Model (DSAM). Security assurance involves a systematic assessment of information security risks, the identification and application of appropriate and proportional controls, and the formal acceptance by the Senior Responsible Owner of any residual risks to the system, application or network. Commencing at project start-up, the Supplier must work with STA to achieve DSAM sign-off by 27 March 2020. Any sub-contractors must complete the HM Government Supplier Assurance Questionnaire as part of the DSAM process. Information on the DSAM process is provided at Annexe B. Sections G3.5 to G3.7 of the Trialling and Sampling Framework also apply. All breaches and potential breaches of security and confidentiality, such as missing materials, loss or leak of pupil data and test misadministration must be treated as critical incidents by the Supplier and must be reported immediately to STA, with a detailed security incident report to follow within 2 hours. The Supplier must provide updates twice daily and submit a final report on resolution. This includes known security incidents reported by trial administrators, incidents identified through administrator questionnaires or feedback from other sources. If any tests are not administered in accordance with STA requirements, the Supplier must inform STA immediately. A security incident reporting template is provided at Appendix 3. Any other – non critical – incidents must be reported to STA within 24 hours, with daily updates and submission of a final report on resolution. |  |  |
| Helplines | Suppliers will be required to provide a helpline to deal with calls regarding all aspects of the testing to support schools, administrators and coders at all times during the working day (8am to 6pm). STA will require MI on this as detailed in the MI section. The precise nature of the MI will be agreed between STA and the Supplier in the Helplines product description. As a minimum, MI will include the number of calls received by day and the nature of those calls. Abandoned calls would also be desirable. All complaints should be reported. Helpline MI will be required weekly, moving to daily following school notification of selection and until one week after the testing period. The helpline must be able to: - accept multiple inbound calls on the same telephone number - make outbound calls - accept warm transfers of calls from the STA helpline - send warm transfers to the STA helpdesk or the modified test agency - respond to queries in the form of email and letter as well as telephone The Supplier must ensure that all helpline staff are adequately trained to be able to respond to queries effectively and that there are sufficient staff to meet SLAs, which will be defined in the product description. As a guide, the expectation is that 97.5% of calls are answered according to forecast. The Supplier should submit a helpline forecast, resource management plan and training schedule to STA for approval by the date specified in section 1.b. Section H1.3 of the Trialling and Sampling Framework also applies – the Supplier may source FAQs from STA where appropriate. |  |  |
| ICT Requirements | The supplier must: - ensure that their solution supports web accessibility - ensure that for all school facing systems, STA branding takes precedence over any Supplier branding so that it is immediately clear to schools that they have accessed an STA site - ensure that all school facing web-content is reviewed and signed off by STA prior to the system going live so that either: STA may make changes directly using a Content Management System (CMS) or the Supplier must make changes on STA’s behalf within 24 hours of receipt of a request - ensure that systems are capable of handling the project user load and provide load testing evidence to support this - submit the systems test strategy and plan to STA for review no more than 5 working days following the start-up meeting - agree a suitable platform for STA to carry out UAT in advance of any system’s go-live, especially where those systems are to be used by schools - agree with STA the scope of the IT documentation required - provide proposed audit reports to STA for review - propose the access control model for any system it intends to implement for agreement with STA - provide STA with access to data as required, on request having been given reasonable notice - document how they will minimise burden on schools, whilst supporting them to engage with system requirements. The Supplier’s solution should align with the principles of the Government Digital Service (GDS) Service Standards. Section ANS1 of the Trialling and Sampling Framework also applies. |  |  |
| Service Management | The STA approach to service management is currently aligned with ITIL version 3. The Supplier must ensure their approach to service management is aligned with ITIL version 3. The supplier must submit a monthly service management report providing evidence of compliance with ITIL version 3. The Supplier’s documented approach to incident and problem management must be submitted to STA no later than 5 days after the start-up meeting. The Supplier must ensure that external facing systems are available for a minimum of 99.8% of the time during periods where the system is in use by the end users of that system (including STA). Availability must not include periods of planned maintenance, which must be agreed in advance with STA. The Supplier must operate best endeavours to ensure that system maintenance is not required during operational periods. Any test system which is made available to STA must be available for a minimum of 95% of the time. Service reports must be provided upon closure of systems and/or the end of the period of system activity relating to this call-off. The Supplier must detail the period of activity and include: - availability / non availability - incidents and problems raised, resolved and outstanding - impact assessments - risks and issues - SLA performance - service call response times and any target breaches - service points and credits |  |  |

| 1. Specification of Requirements 1.c Functional Requirements – Printing |  |
| --- | --- |
| Printing | The Supplier must print test booklets and other materials, including administrator guide, attendance registers, questionnaires, coding frames, coder training materials, letters, manifests and other incidentals. The supplier must provide production proofs to STA for approval before production can commence. The Supplier must ensure that they print sufficient materials to fulfil the requirements of all stakeholders, that is, schools, coders, administrators and STA and have sufficient materials to deal with any exceptions that occur during the process, such as, stock damaged in transit or losses. The supplier must output the correct quantity of each test booklet as set out in the STA supplied data so that each pupil at each participating school receives the correct materials. The supplier must present STA with its method for producing the materials and demonstrate the approach works via an assurance test. This test will show that the materials can be output correctly (that is, the quality assurance regime can be applied and is effective) and the manufacturing solution, including any asset management software or database functions that support it, functions as intended. The assurance test must also demonstrate that the materials can be scanned by the operational scanners to be used to capture images for onscreen coding. There must be no deviation from the print specification unless agreed with STA in advance. The Supplier must manage all production activity, including that at any sub-contractors’ sites, to the security requirements set out in this ITQ. Test materials artwork specifications and setup The STA will provide the Supplier with press-ready PDFs of the test materials on the dates specified in Section 1.b. See also Appendix 4 for examples of the test materials templates. The Supplier must provide STA with its specification for static scanning elements, for example, timing marks, static barcodes etc. that STA must apply to the design of the test materials. STA recognises the Supplier may need to apply barcodes and other variable data to the SST and TPT materials to support its solution – see Appendix 4 for the test booklet templates which indicate the space available for placement of these elements. The Supplier must advise STA of any other artwork considerations driven by its solution, for example, whether STA needs to include trim marks and bleed, colour space requirements, or minimum resolution for compatibility with the reprographics or printing processes. The final Test Booklet Scanning Specification must be agreed with STA on the date specified in section 1.b. Quantities The production quantities in the table below are an estimated minimum requirement for the purposes of bidding. They do not include any contingency, for example, allowance for quality assurance samples or wastage. The Supplier must define the additional quantities it will apply for these purposes and agree them with STA. The modified materials and access arrangements document at Appendix 4 sets out the estimated number of pupils who might require materials printed on different coloured papers, based on the last science sampling administration. The Supplier must document any changes required to the materials list in order to deliver its solution, for example, additional code training materials. STA will confirm final quantities with the Supplier via change control. Substrates Further information on modified test specifications can be found at Appendix 4, including Braille, and variations such as printing on coloured paper. The specifications for Modified Large Print and Braille materials are confirmed for 2018. The specifications for Enlarged Print materials are provisional and actual extents will be confirmed during SST handover in January 2018. Standard test booklets must be printed on white, uncoated, 90gsm paper. Enlarged print and modified large print must be printed on white, uncoated, 120 gsm paper. Braille tests must be manufactured using an appropriate combination of Braille paper, braillon, Minolta, film and thermoform or similar substrates. Coder and administrative materials should be printed on paper of at least 80gsm or as agreed with STA. Specifications The table below outlines the estimated specifications for the materials STA envisages the supplier will produce, subject to any changes proposed by the Supplier to support its solution and change control to confirm the final specifications. These specifications are indicative and will be confirmed as the materials are finalised. The Supplier may propose a four process colour alternative to Pantone 319U (cyan / light blue) to STA and provide a production sample to STA for approval. After approval, the Supplier must use the production sample as the baseline for colour management during production. SST / TPT; Document; Number of versions; Estimated pagination (per version); Impressions (front/back) and colours; Dimensions (height x width) and finishing; Minimum production quantity. SST & TPT; Administrator guide; 1; 52; 1/1 Black only; 297 x 210mm, saddle stitched; 1 copy per administrator. SST & TPT; Administrator questionnaire; 1; 20; 1/1 Black only; 297 x 210mm, saddle stitched; 1 copy per school. SST & TPT; Attendance register; 1; 1; 1/0 Black only; 297 x 210mm, trim to leaves; 1 copy per school. SST & TPT; Anchor test booklets; 1 x Biology 1 x Chemistry 1 x Physics; 12-16; All versions: 2/2 Black & PMS 319U; 297 x 210mm, saddle stitched; 3,027 copies per version 5 file copies for STA. SST; Standard test booklets (non-anchor); 4 x Biology 4 x Chemistry 4 x Physics; 12-16; All versions: 2/2 Black & PMS 319U; 297 x 210mm, saddle stitched; 1,900 copies per version 5 file copies for STA. TPT; Standard test booklets (non-anchor); 3 x Biology 3 x Chemistry 3 x Physics; 12-16; All versions: 2/2 Black & PMS 319U; 297 x 210mm, saddle stitched; 1,125 copies per version 5 file copies for STA, plus 20 copies for STA for use in teacher interviews. SST; Braille booklets (UEB); 1 x Biology 1 x Chemistry 1 x Physics; 16; 1/0 Black only plus Braille impressions, thermoform, heatswell, and film.; 270 x 295 mm; 5 copies per version. SST; Braille transcripts; 1 x Biology 1 x Chemistry 1 x Physics; 8; 1/1 Black only; 297 x 210mm, stitch to top left corner; 5 copies per version. SST; Modified large print booklets; 1 x Biology 1 x Chemistry 1 x Physics; 20-24; All versions: 1/1 Black only; 364 x 257mm, saddle stitched or wiro-bound; 10 copies per version. SST; Enlarged print booklets; 1 x Biology 1 x Chemistry 1 x Physics; 12-16; All versions: 2/2 Black & PMS 319U; 364 x 257mm, saddle stitched or wiro-bound; 16 copies per version. TPT; Enlarged print booklets; 1 x Biology 1 x Chemistry 1 x Physics; 12-16; All versions: 2/2 Black & PMS 319U; 364 x 257mm, saddle stitched or wiro-bound; 10 copies per version. SST; Hearing impairment guidance; 1; 4; 1/1 Black only; 297 x 210mm, fold and trim to size or print to leaves and stitch to top left corner; 1 copy per administrator. SST & TPT; Draft coding frames (and existing coding frames for re-used tests); 1 per booklet; 20; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per senior coder. SST & TPT; Standard test booklets; 1 per booklet; 12-16; All versions: 2/2 Black & PMS 319U; 297 x 210mm, saddle stitched; 1 copy per coder (according to booklets assigned). SST & TPT; Standardisation 1 commentary; 1 per booklet; 30; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per senior coder. SST & TPT; Standardisation 2 commentary; 1 per booklet; 30; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per senior coder. SST & TPT; Training scripts; 1 per booklet; 32; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per coder (according to booklets assigned). SST & TPT; Practice scripts; 1 per booklet; 32; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per coder (according to booklets assigned). SST & TPT; Coding frames; 1 per booklet; 20; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per coder (according to booklets assigned). SST & TPT; Training commentaries; 1 per booklet; 5-8; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per coder (according to booklets assigned). SST & TPT; Practice commentaries; 1 per booklet; 5-8; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per coder (according to booklets assigned). SST & TPT; Coding instructions / principles; 1; 4; 1/1 Black only; 297 x 210mm, stitch to top left corner; 1 copy per coder. |
| End-to-end testing | Before commencing production of the live tests materials, the Supplier must complete an end-to-end test of production and scanning using the same processes, software, and equipment that will be used during live processing. The Supplier must document its approach in the End-to-End Testing product description. It may be appropriate to test parts of the process at different times and implement corrections before moving to the next stage. The purpose of the End-to-End test is to ensure the live operation will function as intended. It is not appropriate to use live test materials or pupil data for testing purposes. Therefore, STA will provide sample test booklets of the same specification as the final test materials and sample pupil data. The Supplier must produce a representative quantity of materials so that the test provides evidence and assurance to STA that: - The Supplier’s process for manufacturing the live test materials is set up correctly and functions as intended. The evidence should demonstrate the application of barcodes and other variable data, along with the efficacy of any digital asset management or similar systems or software to be utilised - The Supplier can apply the quality assurance process to produce test and ancillary materials that meet the specifications and match approved production proofs - The test and ancillary materials produced are compatible with the operational scanning solution, within agreed levels of tolerance in consideration of the provisions that have been made for coding unscannables in the coding capacity model, to enable upload onto the onscreen coding (OSC) system - The images captured in the OSC system are an accurate representation of the item and response on each test paper The Supplier must provide STA with an Outcome Report which must document for each stage of the process: - the approach that will be taken during live production and processing - the tests that have been conducted - any limitations in testing, in terms of alignment with the live process - outcomes, including any issues encountered, remedial action taken and final position - residual risk |
| Production quality assurance | - The Supplier must put in place an appropriate quality assurance (QA) regime to manage the quality of outputs at all stages of test materials production, removing and replacing any items identified within the quality checks that are not acceptable from the stock for onward delivery for fulfilment. STA defines the standard of acceptability as: ‘The supplier shall implement a Quality Assurance regime that gives confidence that the final manufactured items are free from errors or faults that might prevent a pupil accessing the test fully, prevent timely and accurate training or administration of the coders or administrators, or hinder the scanning of the completed pupil answer papers. Each quality pull should match the approved proof and specifications for imposition, dimensions, pagination, tint values and colour, clarity and consistency of image/text, variable data, and finishing.’ The Supplier must document its production QA regime, including that for modified tests, in the Tests and administrative materials produced product description. This document must describe the quality criteria and frequency of checks at each stage of production, for example: - production proof/pre-flight check - reprographics/preparation for print - on press - application of variable data - guillotine - folding - finishing and stitching - packaging for onward shipment The Supplier must notify the STA if it discovers a defect at any stage of production and describe the corrective actions it will take, including plans to replace the defective materials. An independent post-production proof must be completed on Braille and modified large print materials and STA can provide contact details for suitable individuals to the Supplier. The Supplier must keep samples as evidence of its application of the QA regime at its production site, which STA may request to review. Production proofing and approval to manufacture - the supplier must run pre-flight checks on all artwork supplied by STA and report any issues found to STA’s Test Design Team so they can amend and replace the artwork - the Supplier must produce proofs (PDF for standard materials and hard copy proofs for modified materials) and supply them to STA for approval prior to the start of production - the supplier must provide production proofs demonstrating the application of barcodes and variable data - for modified tests, including Braille, the Supplier must provide machine proofs to STA for approval - production cannot commence without approval from STA The Supplier must provide MI reports to STA to confirm their application of the QA regime that checks are being completed and STA may visit the Supplier and perform random checks on quality assurance materials. |

| 1. Specification of Requirements 1.d. Performance Requirements |  |  |  |
| --- | --- | --- | --- |
| - The management of key performance requirements is essential to delivering this project on time and in full, and will be monitored throughout the life of the project and will form part of the contractual relationship. Please review, and confirm acceptance of these requirements within your submission. - The following table lists the key performance requirements for this contract. Failure to complete one or more of these requirements according to the performance measure will affect payment of the corresponding payment milestones defined in the schedule in section 1.e. STA reserve the right to withhold payment for all or part of a payment milestone dependent on the nature of the failure. |  |  |  |
| No. |  | Service Requirement | Performance Measure |
|  | Project management | Full attendance at project start-up meeting, process walk-through, project management meetings and lessons learnt meetings (face to face and teleconference as agreed). Progress reports, product descriptions, strategies, exit and transition plans, and risk and issue reports are submitted. Management information (MI) is provided as agreed in product descriptions. Change requests are written for any deviations from the agreed contract. Security incident reports are written for all breaches and potential breaches of security and confidentiality. STA are notified of critical issues or incidents immediately upon discovery on the working day that the event occurs and receive an incident report within 2 hours of the event and twice daily updates thereafter until the issue / incident is resolved. For non-critical issues and incidents, STA are notified via an incident report within 24 hours of the event and receive daily updates thereafter until the issue / incident is resolved. After resolution of all issues and incidents, STA receives a final report that describes the incident, timelines and steps taken to resolve it and to prevent it happening in future. | 100% Meeting documents to be provided at least 24 hours prior to organised project checkpoint meetings. MI to be submitted as agreed in signed off product descriptions. All project documentation submitted according to the timescales in this document. All incident reports submitted and updated according to the timelines in this document. |
|  | Equalities | The Supplier provides reports at intervals as agreed, fulfilling their obligations under the Equality Act 2010. | 100% |
|  | Exit and transition | The Supplier provides and maintains detailed, fully resourced and costed routine and emergency exit and transition plans. | 100% |
|  | Informing schools | The Supplier provides confirmation of the complete testing timetable by the date specified in section 1.b. | 100% |
|  | Pupil selection | Schools acknowledge selected pupils and provide necessary administration details in advance of test administration, allowing the appropriate arrangements to be made. | 100% |
|  | Updating of trialling documentation | Supplier updates the administrator guidance, attendance register, administrator questionnaire and administrator training materials to quality criteria agreed with STA. | 100% |
|  | Helpline availability | Helpline SLAs are achieved, according to signed off product description. | 100% |
|  | Recruitment of administrators | Sufficient administrators are recruited to administer the tests. | 100% |
|  | Training of administrators | All administrators have received specific training for this testing. | 100% |
|  | Collation and distribution of test booklets to administrators | Correct test materials are collated and distributed to correct test administrators. All test papers, scripts and other test materials are returned from administrators. Notification and acknowledgement of delivery of all materials is confirmed. | 100% – all materials to be accounted for at all stages of the administration process. |
|  | Test administration | Tests are administered securely and completed on time in all schools selected. Test combinations are administered to the correct pupils, in the correct order and attendance status is accurately captured. | 100% |
|  | Validation of returned scripts and reporting of nil responses | Supplier confirms that all scripts and supporting documents, including unused papers, have been returned from administrators following administration. | 100% |
|  | Scanning and matching | Supplier confirms that all scripts have been scanned within the agreed exception rate and that the electronic matching of expected pupils to scripts is completed with all exceptions being resolved by the required date. | 100% |
|  | Recruitment of coders | Supplier confirms that coder recruitment has been completed and that the agreed capacity requirement has been met. | 100% |
|  | Coder training | All coders are trained as documented in the coder training plan. | 100% |
|  | Data capture of attendance registers | Accurate capture of all attendance codes as documented on attendance registers and reconciliation with results data. | 100% |
|  | Initial sample of scripts (SST) | Initial sample of scripts is made available for selection of standardisation scripts and items for ongoing quality assurance by the date specified in this ITQ. | 100% |
|  | Initial sample of scripts for pre-coding (TPT) | Initial sample of scripts is made available for pre-coding by the date specified in this ITQ. | 100% |
|  | Completion of coding (SST) | Coding of scripts is completed within the designated coding window (as per On-screen coding and coding quality assurance measures product description). | 100% |
|  | Completion of coding (TPT) | Coding of scripts is completed within the designated coding window (as per On-screen coding and coding quality assurance measures product description). | 100% |
|  | Coder quality assurance | Supplier provides evidence that the coder quality assurance processes are being carried out as documented in the product description. | 100% |
|  | Coder coding and quality assurance data | Supplier captures and provides to STA all standardisation, ongoing coder quality assurance and re-coding data including all required management information. | 100% |
|  | Coder register | Supplier captures and provides to STA a valid record in the coder register for all data fields required by STA. | 100% |
|  | Data capture of questionnaires | Accurate data capture of all responses from administrator questionnaires is provided to STA in an electronic file format as agreed with STA. Outcomes from the analysis of the questionnaires is provided in a spreadsheet formatted in line with STA instructions. | 100% |
|  | Data feed of item level data (100% of codes) | Supplier provides data feeds to STA on agreed dates with evidence that all checks have been completed as documented in the relevant product descriptions. | 100% |
|  | Final TPT administration report | TPT administration report, comprising: Part A – administration report Part B – analysis of questionnaire responses. Part C – reporting on the test papers Report content to be reviewed and agreed by STA prior to handover. | Parts A, B and C completed and submitted to STA by required date to agreed quality standard. |
|  | Handover of electronic archive | Electronic archive (questionnaires and scripts) is handed over to STA on the required date. All scanned script files must follow the naming convention specified in this ITQ. | 100% accurate |
|  | Handover of coder training materials and coding frames | All training materials and finalised coding frames are handed over on the required date and in the format agreed with STA. | 100% |
| 29. | End-to-end testing | End-to-end testing demonstrates Supplier’s capability to produce test materials of appropriate quality, in terms of readability, scanning and data transposition. | STA acceptance of Supplier’s End-to-End testing outcome report. |
| 30. | Printing | - A print proof of each test version is signed off by STA before printing commences - The correct quantity and type of materials are produced by the required date - No defective materials are presented for use by pupils, coders or administrators - Test materials are compatible with the scanning solution | - All proofs approved by STA Test Development Deputy Director - Manufacturing MI demonstrates actual quantity of each item produced is equal to 100% of the quantity requested by the required date. - Manufacturing QA MI demonstrates application of QA regime. No incidents of irreplaceable defective materials reported by pupils, coders, or administrators - Scanning MI demonstrates scanning exception rates do not exceed 2% - 100% tests meet print quality standards, on time and are signed off by STA. |
| 31. | Apprentices | The Supplier is required to support the DfE apprenticeship policy and shall employ apprentices and report the numbers of apprentices employed during the delivery of this contract to the STA. | 100% |

| 1. Specification of Requirements 1.e. Payment Milestones |  |  |  |
| --- | --- | --- | --- |
| Payment will follow the completion of the milestones listed below. |  |  |  |
| Milestone (see Deliverables and Outputs section 1.b for further information) |  | Payment due date | Payment % |
| 1 | Project management activity associated with mobilisation (including documentation and meetings) | 31 March 2020 | 25% |
| 2 | Equalities report |  |  |
| 3 | Exit and transition plans |  |  |
| 4 | Security plan & DSAM security assurance assessment |  |  |
| 5 | Systems test strategy and plan |  |  |
| 6 | Approach to incident and problem management |  |  |
| 7 | Helplines forecast, resource management plan and training schedule |  |  |
| 9 | Update of documentation |  |  |
| 10 | Recruitment of administrators |  |  |
| 13 | Test Booklet Scanning Specification |  |  |
| 14 | End-to-end testing |  |  |
| 20 | Coding capacity model |  |  |
| 21 | Approach to management of coding windows |  |  |
| 22 | Coder training plan |  |  |
| 23 24 | Senior coder recruitment (SST and TPT) |  |  |
| 25 | Coder recruitment (SST) |  |  |
| 2 | Equalities report | 10 July 2020 | 30% |
| 8 | Inform schools of statutory participation |  |  |
| 11 | Allocation of administrators |  |  |
| 12 | Training of administrators |  |  |
| 15 | Production |  |  |
| 16 | Collate and distribute materials to administrators |  |  |
| 17 | Test administration |  |  |
| 18 | Validate returned scripts and report nil responses |  |  |
| 19 | Scanning and matching |  |  |
| 26 | Coder recruitment (TPT) |  |  |
| 29 | Coders trained (SST) |  |  |
| 27 | Initial sample of scripts (SST) |  |  |
| 1 | Project management activity relating to delivery and exit | 6 November 2020 | 45% |
| 2 | Equalities report |  |  |
| 30 | Coders trained (TPT) |  |  |
| 31 | Coders Standardised (SST) |  |  |
| 32 | Coders Standardised (TPT) |  |  |
| 28 | Initial sample of scripts (TPT) |  |  |
| 33 | SST coding window management |  |  |
| 34 | TPT coding window management |  |  |
| 35 | Coding quality assurance data (SST) |  |  |
| 36 | Coding quality assurance data (TPT) |  |  |
| 37 | Coder register |  |  |
| 38 | Data capture of questionnaires |  |  |
| 39 | Data capture of attendance codes |  |  |
| 40 | Preliminary data feed – item level (SST) |  |  |
| 41 | Data feed – item level (SST) |  |  |
| 42 | Preliminary data feed – item level (TPT) |  |  |
| 43 | Data feed – item level (TPT) |  |  |
| 44 | Final administration report |  |  |
| 45 | Handover electronic archive |  |  |
| 46 | Handover of coder training materials and coding frames |  |  |
| 47 | Call off exit completed |  |  |
| 48 | Apprentices report |  |  |

1. Specification of Requirements 1.f. Instructions to Tenderers

- Tenderers should read these instructions carefully before completing their Tenders. - These instructions are designed to ensure that all Tenderers are given equal and fair consideration. It is important therefore that you provide all the information asked for in the format and order specified. - The Tenderer shall not make contact with any other employee, agent or consultant of STA who is in any way connected with this ITQ exercise during the period of this ITQ exercise, unless instructed otherwise by the STA’s SST-TPT Project Manager, Debbie Hughes. - All material issued in connection with this ITQ shall remain the property of STA and shall be used only for the purpose of this ITQ exercise. Any confidential STA Information shall either be returned to STA or securely destroyed by the Tenderer, with the permission of the STA, at the conclusion of the exercise. - The Tenderer shall ensure that each and every proposed sub-Contractor, consortium member and adviser abides by the terms of these instructions and by the requirements of the Trialling and Sampling Framework Agreement (STA-0166) and this ITQ. - STA shall not be committed to any course of action as a result of: - issuing this ITQ or any invitation to participate in this ITQ exercise - communicating with a Tenderer or a Tenderer’s representatives or agents in respect of this ITQ exercise - any other communication between STA (whether directly or by its agents or representatives) and any other party - Tenderers shall accept and acknowledge that, by issuing this ITQ, STA shall not be bound to accept any tender and reserves the right not to conclude a contract for the services for which Tenders are invited. - STA reserves the right to amend, add to, or withdraw all or any part of this ITQ at any time during the ITQ exercise. ## Tender Validity - Your Tender should remain valid for a period of 40 working days from the submission date. ## Proposed Contract - Contracts for the provision of a Sample Test and Technical Pre-Test will be let under the STA’s Trialling and Sampling Framework Agreement (STA-0166). ## Clarification Questions - Clarification Questions should be submitted by email to: ks2science.sampling@education.gov.uk. No further requests for clarifications will be accepted after the date shown in table 1.g. All communications should be clearly headed ‘2020 SST-TPT STA-0166 Call-off 8’ and should include the name, contact details and position of the person making the communication. - STA will endeavour to answer all questions as quickly as possible, but cannot guarantee a minimum response time. - In order to ensure equality of treatment of Tenderers, STA intends to publish the questions and clarifications raised by Tenderers, together with the STA’s responses (but not the source of the questions), to all participants on a regular basis via email. - Tenderers should indicate if a query is of a commercially sensitive nature – where disclosure of such query and the answer would or would be likely to prejudice its commercial interests. However, if STA at its sole discretion either does not consider the query to be of a commercially confidential nature, or considers the query to be one which all Tenderers would potentially benefit from seeing, then STA will either: - invite the Tenderer submitting the query to either declassify the query and allow the query, along with the STA’s response, to be circulated to all Tenderers; or - request the Tenderer, if it still considers the query to be of a commercially confidential nature, to withdraw the query. - STA reserves the right not to respond to a Clarification Question or to circulate such a question where it considers that the answer to that question would be likely to prejudice its own commercial interests. ## Preparation of Tender - Tenderers are solely responsible for their costs and expenses incurred in connection with the preparation and submission of their Tender. Under no circumstances will STA, or any of its advisers, be liable for any costs or expenses borne by Tenderers, sub-contractors, Suppliers or advisers in this process. - Tenders must contain details of fixed and variable costs for testing. Costs must be transparent and presented in a way which will allow STA to pre-estimate costs of call-off orders. - Tenderers are required to complete and provide all information required by STA. Failure to comply with the ITQ requirements may lead STA to reject a Tender. - STA relies on Tenderers' own analysis and review of information provided. Consequently, Tenderers are solely responsible for obtaining the information which they consider is necessary in order to make decisions regarding the content of their Tenders and to undertake any investigations they consider necessary in order to verify any information provided to them by STA during the procurement process. ## STA Point of Contact - Unless stated otherwise in these instructions or in writing from STA, all communications from Tenderers (including their sub-contractors, consortium members, consultants and advisers) during the period of this procurement exercise must be directed to the contact above. - All communications should be clearly headed ‘2020 SST-TPT STA-0166 Call-off 8’and should include the name, contact details and position of the person making the communication. ## Confidentiality - All information supplied by STA to you must be treated in confidence and not disclosed to third parties except insofar as this is necessary to obtain sureties or quotations for the purposes of submitting the Tender. - All information supplied by Tenderers to STA will similarly be treated in confidence except for the disclosure of such information as may be required in accordance with the requirements of UK government policy on the disclosure of information relating to government contracts including the Freedom of Information Act and forthcoming transparency procedures. ## Conflict of Interest - Any known conflicts of interest, or any potential conflicts of interest that may be reasonably foreseen, should be declared in the Tender. ## Value Added Tax (VAT) - STA is VAT registered. It is also an “eligible body” as classified in VAT Notice 701/30 "Education and Vocational Training". Proposals must therefore include VAT where applicable. Where any doubt exists, Tenderers are expected to have sought clarification from HMRC. Prices in the Tender will be accepted on this basis. - Tenderers are requested to set out their understanding of the VAT status of the contract based on the services to be provided and the status of STA. There will be no adjustment to the contract sum if VAT is subsequently found to be payable. ## Submission of Tenders - The Tender must be submitted in the format specified by completing the Tenderer's Response using Arial 11 font and in English and using pounds sterling. Where applicable, word limits must be adhered to and material in excess of these limits will not be evaluated. - Tenderers must submit their response to TendersTD.STA@education.gov.uk in the following format: - One complete and signed electronic version in MS Word 2016 (or compatible) format labelled 'priced' of their Tender and with their organisation name in the document title - One electronic version in MS Word 2010 (or compatible) format labelled 'not priced' of their Tender excluding the pricing information and with their organisation name in the document title - Tenders must be received by 12:00 noon on 15 August 2019. - Tenders will be accepted at any time up to this deadline but will not be opened or evaluated until the deadline has passed. - Any Tender received after the deadline may be rejected unless the Tenderer can provide irrefutable evidence that the Tender was capable of being received by the due date and time and that delivery failure was beyond their reasonable control. ## Right to Reject/Disqualify - STA reserves the right to reject or disqualify a Tenderer where: - The Tenderer fails to comply fully with the requirements of this ITQ, including proper completion of the format for response, or is guilty of a serious misrepresentation in supplying any information required in this document; or - There is a change in identity, control, financial standing or other factor relating to the Tenderer that impacts on the selection and/or evaluation process. ## Debriefing - Following the conclusion of the ITQ exercise, all unsuccessful Tenderers will have the opportunity of a debriefing. Unsuccessful Tenderers should notify STA by email that they wish to be debriefed. STA will aim to debrief unsuccessful Tenderers within 10 working days of receiving such a request.

| 1. Specification of Requirements 1.g. Procurement Timescales |  |
| --- | --- |
| Date | Activity |
| 4 July 2019 | STA issue ITQ |
| 1 August 2019 | Questions on ITQ due to STA by midday |
| 15 August 2019 | Bids on ITQ due to STA by midday |
| 13 September 2019 | Contract awarded |
| 9 October 2019 | Contract start-up meeting – face to face held in either Coventry or London |

| 1. Specification of Requirements 1.h. Tender Evaluation Methodology |  |
| --- | --- |
| - The objective of the Invitation to Quote (ITQ) is to evaluate the technical and pricing proposals of Suppliers, who have been awarded a Trialling and Sampling Framework Agreement, to meet STA's requirements in 2020. The ITQ will award a single call-off contract to the Supplier offering the most economically advantageous compliant proposal. - The most economically advantageous compliant tender will be determined by combining a technical evaluation of the proposed solution (Part A), and a commercial evaluation of the proposed price (Part B) according to the following weightings: - Technical Evaluation 70% - Commercial Evaluation 30% - The ITQ evaluation process will consist of the following phases: - Opening and compliance checks for the completeness of the response to the required format including the Tenderer's declaration - Technical evaluation of the un-priced responses by an independent evaluation panel according to the scoring criteria set out for each question in Part A, and with a minimum score threshold of 50% across the technical section. - Each question in Part A will receive a score of: 0, 1, 2, 3, 4 or 5 (0 being the lowest and 5 being the highest). - Commercial evaluation of the priced responses (Part B) for qualified and compliant bids will only be undertaken on those that have exceeded the technical evaluation threshold of 50%. Call-off Contract Award Decision - The technical and commercial evaluation scores will then be combined using the following methodology: - Technical score = 100 x (bidder's technical score / best technical score) - Price score = 100 x (lowest price / bidder's price) - Combined score = (70% x technical score) + (30% x price score) - Following evaluation, a summary of the relative quality score and relative price score will be fed back to all bidders. An example of the level of information provided is given below: Technical threshold result; Relative Quality Score; Relative Price Score; Weighted Combined Score; Rank for Compliant Bidders. 70%; 30%. Tenderer A; PASS; 0.73; 0.12; 0.55; 2. Tenderer B (WINNER 1); PASS; 1.00; 1.00; 1.00; 1. |

| 2. Annexe A: Supplier’s Proposal Q1) Method Statement – (Weighting 20%, word limit 2000) Please provide a method statement on how your organisation will ensure this project is delivered successfully. In your response, provide particular focus on: - administrator recruitment, allocation, training and management - Communication with schools (including helpdesk) - materials management – operational processes and quality regimes for test booklet design, print, collation, scanning and storage - overview only of the management of on-screen coding and coder recruitment (details to be provided in Q2) - system development including use of data, testing, customisation, file-transfer protocol and hosting environment and demonstration of alignment with the principles of the Government Digital Service (GDS) Service Standards - capture of questionnaire and attendance register data - project management of end-to-end delivery, including a draft project plan - management of sub-contractors |  |
| --- | --- |
| Scoring | Evidence; Score; Definition. None; 0; No evidence demonstrated. Very Poor; 1; Very little evidence of appropriate skills or experience relating to these criteria. Strong reservations would exist over the bidder’s capability to perform satisfactorily.. Poor; 2; Some evidence of appropriate skills or experience relating to these criteria. Some reservations would exist over the bidder’s capability to perform satisfactorily.. Adequate; 3; Reasonable evidence of appropriate skills and experience has been provided in relation to these criteria. Displays an understanding of the work required with some evidence of innovative thinking.. Good; 4; Good evidence of appropriate skills and experience has been provided in relation to these criteria. Displays a good understanding of the work required with extensive evidence of innovative thinking.. Excellent; 5; Exceeds expectations. Very strong evidence of appropriate skills and experience in relation to these criteria. Adds extra value and it is clear the bidder has extensive knowledge of the issues it faces. No reservations.. |
| Enter Response |  |

| Q2) On-screen coding and coder recruitment (Weighting 25%, word limit 2000) Please describe the end-to-end process you will implement in order to deliver on-screen coding for SST and TPT successfully, as specified in this ITQ. In your response, provide particular focus on: - Recruitment, contracting, management and payment of coders - The functionality of your proposed on-screen coding system, describing how the system meets the requirements detailed in the Trialling and Sampling Framework - Generation of materials for coder training, standardisation and ongoing quality assurance that can be reused in future - Coder administration and training - Management of pre-coding meetings and user acceptance testing - Coder quality assurance - Performance management and grading approach - Data capture You should fully consider all of the above on the basis of the requirement to code the following test types: - SST reused tests from 2018 - Anchor tests - TPTs |  |
| --- | --- |
| Scoring | Evidence; Score; Definition. None; 0; No evidence demonstrated. Very Poor; 1; Very little evidence of appropriate skills or experience relating to these criteria. Strong reservations would exist over the bidder’s capability to perform satisfactorily.. Poor; 2; Some evidence of appropriate skills or experience relating to these criteria. Some reservations would exist over the bidder’s capability to perform satisfactorily.. Adequate; 3; Reasonable evidence of appropriate skills and experience has been provided in relation to these criteria. Displays an understanding of the work required with some evidence of innovative thinking.. Good; 4; Good evidence of appropriate skills and experience has been provided in relation to these criteria. Displays a good understanding of the work required with extensive evidence of innovative thinking.. Excellent; 5; Exceeds expectations. Very strong evidence of appropriate skills and experience in relation to these criteria. Adds extra value and it is clear the bidder has extensive knowledge of the issues it faces. No reservations.. |
| Enter Response |  |

| Q3) Administrator Training (Weighting 10%, word limit 1200) Please describe the training, information and support you will provide to administrators to ensure that: - all materials are administered securely - they present a professional image to schools - they are aware of the purpose of the testing - they administer the correct tests to the correct pupils - they are equipped to administer to pupils with impairments - all materials are returned correctly for coding - a pupil safeguarding policy is implemented |  |
| --- | --- |
| Scoring | Evidence; Score; Definition. None; 0; No evidence demonstrated. Very Poor; 1; Very little evidence of appropriate skills or experience relating to these criteria. Strong reservations would exist over the bidder’s capability to perform satisfactorily.. Poor; 2; Some evidence of appropriate skills or experience relating to these criteria. Some reservations would exist over the bidder’s capability to perform satisfactorily.. Adequate; 3; Reasonable evidence of appropriate skills and experience has been provided in relation to these criteria. Displays an understanding of the work required with some evidence of innovative thinking.. Good; 4; Good evidence of appropriate skills and experience has been provided in relation to these criteria. Displays a good understanding of the work required with extensive evidence of innovative thinking.. Excellent; 5; Exceeds expectations. Very strong evidence of appropriate skills and experience in relation to these criteria. Adds extra value and it is clear the bidder has extensive knowledge of the issues it faces. No reservations.. |
| Enter Response |  |

| Q4) Data integrity (Weighting 20%, word limit 2000) Please describe the procedures that you will use and processes that you will undertake in order to maintain data integrity and deliver to 100% data quality. Consider specifically: - how you will ensure that the correct tests are attributed to the correct pupils - how you will ensure the quality of coded data - how you will ensure the quality of data captured from questionnaires and attendance registers and how this data will be matched to pupil records - how you will provide assurance that data will be in the format specified - how you will ensure compliance with the GDPR |  |
| --- | --- |
| Scoring | Evidence; Score; Definition. None; 0; No evidence demonstrated. Very Poor; 1; Very little evidence of appropriate skills or experience relating to these criteria. Strong reservations would exist over the bidder’s capability to perform satisfactorily.. Poor; 2; Some evidence of appropriate skills or experience relating to these criteria. Some reservations would exist over the bidder’s capability to perform satisfactorily.. Adequate; 3; Reasonable evidence of appropriate skills and experience has been provided in relation to these criteria. Displays an understanding of the work required with some evidence of innovative thinking.. Good; 4; Good evidence of appropriate skills and experience has been provided in relation to these criteria. Displays a good understanding of the work required with extensive evidence of innovative thinking.. Excellent; 5; Exceeds expectations. Very strong evidence of appropriate skills and experience in relation to these criteria. Adds extra value and it is clear the bidder has extensive knowledge of the issues it faces. No reservations.. |
| Enter Response |  |

| Q5) Security (Weighting 15%, word limit 1200) 5.1) Please describe the procedures that you will use and processes that you will undertake in order to maintain the security of test materials and any information assets, such as data, during the provision of the services. 5.2) Please describe the approach you will take in order to demonstrate compliance with the Departmental Security Assurance Model (DSAM). 5.3) Please describe how you will deal with any breach of security of test materials or data. |  |
| --- | --- |
| Scoring | Evidence; Score; Definition. None; 0; No evidence demonstrated. Very Poor; 1; Very little evidence of appropriate skills or experience relating to these criteria. Strong reservations would exist over the bidder’s capability to perform satisfactorily.. Poor; 2; Some evidence of appropriate skills or experience relating to these criteria. Some reservations would exist over the bidder’s capability to perform satisfactorily.. Adequate; 3; Reasonable evidence of appropriate skills and experience has been provided in relation to these criteria. Displays an understanding of the work required with some evidence of innovative thinking.. Good; 4; Good evidence of appropriate skills and experience has been provided in relation to these criteria. Displays a good understanding of the work required with extensive evidence of innovative thinking.. Excellent; 5; Exceeds expectations. Very strong evidence of appropriate skills and experience in relation to these criteria. Adds extra value and it is clear the bidder has extensive knowledge of the issues it faces. No reservations.. |
| Enter Response |  |

| Q6) Resource Strategy (weighting 10%, word limit 1000) 6.1) Please describe your resource strategy for delivering the services outlined in this ITQ, including: - an organisational chart relevant to this contract, including the name, role and the percentage of each individual’s contracted hours that will be allocated to this project for the duration of the delivery period (this percentage should consider all work commitments that the Supplier’s staff have for STA and other, non STA projects) - abridged CVs for named project staff showing relevant expertise and qualifications as a single, combined PDF or document - management of sub-contractors, their roles, responsibilities and staff numbers - availability of additional capacity to address contingencies 6.2) Please describe your approach to managing multiple contracts and conflicting demands to ensure that all deliverables are met with no degradation of performance. |  |
| --- | --- |
| Scoring | Evidence; Score; Definition. None; 0; No evidence demonstrated. Very Poor; 1; Very little evidence of appropriate skills or experience relating to these criteria. Strong reservations would exist over the bidder’s capability to perform satisfactorily.. Poor; 2; Some evidence of appropriate skills or experience relating to these criteria. Some reservations would exist over the bidder’s capability to perform satisfactorily.. Adequate; 3; Reasonable evidence of appropriate skills and experience has been provided in relation to these criteria. Displays an understanding of the work required with some evidence of innovative thinking.. Good; 4; Good evidence of appropriate skills and experience has been provided in relation to these criteria. Displays a good understanding of the work required with extensive evidence of innovative thinking.. Excellent; 5; Exceeds expectations. Very strong evidence of appropriate skills and experience in relation to these criteria. Adds extra value and it is clear the bidder has extensive knowledge of the issues it faces. No reservations.. |
| Enter Response |  |

Q7) Sub-contractors Please provide details of all sub-contractors, consortium members and advisers you intend to use (including those that may be used as contingency options) if successful with your bid. Please provide: - contact details and full physical address, including an individually named contact - details of the elements that they will have responsibility for in this call-off - confirmation that each sub-contractor, consortium member and adviser is aware of and will adhere to the confidentiality and security requirements on the Framework Agreement and this ITQ

Not scored – for information purposes only.

Enter Response

3. Pricing Schedule

- Please complete the detailed Cost Breakdown spreadsheet at Appendix 1 for SST and TPT costs. SST and TPT costs must be itemised separately wherever possible. Where this is not possible, the supplier should split the costs evenly across the SST and TPT worksheets, adding a clear note in column G (bidder’s explanatory notes) stating that the costs are not proportionate across SST and TPT. - The costs provided must include all charges that are applicable to the delivery of the STA Requirements. All prices will be evaluated excluding VAT, but any VAT charged must be declared in the Total Price. The Total Price submitted will be the fixed price included within any subsequent contract and there will be no adjustment to the contract pricing if additional charges are subsequently identified. - All amounts stated in this Agreement including supporting Schedules are inclusive of VAT where applicable unless the contrary is expressly stated. - The Fixed Price to deliver the project in full is £ (inc. VAT) and is split into three instalments , which correspond to the Deliverables and Outputs section 1.b and Payment Milestones section 1.e.

4. Appendices

Appendix 1 – Cost Breakdown

Appendix 2 – Data Templates

Attendance register example

Sample data specification example

Item level data specification example

Administrator questionnaire report example

Coder register requirements

Appendix 3 – Reporting Templates

Administrator questionnaire example (SST)

Product description and end product report template

Exit plan template and guidance

Security incident report template

Change control template

Training venue checklist

Appendix 4 – Supplementary Information

Trialling and Sampling Framework agreement

Test booklet template

Senior coder hierarchy

Coder payment model

Modified materials specification

Modified materials and access arrangements data

GDPR Processing, Personal Data and Data Subjects

5. Annexe B

Departmental Security Assurance Model (DSAM) process

The DSAM process is comprised of the following forms plus an authority to operate. The required activities will depend on the scale of the project.

DSAM Guidance – Security Assurance Process – Swimlanes

DSAM Self-Assessment Questionnaire

DSAM Form 1 – System Assurance Engagement Form

The engagement form details core information about the project.

DSAM Form 2 – Security Assurance Triage

The triage form identifies the level or tier of assurance required. STA will contribute to content and will ask the Supplier to complete the form in order to assess the service.

DSAM Form 3 – ITHC Remedial Action Plan

The remedial action plan captures technical vulnerabilities and tracks their remediation. This should be completed and maintained by the Supplier following an IT Health Check and/or penetration test.

DSAM Guidance – IT Health Check Requirements

Guidance for carrying out an IT health check.

DSAM Form 4 - System Assurance Report

The system assurance report describes the technical controls and assurance present in the system and is maintained by the supplier.

DSAM Form 5 – Residual Risk & Security Assurance Statement

A summary of all technical vulnerabilities, design and process risks left open after treatment

Business Service Assurance Model (BSAM) Process

Business Service contracts involving the processing of departmental data on non-DfE systems, should follow the Business Service Assurance Model (BSAM) Process.

Under this process, the Supplier must provide a security self-assessment by completing the Statement of Assurance Questionnaire.

The latest HMG security assurance checklist is available at:

https://www.gov.uk/government/publications/government-supplier-assurance-framework

- Declaration by Tenderer

I have examined STA's requirements under the Contract STA-0166 Trialling and Sampling Framework and proposed Call-Off terms and conditions and hereby offer to enter into a contract with STA for the required services and at the rates and prices set out in my enclosed technical and pricing proposal. I furthermore warrant that: I have the required corporate authority to sign this tender. There has been no breach of STA's confidentiality requirements. There is no conflict of interest in our proposed delivery of this service. There has been no collusion with other Tenderers or potential Tenderers. There has been no canvassing of STA staff. The Tender shall remain open for acceptance by STA for a period of 30 days after the due date for return of tenders.

| Signed | [Please complete] |
| --- | --- |
| Name |  |
| Date |  |
| Role |  |
| Authorised to sign tenders on behalf of [organisation name] |  |

An anchor test is a set of items that is similar in content and coverage to a live test. Anchor tests are used during each technical pre-test to compare how items perform each year. STA can then make judgements about the comparative difficulty of different items within different tests.

A seed is a pre-coded test question that appears as a quality assurance check for coders. The code awarded by the coder is compared to the code awarded by the senior hierarchy to ensure the coding scheme is being accurately applied.

For more information about the likely specification for modified materials, please see Appendix 4