# Annex A

| Title of project: | Guidance and Best Practice for DNA-based Species Monitoring |
| --- | --- |
| Date and time for return of tenders: | Friday 6 December 2019 @ 16:00 hours |
| Contract Reference No: | C19-0382-1389 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO PAUL WOODCOCK OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Joint Nature Conservation Committee Email: Paul.Woodcock@jncc.gov.uk Tel: 01733 866953 OR Joint Nature Conservation Committee Email: Mike.Nelson@jncc.gov.uk Tel: 01733 866816 |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca or Sue Williams Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | w/e 13 December 2019 |
| Proposed end-date: | 20 March 2020 |

Title of Project (contents page is optional)

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Aims	3

3.	Project Background	3

4.	Project Objectives	3

5.	Project Objectives: Detailed tasks	3

6.	Potential follow-on work	3

7.	Outputs	4

8.	Dissemination	4

9.	Timescale	4

10.	Health and safety	4

11.	Product specification	4

12.	Project management	5

13.	Instructions for tender submission	5

14.	Evaluation Criteria	6

15.	Payment	7

16.	Additional Contractor requirements	7

17.	References	7

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet: http://jncc.defra.gov.uk/page-1729

## Project Aims

The overall aim is to help facilitate greater use of DNA-based monitoring of species and ecosystems by environmental public bodies. This will be achieved by providing information and guidance to improve understanding of how decisions in the application of DNA-based methods can influence results, and by identifying practices that allow cost-effective DNA-based methods to be developed and implemented with confidence.

## Project Background

DNA-based methods for detecting and identifying species have many potential applications within the Defra group of organisations (APHA, Defra, CEFAS, Environment Agency, Forest Research, JNCC, Kew, MMO, Natural England). These include surveillance for invasive or rare species, characterising communities to assess the condition of protected sites, understanding the effects of management interventions, and describing the functioning and resilience of ecosystems. However, uptake for operational use faces several challenges. To contribute to addressing these challenges, Defra have established a Centre of Excellence (CoE) to support greater uptake of DNA-based methods for monitoring species and ecosystems. The CoE brings together expertise from across the Defra group of organisations to identify and tackle shared priorities through a series of projects.

A major difficulty for several CoE organisations is the diversity of potential approaches to using DNA-based monitoring methods and the way these differing approaches can affect results,2. This is a problem because organisations require robust methods that produce spatially and temporally comparable results (e.g. long-term monitoring, informing conservation actions, guiding environmental management and regulation, reporting under intentional biodiversity agreements). Accordingly, initial consultation within the CoE highlighted uncertainty over methods as a key barrier to uptake across marine, freshwater, and terrestrial systems. Furthermore, government organisations have constraints that mean the ideal solution may not be logistically or financially viable to apply at the required scale. For operational use, it is therefore also important to identify methodological areas where pragmatic decisions can be made that help alleviate these constraints without overly compromising results.

## Project Objectives

To meet the overall aim of this project (Section 2), the objectives are to:

- Clarify uncertainties that public bodies have over how the approach to sample collection, storage, processing, and data analysis affect the results of DNA-based monitoring, and identify any areas of remaining uncertainty

- Understand the requirements and operational constraints that public bodies have in relation to using DNA for monitoring

- Provide guidance to support public bodies commissioning the development of DNA-based monitoring methods

- Scope the content and structure for a best practice guidance document to support the operational use of DNA in monitoring species and communities. In addition to methodological issues, this document would need to take into account costs and logistical constraints for public bodies who are users or potential users of the technology.

## Project Objectives: Detailed tasks

Tenderers are invited to describe how each of the following tasks would be addressed:

Task 1: Addressing Uncertainties and Understanding Needs

This Task addresses the key uncertainties that government organisations hold over how methodological decisions affect the results from DNA-based monitoring methods, and the constraints and needs of these organisations. It should form the basis for subsequent Tasks, and involve two activities:

- Addressing questions over how the choice of methods affects results. Questions from government organisations potentially encompass the approach to sample collection, storage, lab processing, and data analysis. A list of questions is being collated from each CoE organisation – see Appendix 1 for illustrative examples. The list will be consolidated and provided to the Contractor, with scope for discussion and refinement if required. Clarity on the state of knowledge for these questions will help government organisations make informed choices over the development and implementation of methods, and improve the ability to interpret results. Responses to questions may not necessarily need to be extensive (e.g. in uncontentious areas), but proposals should explain the general approach to compiling and presenting an appropriate evidence base to support answers, as well as how levels of certainty would be communicated such that government organisations can use the resulting information appropriately.

- Understanding needs and constraints for government organisations and agencies. Producing guidance on implementation requires understanding how DNA is currently being used in monitoring by government and the constraints and needs for these organisations (e.g. logistics, costs, required confidence in results), as well as the potential future uses envisaged for the technique. Proposals should explain how this information will be collected and presented.

Required Outputs

- Evidence-based responses to questions identified by CoE organisations

- Brief summary of the current practices for DNA-based monitoring used by each CoE organisation, and the constraints and needs for these organisations

Task 2: Guidance on Methods Development

Developing a method for using DNA in monitoring involves several stages, including initial exploration, proof-of-concept, cost assessments, assay design and testing, and field validation. Clear and concise guidance on what should be involved to ensure each stage in this process is robust is needed, particularly where methods development is commissioned by non-specialists.

Proposals should identify the key stages involved in methods development and describe how guidance on these stages will be produced and presented, considering end-user needs and compatibility with related methods development initiatives and projects.

Required Output

- Concise accessible guidance that can be used by public bodies commissioning the development of DNA-based monitoring methods to give confidence that standardised protocols proposed for operational use have been developed in a robust way with appropriate validation

Task 3: Best Practice for Operational Implementation

Operational use of DNA in monitoring involves balancing the ideal approach with what is practical to implement at the required scale. For example, the best method for decontamination in the field may be expensive to apply but there could be a viable alternative that is sufficiently effective for end-user needs. Best practice recommendations that take into account the logistical and financial constraints on government organisations and the required quality of results are therefore valuable for public bodies applying DNA in operational monitoring.

Task 3 should produce an outline for a Best Practice guidance document that would include field, lab, and data analysis recommendations and would have content relating to freshwater, marine and terrestrial systems, eDNA and DNA, and single species detection and metabarcoding. This should draw on the information obtained in Task 1, and propose content and structure

Proposals should briefly:

- Explain the approaches that will be used to produce the scoping document

- Suggest key contents the guidance should contain, and potential structure and presentation

- Identify potential problems with producing best practice guidance, and suggest how these could be overcome

- Suggest how a final guidance document could be presented and communicated

Required Output

- Proposed content, structure and costing for producing a best practice guidance document for using DNA in monitoring

## Potential follow-on work

Tenderers should be aware that there is the potential for the successful contractor to be requested by JNCC to undertake additional work on this contract into the financial year 2020/21 as follows:

- There is the potential to continue this work in 2020/21 to produce the Best Practice guidance document proposed in Task 3.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given, that you will be asked to undertake the potential additional work outlined within this Annex A document. Tenderers are not asked to provide project plans for these follow-on aspects at this stage.

## Outputs

The outputs will be a key underpinning resource to facilitate more widespread use of DNA-based methods by government organisations and agencies with remits in monitoring marine, freshwater, or terrestrial ecosystems. It is expected that outputs will be important to (1) support organisations involved in commissioning the development of new DNA-based monitoring methods, and (2) inform the operational implementation of DNA-based methods. As such, outputs must be designed to communicate effectively with Centre of Excellence organisations. All outputs are subject to approval and sign-off by the Project Steering Group, and the final outputs will be peer-reviewed and published. The Contractor will be responsible for ensuring the quality of the work as well as the presentation of the material (e.g. proof-reading, formatting). Planned publication of outputs by the Contractor should be notified to JNCC prior to initial submission.

The outputs in 2019/20 are:

- Evidence-based responses to questions identified by CoE organisations

- Brief summary of the current practices for DNA-based monitoring used by each CoE organisation, and the key constraints these organisations operate under

- Concise accessible guidance that can be used by public bodies to give confidence that methods proposed for operational use are developed in a robust way with appropriate validation

- Brief scoping of potential content, structure and risks associated with producing a best practice guidance document

## Dissemination

Outputs produced under this contract shall not be published or disseminated without the written permission of JNCC. Outputs may at some point be made openly available on the JNCC website and all material supplied as part of the contract shall remain property of JNCC. The findings from this contract will also be made available to all organisations participating in the Centre of Excellence (APHA, Defra, CEFAS, Environment Agency, Forest Research, JNCC, Kew, MMO, Natural England) as well as other public bodies (including SNH, SEPA, Scottish Forestry, NRW)

## Timescale

A project inception meeting between JNCC and the Contractor will be required at the start of the project. Final drafts will be submitted at least 3 weeks before the end of the 2019/20 financial year for comments. Tenderers should propose any additional milestones and meetings that can be used to demonstrate progress and note timings of outputs.

| Milestones | Provisional dates |
| --- | --- |
| Inception meeting | Aim for w/c 16th December 2019. Monthly teleconferences thereafter |
| Final drafts for Outputs 1-4 (as listed in Section 7) sent to JNCC project officer in digital format via e-mail | No later than 10th March 2020 |
| Final Outputs 1-4 (as listed in Section 7) sent to JNCC project officer in digital format via e-mail | 20th March 2020 |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by JNCC H&S advisor).

Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

Any reports must adhere to the JNCC report template and house style guidance unless agreed otherwise. The draft and final reports should be provided electronically via email both as a Microsoft Word document and an Adobe PDF. Outputs should comply with JNCC Evidence Quality Assurance policy (https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/)

## Project management

The contract will be managed by a JNCC Project Officer who will be responsible for signing off deliverables and will be the main contact point. The Contractor shall nominate a Project Manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

A Project Steering Group has been established comprising of representatives of Centre of Excellence organisations that are potential users of the project outputs. The Steering Group will monitor progress and provide guidance. The Contractor will be responsible for organising meetings with the Project Steering Group and for providing administrative support as needed, including maintaining records of key correspondence. A project inception meeting between JNCC and the Contractor will be required at the start of the project. We envisage that most or all meetings will be possible by teleconference.

JNCC’s main contact points will be:

Name:	Paul Woodcock

Email: Paul.Woodcock@jncc.gov.uk

Tel: +44 (0)1733 866953

Email:  Mike.Nelson@jncc.gov.uk

Tel: +44 (0)1733 866816

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract, and delivering the detailed tasks identified within each objective as described in Section 5. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 14);

A project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

Details of Quality Control procedures to be followed (see JNCC EQA Policy - https://jncc.gov.uk/about-jncc/corporate-information/evidence-quality-assurance/) .

Details of the Contractor’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Meeting and travel costs. There is no obligation for face-to-face meetings, but if these do form part of the project proposal then the attached costs for travel and accommodation should be used. These rates are analogous to the civil service rates;

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates; and

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

The tender evaluation will be undertaken by a panel consisting of JNCC staff and members of the Project Steering Group (Natural England, Environment Agency, Defra, Forest Research, Royal Botanic Gardens Kew, CEFAS, APHA, Scottish Natural Heritage, Scottish Environmental Protection Agency, Natural Resources Wales).  Unless otherwise stated in your tender submission, bids will be forwarded to these organisations for evaluation purposes only.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (50% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 12 |  |
|  | Understanding of, and relevance to, the requirements (in particular, the adequacy of outputs and understanding of DNA based monitoring methods and their operational application) | 12 |  |
|  | Soundness and logicality of methods | 12 |  |
|  | Identification and proposed solutions to potential problems/risks | 7 |  |
|  | Probability of success | 7 |  |
|  | Sub Totals | 50 |  |
| 2. Details of Contractor (20 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team, including adequacy of subcontractors (if any) | 15 |  |
|  | Risks and proposed solutions if important team members drop out | 10 |  |
|  | Sub Totals | 25 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 10 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Payment will be made on completion of the objectives, following the submission of an invoice(s); and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

## References

Appendix 1: Example Questions from CoE Organisations (illustrative – to be consolidated and prioritised)

| Theme | Question | Rationale |
| --- | --- | --- |
| Sample collection | How long can traps be left in the field before DNA degradation becomes a problem? Is this affected by weather conditions (e.g. heavy rain)? | Traps are sometimes left in the field for several days or more |
|  | What effect do different approaches to decontamination in the field have on results? | May affect feasibility of operational use (e.g. costs, availability to citizen scientists, logistics, COSHH) |
|  | What effect do different DNA preservatives have on results? | May affect feasibility of operational use (e.g. costs, availability to citizen scientists, logistics, COSHH) |
|  | Are negative field controls necessary, and if yes how should these be applied? | May affect costs, and the robustness of results |
| Sample processing | What effect does size-sorting/adjustment prior to analysis have on the results of metabarcoding? | May affect costs and the ability to detect rare species |
|  | What is the effect of DNA extraction kit on results? | May affect the comparability of results and the flexibility of standard monitoring protocols to modify approaches |
|  | What is the effect of the choice of primers on results? | May affect the comparability of results and flexibility of any standard protocols |
|  | Is there an advantage to using degenerate primers when a broad taxonomic range is of interest? | Informative for methods design |
|  | How much effect does inhibition have on results, and how can this be understood and minimised? | Informs interpretation of results |
|  | What effect does using different numbers of PCR replicates have on results and costs? | Informs interpretation of results, and may affect costs? |
|  | What effect does one vs. two-step PCR have on results? | May affect the comparability of results and flexibility of any standard protocols |
|  | What effect do differences in sequencing depth have on results? | Informs interpretation of results |
|  | What effect do different lab decontamination procedures have (decontamination solutions, UV etc.), and how can we be confident that appropriate procedures are in place? | May affect costs, and the robustness of results |
|  | How does the sensitivity of different PCR methods compare with each other? | Informative for methods design |
| Data Analysis | What is the effect of different approaches to using PCR replicates on results? | Informs interpretation of results |
|  | Is it advisable to develop a mock community of the most likely organisms? If yes, how should this be constructed? | Informative for methods design |
|  | What are the approaches to removing potentially erroneous sequences from datasets, and do these produce different results? | Informs interpretation of results |
|  | What are the effects of OTU clustering vs amplicon sequence variant analysis on results? | Informs interpretation of results |
|  | What are the effects of using different algorithms for assigning taxonomy? | Informs interpretation of results |
|  | What are the effects of using different OTU clustering thresholds? | Informs interpretation of results |
|  | What are the effects of using different sequencing platforms? | May affect the comparability of results and the flexibility of any standard protocols |
| Other | What metadata need to be reported with DNA data? | Facilitates re-use of data |
|  | What is the minimum methodological information needed to validate and repeat the work? | Informs interpretation and validation |
|  | How should samples be archived to facilitate future use? | Facilitate re-use of samples |
|  | Which aspects of sample processing and data analysis are influenced by the sampling media (e.g. water, soil, bulk specimens etc.) and which can follow similar approaches irrespective? | General approaches can provide consistency and efficiencies across systems, but can only be implemented where appropriate. |

1 Elbrecht et al. (2017) Methods Ecol Evol., 8, 1265-1275. 2 Alberdi et al. (2018) Methods Ecol. Evol., 9, 134-147