SCHEDULE 3.5

TERMS AND CONDITIONS

ACT/04380

PROGRAMME HADES REGION 3

PROVISION OF TECHNICAL SUPPORT SERVICES

TO SCOTLAND, THE NORTH AND EAST OF ENGLAND

PERFORMANCE MANAGEMENT

THIS PAGE IS INTENTIONALLY BLANK

TABLE OF CONTENTS

PERFORMANCE MANAGEMENT	5

1.	KEY PERFORMANCE INDICATOR PROCESSES	5

ANNEX A	9

1.	PERFORMANCE INDICATOR DEFINITIONS	9

1.2	Definitions For Task Priority	10

1.3	PI To KPI Associations	11

ANNEX B	14

1.	MANAGEMENT HIERARCHY LEVELS	14

2.	MANAGEMENT ROLES	14

ANNEX C	16

1.	RELIEF EVENTS	16

THIS PAGE IS INTENTIONALLY BLANK

# PERFORMANCE MANAGEMENT

## 1.	KEY PERFORMANCE INDICATOR PROCESSES

- 1.1	Performance Indicators (PI) and Key Performance Indicators (KPI) for the delivery of each of the Contracted Services are defined at Schedule 2 Module 1 Section 2 (Management and Administration).

- 1.2	Where a KPI failure has been identified but resulted from the Contractor’s dependency on the Authority to provide GFX or Services for which the Contractor was unable to compensate then no KPI failure shall be attributed to the Contractor.

- 1.3	If there has been an event that the Contractor considers to be outside of their reasonable control and wishes to claim as a Relief Event (refer to Annex C for a list of Relief Events) then the Contractor is to notify the Authority’s Local Representative or the HADES team as appropriate of the event.  If a KPI failure does result from the event, and the Contractor has been unable to compensate after taking all reasonable measures, then no KPI failure, or a reduced KPI failure, shall be attributed to the Contractor if it has been agreed that such an event qualifies as a Relief Event.  A proposal to overcome the difficulty is to be generated by the Contractor as soon as practicable and agreed with the Authority for immediate implementation.  Once the event, or 3 months, has passed then full provision of the contracted Services is to resume, else a KPI failure will then be attributed.  If the relief event remains in effect at the 3 month point, then the Relief Event may be claimed again, or alternative methods of addressing the issue may be taken after consultation with all stakeholders.  These alternative methods may include partial, or full termination, or Authority Step-in if there are no other acceptable means of restoring delivery of the contracted Services.

- 1.4	Where the Contractor is in breach of one of the KPI’s and this can be attributed to the Contractor then payment retention or deduction may be applied.  The amount of any payment retention or deduction is dependent on the type, severity and the frequency of KPI failures occurring.  Instances of the same type of failure across multiple stations will be addressed at more senior levels of the Authority’s management chain and the amounts of payment retention or deduction are correspondingly potentially higher.

- 1.5	The severity of KPI failures are categorised as being Minor, Major, Critical and Catastrophic (Refer to Schedule 3.1 for definitions).  Decisions on categorisation of failures shall be made in accordance with the governance process at Schedule 3.6 and Annex B of this Schedule.  KPI failures categorised as Minor or Major failures will result in retention of payment.  KPI failures categorised as Critical or Catastrophic will result in payment deductions.  No single event at a single station that is not safety or environmental impact related will be categorised as Critical or Catastrophic.

- 1.6	KPI failures that are unresolved to the satisfaction of the Authority shall escalate through the severity categories according to the following series:

- a.	For a failure categorised as Minor KPI failure initially

- i.	will escalate to a Major KPI failure after 3 (three) months and attract retention of payments on the Major failure scale if left unresolved;

- ii.	If the same failure is still unresolved after a further month it will escalate to a Critical KPI failure and result in a permanent deduction of any previously retained funds;

- iii.	If the same failure is still unresolved after a further month it will escalate to a Catastrophic KPI failure.

- b.	For a failure categorised as a Major KPI failure initially

- i.	If the same failure is still unresolved after 3 (three) months it will escalate to a Critical KPI failure and result in a permanent deduction of any previously retained funds;

- ii.	If the same failure is still unresolved after a further month it will escalate to a Catastrophic KPI failure.

- c.	For a failure categorised as a Critical KPI failure initially

- i.	If the same failure is still unresolved after 3 (three) months it will escalate to a Catastrophic KPI failure.

- 1.7	Where there are occurrences of 2 (two) Critical KPI failures or a single Catastrophic KPI failure in any one month then that will constitute grounds for declaration of a material breach.  After consideration of all the facts and any mitigating circumstances, it shall be at the Authority’s discretion whether to terminate the contract in part (see Special Condition 20) or in full as a consequence of a material breach by the Contractor.

- 1.8	If sums have been retained pending a satisfactory resolution of a KPI failure then those sums will be included in full in the next monthly payment after resolution.

- 1.9	For the avoidance of doubt, sums deducted from payments due to a KPI failure, whether due to escalation of severity classification or not, shall be permanent.

- 1.10	Except where the KPI failure is categorised as Catastrophic severity then the following shall apply:

- The retention or deduction of sums will commence in the monthly payment after that in which the initial KPI failure report was raised, i.e. after 2 monthly Level 1 meetings have been held.  Where the KPI failure has been resolved to the satisfaction of the Authority before the date when the first retention or deduction would be due then no payment adjustment for this cause will be made.  If the KPI failure is resolved at one station but re-occurs at another station in the same month then the retention/deduction period shall continue as if the problem had not been rectified.

- Any instance of a KPI failure categorised as Catastrophic severity will result in other measures being immediately applicable as determined by the Authority on a case by case basis.  The Authority will investigate the incident and take into consideration any mitigating circumstances made known to them by the Contractor before making a decision.  At the conclusion of the investigation, the Authority will announce its conclusions and any measures to be taken.  These measures may include the application of DEFCON 514 (Material Breach) and result in full or partial termination of the contract, or step-in by the Authority or a third party nominated by the Authority.

- 1.11	Application of any of the above measures shall be without prejudice to any other rights or remedies of the Authority.

- 1.12	Key Performance Failure Reporting.  It is the responsibility of the Authority’s Local Representative to notify in writing:

- Def Comrcl;

- The HADES Team; and

- The Contractor;

- of any category of Key Performance Indicator failure as soon as practicable.

  - The KPI failure notification is to include the following:

- The date of the notification;

- A unique reference number for the notification;

- The KPI failure category assigned by the Authority’s Local Representative;

- The date of the incident(s) to which this report relates;

- Details of the KPI failure if an event, or the issues leading up to a KPI failure report if it is the result of a trend;

- Any immediate actions taken by the Authority;

- Any immediate actions taken by the Contractor;

- Any notifications made to other enforcement authorities (e.g. HSE, Local Authorities, Military Aviation Authority, etc.).

- 1.14		Where a KPI failure has been satisfactorily resolved then the Authority’s Local Representative will notify in writing:

- Def Comrcl;

- The HADES Team; and

- The Contractor

to that effect. This notice shall be made within 5 Business Days after satisfactory resolution has been achieved.

- 1.15	The KPI failure resolution notice is to include the following:

- The date of this notification

- The unique reference number of the original KPI failure notification;

- The date on which resolution of the KPI failure was accepted;

- Details of the measures taken by the Authority to prevent re-occurrence of the failure(s);

- Details of the measures taken by the Contractor to prevent re-occurrence of the failure(s).

THIS PAGE IS INTENTIONALLY BLANK

## ANNEX A

## 1.	PERFORMANCE INDICATOR DEFINITIONS

- 1.1	The Performance Indicator (PI) assessment criteria as defined below shall be used when monitoring the operation of this contract:

- “Accurate” or “accuracy” means that the contracted Service(s) is error free;

- “Achievable” means that, unless otherwise agreed, the contracted Service(s) can be provided within existing resource, to the required quality, and at the time specified.  If additional resource, change in quality, or extra time is required then these must be specified, quantified, and agreed with the Authority before the contracted Service(s) becomes “Achievable”;

- “Availability” means the percentage of time that a contracted Service(s) can be used for the purposes of the contract less the time that the contracted Service(s) cannot be used for the purposes of the contract;

- “Commensurate” means that the contracted Service(s) provided is proportionate in depth, scope and complexity with the importance and value assigned to the object or activity by the Authority;

- “Compliant” means the output is in all respects in accordance with:

- i.	Legislation;

- ii.	This Contract;

- iii.	MOD Policy;

- iv.	RAF Engineering Policy;

- v.	Standing Orders; and

- vi.	Standards (including Quality Assurance standards, Defence Standards, Engineering standards, etc.); and

- “Cost” means the price charged for the contracted Service(s);

- “Effective” means that where action needs to be taken to provide the Contracted Deliverable, that action brings about the desired result without any unacceptable side effects;

- “Efficient” means that the amount of waste resource is reduced to a minimum while maximising the required utility or output;

- “Flexibility” means the ability to adapt, or be adapted, to allow for changes in circumstances or priorities and still provide the contracted Service(s) to a standard acceptable to the Authority;

- “Husbandry” means the careful use of a facility, piece of equipment, or consumable to maintain it in a good working order, ascetic appearance, and avoiding clutter or waste.

- “Measurable” means that the progress and final presentation of the contracted Service(s) can (as far as is reasonably practicable) be objectively assessed against the specified criteria;

- “Monitored” or “Monitoring” means the delivery of the output has been or can be checked at various points during the process to identify any discrepancy from the plan or specification;

- “Performance” means conduct of a task in a manner that satisfies the Authority as being in conformance with:

- i.	Legislation;

- ii.	This Contract;

- iii.	MOD Policy;

- iv.	RAF Engineering Policy;

- v.	Standing Orders;

- vi.	Standards (including Quality Assurance standards, Defence Standards, Engineering standards, etc.);

as applicable to the particular contracted Service(s).

- “Presentation” in this context means the appropriate clothing for the function performed by the individual is being used and as far as is practicable is in a clean condition and good state of repair; the individual is clean and tidy in their appearance as appropriate to the occasion.

- “Prioritise” or “Prioritised” means that where there are insufficient resources available to conduct all activities at the required time, the order in which the activities are sequenced in accordance with the orders of the Authority Representatives involved;

- “Progressed” means that any issues with providing the contracted Service(s) have been identified and resolved in a fashion acceptable to the Authority;

- “Relevant” means that the contracted Service(s) only includes those items necessary for provision of the specified output;

- “Responsive” means that the Contractor responds to events in an appropriate manner agreed with the Authority;

- “Scheduled” means a timeframe for an activity be performed that is acceptable to the Authority;

- “Specific” means that it defines precisely the measure or measures that the contracted Service(s) will satisfy;

- “On-time” or “Timeliness” means the agreed period or date and time for provision of the contracted Service(s);

- “Up-to-date” means that the contracted Service(s) is at the standard and issue specified by the Authority at the time of use – this is usually (but not always) the latest version;

- 1.2	Definitions For Task Priority

- When assessing a KPI or PI failure the importance of the task will have bearing on the severity assigned to the failure; to address this 3 task priority ratings are defined:

- “Routine” means a task which is scheduled, well defined, and any failure to perform is manageable by the Contractor and the Authority without exceptional measures;

- “Priority” means a task that may or may not be scheduled or well defined at the outset but the failure to perform may require the Contractor and the Authority to use exceptional measures to compensate for any shortfall in delivery;

- “Urgent” means a task that comes about as a result of an “event” and must be completed at the expense of other lower importance tasks if necessary.  Failure to perform an “Urgent” task would require disproportionate measures by the Contractor and the Authority to compensate for the shortfall in delivery, or a complete inability to proceed with recovery from the event and restore normal Service.

- 1.3	PI To KPI Associations

- Note that not all PI assessment criteria will apply to every task or sub-component of a task.  Exceptionally, the criteria applicable in each case may be tailored by the Authority Local Representative to meet the needs of the moment and the priority of the task.

- The Service Delivery KPI has only 2 (two) possible values, either the contracted Service(s) have been provided or have not, accordingly there are no other assessment criteria defined.

- The Service Quality KPI assesses whether the contracted Service(s) has been provided to an acceptable standard.  The PI assessment criteria used when reviewing contract output(s) against this KPI are:

- i.	Accurate or accuracy;

- ii.	Achievable or achievability;

- iii.	Commensurate;

- iv.	Effective;

- v.	Flexible or Flexibility;

- vi.	Husbandry

- vii.	Measurable;

- viii	Presentation

- ix.	Relevant or Relevance;

- x.	Up-to-date.

- d.	Timeliness KPI measures whether the contracted Service(s) is provided at the time agreed with the Designated Officer (DO) for the task or in accordance with the agreed schedule.  The assessment criteria when reviewing contract output(s) against this KPI are:

- i.	Monitored

- ii.	On-time

- iii.	Prioritised;

- iv.	Progressed; and

- v.	Scheduled.

- e.	The Targets KPI is whatever target may reasonably be applied to the contracted Service(s).  The assessment criteria when reviewing contract output(s) against this KPI are:

- i.	Cost;

- ii.	Efficiency – this includes energy and waste reduction, re-use, etc.; and

- iii.	Availability;

- f.	The Safety KPI encompasses a number of different features including Health, Safety, Environmental, and Fire.  This measure assesses how well the Contractor conforms to these requirements and deals with any breaches or events.  The assessment criteria when reviewing contract output(s) against this KPI are:

- i.	Compliance;

- ii.	Performance; and

- iii.	Responsiveness.

THIS PAGE IS INTENTIONALLY BLANK

# ANNEX B

## 1.	MANAGEMENT HIERARCHY LEVELS

- 1.1	The Authority will adopt 3 levels of management hierarchy for overseeing operation Programme HADES as summarised below:

- Level 1. This is Establishment level – this includes any Dependent, Lodger or Satellite Units (refer to Schedule 3.1 for definitions of Dependent, Lodger and Satellite Units) of that Establishment.  This management level is provided by the Authority’s Local Representative at each Establishment, except where an Establishment is a satellite unit.  The Commanding Officer (CO) of a lodger or satellite unit will feed their information into the Authority Local Representative at the Parenting Unit;

- Level 2. This management level is provided by the Air Command Programme HADES team and led by the Authority Technical Representative.  This team provides higher level management functions across all the Establishments using the Programme HADES contracting arrangements.

- Level 3. The Programme Board is the highest level of the Authority Management Hierarchy for Programme HADES and all the Establishments using HADES Services fall under their remit.

## 2.	MANAGEMENT ROLES

- 2.1	Level 1. The day-to-day running of the Programme HADES Services will be monitored, reviewed, authorised, audited and investigated as necessary by the Authority Local Representative or their delegated representatives. The Authority Local Representative will assign any KPI failure categorisation applicable to the Programme HADES Services at their Establishment.  Each Authority Local Representative will routinely formally report monthly to the HADES team on the performance of the Contractor providing the Services for the preceding month.  Where issues are encountered then exceptional reporting upward may occur.

- 2.2	Level 2. The HADES team receive monthly reports on the provision of the Programme HADES Services from the Authority Local Representatives, along with any exceptional reports.  The HADES team is responsible for checking to see if any issues reported by the Authority Local Representative are appearing at more than one Establishment.  The HADES team are responsible for initiating any reviews, audits, additional monitoring or investigations that maybe required that affect more than one Establishment.  Where systemic issues are identified then the HADES team will address these at a corporate level with the Contractor.  The HADES team are responsible for calculating and notifying all parties of any payment retentions or deductions each month that may be necessary.  Where a KPI categorisation issue is in dispute at a particular Establishment then it can be raised by either the Authority Local Representative or the Contractor to the HADES team for further review/adjudication.  Where a KPI failure is across several stations and sufficient severity then the HADES team shall notify the affected Authority Local Representative that the HADES team are allocating the KPI failure severity.  Where a KPI failure is being addressed by the HADES team they will arrange any exceptional meetings necessary at any level of the management hierarchy to resolve the issue.  Routine HADES team meetings with the Authority Local Representative shall be held quarterly.  Routine HADES team meetings with the Contractor’s Corporate Representatives shall be held quarterly.  These quarterly meetings with Authority Local Representative and Contractor’s Corporate Representatives may or may not be held simultaneously dependent on the needs of the Programme.

- 2.3	Level 3. This board will normally meet annually and conduct the Contract Annual Performance Review. Exceptionally the board may become involved in the event of catastrophic or multiple critical KPI failures in provision of Services.  Where a KPI categorisation issue is in dispute then it may be raised to the Level 3 board by either the HADES team or the Contractor for a final adjudication.  The Level 3 board provides direction and authority as necessary to terminate the contract either in part or in full, expand the scope of the contract, or have the Authority step-in for a period.

- 2.4	The application of any of the above measures do not preclude the use of the dispute resolution process contained in Schedule 3 of this Contract by either party.

- 2.5	Further details of the contract management arrangements, scheduled meeting agendas, terms of reference, etc. can be found in Schedule 3.6 of this contract.

# ANNEX C

## 1.	RELIEF EVENTS

- 1.1.	References to Relief Events in this Schedule 3.5 shall be taken to mean:

- A breach by the Authority of any of its obligations under this Contract which affects the delivery of the Contracted Services;

- Fire, explosion, lightning, storm, tempest, flood, bursting or overflowing of water tanks, apparatus or pipes, earthquakes, riot and civil commotion, war, crisis, or terrorist act, and/or compliance with the directions of military/MOD personnel associated with the above;

- Failure by any statutory body, utility company, local authority or other like body to carry out essential works or to provide essential services;

- Any accidental loss or damage to the Authority sites or any roads servicing them;

- Any national failure or shortage of power, fuel or transport;

- Any blockade or embargo;

- Any labour dispute, subject to the Contractor being able to demonstrate that he has taken all reasonable steps to mitigate the impact of or to resolve any such dispute, to the extent that it is within his power to do so; or

- Instances where the Contractor has been unable to compensate without using disproportionate additional resource following the Authority’s Local Representative directing a temporary re-prioritisation of activities.

Refer to Annex B of this document for the Authority management bodies making this determination based upon the severity of the potential KPI failure.