A10	PROJECT PARTICULARS

A10/110	THE PROJECT

-	Name: CONGLETON TOWN HALL DECARBONISATION WORKS

-	Nature: The works comprise of the following:

Installation of Air Source Heat Pump, Solar PV, LED Lighting and fabric upgrades.

-	Location: Congleton Town Council, 7 High Street, Congleton CW12 1BN

-	Length of contract: To be confirmed

A10/120	EMPLOYER (CLIENT):

Congleton Town Council

7 High Street

Congleton

CW12 1BN

A10/130	PRINCIPAL CONTRACTOR (CDM): The Contractor

A10/140	PERSON EMPOWERED BY THE CONTRACT TO ACT ON BEHALF OF THE EMPLOYER

Employers Agent/Project Manager

Pearson Surveyors Ltd

C/O Fischer Crowne

21 Cheapside, Liverpool, Merseyside, United Kingdom, L2 2D

Telephone: 07876443520

E-mail: chris@pearsonsurveyors.co.uk

Contact: Chris Pearson

A10/150	PRINCIPAL DESIGNER

Pearson Surveyors Ltd

C/O Fischer Crowne

21 Cheapside, Liverpool, Merseyside, United Kingdom, L2 2D

Telephone: 07876443520

E-mail: chris@pearsonsurveyors.co.uk

Contact: Chris Pearson

A10/160	QUANTITY SURVEYOR

Pearson Surveyors Ltd

C/O Fischer Crowne

21 Cheapside, Liverpool, Merseyside, United Kingdom, L2 2D

Telephone: 07876443520

E-mail: chris@pearsonsurveyors.co.uk

Contact: Chris Pearson

A10/210	ARCHITECT:

Pearson Surveyors Ltd

C/O Fischer Crowne

21 Cheapside, Liverpool, Merseyside, United Kingdom, L2 2D

Telephone: 07757709318

E-mail: architect@pearsonsurveyors.co.uk

Contact: Brian Sherriff

220	STRUCTURAL/CIVIL & DRAINAGE ENGINEER:

To be proposed and appointed by contractor

230	BUILDING SERVICES ENGINEER:

Pearson Surveyors Ltd

C/O Fischer Crowne

21 Cheapside, Liverpool, Merseyside, United Kingdom, L2 2D

Telephone: 07784971945

E-mail: services@pearsonsurveyors.co.uk

Contact: Alex Wilson

A11	TENDER AND CONTRACT DOCUMENTS

A11/110	TENDER DRAWINGS

-	The tender drawings are: as listed in Section 1.2 of these Employers Requirements.

A11/120	CONTRACT DRAWINGS

-	The contract drawings: Same as the tender drawings.

A11/160	PRECONSTRUCTION INFORMATION

-	Format: The Preconstruction information is described in these preliminaries in Section A34. It refers to information given elsewhere in the preliminaries and other tender documents.

The Pre-Construction Information document(s) are included within Appendix ‘A of these Employers Requirements.

A11/180	OTHER DOCUMENTS

-	Inspection: Drawings and other documents relating to the Contract but not included in the tender documents may be seen by appointment during normal office hours at the office of the Project Manager.

A12	THE SITE/ EXISTING BUILDINGS

A12/110	THE SITE

-	The site is located at 7 High Street Congleton CW12 1BN

A12/120	EXISTING BUILDINGS ON/ ADJACENT TO THE SITE

-	The existing Town Hall will all remain occupied and in full trading operation during the whole construction process.

-	The Town Hall will be used by Tenants and Members of the Public throughout the course of the Contract and the Works are to be programmed and executed in a manner which will ensure that no nuisance is caused to the Tenants and Public.

-	The Contractor shall allow for any special provisions necessary to ensure the safety of the Public and where necessary for the provision of alternative pedestrian/vehicular routes.

-	The Contractor is to provide suitable signage for redirected pedestrian and vehicle traffic flows if required.

-	The Contractor shall note the requirement to maintain the full and unimpeded access of service vehicles and emergency vehicles at all times, including any special provisions necessary to ensure the safe and proper use of such access.

-	Free and uninterrupted pedestrian and vehicular access and egress, including access for emergency services, shall be maintained to the Town Hall at all times.

-	Existing escape doors from neighbouring buildings must be left unobstructed at all times.

-	Contractor will be responsible for providing pedestrian protection as necessary.

-	Contractor will allow for all required safety signage and directions for both vehicle and pedestrian diversions.

A12/140	EXISTING MAINS AND SERVICES

-	The Contractor shall take all measures necessary to avoid damage to services which are manifestly put at risk by the execution of the works and shall comply with the direction of the competent authorities with regard to the protection of services generally and the making good without charge to the Employer of any damage caused by the Contractor.

-	No interruption to any of the services to the Town Hall will be permitted during normal operating hours and the contractor must therefore, include in his services installations to necessitate a temporary interruption of supplies. Two weeks clear notice of such interruption shall be given to the Employers Agent.

-	Wherever any existing service is exposed in the course of carrying out the works, immediately notify the Employers Agent or his site representative so that the service may be examined and identified. Make a dimensioned sketch describing the exposed service and locating it in plan and section to permanent and accessible reference points, date and sign the sketch and submit it same to the Employers Agent. Any service so exposed shall only be covered up as permanent works with the written consent of the Employers Agent.

-	Utility trenching to be phased to minimise disruption to Tenants and deliveries if required. Temporary cover plates are to be provided and appropriate safety signage and barriers for openings to be erected by the contractor.

-	All underground services to be identified using appropriate existing information and detection equipment before breaking ground for the works.

A12/170	SITE INVESTIGATION

-	There are no Site Investigation Reports included within these Employers Requirements.

A12/180	HEALTH AND SAFETY FILE

-	Availability for inspection: The Health and Safety File for the site/ building may be seen by appointment during normal office hours of the Town Hall.

A12/200	ACCESS TO THE SITE

-	Refer also to Section A35/140.

A12/210	PARKING

-	Parking of the Contractor's and employees' vehicles will be restricted to the area of the site.

A12/220	USE OF THE SITE

- Do not use the site for any purpose other than carrying out the Works.

- Site cabins, storage compounds etc will be restricted to the Contractors compound areas.

A12/230	SURROUNDING LAND/ BUILDING USES

-	The Contractor shall note that the site is within a busy town centre high street and that the trading function of the town hall and neighbouring premises must continue throughout the currency of the works.

A12/240	HEALTH AND SAFETY HAZARDS

-	The nature and condition of the site/building cannot be fully and certainly ascertained before it is opened up. However, the following hazards may be present:

- Working in and Transporting debris/rubbish and materials from the site compound into the site of the Works and through areas accessible to the town hall staff, visitors or to the general public.

- The Contractor shall note that the site is within an occupied and operating Town Hall and that the trading function of the Town Hall must continue throughout the duration of the works.

3. All other risks shown or stated on the drawings or included in the Pre-Construction Information Document within Appendix ‘A’ of these Employers Requirements.

-	It is a requirement of the Contractor to be the Principal Contractor and he is to make-due allowance for complying with all provisions and requirements of the Construction (Design and Management) Regulations 2015.

-	The Principal Contractor is also responsible for stating how he will follow the Health and Safety Plan and he will be responsible for implementing, adding and developing the plan through the construction phase of the project.

-	The accuracy and sufficiency of this information is not guaranteed by the Employer or the EA and the Contractor must ascertain if any additional information is required to ensure the safety of all persons and the Works.

-	Site Staff: Draw to the attention of all personnel working on the site the nature of any possible contamination and the need to take appropriate measures.

A12/250	SITE VISIT

-	Before tendering: Ascertain the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the Works.

-	Arrangements for visit: May be made by arrangement with Mark Worthington, Town Hall Manager Telephone: 01260 270350 ext 5

A12/260	SCHEDULE OF CONDITIONS

Prior to commencement of the works (during the mobilisation period), the Contractor is required to undertake a photographic survey of the areas around the proposed location of Contractor’s compound, access routes for contractor’s vehicles into the park, existing paths, existing roads, walls, fences, etc. and any other areas which is likely to be affected by the works described herein. Provide two copies of the survey to the EA within 1 week of commencement. The Contractor is to include for all costs associated with carrying out, copying and distributing this survey.

A13	DESCRIPTION OF THE WORKS

A13/120	THE WORKS

-	The location, extent and parameters of the Works are identified on the Drawings/Specifications/Method Statements/Agreement to Leases.

The works comprise of the following:

Installation of Air Source Heat Pump, Solar PV, LED Lighting and fabric upgrades.

125	The scope of works is described within the Tender Document including the Appendices and the Contractor shall consider all this information as defining the works.  This tender shall comprise the works referred to in this document including appendices.  The Principal Contractor shall be responsible for general management of the work site and programme co-ordination including the co-ordination and on-site management of all sub-contractors and suppliers.  All site activities are to be co-ordinated by the Principal Contractor.

The Tenderer shall be deemed to have included for all items of work shown on the tender drawings, schedules, specifications and general conditions of contract or reasonably inferred there from, including labour, materials, plant and tool's (whether temporary or permanent) necessary for the purposes aforesaid.

130	WORKS BY OTHERS CONCURRENT WITH THE CONTRACT

-	Scope: See Section A50.

A20	JCT DESIGN AND BUILD CONTRACT (DB)

A20/222	JCT DESIGN AND BUILD CONTRACT

-	The contract: JCT Design and Build Contract 2016

-	Requirement: Allow for the obligations, liabilities and services described.

THE RECITALS

First

THE WORKS

-	The works comprise of the following:

Installation of Air Source Heat Pump, Solar PV, LED Lighting and fabric upgrades.

Fifth

DIVISION OF WORKS INTO SECTIONS

-	The Fifth Recital will be deleted.

THE ARTICLES

3

EMPLOYER’S AGENT

-	Employer’s Agent: See clause A10/140.

5

PRINCIPAL DESIGNER

-	Principal Designer: See clause A10/150.

6

PRINCIPAL CONTRACTOR (CDM AND SWMP)

-	Principal Contractor: See clause A10/130.

9

LEGAL PROCEEDINGS

-	Amendments: None.

CONTRACT PARTICULARS

PART 1: GENERAL

Fourth recital and clause 4.5

CONSTRUCTION INDUSTRY SCHEME (CIS)

-	Employer at the Base Date is a ‘contractor’ for the purposes of the CIS.

Sixth Recital

FRAMEWORK AGREEMENT

-	Framework agreement: Does not apply.

Seventh Recital and Part 1 of Schedule 2

SUPPLEMENTAL PROVISIONS - PART 1

-	Named subcontractors: Supplemental Provision 1 applies.

-	Valuation of changes - Contractor's estimates: Supplemental Provision 2 applies.

-	Loss and expense - Contractor's estimates: Supplemental Provision 3 applies.

Seventh Recital and Part 2 of Schedule 2

SUPPLEMENTAL PROVISIONS - PART 2

-	Acceleration quotation: Supplemental Provision 4 applies.

-	Collaborative working: Supplemental Provision 5 applies.

-	Health and safety: Supplemental Provision 6 applies.

-	Cost savings and value improvements: Supplemental Provision 7 applies.

-	Sustainable development and environmental considerations: Supplemental Provision 8 applies.

-	Performance indicators and monitoring: Supplemental Provision 9 does not apply.

-	Notification and negotiation of disputes: Supplemental Provision 10 applies.

-	Where Supplemental Provision 10 applies, the respective nominees of the parties are:

-	Employer's nominee: To be confirmed.

-	Contractor's nominee: To be confirmed.

-	Or such replacement as each party may notify to the other from time to time.

Article 4

EMPLOYER'S REQUIREMENTS, CONTRACTOR'S PROPOSALS, CONTRACT SUM ANALYSIS

-	Employer's Requirements: Are comprised within the Employers Requirements dated January 2025.

-	Contractor's Proposals: To be completed by Contractor.

-	Contract Sum Analysis: Is comprised within the Employers Requirements dated January 2025 (Refer to Section 3 – Pricing Document).

-	Specific Requirements: not available at tender stage.

Article 8

ARBITRATION

-	Article 8 and clauses 9.3 to 9.8 (arbitration) does not apply.

Clause 1.1

BASE DATE

-	Base Date: 10 days prior to tender return date.

Clause 1.1

DATE FOR COMPLETION OF THE WORKS

-	Date for completion of the works: To be confirmed

Clause 1.7

ADDRESSES FOR SERVICE OF NOTICES

-	Employer:

-	See Clause A10/120

-	Contractor:

-	See Clause A10/130

Clause 2.3

DATE OF POSSESSION OF THE SITE

-	Date of Possession of the site: To be confirmed

Clause 2.4

DEFERMENT OF POSSESSION OF THE SITE

-	Clause 2.4 applies.

-	Where clause 2.4 applies, maximum period of deferment (if less than 6 weeks) is 6 weeks.

Clause 2.17.3

LIMIT OF CONTRACTOR'S LIABILITY FOR LOSS OF USE, ETC.

-	Limit of Contractor's liability for loss of use: No limit.

Clause 2.29.2

LIQUIDATED DAMAGES

-	Damages: At the rate of £1000.00 per week or part thereof.

Clause 2.35

RECTIFICATION PERIOD

-	Period: 12 months from the date of practical completion of the Works.

Clause 4.2, 4.12 and 4.13

FLUCTUATIONS PROVISION

-	Fluctuations Provision: No Fluctuations Provision applies.

Clause 4.6

ADVANCE PAYMENT

-	Advance payment: Clause 4.6 does not apply.

Clause 4.6

ADVANCE PAYMENT BOND

-	Advance Payment Bond: An advance payment bond is not required.

Clause 4.7.1

METHOD OF PAYMENT – ALTERNATIVE B

-	Payment: Periodically, in accordance with Alternative B (clause 4.13).

Clause 4.7.2

INTERIM PAYMENTS – INTERIM VALUATION DATES

-	Dates of Applications for Interim Payment: The first Interim Valuation date is one calendar month after commencement on site and thereafter the same date in each month or the nearest Business Day in that month.

Clause 4.15.4

LISTED ITEMS - UNIQUELY IDENTIFIED

-	Listed items: Clause 4.15.4 will be deleted.

Clause 4.15.5

LISTED ITEMS - NOT UNIQUELY IDENTIFIED

-	Listed items: Clause 4.15.5 will be deleted.

Clause 4.17

CONTRACTOR'S RETENTION BOND

-	Clause 4.17 does not apply.

Clause 4.18.1

RETENTION PERCENTAGE

-	Retention: 5 per cent.

Clause 5.5

DAYWORK

-	Percentage additions to each section of the prime cost or, if they apply in respect of labour, the All-Inclusive Rates, are set out in the following document: NOT USED

Clause 6.4.1

CONTRACTOR'S PUBLIC LIABILITY INSURANCE - INJURY TO PERSONS OR PROPERTY

-	The required level of cover is not less than £10,000,000 for any one occurrence or series of occurrences arising out of one event.

Clause 6.5.1

INSURANCE - LIABILITY OF EMPLOYER

- 	Insurance not required.

Clause 6.7 and Schedule 3

WORKS INSURANCE - INSURANCE OPTION

-	Schedule 3: Insurance option C applies.

-	Percentage to cover professional fees: 15 per cent.

-	If Option A applies, annual renewal date (as supplied by the Contractor): Not Applicable

Clause 6.10 and Schedule 3

TERRORISM COVER

-	Details of the required cover:

-	To be confirmed

Clause 6.15

PROFESSIONAL INDEMNITY INSURANCE

-	Level of cover: Amount of indemnity required:

-	in the aggregate with automatic unlimited reinstatements.

-	and is £ 5,000,000.

-	Cover for pollution and contamination claims: £5,000,000.

-	Cover for asbestos claims: £5,000,000.

-	Cover for fungal mould claims: £5,000,000.

-	Expiry of required period of Professional Indemnity Insurance: 12 years.

Clause 6.17

JOINT FIRE CODE

-	The Joint Fire Code: Applies.

-	Application: State whether the insurer under Insurance Option A, B or C (paragraph C.2) has specified that the works are a 'Large Project': No.

Clause 6.20

JOINT FIRE CODE - AMENDMENTS/ REVISIONS

-	Joint Fire Code - Amendments/ revisions: The cost, if any, of compliance with amendments or revisions to the Joint Fire Code shall be borne by the Contractor.

Clause 7.2

ASSIGNMENT/ GRANT BY EMPLOYER OF RIGHTS UNDER CLAUSE 7.2

-	Sections: Rights under clause 7.2 apply to each Section.

Clause 7.3.1

PERFORMANCE BOND OR GUARANTEE FROM BANK OR OTHER

APPROVED SURETY

-	Performance bond or guarantee from bank or other approved surety: Is not required.

Clause 7.3.2

GUARANTEE FROM THE CONTRACTOR’S PARENT COMPANY

-	Guarantee from the Contractor’s parent company: Is not required.

Clause 7.4

THIRD PARTY RIGHTS AND COLLATERAL WARRANTIES

-	Third Party Rights and Collateral Warranties: Details of the requirements for the grant by the Contractor and sub-contractors of P&T Rights, Funder Rights and/or (in the case of sub-contractors) Employer Rights in respect of the Works, either as third-party rights or by collateral warranties (‘Rights Particulars’) are set out in the following document: To Be Confirmed

Clause 8.9.2

PERIOD OF SUSPENSION (TERMINATION BY CONTRACTOR)

-	Period of suspension: 6 Months.

Clauses 8.11.1.1 to 8.11.1.6

PERIOD OF SUSPENSION (TERMINATION BY EITHER PARTY)

-	Period of suspension: 6 Months

Clause 9.2.1

ADJUDICATION

-	The Adjudicator is:

-	Nominating body: Where no Adjudicator is named or where the named Adjudicator is unwilling or unable to act (whenever that is established): President or a Vice-President or Chairman or a Vice-Chairman of the Royal Institution of Chartered Surveyors.

PART 2: THIRD PARTY RIGHTS AND COLLATERAL WARRANTIES

Part 2(A) Clauses 7A, 7C and 7E

P&T RIGHTS PARTICULARS

Part 2(B)

P&T RIGHTS FROM THE CONTRACTOR

Part 2(C and D)

FUNDER RIGHTS PARTICULARS

Part 2 (E)

COLLATERAL WARRANTIES FORM SUBCONTRACTORS

THE CONDITIONS

SECTION 1: DEFINITIONS AND INTERPRETATION

1.5

RECKONING PERIODS OF DAYS

-	Amendments: To be deleted.

1.10

APPLICABLE LAW

-	Amendments: To be deleted.

SECTION 2: CARRYING OUT THE WORKS

SECTION 3: CONTROL OF THE WORKS

SECTION 4: PAYMENT

SECTION 5: CHANGES

SECTION 6: INJURY, DAMAGE AND INSURANCE

SECTION 7: ASSIGNMENT, THIRD PARTY RIGHTS AND COLLATERAL WARRANTIES

SECTION 8: TERMINATION

SECTION 9: SETTLEMENT OF DISPUTES

JCT PUBLIC SECTOR SUPPLEMENT

-	Document: The JCT Public Sector Supplement 2011 – Fair Payment, Transparency and Building Information Modelling.

-	Fair Payment provisions: Do not apply.

-	Transparency provisions: Do not apply.

-	Building information modelling provisions: Do not apply.

-	The BIM protocol: Do not apply.

EXECUTION

-	The Contract: Will be executed as a deed.

CONTRACT GUARANTEE BOND

-	Contract Guarantee Bond: Will not be required.

A30	TENDERING/ SUBLETTING/ SUPPLY

MAIN CONTRACT TENDERING

A30/110	SCOPE

-	General: These conditions are supplementary to those stated in the Invitation to Tender and on the form of tender.

A30/145	TENDERING PROCEDURE

-	General: In accordance with JCT Tendering Practice Note 2017.

-	Errors: Alternative 2 is to apply.

A30/150	PURCHASER'S AND TENANT'S WARRANTY

-	The Agreement: Enter into the JCT Standard Form of Agreement for Collateral Warranty MCWa/P&T, a copy of which, with the relevant parts completed, is included with the tender documents. The Form gives the text of the enabling clause which is to be included in the Conditions of Contract.

-	Maximum number of Warranties which the Employer may require: Two.

A30/151	FUNDER'S WARRANTY

-	The Agreement: Enter into the JCT Standard Form of Agreement for Collateral Warranty MCWa/F, a copy of which, with the relevant parts completed, is included with the tender documents. The Form gives the text of the enabling clause which is to be included in the Conditions of Contract.

155	Specialist Sub-Contractors and any additional Design Consultants appointed by the Contractor shall without payment execute a warranty in the form set out in Appendix ‘B’, hereto in favour of the Purchaser/Tenant and or fund. The Warranties must be entered into within 14 Days of the Employers request.

Specialist sub contractor warranties will  be required from:

- ASHP specialist contractor/installer

- PV specialist contractor/installer

- Window specialist contractor/installer

- LED specialist contractor/installer

156	The contractor is to ensure that all Warranties have been received from the Specialist Sub-contractors and the like who has not provided a warranty.

157	The Employer reserves the right to withhold payment from the contractor in respect of any Specialist Sub-contractor and the like who has not provided a warranty.

158	The Main Contractor shall not engage any Specified Sub-contractors without the prior approval of the Employer. The Main Contractor shall ensure that all warranties so required are delivered prior to a start on site.

159	The Building Contractor should include in every engagement of a Relevant Subcontractor an obligation to deliver to the Tenant a Warranty as soon as reasonably practicable after completion of such engagement.

A30/160	EXCLUSIONS

-	Inability to tender: Immediately inform if any parts of the work as defined in the tender documents cannot be tendered.

-	Relevant parts of the work: Define those parts, stating reasons for the inability to tender.

A30/170	ACCEPTANCE OF TENDER

-	Acceptance: No guarantee is offered that any tender will be recommended for acceptance or be accepted, or that reasons for non-acceptance will be given.

-	Costs: No liability is accepted for any cost incurred in the preparation of any tender.

A30/180	CDM PLANNING PERIOD

-	Minimum: 2 Weeks ending on date of possession.

A30/190	PERIOD OF VALIDITY

-	Period: After submission or lodgement, keep tender open for consideration (unless previously withdrawn) for not less than 90 days.

-	Date for possession/ commencement: See section A20.

PRICING/ SUBMISSION OF DOCUMENTS

A30/210	PRELIMINARIES IN THE SPECIFICATION

-	Measurement rules: Preliminaries/ General Conditions sections (A10-A55 inclusive) must not be relied on as complying with SMM7.

A30/220	PRICING OF PRELIMINARIES

-	Charges: If the Contractor requires interim payments to include fixed and time related charges for specific items in the Preliminaries, those charges must be clearly shown against the items. In the absence of such notation, the charges will be considered as fixed.

A30/250	PRICED DOCUMENTS

-	Alterations: Do not alter or qualify the priced documents without written consent. Tenders containing unauthorised alterations or qualifications may be rejected.

-	Measurements: Where not stated, ascertain from the drawings.

-	Deemed included: Costs relating to items, which are not priced, will be deemed to have been included elsewhere in the tender.

-	Submit: With tender.

A30/310	TENDER

-	General: Tenders must include for all work shown or described in the tender documents as a whole or clearly apparent as being necessary for the complete and proper execution of the Works.

A30/440	CONTRACT SUM ANALYSIS

-	Content of the Analysis: A breakdown of the Contract Sum into at least the following categories:

-	As detailed within Section 3 of the Employers Requirements.

-	Form: As detailed within Section 3 of the Employers Requirements.

-	Fully priced copy: Submit with tender.

445	ERRORS IN THE CONTRACT SUM ANALYSIS

-	Errors in the Contract Sum Analysis will be dealt with in accordance with JCT Tendering Practice Note 2017.

-	Errors: Alternative 2 is to apply.

A30/480	PROGRAMME

The Contractor's proposed programme as specified in Section A32 or a summary thereof showing the sequence and timing of the principal parts of the Works, periods for planning and design, and itemising any work which is excluded must be submitted with the Form of Tender.

The programme will clearly define the proposed contract period and completion date.

Following execution of the Contract the Contractor shall provide two copies of his master programme (Bar Chart), which should be maintained on site and updated and reissued to reflect any changes.

The programme must clearly indicate the work of all subcontractors and suppliers and clearly indicate the relationship between operations. The Critical path is to be clearly identified.

The program should reflect the following:

1.) Progress on a week-by-week basis.

2.) Critical Path.

3.) Holidays.

4.) Time for pre-handover inspections and remedials.

A method statement must be produced based on the programme clearly indicating the Contractors method of work.

The above requirements will demonstrate that the Contractor has understood the proposed project and has the necessary management expertise to undertake the project and will be taken into consideration during the tender review.

A30/500	TENDER STAGE METHOD STATEMENTS

- Tender Stage Method Statements must be submitted within one week of request describing how and when the Contractor proposes and undertakes to carry out the following types of work: -

-	How all stages of the works will be executed within an existing building including manner, method, sequence and execution of work generally taking into account the overall programme. In particular any temporary works required, means of access to the town hall and adjacent premises, methods of minimising noise levels and vibration, maintaining means of escape and protection to the public, environmental pollutants & omissions.

-	Proposals for location of site compound, site accommodation and storage of materials and access into the site of the Works from the site compound.

-	Location, methods/details of temporary screens, hoardings and barriers separating members of the public/other tenants from the works, access routes to the site, and around the pavements and car parking areas. This to include hoarding plan in relation to programme as part of the tender submission.

-	Timing and deliveries of materials, including offloading and distribution around the site; also, method and timing of removal from site of rubbish.

-	Waste management strategy.

-	Arrangements and details of the method for controlling dust and escape onto paving’s, roads and other tenant’s units affected by the Works including proposals for daily cleaning and general cleaning.

-	Methods and arrangements for security on site.

-	The approach to Health & Safety requirements and training those personnel will undergo prior to working on site.

- 	Methods and procedures for executing elements of work outside normal working hours. Statement to include list of principal elements of construction to be so undertaken, including Sub-contract works.

-	Statement describing resources which are intended to be allocated to the Project, so that it can be established if such resources are adequate.

-	At the Contractor’s discretion other appropriate method statements.

- The contractor will be deemed to have included for all costs and programme allowances to undertake such works.

-	Statements: Submit with the tender.

A30/505	ORGANISATION AND MANAGEMENT

-	Team Details: Provide an organisation chart showing the members of your team likely to be allocated to the proposed project. This should include those on site and those off site at the regional head office.

-	List the names, duties and provide CV’ details of the proposed project team, in particular the senior project personnel with reasoning behind their selection for involvement with the proposed project. These shall include but not be limited to: -

-	Contracts Manager/Project Manager,

-	Site Manager/Trade Foreman,

- 	other key members of staff.

-	Submit: As part of the Tender Submission.

A30/510	ALTERNATIVE METHOD TENDERS

-	General: In addition to and at the same time as tendering for the Works as defined in the tender documents, alternative methods of construction/ installation may be submitted for consideration. Alternatives, which would involve significant changes to other work, may not be considered.

-	Alternative tenders: Such alternatives will be deemed to be alternative tenders, and each must include a complete and precise statement of the effects on cost and programme.

-	Safety method statement: Carry out a health and safety risk assessment for each alternative and where appropriate provide a safety method statement suitable for incorporation in the Health and Safety Plan.

-	Full technical data: Submit for each alternative together with details of any consequential amendments to the design and/ or construction of other parts of the Works.

-	Submit: With the tender.

A30/515	ALTERNATIVE TIME TENDERS

-	General: In addition to and at the same time as tendering based upon the date or period specified in section A20, an alternative tender based upon a different date for completion or period may be submitted.

-	Date for completion: If any such tender is accepted the date for completion inserted in the Contract will be the date stated in the alternative tender or determined from the period stated in the alternative tender.

A30/520	DESIGN DOCUMENTS

-	Design drawings in respect of architectural, structural and service engineer services to be included in the Contractor's Proposals must include:

-	Ground Floor Plan

-	Roof Plan

-	Elevations

-	External Works

-	Drainage

-	Sections

-	Details

-	Any other drawings necessary to support the Contractors Proposals.

A30/530	SUBSTITUTE PRODUCTS

-	Details: If products of different manufacture to those specified are proposed, submit details with the tender giving reasons for each proposed substitution. Substitutions, which have not been notified at tender stage, may not be considered.

-	Compliance: Substitutions accepted will be subject to the verification requirements of clause A31/200.

A30/540	QUALITY CONTROL RESOURCES

-	Statement: Describe the organisation and resources to control the quality of the Works, including the work of subcontractors.

-	QA staff: Identify in the statement the number and type of staff responsible for quality control, with details of their qualifications and duties.

-	Submit: Within one week of request.

A30/550	HEALTH AND SAFETY INFORMATION

-	Content: Describe the organisation and resources to safeguard the health and safety of operatives, including those of subcontractors, and of any person whom the Works may affect.

-	Include:

-	A copy of the contractor's health and safety policy document, including risk assessment procedures.

-	Accident and sickness records for the past five years.

-	Records of previous Health and Safety Executive enforcement action.

-	Records of training and training policy.

-	The number and type of staff responsible for health and safety on this project with details of their qualifications and duties.

-	Submit: One copy of all Health and Safety Information with the Contractors Proposals.

A30/570	OUTLINE CONSTRUCTION PHASE HEALTH AND SAFETY PLAN

-	Content: Submit the following information within one week of request:

-	Method statements on how risks from hazards identified in the pre-construction information and other hazards identified by the contractor will be addressed.

-	Details of the management structure and responsibilities.

-	Arrangements for issuing health and safety directions.

-	Procedures for informing other contractors and employees of health and safety hazards.

-	Selection procedures for ensuring competency of other contractors, the self-employed and designers.

-	Procedures for communications between the project team, other contractors and site operatives.

-	Arrangements for cooperation and coordination between contractors.

-	Procedures for carrying out risk assessment and for managing and controlling the risk.

-	Emergency procedures including those for fire prevention and escape.

-	Arrangements for ensuring that all accidents, illness and dangerous occurrences are recorded.

-	Arrangements for welfare facilities.

-	Procedures for ensuring that all persons on site have received relevant health and safety information and training.

-	Arrangements for consulting with and taking the views of people on site.

-	Arrangements for preparing site rules and drawing them to the attention of those affected and ensuring their compliance.

-	Monitoring procedures to ensure compliance with site rules, selection and management procedures, health and safety standards and statutory requirements.

-	Review procedures to obtain feedback.

A30/630	DOMESTIC SUBCONTRACTS

-	General: Comply with the Construction Industry Board ‘Code of Practice for the selection of sub-contractors’.

-	List: Provide details of all subcontractors and the work for which they will be responsible.

-	Submit: With the tender.

A31	PROVISION, CONTENT AND USE OF DOCUMENTS

DEFINITIONS AND INTERPRETATIONS

A31/110	DEFINITIONS

-	Meaning: Terms, derived terms and synonyms used in the preliminaries/ general conditions and specification are as stated therein or in the appropriate British Standard or British Standard glossary.

A31/120	COMMUNICATION

-	Definition: Includes advise, inform, submit, give notice, instruct, agree, confirm, seek or obtain information, consent or instructions, or make arrangements.

-	Format: In writing to the person named in clause A10/140 unless specified otherwise.

-	Response: Do not proceed until response has been received.

A31/130	PRODUCTS

-	Definition: Materials, both manufactured and naturally occurring, and goods, including components, equipment and accessories, intended for the permanent incorporation in the Works.

-	Includes: Goods, plant, materials, site materials and things for incorporation into the Works.

A31/135	SITE EQUIPMENT

-	Definition: All appliances or things of whatsoever nature required in or about the construction for completion of the Works but not materials or other things intended to form or forming part of the Permanent Works.

-	Includes: Construction appliances, vehicles, consumables, tools, temporary works, scaffolding, cabins and other site facilities.

A31/140	DRAWINGS

-	Definitions: To BSRIA BG 6/2009 A design framework for building services. Design activities and drawing definitions.

-	CAD data: In accordance with BS 1192.

A31/150	CONTRACTOR'S DESIGN

-	Meaning: Design to be carried out or completed by the Contractor and supported by appropriate contractual arrangements, to correspond with specified requirements.

A31/155	SUBMIT PROPOSALS

-	Meaning: Submit information in response to specified requirements.

A31/160	TERMS USED IN SPECIFICATION

-	Remove: Disconnect, dismantle as necessary and take out the designated products or work and associated accessories, fixings, supports, linings and bedding materials. Dispose of unwanted materials. Excludes taking out and disposing of associated pipework, wiring, ductwork or other services.

-	Fix: Unload, handle, store, place and fasten in position including all labours and use of site equipment.

-	Supply and fix: Include all labour and site equipment for unloading, handling, storing and execution. All products to be supplied and fixed unless stated otherwise.

-	Keep for reuse: Do not damage designated products or work. Clean off bedding and jointing materials. Stack neatly, adequately protect and store until required by the Employer/ Purchaser or for use in the Works as instructed.

-	Make good: Execute local remedial work to designated work. Make secure, sound and neat. Excludes redecoration and/ or replacement.

-	Replace: Supply and fix new products matching those removed. Execute work to match original new state of that removed.

-	Repair: Execute remedial work to designated products. Make secure, sound and neat. Excludes redecoration and/ or replacement.

-	Refix: Fix removed products.

-	Ease: Adjust moving parts of designated products or work to achieve free movement and good fit in open and closed positions.

-	Match existing: Provide products and work of the same appearance and features as the original, excluding ageing and weathering. Make joints between existing and new work as inconspicuous as possible.

-	System: Equipment, accessories, controls, supports and ancillary items, including installation, necessary for that section of the work to function.

A31/170	MANUFACTURER AND PRODUCT REFERENCE

-	Definition: When used in this combination:

-	Manufacturer: The firm under whose name the particular product is marketed.

-	Product reference: The proprietary brand name and/ or reference by which the particular product is identified.

-	Currency: References are to the particular product as specified in the manufacturer’s technical literature current on the date of the invitation to tender.

A31/200	SUBSTITUTION OF PRODUCTS

-	Products: If an alternative product to that specified is proposed, obtain approval before ordering the product.

-	Reasons: Submit reasons for the proposed substitution.

-	Documentation: Submit relevant information, including:

-	manufacturer and product reference;

-	cost;

-	availability;

-	relevant standards;

-	performance;

-	function;

-	compatibility of accessories;

-	proposed revisions to drawings and specification;

-	compatibility with adjacent work;

-	appearance;

-	copy of warranty/ guarantee.

-	Alterations to adjacent work: If needed, advise scope, nature and cost.

-	Manufacturer’s guarantees: If substitution is accepted, submit before ordering products.

A31/210	CROSS REFERENCES

-	Accuracy: Check remainder of the annotation or item description against the terminology used in the section or clause referred to.

-	Related terminology: Where a numerical cross-reference is not given the relevant sections and clauses of the specification will apply.

-	Relevant clauses: Clauses in the referred to specification section dealing with general matters, ancillary products and execution also apply.

-	Discrepancy or ambiguity: Before proceeding, obtain clarification or instructions.

A31/220	REFERENCED DOCUMENTS

-	Conflicts: Specification prevails over referenced documents.

A31/230	EQUIVALENT PRODUCTS

-	Inadvertent omission: Wherever products are specified by proprietary name the phrase 'or equivalent' is to be deemed included.

A31/240	SUBSTITUTION OF STANDARDS

-	Specification to British Standard or European Standard: Substitution may be proposed complying with a grade or category within a national standard of another Member State of the European Community or an international standard recognised in the UK.

-	Before ordering: Submit notification of all such substitutions.

-	Documentary evidence: Submit for verification when requested as detailed in clause A31/200. Any submitted foreign language documents must be accompanied by certified translations into English.

A31/250	CURRENCY OF DOCUMENTS

-	Currency: References to published documents are to the editions, including amendments and revisions, current on the date of the Invitation to Tender.

A31/260	SIZES

-	General dimensions: Products are specified by their co-ordinating sizes.

-	Timber: Cross section dimensions shown on drawings are:

-	Target sizes as defined in BS EN 336 for structural softwood and hardwood sections.

-	Finished sizes for non-structural softwood or hardwood sawn and further processed sections.

DOCUMENTS PROVIDED ON BEHALF OF EMPLOYER

A31/410	ADDITIONAL COPIES OF THE DRAWINGS/ DOCUMENTS

-	Additional copies: Two copies of drawings (not counting any certified copy of the Contract Drawings) will be issued to the Contractor free of charge. Additional copies will be issued on request but will be charged to the Contractor.

A31/440	DIMENSIONS

-	Scaled dimensions: Do not rely on.

A31/460	THE SPECIFICATION

-	Coordination: All sections must be read in conjunction with Main Contract Preliminaries/ General conditions.

A31/470	DIVERGENCE FROM THE STATUTORY REQUIREMENTS

-	Divergence: Between the drawings or specification and the requirements of the Building Regulations, other Statutes, statutory undertakers and other regulatory authorities.

-	Action: Inform immediately.

DOCUMENTS PROVIDED BY CONTRACTOR/ SUBCONTRACTORS/ SUPPLIERS

A31/510	CHANGES/ AMENDMENTS TO EMPLOYER'S REQUIREMENTS

-	Contractor’s changes to Employer's Requirements: Support request for substitution or variation with all relevant information.

-	Employer’s amendments to Employer’s Requirements: If considered to involve a variation, which has not already been acknowledged as a variation, notify without delay (maximum period 7 days), and do not proceed until instructed. Claims for extra cost, if made after the variation has been carried out, may not be allowed.

-	Submit: With the tender.

A31/520	DESIGN AND PRODUCTION INFORMATION

-	General: Complete the design and detailing of parts of the Works as specified.

-	Provide:

-	Production information based on the drawings, specification and other information.

-	Liaison to ensure coordination of the work with related building elements and services.

-	Master programme: Make reasonable allowance for completing design/ production information, submission (including to the Principal Designer), comment, inspection, amendment, resubmission and reinspection.

-	Design/ production information: Submit two copies, one can be returned with comments. Ensure that any necessary amendments are made without delay.

-	Contractor’s changes to Employer's Requirements: Support request for substitution or change with all relevant information.

-	Employer’s amendments to Employer’s Requirements: If considered to involve a change, which has not already been acknowledged as a change, notify without delay (maximum period 7 days), and do not proceed until instructed. Claims for extra cost, if made after it has been carried out, may not be allowed.

-	Final version of design/ production information: Submit to the EA the required number of copies.

A31/540	PERFORMANCE SPECIFIED WORK: CONTRACTOR’S PROPOSALS

-	Master programme: Make reasonable allowance for completing performance specified work, submission (including to the Principal Designer), comment, inspection, amendment, resubmission and re-inspection.

-	Proposals: Submit two copies, one could be returned with comments and this will be deemed to be a direction, notice or instruction under the Contract. Ensure that any necessary amendments are made without delay and resubmit unless it is confirmed that it is not required.

-	Request for substitution or variation: Submit, supported by all relevant information, if proposals differ from the performance requirements or require changes at the interface with adjacent work.

-	Employer’s amendments to Performance Specified Work: If considered to involve a variation, which has not already been acknowledged as a variation, notify without delay (maximum period 7 days), and do not proceed until instructed. Claims for extra cost, if made after it has been carried out, may not be allowed.

-	Submit: Two copies of final version of proposals.

A31/555	SUBMISSION OF INFORMATION

-	Master programme: Make reasonable allowance, based on information in sections A51 or A52, for completing design/ production information, checking, submission (including requirements under health and safety legislation), comment, inspection, amendment, resubmission and re-inspection.

-	Information from Subcontractors/ Suppliers:

-	Obtain in time to meet the programme and in accordance with conditions of nomination where applicable.

-	Check dimensions are correct, account is taken of all related work, and construction is practicable.

-	Note any comments on one copy of the design/ production information, then submit with the required number of additional unmarked copies. Such checking will not relieve the consultant designer or the Subcontractors/ Suppliers of their respective responsibilities for design, co-ordination and documentation.

-	Inspection and comments: May be marked on one copy and returned to Contractor. This will not relieve the Subcontractors/ Suppliers of their responsibility for design and documentation. Ensure that any necessary amendments are made without delay and resubmit unless it is confirmed that it is not required.

-	Final version of information: Distribute copies to all affected parties and keep one copy on site.

-	Submit to the EA the required number of copies.

A31/600	CONTRACTOR’S DESIGN INFORMATION

-	General: Complete the design and detailing of parts of the Works as specified.

-	Provide:

-	Production information based on the drawings, specification and other information.

-	Liaison to ensure coordination of the work with related building elements and services.

-	Master programme: Make reasonable allowance for completing design/ production information, submission (including to the Principal Designer), comment, inspection, amendment, resubmission and re-inspection.

-	Format: A3 Drawings.

-	Number of copies: Two.

-	Submit: Within one week of request

A31/610	PRODUCTION INFORMATION

-	Contractor/ Domestic subcontractor provide: Two electronic copies on CD.

-	Submit:

-	For comment and make any necessary amendments.

-	Sufficient copies of final version for distribution to all affected parties.

A31/620	AS BUILT DRAWINGS AND INFORMATION

-	General: Provide the following Drawings / information:

-	all relevant information accurately detailing the constructed building

-	Submit: At least two weeks before date for completion.

625	The Building Contractor shall keep available for inspection by the Tenant and the Tenant's Professional Team (on not less than three working days' notice during normal working hours) in a location at the Estate:

a register and full-sized copies of all drawings, plans and specifications relating to the Landlord's Works prepared by the Contractor or any other person from time to time designing elements of the Landlord's Works;

all other working and design drawings for the Landlord's Works insofar as they set out the Premises.

A31/630	TECHNICAL LITERATURE

-	Information: Keep on site for reference by all supervisory personnel:

-	Manufacturers' current literature relating to all products to be used in the Works.

-	Relevant British Standards.

A31/640	MAINTENANCE INSTRUCTIONS AND GUARANTEES

-	Components and equipment: Obtain or retain copies, register with manufacturer and hand over on or before completion of the Works.

-	Emergency call out services: Provide telephone numbers for use after completion and details regarding extent of cover.

A32	MANAGEMENT OF THE WORKS

GENERALLY

A32/110	SUPERVISION

-	General: Accept responsibility for coordination, supervision and administration of the Works, including subcontracts.

-	Coordination: Arrange and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work.

A32/115	CONSIDERATE CONSTRUCTORS SCHEME

-	Registration: Before starting work, register the site and pay the appropriate fee:

-	Contact:

-	Address: Considerate Constructors Scheme Office, PO Box 75, Great Amwell, Ware, Hertfordshire, SG12 0YX.

-	Tel. 01920 485959.

-	Fax. 01920 485958.

-	Free phone 0800 7831423.

-	Web. www.ccscheme.org.uk.

-	Standard: Comply with the Scheme's Code of Considerate Practice.

A32/120	INSURANCE

-	Documentary evidence: Before starting work on site submit details, and/ or policies and receipts for the insurances required by the Conditions of Contract.

A32/130	INSURANCE CLAIMS

-	Notice: If any event occurs which may give rise to any claim or proceeding in respect of loss or damage to the Works or injury or damage to persons or property arising out of the Works, immediately give notice to the Employer, the person named in clause A10/140 and the Insurers.

-	Failure to notify: Indemnify the Employer against any loss, which may be caused by failure to give such notice.

A32/140	CLIMATIC CONDITIONS

-	Information: Record accurately and retain:

-	Daily maximum and minimum air temperatures (including overnight).

-	Delays due to adverse weather, including description of the weather, types of work affected, and number of hours lost.

A32/150	OWNERSHIP

-	Alteration/ clearance work: Materials arising become the property of the Contractor except where otherwise stated. Remove from site as work proceeds.

PROGRAMME/ PROGRESS

A32/210	PROGRAMME

-	Master programme: When requested and before starting work on site, submit in an approved form a master programme for the Works, which must include details of:

-	Design, production information and proposals provided by the Contractor/ Subcontractors/ Suppliers, including inspection and checking (see section A31).

-	Planning and mobilization by the Contractor.

-	Earliest and latest start and finish dates for each activity and identification of all critical activities.

-	Running in, adjustment, commissioning and testing of all engineering services and installations

-	Work resulting from instructions issued in regard to the expenditure of provisional sums (see section A54)

-	Work by or on behalf of the Employer and concurrent with the Contract (see section A50). The nature and scope of which, the relationship with preceding and following work and any relevant limitations are suitably defined in the Contract Documents.

-	Exclusions: Where and to the extent that the programme implications for work which is not so defined are impossible to assess, the Contractor should exclude it and confirm this when submitting the programme.

A32/215	REVISED PROGRAMME

-	Format and content: Compatible with master programme.

-	Revised programme interval: Described in the contract data part one.

-	Number of copies: One copy to each Consultant.

A32/230	SUBMISSION OF PROGRAMME

-	Further information: Submission of the programme will not relieve the Contractor of the responsibility to advise of the need for further drawings or details or instructions in accordance with the Contract.

A32/240	COMMENCEMENT OF WORK

-	Notice: Before the proposed date for commencement of work on site give minimum notice of 5 working days.

A32/250	MONITORING

-	Progress: Record on a copy of the programme kept on site.

-	Avoiding delays: If any circumstances arise which may affect the progress of the Works submit proposals or take other action as appropriate to minimize any delay and to recover any lost time.

255	FINISHING PROGRAMME

-	A minimum of 4 weeks prior to the anticipated date of Practical Completion, the Contractor must prepare and issue to the EA a detailed finishing programme indicating the following items:

- Date of Practical Completion.

- Incoming Services installation date.

- Meter installation dates.

- Services commissioning dates and periods.

- Builder’s clean dates.

- Air test dates.

- Acoustic test dates.

- Ensure that this finishing programme provides for areas of the building to be offered up for inspection by the EA and incoming tenants representatives in a phased manner. No part of the building shall be offered up for inspection until it is completed and cleaned.

A32/260	SITE MEETINGS

-	General: Site meetings will be held to review progress and other matters arising from administration of the Contract.

-	Frequency: Monthly (to be confirmed).

-	Location: On Site.

-	Accommodation: Ensure availability at the time of such meetings.

-	Attendees: Attend meetings and inform subcontractors and suppliers when their presence is required.

-	Chairperson (who will also take and distribute minutes): Employers Agent.

A32/265	CONTRACTOR’S PROGRESS REPORT

-	General: Submit a progress report at least three days before the site meeting.

-	Content: Notwithstanding the Contractor's obligations under the Contract the report must include:

-	A progress statement by reference to the master programme for the Works.

-	Details of any matters materially affecting the regular progress of the Works.

-	Any requirements for further drawings or details or instructions.

-	Marked up Activity Schedule indicating planned progress and actual progress, together with comments, advising reason for any deviation.

-	Schedule of key dates anticipated for completion of parts of the building or in cases of phased possession, dates when areas will be required to be taken into possession.

-	List of EA’s Instructions issued since the last meeting and any conformity instructions issued by the Contractor or requests for information issued since the last meeting.

-	Updated schedule of information requirements and a record of requests for information issued by the Contractor noting those where a response is awaited and of those, which are critical.

-	List of status of main subcontract/supply items including whether orders have been placed and any critical delivery items.

-   Record of currently approved Sub-contractors, those being submitted for approval and those trades likely to be sublet, prior to the next meeting.

-  List of any incidents on site, including those concerning Health and Safety.

-   Such additional information as may be requested by the EA.

A32/270	CONTRACTOR’S SITE MEETINGS

-	General: Hold meetings with appropriate subcontractors and suppliers shortly before main site meetings to facilitate accurate reporting of progress.

A32/285	EARLY POSSESSION/ TAKE OVER OF PARTS OF THE WORKS BY THE EMPLOYER

-	Possession/ takeover of parts of the Works: As completed, provided all necessary access, services and other associated facilities are also complete.

A32/290	NOTICE OF COMPLETION

-	Requirement: Give notice of the anticipated dates of completion of the whole or parts of the Works.

-	Associated works: Ensure necessary access, services and facilities are complete.

-	Period of notice (minimum): Two weeks.

-	The Contractor should note that Practical Completion will be considered as having taken place only when:

1.	The Works or parts of the Works are fully complete to the satisfaction of the EA;

2.	All Contractor’s staff and those of his Sub-Contractors have vacated the site or at least that section thereof;

3.	All surplus materials, plant and equipment etc. have been removed from the site, or section thereof;

4.	All defects apparent and notified to the Contractor before Practical Completion or section thereof have been made good;

5.	The Works have been thoroughly cleaned to the entire satisfaction of the EA;

6.	No further work of any respect will be required to fully complete the Works; in accordance with the Contract with the exception only of defects arising during the rectification period(s).

7.  Appropriate health and safety documentation, building manuals and 'as fitted' drawings are complete for the whole or parts of the Works.

8.  Confirmation from Building Control that the Works have been

undertaken in accordance with and both satisfy and comply with

building regulations.

9.  All relevant planning conditions have been discharged.

A32/310	EXTENSIONS OF TIME

-	Notice: When a notice of the cause of any delay or likely delay in the progress of the Works is given under the conditions of contract, written notice must also be given of all other causes which apply concurrently.

-	Details: As soon as possible submit:

-	Relevant particulars of the expected effects, if appropriate, related to the concurrent causes.

-	An estimate of the extent, if any, of the expected delay in the completion of the Works beyond the date for completion.

-	All other relevant information required.

CONTROL OF COST

A32/410	CASH FLOW FORECAST

-	Submission: Before starting work on site, submit a forecast showing the gross valuation of the Works at the date of each Interim Certificate throughout the Contract period. Base on the programme for the Works.

A32/420	REMOVAL/ REPLACEMENT OF EXISTING WORK

-	Extent and location: Agree before commencement.

-	Execution: Carry out in ways that minimize the extent of work.

A32/430	PROPOSED INSTRUCTIONS

-	Estimates: If a proposed instruction requests an estimate of cost, submit without delay and in any case within seven days.

-	Include:

-	A detailed breakdown of the cost, including any allowance for direct loss and expense.

-	Details of any additional resources required.

-	Details of any adjustments to be made to the programme for the Works.

-	Any other information as is reasonably necessary to fully assess the implications of issuing such an instruction.

-	Inability to comply: Inform immediately if it is not possible to comply with any of the above requirements.

435	CHANGE CONTROL PROCESS

-	Contractor is to note that any Change Control Process is to be strictly in accordance with the process outlined within Appendix ‘B’ of the Employers Requirements.

A32/440	MEASUREMENT

-	Covered work: Give notice before covering work required to be measured.

A32/450	DAYWORK VOUCHERS

-	Before commencing work: Give reasonable notice to person countersigning daywork vouchers.

-	Content: Before delivery, each voucher must be:

-	Referenced to the instruction under which the work is authorized.

-	Signed by the Contractor's person in charge as evidence that the operatives' names, the time daily spent by each and the equipment and products employed are correct.

-	Submit: No later than the end of the week following that in which the work has been recorded.

A32/460	INTERIM VALUATIONS

-	Applications: Include details of amounts requested under the Contract together with all necessary supporting information.

-	Submission: At least seven days before established dates.

A32/470	PRODUCTS NOT INCORPORATED INTO THE WORKS

-	Ownership: At the time of each valuation, supply details of those products not incorporated into the Works which are subject to any reservation of title inconsistent with passing of property as required by the Conditions of Contract, together with their respective values.

-	Evidence: When requested, provide evidence of freedom of reservation of title.

A32/475	LISTED PRODUCTS STORED OFF SITE

-	No application for the payment of materials or goods, stored off site will be considered.

A32/480	LABOUR AND EQUIPMENT RETURNS

-	Records: Provide for verification at the beginning of each week in respect of each of the previous seven days.

-	Records must show:

-	The number and description of craftsmen, labourers and other persons directly or indirectly employed on or in connection with the Works or Services, including those employed by subcontractors.

-	The number, type and capacity of all mechanical, electrical and power-operated equipment employed in connection with the Works or Services.

MANAGEMENT OF FIRE AND FLOOD RISK

481	FIRE RISK MANAGEMENT

- Unless work the contractor has undertaken can be secured and fenced (so that only the contractor has access to the area) then, on entering or leaving the site, the contractor should always report to a responsible person.

- Care should always be taken to ensure suitable fire precautions are being taken. In particular, the daily cleaning up and removal of waste during work involved in heat applications such as wiring, gas cutting, roof tarring and whilst flammable liquids are being used.

- Work involving heating applications should always be strictly supervised and the implementation of a ‘Hot Work Permit’ system is a condition of the contract. Permits should not be for more than half a day at a time.

- Where liquids having a flash point of less than 32 degrees centigrade are used, no more than 50 litres should be stored in the building and they should be kept in a fire-resistant metal cabinet. Only the gas cylinder in use should be kept on the premises.

- Any new extensions, floors or ceilings should be of non-combustible materials.

- No space heaters should be brought on to site.

- Contractors having to work in hazardous areas, on electrical equipment, enter tanks, or work in areas where toxic fumes could be emitted should also be controlled by a ‘Permit to Work’ system. This involves drawing up a list of precautions to be taken and providing suitable locking-off devices so that no other person can either enter or turn on the power source.

- Any smoking policy must be observed.

- Contractors should be made fully aware of all the safety precautions which have to be taken on site and be required to sign a form issued by Workman to the effect that they have seen these standards and have agreed to work by them whilst on site.

- Cutting, welding, soldering, brazing, bitumen heating, blow lamps or torches and any other process requiring heat should not be left unattended.

482	FLOOD RISK MANAMENT

Project Management

- The main contractor should appoint a nominated individual with responsibility for management of water damage risk.

- The works should be phased to reduce the likelihood and severity of damage from burst pipes or weather-related incidents. Roof and cladding to be complete and the envelope made watertight before internal works are carried out.

- Drainage should be installed early with full functionality as early as possible.

- Ensure bunding is complete and drainage from plant rooms connected before tanks are filled.

Sub-Contractor Appointment

- Only professional qualified plumbers to be permitted to work on water distribution systems.

- All operatives should be fully trained by the manufacturer on new systems or bespoke machinery and training records kept.

- The main contractor should ensure the on-site inspection and certification of the sub-contractor’s work throughout the process.

- Companies employed to work on plumbing installations should be affiliated to an industry body (IPHE, IP, APHC or HVCA). Plumbing and Heating Ventilation companies should also be members of approved schemes such as IPHE and WIAPS.

Quality Control

- The main contractor should implement a procedure for independent third-party certification carried out through the installation which should be documented.

- All contractors should be required to work to industry recognised codes clearly defined in work specifications and contract documents. The main applicable documents are Water Supply (Water Fittings) Regulations 2000; BS6700:2006 Design, installation, testing and maintenance of services supplying water for domestic use within buildings and their curtilages: specification; HVCA Good Practice Guides; and CIBSE (Chartered Institute of Building Services Engineers) standards.

- Ensure strict compliance with design guidelines and manufacturer’s installation manuals. Ensure training records are retained.

- All joints should be subject to a visual inspection as part of commissioning and for a period not less than 2 weeks thereafter.

- All pipework should be subjected to a clearing defined pressure testing regime in accordance with the manufacturer’s guidelines.

- Pipework should be subject to an initial air test followed by hydraulic testing – account needs to be taken of the daily variation in mains pressures when determining the “normal working pressures.

- Pressure testing should be witnessed by the main contractor.

- All sections of pipework should be certified to have met the test standard and certificates should be issued for each section of pipework tested. There should be an independent party responsible for auditing this paperwork.

- Industry-recognised guidance documents should be regarded as the default position if manufacturer’s guidance is not forthcoming.

- Full commissioning tests should be carried out on systems in their entirety, including all equipment and fittings at their working pressure, in line with equipment supplier’s guidelines.

- It is advised that water management devices are installed with audible signalling to provide a warning of failure in any part of the system. Commissioning should be carried out during the day when there is more chance of a leak being detected and swiftly dealt with. Commissioning of systems when the building is vacant should be avoided at all costs.

- There should be a full audit trail of all components used, the testing regime, commissioning procedures and approval certificates.

Mitigation

- Switch off the water supply outside working hours. It is recommended that a master valve is located in an accessible location and a designated person nominated to perform the task. Where a boosted supply is installed, the booster pumps should be isolated. Consideration should be given to the effects of thrust pressure when these are turned back on.

- Install a water management device on the incoming riser and programme it to shut down the water supply when water flows exceed pre-determined parameters; these parameters should be set in relation to normal water usage.

- The water management device should have an integral battery back-up to ensure that it is effective during the testing and commissioning stage when power is often isolated for long periods. On unmanned sites such a device should be configured for remote monitoring.

- Dependent upon the configuration of the HVAC system, consideration should also be given to installing water management devices on header tanks of enclosed systems.

- Install and commission leak detection, with temporary alarms, in areas such as bunds, the bottoms of risers, equipment rooms, around AC units and in vulnerable cable trays. In an unattended building, alarms should be linked to pagers, or other form of remote monitoring, and an emergency procedure put in place.

- Security guards, where present, should be trained to provide an early emergency response and to manually shut down systems, where appropriate. Un-manned sites should have personnel cover for emergency out of hours call out to respond to remote monitoring of leak and flow detection.

- Guard’s duties should be extended to routine patrols to check for escape of water where wet services are live.

- A clear plan to be drawn up which must include well defined emergency procedures, a call out list & knowledge of, and access to, isolation valves.

- Establish a plan for bringing in, handling and discharging temporary and permanent water supplies in the buildings under construction.

- Temporary rising mains for use of wet trades should be tightly controlled with lockable discharge points. Water butts can be used to ensure only limited quantities of water are available inside the building.

- Wherever possible, a permanent supply should be installed in preference to a less reliable temporary mains e.g., through utilising a fire fighting water supply. Temporary water discharge pipes must not be placed in electrical (or other water-susceptible) service risers.

- All incidents of water escape or water damage should be fully investigated and documented. This information should be shared with Insurers.

A33	QUALITY STANDARDS/ CONTROL

STANDARDS OF PRODUCTS AND EXECUTIONS

A33/110	INCOMPLETE DOCUMENTATION

-	General: Where and to the extent that products or work are not fully documented, they are to be:

-	Of a kind and standard appropriate to the nature and character of that part of the Works where they will be used.

-	Suitable for the purposes stated or reasonably to be inferred from the project documents.

-	Contract documents: Omissions or errors in description and/ or quantity shall not vitiate the Contract nor release the Contractor from any obligations or liabilities under the Contract.

A33/120	WORKMANSHIP SKILLS

-	Operatives: Appropriately skilled and experienced for the type and quality of work.

-	Registration: With Construction Skills Certification Scheme.

-	Evidence: Operatives must produce evidence of skills/ qualifications when requested.

A33/130	QUALITY OF PRODUCTS

-	Generally: New (Proposals for recycled products may be considered).

-	Supply of each product: From the same source or manufacturer.

-	Whole quantity of each product required to complete the Works: Consistent in kind, size, quality and overall appearance.

-	Tolerances: Where critical, measure a sufficient quantity to determine compliance.

-	Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate sequence.

A33/135	QUALITY OF EXECUTION

-	Generally: Fix, apply, install or lay products securely, accurately, plumb, neatly and in alignment.

-	Colour batching: Do not use different colour batches where they can be seen together.

-	Dimensions: Check on-site dimensions.

-	Finished work: Not defective, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance.

-	Location and fixing of products: Adjust joints open to view so they are even and regular.

A33/140	COMPLIANCE

-	Compliance with proprietary specifications: Retain on site evidence that the proprietary product specified has been supplied.

-	Compliance with performance specifications: Submit evidence of compliance, including test reports indicating:

-	Properties tested.

-	Pass/ fail criteria.

-	Test methods and procedures.

-	Test results.

-	Identity of testing agency.

-	Test dates and times.

-	Identities of witnesses.

-	Analysis of results.

A33/150	INSPECTIONS

-	Products and executions: Inspection or any other action must not be taken as approval unless confirmed in writing referring to:

-	Date of inspection.

-	Part of the work inspected.

-	Respects or characteristics which are approved.

-	Extent and purpose of the approval.

-	Any associated conditions.

A33/160	RELATED WORK

-	Details: Provide all trades with necessary details of related types of work. Before starting each new type or section of work ensure previous related work is:

-	Appropriately complete.

-	In accordance with the project documents.

-	To a suitable standard.

-	In a suitable condition to receive the new work.

-	Preparatory work: Ensure all necessary preparatory work has been carried out.

A33/170	MANUFACTURER’S RECOMMENDATIONS/ INSTRUCTIONS

-	General: Comply with manufacturer's printed recommendations and instructions current on the date of the Invitation to tender.

-	Changes to recommendations or instructions: Submit details.

-	Ancillary products and accessories: Use those supplied or recommended by main product manufacturer.

-	Agrément certified products: Comply with limitations, recommendations and requirements of relevant valid certificates.

A33/180	WATER FOR THE WORKS

-	Mains supply: Clean and uncontaminated.

-	Other: Do not use until:

-	Evidence of suitability is provided.

-	Tested to BS EN 1008 if instructed.

SAMPLES/ APPROVALS

A33/210	SAMPLES

-	Products or executions: Comply with all other specification requirements and in respect of the stated or implied characteristics either:

-	To an express approval.

-	To match a sample expressly approved as a standard for the purpose.

A33/220	APPROVAL OF PRODUCTS

-	Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

-	Approval: Relates to a sample of the product and not to the product as used in the Works. Do not confirm orders or use the product until approval of the sample has been obtained.

-	Complying sample: Retain in good, clean condition on site. Remove when no longer required.

A33/230	APPROVAL OF EXECUTION

-	Submissions, samples, inspections and tests: Undertake or arrange to suit the Works programme.

-	Approval: Relates to the stated characteristics of the sample. (If approval of the finished work as a whole is required this is specified separately). Do not conceal or proceed with affected work until compliance with requirements is confirmed.

-	Complying sample: Retain in good, clean condition on site. Remove when no longer required.

ACCURACY/ SETTING OUT GENERALLY

A33/320	SETTING OUT

-	General: Submit details of methods and equipment to be used in setting out the Works.

-	Levels and dimensions: Check and record the results on a copy of drawings. Notify discrepancies and obtain instructions before proceeding.

-	Inform: When complete and before commencing construction.

A33/330	APPEARANCE AND FIT

-	Tolerances and dimensions: If likely to be critical to execution or difficult to achieve, as early as possible either:

-	Submit proposals; or

-	Arrange for inspection of appearance of relevant aspects of partially finished work.

-	General tolerances (maximum): To BS 5606, tables 1 and 2.

A33/340	CRITICAL DIMENSIONS

-	Critical dimensions: Set out and construct the Works to ensure compliance with the tolerances stated.

A33/350	LEVELS OF STRUCTURAL FLOORS

-	Maximum tolerances for designed levels to be:

-	Floors to be self-finished, and floors to receive sheet or tile finishes directly bedded in adhesive: +/- 10 mm.

-	Floors to receive dry board/ panel construction with little or no tolerance on thickness: +/- 10 mm.

-	Floors to receive mastic asphalt flooring/ underlays directly: +/- 10 mm.

-	Floors to receive mastic asphalt flooring/ underlays laid on mastic asphalt levelling coat(s): +/- 15 mm.

-	Floors to receive fully bonded screeds/ toppings/ beds: +/- 15 mm.

-	Floors to receive unbonded or floating screeds/ beds: +/- 20 mm.

A33/360	RECORD DRAWINGS

-	Site setting out drawing: Record details of all grid lines, setting-out stations, benchmarks and profiles. Retain on site throughout the contract and hand over on completion.

SERVICES GENERALLY

A33/410	SERVICES REGULATIONS

-	New or existing services: Comply with the Byelaws or Regulations of the relevant Statutory Authority.

A33/420	WATER REGULATIONS/ BYELAWS NOTIFICATION

-	Requirements: Notify Water Undertaker of any work carried out to or which affects new or existing services and submit any required plans, diagrams and details.

-	Consent: Allow adequate time to receive Undertaker's consent before starting work. Inform immediately if consent is withheld or is granted subject to significant conditions.

A33/430	WATER REGULATIONS/ BYELAWS CONTRACTOR’S CERTIFICATE

-	On completion of the work: Submit (copy where also required to the Water Undertaker) a certificate including:

-	The address of the premises.

-	A brief description of the new installation and/ or work carried out to an existing installation.

-	The Contractor's name and address.

-	A statement that the installation complies with the relevant Water Regulations or Byelaws.

-	The name and signature of the individual responsible for checking compliance.

-	The date on which the installation was checked.

A33/435	ELECTRICAL INSTALLATION CERTIFICATES

-	Submit: When relevant electrical work is completed.

-	Original certificate: To be lodged in Building Manual.

A33/440	GAS, OIL AND SOLID FUEL APPLIANCE INSTALLATION CERTIFICATE

-	Before the completion date stated in the contract: Submit a certificate stating:

-	The address of the premises.

-	A brief description of the new installation and/ or work carried out to an existing installation.

-	Any special recommendations or instructions for the safe use and operation of appliances and flues.

-	The Contractor's name and address.

-	A statement that the installation complies with the appropriate safety, installation and use regulations.

-	The name, qualification and signature of the competent person responsible for checking compliance.

-	The date on which the installation was checked.

-	Certificate location: Incorporated within Health and Safety File and/ or Building Manuel, see clause A37/110.

A33/445	SERVICE RUNS

-	General: Provide adequate space and support for services, including unobstructed routes and fixings.

-	Ducts, chases and holes: BWIC and attendances, form during construction rather than cut.

-	Coordination with other works: The Contractor shall attend management and co-ordination meetings with the utilities contractors to ascertain details of locations, types/ methods of fixing of services to fabric and identification of fittings, runs within the units and externally for alterations to incoming services.

A33/450	MECHANICAL AND ELECTRICAL SERVICES

-	Final tests and commissioning: Carry out so that services are in full working order at completion of the Works.

-	Building Regulations notice: Copy to be lodged in the Building Manual.

SUPERVISION/ INSPECTION/ DEFECTIVE WORK

A33/510	SUPERVISION

-	General: In addition to the constant management and supervision of the Works provided by the Contractor's person in charge, all significant types of work must be under the close control of competent trade supervisors to ensure maintenance of satisfactory quality and progress.

-	Replacement: Give maximum possible notice before changing person in charge or site agent.

A33/520	COORDINATION OF ENGINEERING SERVICES

-	Suitability: Site organisation staff must include one or more persons with appropriate knowledge and experience of mechanical and electrical engineering services to ensure compatibility between engineering and the Works generally.

-	Evidence: Submit when requested CVs or other documentary evidence relating to the staff concerned.

A33/530	OVERTIME WORKING

-	Notice: Prior to overtime being worked, submit details of times, types and locations of work to be done.

-	Minimum period of notice: Three days.

-	Concealed work: If executed during overtime for which notice has not been given, it may be required to be opened up for inspection and reinstated at the Contractor's expense.

A33/540	DEFECTS IN EXISTING WORK

-	Undocumented defects: When discovered, immediately give notice. Do not proceed with affected related work until response has been received.

-	Documented remedial work: Do not execute work which may:

-	Hinder access to defective products or work; or

-	Be rendered abortive by remedial work.

A33/550	ACCESS FOR INSPECTION

-	Removal: Before removing scaffolding or other facilities for access, give notice of not less than 2 working days.

A33/560	TESTS AND INSPECTIONS

-	Timing: Agree and record dates and times of tests and inspections to enable all affected parties to be represented.

-	Confirmation: One working day prior to each such test or inspection. If sample or test is not ready, agree a new date and time.

-	Records: Submit a copy of test certificates and retain copies on site.

A

A33/570	AIR PERMEABILITY

-	Testing organisation: UKAS Accredited. Registered by the British Institute on Non-destructive Testing.

-	Method: Pressure test in accordance with the ATTMA Technical Standard L2. Measuring air permeability of building envelopes (non-dwellings).

-	Results: Submit to the EA no later than seven days following final test, in the format as directed by the EA.

- Content: Include test results and all supporting data.

- Format: Electronic.

- Number of copies: 1. Include also in Building Manual.

A33/580	CONTINUITY OF THERMAL INSULATION

-	Record and report: Confirm that work to new, renovated or upgraded thermal elements has been carried out to conform to specification. Include:

-	The address of the premises.

-	The Contractor's name and address.

-	The name, qualification and signature of the competent person responsible for checking compliance.

-	The date on which the installation was checked.

-	Submit: Before completion of the Works.

-	Copy: To be lodged in the Building Manual.

A33/590	RESISTANCE TO PASSAGE OF SOUND

-	Copies: Incorporate in the Building Manual.

A33/595	ENERGY PERFORMANCE CERTIFICATES

-	Assessment: UK Standard Assessment Procedure (SAP).

A33/610	PROPOSALS FOR RECTIFICATION OF DEFECTIVE PRODUCTS/ EXECUTIONS

-	Proposals: Immediately any execution or product is known, or appears, to be not in accordance with the Contract, submit proposals for opening up, inspection, testing, making good, adjustment of the Contract Sum, or removal and re-execution.

-	Acceptability: Such proposals may be unacceptable, and contrary instructions may be issued.

A33/620	MEASURES TO ESTABLISH ACCEPTABILITY

-	General: Wherever inspection or testing shows that the work, materials or goods are not in accordance with the contract and measures (e.g. testing, opening up, experimental making good) are taken to help in establishing whether or not the work is acceptable, such measures:

-	Will be at the expense of the Contractor.

-	Will not be considered as grounds for revision of the completion date.

A33/630	QUALITY CONTROL

-	Procedures: Establish and maintain to ensure that the Works, including the work of subcontractors, comply with specified requirements.

-	Records: Maintain full records, keep copies on site for inspection, and submit copies on request.

-	Content of records:

-	Identification of the element, item, batch or lot including location in the Works.

-	Nature and dates of inspections, tests and approvals.

-	Nature and extent of nonconforming work found.

-	Details of corrective action.

WORK AT OR AFTER COMPLETION

A33/710	WORK BEFORE COMPLETION

-	General: Make good all damage consequent upon the Works.

-	Temporary markings, coverings and protective wrappings: Remove unless otherwise instructed.

-	Cleaning: Clean the Works thoroughly inside and out, including all accessible ducts and voids. Remove all splashes, deposits, efflorescence, rubbish and surplus materials.

-	Cleaning materials and methods: As recommended by manufacturers of products being cleaned and must not damage or disfigure other materials or construction.

-	COSHH dated data sheets: Obtain for all materials used for cleaning and ensure they are used only as recommended by their manufacturers.

-	Minor faults: Touch up in newly painted work, carefully matching colour and brushing out edges. Repaint badly marked areas back to suitable breaks or junctions.

-	Moving parts of new work: Adjust, ease and lubricate as necessary to ensure easy and efficient operation, including doors, windows, drawers, ironmongery, appliances, valves and controls.

A33/720	SECURITY AT COMPLETION

-	General: Leave the Works secure with, where appropriate, all accesses closed and locked.

-	Keys: Account for and adequately label all keys and hand over to Employer with itemized schedule, retaining duplicate schedule signed by Employer as a receipt.

A33/730	MAKING GOOD DEFECTS

-	Remedial work: Arrange access with the EA.

-	Rectification: Give reasonable notice for access to the various parts of the Works.

-	Completion: Notify when remedial works have been completed.

A34	SECURITY/ SAFETY/ PROTECTION

SECURITY, HEALTH AND SAFETY

A34/110	PRECONSTRUCTION INFORMATION

-	Location: Integral with the project Preliminaries, including but not restricted to the following sections:

-	Description of project: Sections A10 and A11.

-	Client's consideration and management requirements: Sections A12, A13 and A36.

-	Environmental restrictions and on-site risks: Section A12, A35 and A34.

-	Significant design and construction hazards: Section A34.

-	The Health and Safety File: Section A37.

A34/120	EXECUTION HAZARDS

-	Common hazards: Not listed. Control by good management and site practice.

-	Significant hazards: Are identified in the Pre-Construction Information Document (Refer to Appendix ‘A’ of the Employers Requirements).

A34/130	PRODUCT HAZARDS

-	Hazardous substances: Site personnel levels must not exceed occupational exposure standards and maximum exposure limits stated in the current version of HSE document EH40: Occupational Exposure Limits.

-	Common hazards: Not listed. Control by good management and site practice.

-	Significant hazards: Are identified in the Pre-Construction Information Document.

A34/140	CONSTRUCTION PHASE HEALTH AND SAFETY PLAN

-	Submission: Present to the Employer/ Client no later than within two weeks of request.

-	Confirmation: Do not start construction work until the Employer has confirmed in writing that the Construction Phase Health and Safety Plan includes the procedures and arrangements required by CDM Regulations.

-	Content: Develop the plan from and draw on the Outline Construction Phase Health and Safety Plan, clause A30/570, and the Pre-tender Health and Safety Plan/ Preconstruction information.

A34/150	SECURITY

-	Protection: Safeguard the site, the Works, products, materials, and any existing buildings affected by the Works from damage and theft.

-	Access: Take all reasonable precautions to prevent unauthorized access to the site, the Works and adjoining property.

-	Contractor will be responsible for providing an Independent Security Guard if and when works are to be carried out during out of hours.

A34/160	STABILITY

-	Responsibility: Maintain the stability and structural integrity of the Works and adjacent structures during the Contract.

-	Design loads: Obtain details, support as necessary and prevent overloading.

A34/170	OCCUPIED PREMISES

-	Extent: Existing buildings will be occupied and/ or used during the Contract as follows:

The Contractor shall note that the site is within an occupied and operating Town Hall and that the trading function of the Town Hall must continue throughout the currency of the works.

-	Works: Carry out without undue inconvenience and nuisance and without danger to occupants and users.

-	Overtime: If compliance with this clause requires certain operations to be carried out during overtime, and such overtime is not required for any other reason, the extra cost will be paid to the Contractor, provided that such overtime is authorized in advance.

A34/190	OCCUPIER'S RULES AND REGULATIONS

-	Compliance: Conform to the occupier's rules and regulations affecting the site.

A34/200	MOBILE TELEPHONES

-	Use: Not permitted.

A34/210	EMPLOYER'S REPRESENTATIVES SITE VISITS

-	Safety: Submit details in advance, to the Employer or the person identified in clause A10/140, of safety provisions and procedures (including those relating to materials, which may be deleterious), which will require their compliance when visiting the site.

-	Protective clothing and/ or equipment: Provide and maintain on site for the Employer and the person stated in clause A10/140 and other visitors to the site.

PROTECT AGAINST THE FOLLOWING

A34/310	EXPLOSIVES

-	Use: Not permitted.

A34/330	NOISE CONTROL

-	The Contractor is to particularly note the proximity of adjoining premises the site.

-	Standard: Comply generally with the recommendations of BS 5228-1, clause 9.3 to minimize noise levels during the execution of the Works.

-	Equipment: Fit compressors, percussion tools and vehicles with effective silencers of a type recommended by manufacturers of the compressors, tools or vehicles.

-	Restrictions: Do not use:

-	Pneumatic drills and other noisy appliances without consent during the retail park opening hours.

-	Radios or other audio equipment or permit employees to use in ways or at times that may cause nuisance.

-	The Contractor is to particularly note the proximity of adjoining premises on the site.

-	Give adequate notice to occupiers and tenants of the existing buildings of any works in close proximity.

-	To minimise the effect that noise will have upon the neighbouring premises, the Contractor shall take all necessary steps to ensure that the following constraints are adhered to:

If any demolition of construction activity is audible in any nearby noise sensitive space, then the level at the boundary of the site nearest to the affected space shall not exceed Laeq.1h – 70 dB and in addition the peak level at the same location shall not exceed 90dB(a), when measured with the impulse tie-weighting, at any time.

Operations likely to cause the above to be exceeded may need to be undertaken outside the hours of 9am to 6pm or at other times or at weekends.

Sufficient prior notice of excessively noisy operations must be given.  Such operations cannot commence without previously obtaining the written approval of the EA.

Where practical, portable screens shall be provided to protect noise sensitive facades.

A34/340	POLLUTION

-	Prevention: Protect the site, the Works and the general environment including the atmosphere, lands, streams and waterways against pollution.

-	Contamination: If pollution occurs inform immediately, including to the appropriate Authorities and provide relevant information.

A34/350	PESTICIDES

-	Use: Not permitted.

A34/360	NUISANCE

-	Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes.

-	Surface water: Prevent hazardous build-up on site, in excavations and to surrounding areas and roads.

A34/370	ASBESTOS CONTAINING MATERIALS

-	Duty: Report immediately any suspected materials discovered during execution of the Works.

-	Do not disturb.

-	Agree methods for safe removal or encapsulation.

A34/371	DANGEROUS OR HAZARDOUS SUBSTANCES

-	Duty: Report immediately suspected materials discovered during execution of the Works.

-	Do not disturb.

-	Agree methods for safe removal or remediation.

A34/375	ANTIQUITIES

-	Duty: Report immediately any fossils, antiquities and other objects of interest or value discovered during execution of the works.

-	Preservation: Keep objects in the exact position and condition in which they were found.

A34/380	FIRE PREVENTION

-	Duty: Prevent personal injury or death, and damage to the Works or other property from fire.

-	Standard: Comply with Joint Code of Practice 'Fire Prevention on Construction Sites', published by the Construction Confederation and The Fire Protection Association (The 'Joint Fire Code').

A34/390	SMOKING ON SITE

-	Smoking on site: Not permitted.

A34/400	BURNING ON SITE

-	Burning on site: Not permitted.

A34/410	MOISTURE

-	Wetness or dampness: Prevent, where this may cause damage to the Works.

-	Drying out: Control humidity and the application of heat to prevent:

-	Blistering and failure of adhesion.

-	Damage due to trapped moisture.

-	Excessive movement.

A34/420	INFECTED TIMBER/ CONTAMINATED MATERIALS

-	Removal: Where instructed to remove material affected by fungal/ insect attack from the building, minimize the risk of infecting other parts of the building.

-	Testing: carry out and keep records of appropriate tests to demonstrate that hazards presented by concentrations of airborne particles, toxins and other micro-organisms are within acceptable levels.

A34/430	WASTE

-	Includes: Rubbish, debris, spoil, containers and surplus material.

-	Minimize: Keep the site and Works clean and tidy.

-	Remove: Frequently and dispose off site in a safe and competent manner:

-	Non-hazardous material: In a manner approved by the Waste Regulation Authority.

-	Hazardous material: As directed by the Waste Regulation Authority and in accordance with relevant regulations.

-	Voids and cavities in the construction: Remove rubbish, dirt and residues before closing in.

-	Waste transfer documentation: Retain on site.

A34/440	ELECTROMAGNETIC INTERFERENCE

-	Duty: Prevent excessive electromagnetic disturbance to apparatus outside the site.

A34/450	LASER EQUIPMENT

-	Construction laser equipment: Install, use and store in accordance with BS EN 60825-1 and the manufacturer's instructions.

-	Class 1 or Class 2 laser equipment: Ensure laser beam is not set at eye level and is terminated at the end of its useful path.

-	Class 3A and Class 3B laser equipment: Do not use without approval and subject to submission of a method statement on its safe use.

A34/460	POWER ACTUATED FIXING SYSTEMS

-	Use: Not permitted.

A34/470	INVASIVE SPECIES

-	General: Prevent the spread of species (e.g. plants or animals) that may adversely affect the site or Works economically, environmentally or ecologically.

-	Special precautions: None.

-	Duty: Report immediately any suspected invasive species discovered during execution of the Works.

-	Do not disturb.

-	Agree methods for safe eradication or removal.

PROTECT THE FOLLOWING

A34/510	EXISTING SERVICES

-	Confirmation: Notify all service authorities, statutory undertakers and/ or adjacent owners of proposed works not less than one week before commencing site operations.

-	Identification: Before starting work, check and mark positions of mains/ services. Where positions are not shown on drawings obtain relevant details from service authorities, statutory undertakers or other owners.

-	Work adjacent to services:

-	Comply with service authority's/ statutory undertaker's recommendations.

-	Adequately protect and prevent damage to services: Do not interfere with their operation without consent of service authorities/ statutory undertakers or other owners.

-	Identifying services:

-	Below ground: Use signboards, giving type and depth;

-	Overhead: Use headroom markers.

-	Damage to services: If any results from execution of the Works:

-	Immediately give notice and notify appropriate service authority/ statutory undertaker.

-	Make arrangements for the work to be made good without delay to the satisfaction of service authority/ statutory undertaker or other owner as appropriate.

-	Any measures taken to deal with an emergency will not affect the extent of the Contractor's liability.

-	Marker tapes or protective covers: Replace, if disturbed during site operations, to service authority's/ statutory undertaker's recommendations.

A34/520	ROADS AND FOOTPATHS

-	Duty: Maintain roads and footpaths within and adjacent to the site and keep clear of mud and debris.

-	Damage caused by site traffic or otherwise consequent upon the Works: Make good to the satisfaction of the Employer, Local Authority or other owner.

A34/530	EXISTING TOPSOIL/ SUBSOIL

-	Duty: Prevent over compaction of existing topsoil and subsoil in those areas which may be damaged by construction traffic, parking of vehicles, temporary site accommodation or storage of materials and which will require reinstatement prior to completion of the Works.

-	Protection: Before starting work submit proposals for protective measures.

A34/540	RETAINED TREES/ SHRUBS/ GRASSED AREAS

-	Protection: Preserve and prevent damage, except those not required.

-	Replacement: Mature trees and shrubs if uprooted, destroyed, or damaged beyond reasonable chance of survival in their original shape, as a consequence of the Contractor's negligence, must be replaced with those of a similar type and age at the Contractor's expense.

A34/550	RETAINED TREES

-	Protected area: Unless agreed otherwise do not:

-	Dump spoil or rubbish, excavate or disturb topsoil, park vehicles or plant, store materials or place temporary accommodation within an area which is the larger of the branch spread of the tree or an area with a radius of half the tree's height, measured from the trunk.

-	Sever roots exceeding 25 mm in diameter. If unintentionally severed give notice and seek advice.

-	Change level of ground within an area 3 m beyond branch spread.

A34/555	WILDLIFE SPECIES AND HABITATS

-	General: Safeguard the following:

-	Protected habitats and species: Upon discovery immediately advise. Do not proceed until instruction is received.

-	Education: Ensure employees and visitors to the site receive suitable instruction and awareness training.

A34/560	EXISTING FEATURES

-	Protection: Prevent damage to existing buildings, fences, gates, walls, roads, paved areas and other site features, which are to remain in position during execution of the Works.

A34/570	EXISTING WORK

-	Protection: Prevent damage to existing work, structures or other property during the course of the work.

-	Removal: Minimum amount necessary.

-	Replacement work: To match existing.

A34/580	BUILDING INTERIORS

-	Protection: Prevent damage from exposure to the environment, including weather, flora, fauna, and other causes of material degradation during the course of the work.

A34/620	ADJOINING PROPERTY

-	Permission: Obtain as necessary from owners if requiring to erect scaffolding on or otherwise use adjoining property.

A34/625	ADJOINING PROPERTY RESTRICTIONS

-	Precautions:

-	Prevent trespass of workpeople and take precautions to prevent damage to adjoining property.

-	Pay all charges.

-	Remove and make good on completion or when directed.

-	Damage: Bear cost of repairing damage arising from execution of the Works.

A34/630	EXISTING STRUCTURES

-	Duty: Check proposed methods of work for effects on adjacent structures inside and outside the site boundary.

-	Supports: During execution of the Works:

-	Provide and maintain all incidental shoring, strutting, needling and other supports as may be necessary to preserve stability of existing structures on the site or adjoining, that may be endangered or affected by the Works.

-	Do not remove until new work is strong enough to support existing structure.

-	Prevent overstressing of completed work when removing supports.

-	Adjacent structures: Monitor and immediately report excessive movement.

-	Standard: Comply with BS 5975 and BS EN 12812.

A34/640	MATERIALS FOR RECYCLING/ REUSE

-	Duty: Sort and prevent damage to stated products or materials, clean off bedding and jointing materials and other contaminants.

-	Storage: Stack neatly and protect until required by the Employer or for use in the Works as instructed.

A35	SPECIFIC LIMITATIONS ON METHOD/ SEQUENCE/ TIMING

A35/110	SCOPE

-	General: The limitations described in this section are supplementary to limitations described or implicit in information given in other sections or on the drawings.

A35/130	METHOD/ SEQUENCE OF WORK

-	Specific Limitations: None.

- Generally:

Generally, the method of works is to be programmed and responsibility of the main contractor.

A35/135	ACCESS TO THE SITE: See section A12.

A35/136	USE OF THE SITE: See section A12.

137	ACCESS TO EXISTING PREMISES:

-	Free and uninterrupted access shall be maintained to Town Hall and surrounding buildings entrances, shop fronts, service areas, roads, footpaths and car parks within or adjacent to the Town Hall during all normal trading hours. The Contractor is to liaise with any Tenant whose access will be restricted.

A35/140	SCAFFOLDING

-	Standing scaffolding: Ensure that standing scaffolding is erected early enough and/or dismantled late enough to suit the programmes of all subcontractors.

-	Make available to subcontractors and others at all times.

A35/160	USE OR DISPOSAL OF MATERIALS

-	Specific limitations: Off Site.

A35/170	WORKING HOURS

- Specific limitations: There are no restrictions on working hours by the Employer (save for those restrictions described in A34/135).  Normal working hours unless approval is agreed with the CA.

- There will be no restriction on working hours. The Contractor must notify the Town Hall Manager on a daily basis when working outside normal working hours.

- Certain areas and elements of works may have to be carried out outside normal working hours, due to noisy working/restrictions on working hours due to tenants. The Contractor is to ascertain for himself what limitations may be imposed by others and is to allow in his tender for all necessary out of hour working.

- The Contractor is to include here for all overtime and extra costs necessary to comply with these and any other conditions contained within this document.

- The trading hours of the Town Hall are to be adhered too at all times.

A35/180	COMPLETION IN SECTIONS OR IN PARTS

-	General: Where the Employer is to take possession of any section or part of the Works and such section or part will, after its possession, depend for its adequate functioning on work located elsewhere on the site: Complete such other work in time to permit such possession to take place.

-	Remainder of the Works: During execution, ensure that completed sections or parts of the Works have continuous and adequate provision of services, fire precautions, means of escape and safe access.

190 	SNAGGING / PRACTICAL COMPLETION

Notwithstanding the Contract Conditions, the following additional obligations are placed upon the Contractor:

a) During the Contract Period:

- The Contractor is required to keep a log of items not completed in accordance with the specification whether identified by the Employers Agent, the Consultant Team or otherwise

- The Contractor is required to make good all works so recorded within a reasonable period

- The Contractor is specifically required to pro-actively rectify and correct items not in accordance and ensure that these items do not remain un-rectified until the end of the project.

b) At Practical Completion:

- The Contractor will be required to agree a list of incomplete works and items not completed in accordance with the Building Contract with the Employers Agent on the Date of Completion.

- The Contractor shall rectify identified items within 7 days of the Date of Completion or a period agreed with the Employers Agent.

- If the Contractor fails to comply with the above, the Employer reserves the right to employ a third party to satisfactorily complete the works.  This will not relieve the Contractor of any contractual responsibilities and/or obligations; the cost of this rectification work, together with administration charge and corresponding professional fees of £1,000 will be deducted from the Contractors Final Account.

- The Contractors foreman/site manager in charge of this project will be expected to generally coordinate the making good of the works not undertaken in accordance with the Contract.

c) During the 12-month rectification period:

- The Employer may at any time during the twelve-month rectification period ask the Contractor to carry out repairs or replace items that are defective, at a cost to the contractor.

- Due to the nature of the business carried out by the Town Hall, it is important that any faults that occur are attended to without delay. Consequently, the following time periods allowed, during the 12-month rectification period, for making good will be applied by the Employer depending upon the severity of the fault:

i) Very urgent items are to be attended to within 24 hours of receipt of notification.

ii) Urgent items are to be attended to within 3 days of receipt of notification.

iii) Routine items are to be attended to within 7 days of receipt of notification.

- For defects within classification i) notification may be by telephone subsequently confirmed in writing.  A note of the time date and person accepting the message will be recorded.

- If the Contractor fails to comply with the above, the Employer reserves the right to employ a third party to satisfactorily complete the Works. This will not relieve the Contractor of any or all of his contractual responsibilities and/or obligations. The cost of this rectification work, together with an administration charge of £1,000 will be deducted from the Contractor's Final Account.

d) At expiry of the 12-month rectification period:

- The Contractor will be held liable at the end of the 12 months Rectification Period for making good decoration were affected by the drying out, repairs and replacement of defective items of the building and should allow here or in the rates for the cost of carrying out this work.

- The Contractor will be required to agree a defects list in conduction with the Employers Agent and Design Team twelve months after the Date for Completion.  The Contractor is to fully complete the items listed within 7 days (including Saturday and Sunday).  Works in the trading areas will be required to be executed out of normal trading hours.

- If the Contractor fails to comply with the above, the Employer reserves the right to employ a third party to satisfactorily complete the Works. This will not relieve the Contractor of any or all of his contractual responsibilities and/or obligations. The cost of this rectification work, together with an administration charge of £1,000 will be deducted from the Contractor's Final Account.”

A36	FACILITIES/ TEMPORARY WORK/ SERVICES

GENERALLY

A36/110	SPOIL HEAPS, TEMPORARY WORKS AND SERVICES

-	Location: Give notice of intended siting.

-	Maintenance: Alter, adapt and move as necessary. Remove when no longer required and make good.

ACCOMMODATION

A36/210	ROOM FOR MEETINGS

-	Facilities: Provide suitable temporary accommodation for site meetings, adequately heated and lit. The room may be part of the Contractor's own site offices.

-	Furniture and Equipment: Provide table and chairs for twelve people.

A36/260	SANITARY ACCOMMODATION

-	Facilities: Provide and maintain in a clean condition, sanitary accommodation for the Employer's representatives, either separate or shared with the Contractor's supervisory staff.

285	CONTRACTOR’S COMPOUND:

-	The Contractor will be responsible for the security of his temporary office/designated area for storage of materials, as the Employer and managing agents will not accept responsibility for any damage, theft or the like. The Contractor shall make his own security arrangements for his compound and the works.

290	CAR PARKING:

- Parking of Contractor’s vehicles and those of his Sub-Contractor’s is restricted to the contractors compound.

A

TEMPORARY WORKS

A36/310	ROADS

-	Permanent roads, hard standings and footpaths on the site: May be used, subject to clause A34/520.

A36/320	TEMPORARY WORKS

-	Employer's Specific Requirements: The contractor must include for the general provision and removal of all necessary temporary fencing, hoardings, walkways, guard rails and the like as may be required for protecting the public and visitors to the site, for proper execution of the works and the safeguarding of the materials and plant. These works shall be constructed in such a manner as will meet the requirements of the Employers Agent/Local Authority.

A36/340	NAME BOARDS/ ADVERTISEMENTS

-	General: Obtain approval, including statutory consents, and provide a temporary name board displaying:

-	Title of project.

-	Name of Employer.

-	Names of Consultants:

Project Manager/Employer Agent

Architect

Principal Designer

Quantity Surveyor

Structural Engineer

Services Engineer

-	If the Contractor wishes, names of Contractor and Subcontractors.

SERVICES AND FACILITIES

A36/410	LIGHTING

-	Finishing work and inspection: Provide temporary lighting, the intensity and direction of which closely resembles that delivered by the permanent installation.

A36/420	LIGHTING AND POWER

-	Supply: Contractor to be responsible for the provision and costs associated with the lighting and power for the works.

-	Continuity: The Employer will not be responsible for the consequences of failure or restriction in supply.

A36/430	WATER

-	Supply: Contractor to be responsible for the provision and costs associated with the water supply for the works.

-	Continuity: The Employer will not be responsible for the consequences of failure or restriction in supply.

A36/440	TELEPHONES

-	Temporary on-site telephone: Provide as soon as practicable after the start on site for joint use by the Contractor and Subcontractors and pay all charges.

-	Responses: Make arrangements (e.g. an external bell) to ensure that incoming calls are answered promptly.

A36/460	FAX INSTALLATION

-	General: As soon as practicable after the start on site provide a suitable on-site fax installation, with a separate dedicated telephone line, for use by the Contractor, Subcontractors and those acting on behalf of the Employer.

-	Employer's call charges: Allow for the cost of a reasonable number of transmissions made by those acting on behalf of the Employer.

A36/470	E-MAIL AND INTERNET FACILITY

-	General: As soon as practicable after the start on site provide a suitable e-mail facility on site, with a separate dedicated telephone line, for the use of the Contractor, Subcontractors and those acting on behalf of the Employer.

-	Use on behalf of Employer: Allow for the cost of a reasonable number of transmissions made by those acting on behalf of the Employer.

A36/480	PHOTOCOPIER

-	General: Provide reasonably unrestricted access to and reasonably limited free use of an on-site photocopier, which may be located in the Contractor's own site offices.

A36/520	USE OF PERMANENT HEATING SYSTEM

-	Permanent heating installation: May be used for drying out the Works/ services and controlling temperature and humidity levels.

-	Installation: If used:

-	Take responsibility for operation, maintenance and remedial work.

-	Arrange supervision by and indemnification of the appropriate Subcontractors.

-	Pay costs arising.

A36/540	METER READINGS

-	Charges for service supplies: Where to be apportioned ensure that:

-	Meter readings are taken by relevant authority at possession and/ or completion as appropriate.

-	Copies of readings are supplied to interested parties.

A36/550	THERMOMETERS

-	General: Provide on-site and maintain in accurate condition a maximum and minimum thermometer for measuring atmospheric shade temperature, in an approved location.

A36/560	SURVEYING EQUIPMENT

-	General: Provide on-site and maintain in accurate condition.

A36/570	PERSONAL PROTECTIVE EQUIPMENT

-	General: Provide for the sole use of those acting on behalf of the Employer, in sizes to be specified:

-	Safety helmets to BS EN 397, neither damaged nor time expired. Number required: Contractor to ascertain requirements and provide accordingly.

-	High visibility waistcoats to BS EN 471 Class 2. Number required: Contractor to ascertain requirements and provide accordingly.

-	Safety boots with steel insole and toecap to BS EN ISO 20345. Pairs required: Contractor to ascertain requirements and provide accordingly.

-	Disposable respirators to BS EN 149.FFP1S.

-	Eye protection to BS EN 166.

-	Ear protection - muffs to BS EN 352-1, plugs to BS EN 352-2.

-	Hand protection - to BS EN 388, 407, 420 or 511 as appropriate.

A37	OPERATION/ MAINTENANCE OF THE FINISHED WORKS

GENERALLY

A37/110	THE BUILDING MANUAL

-	Purpose: The Manual is to be a comprehensive information source and guide for owners and users of the completed Works. It should provide an overview of the main design principles and describe key components and systems to enable proper understanding, efficient and safe operation and maintenance.

-	Scope:

-	Part 1: General: [Content as clause 120].

-	Part 2: Fabric: [Content as clause 130].

-	Part 3: Services: [Content as clause 140].

-	Part 4: The Health and Safety File: [prepared and supplied by the CDM Coordinator]. Content as clause 150

-	Responsibility: The Building Manual is to be produced by appropriately qualified personnel and must be complete no later than two weeks prior to practical completion

-	Compilation:

-	Prepare all information for Contractor designed or performance specified work including as-built drawings.

-	Obtain or prepare all other information to be included in the Manual.

-	Reviewing the Manual: Submit a complete draft. Amend in the light of any comments and resubmit. Do not proceed with production of the final copies until authorized.

-	Final copies of the Manual:

-	Number of copies: Two.

-	Format: Electronically and in hard copy

-	Latest date for submission: Two weeks before the date for completion stated in the contract.

-	As-built drawings and schedules:

-	Number of copies: Two.

-	Format: Paper folded to A4 one copy on polyester film unfolded and two sets on magnetic or optical storage media (i.e. Disks or CDRom) in both DXF and AutoCAD V12 formats.

A37/115	THE HEALTH AND SAFETY FILE

-	Responsibility: The Contractor.

-	Format: Electronically and in hard copy.

-	Delivery to: The EA no later than two weeks prior to practical completion.

A37/120	CONTENT OF THE BUILDING MANUAL PART 1: GENERAL

-	Content: Obtain and provide the following, including all relevant details not included in other parts of the manual:

-	Index: list the constituent parts of the manual, together with their location in the document.

-	The Works:

-	Description of the buildings and facilities.

-	Ownership and tenancy, where relevant.

-	Health and Safety information – other than that specifically required by the Construction (Design and Management) Regulations.

-	The Contract:

-	Names and addresses and contact details of all significant consultants, contractors, subcontractors, suppliers and manufacturers.

-	Overall design criteria.

-	Environmental performance requirements.

-	Relevant authorities, consents and approvals.

-	Third party certification, such as those made by "competent" persons in accordance with the Building Regulations.

-	Operational requirements and constraints of a general nature:

-	Maintenance contracts and contractors.

-	Fire safety strategy for the buildings and the site. Include drawings showing emergency escape and fire appliance routes, fire resisting doors, location of emergency alarm and firefighting systems, services, shut off valves switches, etc.

-	Emergency procedures and contact details in case of emergency.

-	Description and location of other key documents.

-	Timescale for completion: No later than two weeks prior to practical completion.

A37/130	CONTENT OF THE BUILDING MANUAL PART 2: BUILDING FABRIC

-	Content: Obtain and provide the following, including all relevant details not included in other parts of the manual:

-	Detailed design criteria, including:

-	Floor and roof loadings.

-	Durability of individual components and elements.

-	Loading restrictions.

-	Insulation values.

-	Fire ratings.

-	Other relevant performance requirements.

-	Construction of the building:

-	A detailed description of methods and materials used.

-	As-built drawings recording the construction, together with an index.

-	Information and guidance concerning repair, renovation or demolition/ deconstruction.

-	Periodic building maintenance guide chart.

-	Inspection reports.

-	Manufacturer's instructions index, including relevant COSHH data sheets and recommendations for cleaning, repair and maintenance of components.

-	Fixtures, fittings and components schedule and index.

-	Guarantees, warranties and maintenance agreements – obtain from manufacturers, suppliers and subcontractors.

-	Test certificates and reports required in the specification or in accordance with legislation, including:

-	Air permeability.

-	Resistance to passage of sound.

-	Continuity of insulation.

-	Electricity and Gas safety.

-	Other specific requirements: None.

-	Timescale for completion: No later than two weeks prior to practical completion.

A37/140	CONTENT OF THE BUILDING MANUAL PART 3: BUILDING SERVICES

-	Content: Obtain and provide the following, including all relevant details not included in other parts of the manual:

-	Detailed design criteria and description of the systems, including:

-	Services capacity, loadings and restrictions.

-	Services instructions.

-	Services log sheets.

-	Manufacturers' instruction manuals and leaflets index.

-	Fixtures, fittings and component schedule index.

-	Detailed description of methods and materials used.

-	As-built drawings for each system recording the construction, together with an index, including:

-	Diagrammatic drawings indicating principal items of plant, equipment and fittings.

-	Record drawings showing overall installation.

-	Schedules of plant, equipment, valves, etc. describing location, design performance and unique identification cross referenced to the record drawings.

-	Identification of services – a legend for colour coded services.

-	Product details, including for each item of plant and equipment:

-	Name, address and contact details of the manufacturer.

-	Catalogue number or reference.

-	Manufacturer's technical literature, including detailed operating and maintenance instructions.

-	Information and guidance concerning dismantling, repair, renovation or decommissioning.

-	Operation: A description of the operation of each system, including:

-	Starting up, operation and shutting down.

-	Control sequences.

-	Procedures for seasonal changeover.

-	Procedures for diagnostics, troubleshooting and faultfinding.

-	Guarantees, warranties and maintenance agreements – obtain from manufacturers, suppliers and subcontractors.

-	Commissioning records and test certificates list for each item of plant, equipment, valves, etc. used in the installations – including:

-	Electrical circuit tests.

-	Corrosion tests.

-	Type tests.

-	Work tests.

-	Start and commissioning tests.

-	Equipment settings: Schedules of fixed and variable equipment settings established during commissioning.

-	Preventative maintenance: Recommendations for frequency and procedures to be adopted to ensure efficient operation of the systems.

-	Lubrication: Schedules of all lubricated items.

-	Consumables: A list of all consumable items and their source.

-	Spares: A list of recommended spares to be kept in stock, being those items subject to wear and tear or deterioration and which may involve an extended delivery time when replacements are required.

-	Emergency procedures for all systems, significant items of plant and equipment.

-	Annual maintenance summary chart.

-	Other specific requirements: None.

-	Timescale for completion: No later than two weeks prior to practical completion.

A37/150	CONTENT OF THE BUILDING MANUAL PART 4: THE HEALTH AND SAFETY FILE

-	Content: obtain and provide the following, including all relevant details not included in other parts of the manual, including:

-	residual hazards and how they have been dealt with.

-	hazardous materials used.

-	information regarding the removal or dismantling of installed plant and equipment.

-	health and safety information about equipment provided for cleaning or maintaining the structure.

-	the nature, location and markings of significant services.

-	information and as-built drawings of the structure, its plant and equipment.

-	Timescale for completion: No later than two weeks prior to practical completion.

-	Submit to: EA.

A37/151	CONTENT OF THE BUILDING MANUAL PART 5: THE BUILDING USER GUIDE

-	Content: Obtain and provide the following:

-	Building services information.

-	Emergency information.

-	Energy & environmental strategy.

-	Water use.

-	Transport facilities.

-	Materials & waste policy.

-	Re-fit/ re-arrangement considerations.

-	Reporting provision.

-	Training.

-	Links & references.

-	Other specific requirements: None.

-	Timescale for completion: No later than two weeks prior to practical completion.

A37/160	PRESENTATION OF BUILDING MANUAL

-	Format: A4 size, plastics covered, loose leaf, four ring binders with hard covers, each indexed, divided and appropriately cover titled.

-	Selected drawings needed to illustrate or locate items mentioned in the Manual: Where larger than A4, to be folded and accommodated in the binders so that they may be unfolded without being detached from the rings.

-	As-built drawings: The main sets may form annexes to the Manual.

A37/190	MAINTENANCE SERVICE

-	Scope: provide a comprehensive maintenance service for the following items of plant and equipment: Include all planned preventative maintenance, as set out within the maintenance schedule and replacement of all consumable items

A37/210	INFORMATION FOR COMMISSIONING OF SERVICES

-	General: Submit relevant drawings and preliminary performance data to enable the building user's staff to familiarise themselves with the installation.

-	Time of submission: At commencement of commissioning.

A37/220	TRAINING

-	Objective: Before Completion, explain and demonstrate to the Employer's maintenance staff the purpose, function and operation of the installations including items and procedures listed in the Building Manual.

-	Operating time: Include a minimum of 1 day.

A37/230	SPARE PARTS

-	General: Before Completion submit a priced schedule of spare parts that the Contractor recommends should be obtained and kept in stock for maintenance of the services installations.

-	Content: Include in the priced schedule for:

-	Manufacturers' current prices, including packaging and delivery to site.

-	Checking receipts, marking and numbering in accordance with the schedule of spare parts.

-	Referencing to the plant and equipment list in Part 3 of the Building Manual.

-	Painting, greasing, etc. and packing to prevent deterioration during storage.

-	Latest date for submission: Two weeks before the date for completion stated in the contract.

A37/250	TOOLS

-	General: Provide tools and portable indicating instruments for the operation and maintenance of all services, plant and equipment (except any installed under Named Subcontracts) together with suitable means of identifying, storing and securing.

-	Quantity: Two complete sets.

-	Time of submission: At completion.

260	Four copies of the Health and Safety File are to be submitted as part of the Practical Completion process.

A40	CONTRACTOR'S GENERAL COST ITEMS: MANAGEMENT AND STAFF

A40/110	MANAGEMENT AND STAFF

A41	CONTRACTOR'S GENERAL COST ITEMS: SITE ACCOMMODATION

A41/110	SITE ACCOMMODATION

-	Details: Site accommodation required or made/ not made available by the Employer: See section A36.

A42	CONTRACTOR'S GENERAL COST ITEMS: SERVICES AND FACILITIES

A42/110	POWER

A42/120	LIGHTING

A42/130	FUELS

A42/140	WATER

A42/150	TELEPHONE AND ADMINISTRATION

A42/160	SAFETY, HEALTH AND WELFARE

-	See clause A34/210.

A42/170	STORAGE OF MATERIALS

A42/180	RUBBISH DISPOSAL

-	See clause A34/430.

A42/190	CLEANING

-	See clause A33/710.

A42/200	DRYING OUT

-	See clause A34/410.

A42/210	PROTECTION OF WORK IN SECTIONS

A42/220	SECURITY

-	See clause A34/150.

A42/230	MAINTAIN PUBLIC AND PRIVATE ROADS

-	See clause A34/520.

A42/240	SMALL PLANT AND TOOLS

A42/250	OTHERS

A42/300	GENERAL ATTENDANCE ON NOMINATED SUBCONTRACTORS

-	See section A51.

A42/310	ADDITIONAL SERVICES AND FACILITIES ITEMS

A43	CONTRACTOR'S GENERAL COST ITEMS: MECHANICAL PLANT

A43/110	CRANES

A43/120	HOISTS

A43/130	PERSONNEL TRANSPORT

A43/140	TRANSPORT

A43/150	EARTHMOVING PLANT

A43/160	CONCRETE PLANT

A43/170	PILING PLANT

A43/180	PAVING AND SURFACING PLANT

A43/200	ADDITIONAL MECHANICAL PLANT

A44	CONTRACTOR'S GENERAL COST ITEMS: TEMPORARY WORKS

A44/110	TEMPORARY WORKS

-	Details: Temporary works required or made/ not made available by the Employer: See section A36.

A44/110	TEMPORARY ROADS

A44/120	TEMPORARY WALKWAYS

A44/130	ACCESS SCAFFOLDING

A44/140	SUPPORT SCAFFOLDING AND PROPPING

A44/150	HOARDINGS, FANS, FENCING, ETC.

A44/160	HARDSTANDING

A44/170	TRAFFIC REGULATIONS

A44/200	ADDITIONAL TEMPORARY WORKS

COLLECTION

Page	1/1

1/2

1/3

1/4

1/5

1/6

1/7

1/8

1/9

1/10

1/11

1/12

1/13

1/14

1/15

1/16

1/17

1/18

1/19

1/20

1/21

1/22

1/23

1/24

1/25

1/26

1/27

1/28

1/29

1/30

1/31

1/32

1/33

1/34

1/35

1/36

1/37

1/38

1/39

1/40

1/41

1/42

1/43

1/44

1/45

1/46

1/47

1/48

Carried Forward

Brought Forward

1/49

1/50

1/51

1/52

1/53

1/54

1/55

1/56

1/57

1/58

1/59

1/60

1/61

1/62

1/63

1/64

1/65

1/66

1/67

1/68

1/69

1/70

1/71

1/72

1/73

1/74