## Instructions for Completion
Instructions for Completion
1 | Instructions to Tenderers
1.1.a | The tab named Estimated days of PM Role is for advice only and is The Pirbright Institute's estimated hours/days for the three phases associated to this procurement and the total number of days.
1.1.b | Bidders should complete the remaining tabs for this file i.e. Tendered days for PM Role (which is a copy of the Estimated days of PM Role) - please leave or amend the indicative hours where applicable in relation to your bid. Bidders must also complete PM Pricing Schedule in line with your Tendered days for PM Role tab and amend resource titles where applicable, insert the number of total days per month against the daily rate for the proposed resources. Please also amend and complete the RATE FOR VARIATIONS/ ADDITIONAL SERVICES section on that tab.
1.2 | The tabs must be completed in the format provided. Individual cells may be increased in size to accommodate your responses but the format of the tables in each tab should not be altered. No additional rows or columns should be created.
1.3 | All prices should be based on services provided in accordance with the Specification and Conditions of Agreement.
1.4 | Prices and any financial data provided must be submitted in or converted into pounds sterling. Where official documents would include financial data in a foreign currency, a sterling equivalent must be provided.
1.5 | The Price evaluation criteria within the tender will be assessed by taking into account the areas indicated in the following tabs.
1.6 | All prices quoted need to be in accordance with the Specification of Requirements, Conditions of Contract and any other documentation relating to this Agreement. All prices quoted shall, unless otherwise instructed, exclude Value Added Tax (VAT) but include delivery, packing and carriage charges (where applicable). All in-scope Services, including any new additions within the duration of the Agreement, will be managed under this model.
1.7 | Following full tender evaluation, The Pirbright Institute may ask some Bidders to verify their tender submissions including proof of the prices quoted from third parties where applicable that form the basis of prices submitted. The Pirbright Institute may not proceed with tender award if verification is unsatisfactory.
2 | Pricing Evaluation
2.1 | The Price evaluation will be conducted by taking into account the full value of your Tender, including the prices quoted and all other discounts and charges.
2.2 | The lowest priced bidder will be awarded 100%; marks for other bidders will be calculated on a pro rata basis as follows:
Pricing score = Lowest Price / Tender Price x Weighting

## Estimated days for PM Role
| Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Total Estimated PM Days required per WP
| w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
BACS Alarm Categorisation | Jan w2: 8; Jan w3: 8; Jan w4: 8; Feb w1: 8; Feb w2: 8; Feb w3: 8; Feb w4: 8; Mar w1: 8; Mar w2: 8; Mar w3: 8; Mar w4: 8; Apr w1: 16; Apr w2: 16; Apr w3: 16; Apr w4: 16; May w1: 16; May w2: 16; May w3: 16; May w4: 16; Jun w1: 16; Jun w2: 16; Jun w3: 16; Jun w4: 16
Total Hrs/Month | Jan w4: 24; Feb w4: 32; Mar w4: 32; Apr w4: 64; May w4: 64; Jun w4: 64
Total Days/Month | Jan w4: 3; Feb w4: 4; Mar w4: 4; Apr w4: 8; May w4: 8; Jun w4: 8 | 35
Installation & Commissioning of additional BACS alarm input/output | Mar w3: 8; Mar w4: 8; Apr w1: 16; Apr w2: 16; Apr w3: 16; Apr w4: 16; May w1: 16; May w2: 16; May w3: 16; May w4: 16; Jun w1: 16; Jun w2: 16; Jun w3: 16; Jun w4: 16; Jul w1: 16; Jul w2: 16; Jul w3: 16; Jul w4: 16; Aug w1: 16; Aug w2: 16; Aug w3: 16; Aug w4: 16; Sep w1: 16; Sep w2: 16; Sep w3: 16; Sep w4: 16
Total Hrs/Month | Mar w4: 16; Apr w4: 64; May w4: 64; Jun w4: 64; Jul w4: 64; Aug w4: 64; Sep w4: 64
Total Days/Month | Mar w4: 2; Apr w4: 8; May w4: 8; Jun w4: 8; Jul w4: 8; Aug w4: 8; Sep w4: 8 | 50
Alarm integration to AMS | Aug w1: 16; Aug w2: 16; Aug w3: 16; Aug w4: 16; Sep w1: 16; Sep w2: 16; Sep w3: 16; Sep w4: 16; Oct w1: 16; Oct w2: 16; Oct w3: 16; Oct w4: 16; Nov w1: 16; Nov w2: 16; Nov w3: 16; Nov w4: 16; Dec w1: 16; Dec w2: 16; Dec w3: 16; Dec w4: 16
Total Hrs/Month | Aug w4: 64; Sep w4: 64; Oct w4: 64; Nov w4: 64; Dec w4: 64
Total Days/Month | Aug w4: 8; Sep w4: 8; Oct w4: 8; Nov w4: 8; Dec w4: 8 | 40
| Nov w3: Total Estimated PM Days Required | 125

## Tendered days for PM Role
| Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Total Estimated PM Days required per WP
| w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
BACS Alarm Categorisation | Jan w2: 8; Jan w3: 8; Jan w4: 8; Feb w1: 8; Feb w2: 8; Feb w3: 8; Feb w4: 8; Mar w1: 8; Mar w2: 8; Mar w3: 8; Mar w4: 8; Apr w1: 16; Apr w2: 16; Apr w3: 16; Apr w4: 16; May w1: 16; May w2: 16; May w3: 16; May w4: 16; Jun w1: 16; Jun w2: 16; Jun w3: 16; Jun w4: 16
Total Hrs/Month | Jan w4: 24; Feb w4: 32; Mar w4: 32; Apr w4: 64; May w4: 64; Jun w4: 64
Total Days/Month | Jan w4: 3; Feb w4: 4; Mar w4: 4; Apr w4: 8; May w4: 8; Jun w4: 8 | 35
Installation & Commissioning of additional BACS alarm input/output | Mar w3: 8; Mar w4: 8; Apr w1: 16; Apr w2: 16; Apr w3: 16; Apr w4: 16; May w1: 16; May w2: 16; May w3: 16; May w4: 16; Jun w1: 16; Jun w2: 16; Jun w3: 16; Jun w4: 16; Jul w1: 16; Jul w2: 16; Jul w3: 16; Jul w4: 16; Aug w1: 16; Aug w2: 16; Aug w3: 16; Aug w4: 16; Sep w1: 16; Sep w2: 16; Sep w3: 16; Sep w4: 16
Total Hrs/Month | Mar w4: 16; Apr w4: 64; May w4: 64; Jun w4: 64; Jul w4: 64; Aug w4: 64; Sep w4: 64
Total Days/Month | Mar w4: 2; Apr w4: 8; May w4: 8; Jun w4: 8; Jul w4: 8; Aug w4: 8; Sep w4: 8 | 50
Alarm integration to AMS | Aug w1: 16; Aug w2: 16; Aug w3: 16; Aug w4: 16; Sep w1: 16; Sep w2: 16; Sep w3: 16; Sep w4: 16; Oct w1: 16; Oct w2: 16; Oct w3: 16; Oct w4: 16; Nov w1: 16; Nov w2: 16; Nov w3: 16; Nov w4: 16; Dec w1: 16; Dec w2: 16; Dec w3: 16; Dec w4: 16
Total Hrs/Month | Aug w4: 64; Sep w4: 64; Oct w4: 64; Nov w4: 64; Dec w4: 64
Total Days/Month | Aug w4: 8; Sep w4: 8; Oct w4: 8; Nov w4: 8; Dec w4: 8 | 40
| Nov w3: Total Estimated PM Days Required | 125

## PM Pricing Schedule
The Pirbright Institute
Project Management Brooksby Building BACS additional works
Project Manager Role - Pricing Schedule
Name of Tenderer: | [10 empty] | Date:
Note: All fees should be quoted excl. of VAT
PROJECT MANAGEMENT SERVICES |  |  | Days / | [12 empty] | Days / Phase
| Name | Day Rate (£) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Director / Partner |  |  | Days / Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Associate |  |  | Days / Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Senior Professional |  |  | Days / Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Professional |  |  | Days / Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Graduate / Trainee |  |  | Days / Total: 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RATE FOR VARIATIONS/ ADDITIONAL SERVICES
| Hourly Rate (£) | Day Rate (£)
Director / Partner
Associate
Senior Professional
Professional
Graduate / Trainee