## Tender Queries
TENDER CLARIFICATIONS | [5 empty] | If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
Project: | Basset Community Centre, Enabling Works
Location: | Camborne
Date: | 08.10.2024
Rev: | 0.4
Note: | Updates from previous revision are highlighted in orange
ITEM | CLARIFICATION | SECTION | DATE RAISED | OPEN / CLOSED | DATE CLOSED | RESPONSE
1 | We note that the client has requested a 10% Performance Bond and a PCG. Could you confirm if it would be acceptable to provide a Bond only? | Preliminaries | 10.09.24 | Closed | 13.09.2024 | If the bidder’s company has a parent company, subject to assets and liquidity in the parent company, the Council would seek a parent company guarantee. If there is no parent company, we would look for supply a price for the bond only. We would not seek both a parent company guarantee and a bond.
2 | Submission: What is the process for submission of tenders? Is it direct to the Council or through a portal? | Invitation to Tender Document | 09.09.24 | Closed | 10.09.2024 | Please provide formal response by email to: tenders@camborne-tc.gov.uk
3 | Site visits: Who do we need to contact for a visit? | Invitation to Tender Document | 09.09.24 | Closed | 10.09.2024 | Please contact Dave Garwood Camborne Town Council (Amenities Officer) for arrangement of a site visit: david.garwood@camborne-tc.gov.uk
4 | ADDENDUM - to Appendix F | APPENDIX F - Basset enabling work PRICING DOCUMENT Final | 19.09.2024 | Closed | 19.09.2024 | Please note addtiional document uploaded - please see Price Schedule Document
5 | Please can you issue the Asbestos Survey report to us? | Support documents | 19.09.2024 | Closed | 19.09.2024 | J3070a - Asbestos Refurb survey of Basset Centre - Camborne Council and J3070b - Refurb survey of White House - Camborne Council added to documents on Contracts Finder
6 | Is it possible to extend the return date as seeking supporting prices from supply chain? | Invitation to Tender Document | 08.10.2024 | Closed | 08.10.2024 | The Council is prepared to extend the return date to noon (12:00) on 25 October 2024