708730451 – Management and Manning of Catterick Garrison CCTV Centre

TIMETABLE

|  | PCR OPEN (above threshold) | PCR/DSPCR (below £100k) | DSPCR RESTRICTED (below threshold) | DSPCR RESTRICTED (above threshold) |
| --- | --- | --- | --- | --- |
| Advert |  |  |  |  |
| Issue Advert (EOI/DPQQ/SAQ) | 20 Sept 2023 (30 days) |  |  |  |
| Clarification period/extension request | 21 Sept - 9 Oct 2023 |  |  |  |
| Response to clarification Q/Ext | 13 Oct 2023 |  |  |  |
| Closing Date | 20 Oct 2023 |  |  |  |
| DPQQ/SAQ Evaluation | 23 – 27 Oct 2023 |  |  |  |
| Results/DEF 157 | 30 Oct 2023 |  |  |  |
| Tender |  |  |  |  |
| Issue ITT | 20 Sept 2023 (35 days – 5 DSP) |  |  |  |
| Site Visit | w/c 2 Oct 2023 (if requested) |  |  |  |
| Clarification period/extension request |  |  |  |  |
| Response to clarification Q/Ext |  |  |  |  |
| Reverse auction |  |  |  |  |
| ITT due | 20 Oct 2023 |  |  |  |
| Tender evaluation complete | 23 Oct – 14 Nov 2023 |  |  |  |
| Start standstill/award notice (10 Days) | 15 Nov 2023 |  |  |  |
| Standstill ends (23:59) | 27 Nov 2023 |  |  |  |
| Contract entry | 28 Nov 2023 |  |  |  |
| Contract start | 1 Apr 2024 |  |  |  |
| Contract expiry | 31 Mar 2027 |  |  |  |
| Options | 2 x 1 yr options (or part thereof) |  |  |  |