DMS Standard Terms

Schedule 2.1

Implementation Plan

Introduction

This Schedule defines the process for agreeing the Detailed Implementation Plan and the maintenance and updating of the Implementation Plan.

Detailed Implementation Plan

The Supplier shall submit a draft of the Detailed Implementation Plan to the Customer for approval within 10 Working Days after the Effective Date.

The Detailed Implementation Plan shall:

include each of the Milestones and Milestone Dates as identified in the outline plan contained at Appendix 3 to the Call-Off Order;

include the Milestone Achievement Criteria for each Milestone;

include all Deliverables, including the development of the Operations Manual, and tasks required to be completed to Achieve each Milestone;

include the start and end date for each task;

clearly outline the required roles and responsibilities of both Parties, including staffing requirements;

indicate which Party is responsible for delivery of each Milestone and task shown in the plan; and

include an overarching plan mapping each of the Milestones, Milestone Dates, tasks and start and end dates for each task.

Following receipt of the draft Detailed Implementation Plan from the Supplier, the Customer shall:

review and comment on the draft Detailed Implementation Plan as soon as reasonably practicable; and

notify the Supplier in writing that it approves or rejects the draft Detailed Implementation Plan no later than 10 Working Days after the date on which the draft Detailed Implementation Plan is first delivered to the Customer.

If the Customer rejects the draft Detailed Implementation Plan:

the Customer shall inform the Supplier in writing of its reasons for its rejection; and

the Supplier shall then revise the draft Detailed Implementation Plan (taking reasonable account of the Customer's comments) and shall re-submit a revised draft Detailed Implementation Plan to the Customer for the Customer 's approval within 10 Working Days of the date of the Customer's notice of rejection. The provisions of Paragraph 2.3 and this Paragraph 2.4 shall apply again to any resubmitted draft Detailed Implementation Plan until the Customer has indicated its acceptance by signing the Detailed Implementation Plan, provided that either Party may refer any disputed matters for resolution by the Dispute Resolution Procedure at any time.

Following the Implementation Plan

The Supplier shall provide each of the Deliverables identified in the Implementation Plan by the date assigned to that Deliverable in the Implementation Plan so as to ensure that each Milestone identified in the Implementation Plan is Achieved on or before its Milestone Date.

The Supplier shall monitor its performance against the Implementation Plan and Milestones (if any) and report to the Customer on such performance.

Time in relation to compliance with the Implementation Plan shall be of the essence and failure of the Supplier to comply with the Implementation Plan shall be a material Default.

Reviewing and changing the Implementation Plan

Subject to Paragraph 4.3, the Supplier shall keep the Implementation Plan under review in accordance with the Customer’s instructions and ensure that it is updated on a regular basis.

The Customer shall have the right to require the Supplier to include any reasonable changes or provisions in each version of the Implementation Plan.

Changes to any Milestones shall only be made in accordance with the Change Control Procedure.

Security requirements before the Start Date

The Supplier shall note that it is incumbent upon the Supplier to understand the lead-in period for security clearances and ensure that all Supplier Personnel have the necessary security clearance in place before the relevant Ordered Service Commencement Date. The Supplier shall ensure that compliance with its obligations under Schedule 3.6 (Security Management) is reflected in the Implementation Plan.

The Supplier shall ensure that all Supplier Personnel and Sub-contractors do not access the Authority System, or any IT systems linked to the Customer or Service Recipient, unless the Supplier has satisfied its obligations under Schedule 3.6 (Security Management) and any additional security requirements specified by the Customer in the Call-Off Order Form.

The Supplier shall be responsible for providing all necessary information to the Customer to facilitate security clearances for Supplier Personnel and Sub-contractors in accordance with the Supplier’s obligations under Schedule 3.6 (Security Management) and any additional security requirements specified by the Customer in the Call-Off Order Form

The Supplier shall ensure that all Supplier Personnel and Sub-contractors requiring access to the Customer Premises have the appropriate security clearance. It is the Supplier's responsibility to establish whether or not the level of clearance will be sufficient for access. Unless prior approval has been received from the Customer, the Supplier shall be responsible for meeting the costs associated with the provision of security cleared escort services.

Government Reviews

The Supplier acknowledges that the Available Services may be subject to Government review at key stages of the project (such as Gateway Reviews). The Supplier shall cooperate with any bodies undertaking such review and shall allow for such reasonable assistance as may be required for this purpose within the Charges.