## COVER PAGE
SCHEDULES OF WORK FOR CEILING REPAIR, INSULATION & SAFE ACCESS WORKS
210572
at:
STUDY COLLECTIONS CENTRE
DREADNOUGHT BUILDING
OLD SCHOOL CLOSE
SE10 0PG
for:
THE HORNIMAN PUBLIC MUSEUM & PUBLIC PARK TRUST
100 LONDON ROAD
LONDON
SE23 3PQ
|  | Issue No : | For Tender
|  | Revision No : | T2
|  | Date : | 2022-01-01
|  | Job No: | 210572
Document Issue Record
Revisions
T2 | For Tender | 06.01.22

## CONTENTS
SCHEDULE OF WORK
FOR
CEILING REPAIR & REINSULATION WORKS
AT
STUDY COLLECTIONS CENTRE
OLD SCHOOLHOUSE LANE, SE10 0PG
FOR
THE HORNIMAN MUSEUM & GARDENS
SECTION NO.1 - CONDITIONS OF CONTRACT/PRELIMINARIES
SECTION NO.2 - CEILING REPAIR & STRENGTHENING WORKS - OPTION A
SECTION NO.3 - CEILING REPAIR, STRENGTHENING & REINSULATION WORKS - OPTION B
SECTION NO.4 - SAFE ACCESS WORKS
SUMMARY
APPENDIX A - DETAILED TERMS OF THE PRELIMINARIES & CONDITIONS OF CONTRACT
| Issue No : | For Tender
| Revision No : | T1
| Date : | 2021-11-01
| Job No: | 210783

## SECTION No.1
ANALYSIS OF TENDER
1 | PRELIMINARIES & CONDITIONS OF CONTRACT
The Contractor should refer to the Preliminaries and Conditions of Contract at Appendix A and following review, insert their proposed costs below. If no specific allowance is made, the Contractor will be deemed to have made allowance elsewhere in the pricing document for costs in respect of fully complying with the terms set out in Appendix A.
1.1 |  | £
1.2 |  | £
1,3 |  | £
1.4 |  | £
1.5 |  | £
1.6 |  | £
1.7 |  | £
1.8 |  | £
1.9 |  | £
1.1 |  | £
1.11 |  | £
1.12 |  | £
1.13 |  | £
1.14 |  | £
1.15 |  | £
| COST CARRIED FORWARD TO COLLECTION PAGE : | 0

## SECTION No.2
STUDY COLLECTIONS CENTRE
DREADNOUGHT BUILDING
OLD SCHOOL CLOSE
SE10 0PG
SECTION NO.2
CEILING REPAIR & STRENGTHENING WORKS - OPTION A
In pricing the works in this section the Contractor is deemed to have have read and understood all tender documents provided and to have have undertaken a visit to the premises to inspect the proposed works and all relevant areas of the site and building.
This document should be priced and submitted electronically. If a paper copy is provided, each page total must be noted and carried forward to a collection page.
ITEM |  | DESCRIPTION OF WORKS TO BE COSTED |  |  | COST
2.1 |  | TEMPORARY WORKS/ACCESS
A |  | The contractor must allow for the provision of all necessary equipment and measures to undertake the works in a safe manner, to include provision of proprietary crawl boards, rope access equipment and any other safe access systems necessary to carry out the work without applying loads to the ceiling back. NOTE: The collections storage area at third floor level contains sensitive objects, in the event that the contractor's actions cause any debris to enter this area, they will be required to undertake comprehensive cleaning to the reasonable satisfaction of site staff. | 1 | Item | £
B |  | Allow for provision of localised temporary propping to provide support to any specific areas of the ceiling deemed to be risk of instability prior to strengthening. Any propping of this nature is to be Contractor Designed. | 1 | Item | £
2.2 |  | STRIP-OUT WORKS
A |  | AREA E: Allow to Lift and remove existing boarding and any timber bearers not forming part of the ceiling structure (Refer to DR-S-4002) | 1 | Item | £
2.3 |  | CEILING REPAIR WORKS
A |  | Allow to locally lift and set aside existing mineral fibre insulation. Supply and install 1 pair of Expamet AP3003030 angle brackets or FB20 steel band supports at all ceiling joist to timber truss connections in Areas A to E (Refer to DR-S-4000, Detail 1). Following installation, reinstate insulation to its original position. | 1 | Item | £
B |  | Provide rate for installation of each additional pair of AP3003030 brackets at joint locations, To be applied pro rata as required (refer to DR-S-4000, Detail 2) - do not carry forward to collection.
£…...................
C |  | Provide rate for installation each of additional pair of FB20 band supports at joint locations, To be applied pro rata if and where required (refer to DR-S-4000, Detail 2) - do not carry forward to collection.
£…...................
D |  | Allow to supply and install bolted plywood gusset plates to repair strut at Truss C1 in accordance with DR-S-4001. | 1 | Item | £
E |  | Allow to supply and install glued hardwood wedges to strut joint at Truss C1 in accordance with DR-S-4001. | 1 | Item | £
F |  | AREA E: Allow to supply and install new 200mm x 50mm and 75mm x 50mm C24 timber joists and WBP plywood decking. Remove and re-fit guard rail. All in accordance with DR-S-4002. | 1 | Item | £
2.4 |  | Any additional items Tenderer considers not included above (detail below).
| i) |  |  |  | £
| ii) |  |  |  | £
| iii) |  |  |  | £
|  | COST CARRIED FORWARD TO COLLECTION PAGE : |  |  | 0

## SECTION No.3
STUDY COLLECTIONS CENTRE
DREADNOUGHT BUILDING
OLD SCHOOL CLOSE
SE10 0PG
SECTION NO.3
CEILING REPAIR, STRENGTHENING WORKS & REINSULATION WORKS - OPTION B
In pricing the works in this section the Contractor is deemed to have have read and understood all tender documents provided and to have have undertaken a visit to the premises to inspect the proposed works and all relevant areas of the site and building.
This document should be priced and submitted electronically. If a paper copy is provided, each page total must be noted and carried forward to a collection page.
ITEM |  | DESCRIPTION OF WORKS TO BE COSTED |  |  | COST
3.1 |  | TEMPORARY WORKS/ACCESS
A |  | The contractor must allow for the provision of all necessary equipment and measures to undertake the works in a safe manner, to include provision of proprietary crawl boards, rope access equipment and any other safe access systems necessary to carry out the work without applying loads to the ceiling back. NOTE: The collections storage area at third floor level contains sensitive objects, in the event that the contractor's actions cause any debris to enter this area, they will be required to undertake comprehensive cleaning to the reasonable satisfaction of site staff. | 1 | Item | £
B |  | Allow for provision of localised temporary propping to provide support to any specific areas of the ceiling deemed to be risk of instability prior to strengthening. Any propping of this nature is to be Contractor Designed. | 1 | Item | £
3.2 |  | STRIP-OUT WORKS
A |  | AREA E: Allow to Lift and remove existing boarding and any timber bearers not forming part of the ceiling structure (Refer to DR-S-4002) | 1 | Item | £
B |  | Lift and remove from site all existing mineral fibre insulation throughout the Third Floor loft spaces (Areas A to E on DR-S-1000). Vaccum clean residual loose fibre material to leave the ceiling backs and structural connections fully visible for inspection. | 1 | Item | £
3.3 |  | CEILING REPAIR WORKS
A |  | Allow to locally lift and set aside existing mineral fibre insulation. Supply and install 1 pair of Expamet AP3003030 angle brackets or FB20 steel band supports at all ceiling joist to timber truss connections in Areas A to E (Refer to DR-S-4000, Detail 1). Following installation, reinstate insulation to its original position. | 1 | Item | £
B |  | Provide rate for installation of each additional pair of AP3003030 brackets at joint locations, To be applied pro rata as required (refer to DR-S-4000, Detail 2) - do not carry forward to collection.
£…...................
C |  | Provide rate for installation each of additional pair of FB20 band supports at joint locations, To be applied pro rata if and where required (refer to DR-S-4000, Detail 2) - do not carry forward to collection.
£…...................
D |  | Allow to supply and install bolted plywood gusset plates to repair strut at Truss C1 in accordance with DR-S-4001. | 1 | Item | £
E |  | Allow to supply and install glued hardwood wedges to strut joint at Truss C1 in accordance with DR-S-4001. | 1 | Item | £
F |  | AREA E: Allow to supply and install new 200mm x 50mm and 75mm x 50mm C24 timber joists and WPB plywood decking. Remove and re-fit guard rail. All in accordance with DR-S-4002. | 1 | Item | £
3.4 |  | REINSULATION WORKS
A |  | Supply and install new Class A rated non-combustible mineral wool insulation in rolls and/or batts to all areas to replace material previously removed. Insulation should be installed between and over the ceiling joists to achieve a minumum U-value of 0.18W/m2K. Provide a calculation from the selected supplier to confirm compliance with this standard. NOTE: Ensure that all existing ventilation paths remain unobstructed and smoke hoods and other heat disapation items remain in place. | 1 | Item | £
2.4 |  | Any additional items Tenderer considers not included above (detail below).
| i) |  |  |  | £
| ii) |  |  |  | £
| iii) |  |  |  | £
|  | COST CARRIED FORWARD TO COLLECTION PAGE : |  |  | 0

## SECTION No.4
STUDY COLLECTIONS CENTRE
DREADNOUGHT BUILDING
OLD SCHOOL CLOSE
SE10 0PG
SECTION NO.4
SAFE ACCESS WORKS (CDP)
In pricing the works in this section the Contractor is deemed to have have read and understood all tender documents provided and to have have undertaken a visit to the premises to inspect the proposed works and all relevant areas of the site and building.
This document should be priced and submitted electronically. If a paper copy is provided, each page total must be noted and carried forward to a collection page.
ITEM |  | DESCRIPTION OF WORKS TO BE COSTED |  |  | COST
4.1 |  | TEMPORARY WORKS/ACCESS
A |  | The contractor must allow for the provision of all necessary equipment and measures to undertake the works in a safe manner, to include provision of proprietary crawl boards, rope access equipment and any other safe access systems necessary to carry out the work without applying loads to the ceiling back. | 1 | Item | £
4.2 |  | WALKWAYS AND HANDRAILS
A |  | Allow to design, supply and install new walkways and handrails within the attic space in general accordance with the existing layout on plan as shown on DR-S-1001. The employer's requirements in respect of the new walkways and handrails are set out in detail on DR-S-1001 and the contractor's design proposals must take these in account. | 1 | Item | £
B |  | Allow to design, supply and install new aluminium fall protection rails to each side of the existing access ladder from 3rd Floor to Attic level. To be securely fixed to the sides of the existing ladder. | 1 | Item | £
4.3 |  | Any additional items Tenderer considers not included above (detail below). |  |  | £
i)
ii)
iii)
|  | COST CARRIED FORWARD TO COLLECTION PAGE : |  |  | 0

## SUMMARY
STUDY COLLECTIONS CENTRE
DREADNOUGHT BUILDING
OLD SCHOOL CLOSE
SE10 0PG
SUMMARY OF TENDER
OPTION A
1 |  | Section No.1 - Preliminaries & Conditions of Contract | 0
2 |  | Section No.2 - Ceiling Repair & Strengthening Works - OPTION A | 0
4 |  | Section No.4 - Safe Access Works | 0
|  | Contingency Sum | 5000
|  | OPTION A TOTAL COST OF WORKS | 5000
OPTION B
|  | Section No.1 - Preliminaries & Conditions of Contract | 0
|  | Section No.3 - Ceiling Repair, Strengthening & Reinsulation Works - OPTION B | 0
|  | Section No.4 - Safe Access Works | 0
|  | Contingency Sum | 5000
|  | OPTION B TOTAL COST OF WORKS | 5000
CONTRACTOR NAME:
ADDRESSS:
DATE: