## Sheet1
Highways Agency Confirmation of Task Order Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
Supplier: | AECOM | Fee Request for this CTO |  | 62398.72
Project Title: | A5 Scheme Development M42 - M69
Contract Ref. | 114/2/1391/2 | CPA No.: | Redcated | BPA No.: | Redacted
PIN Description: | Studies | Sub Pin: | Redcated | PIN No.: | Redcated
HA Reference: | EM 28 15/16 | Start and End Date : |  | 08/10/2015 - 31/01/2016
Task Overview and Expected Outcomes
AECOM undertook a study of the A5 corridor in autumn 2014 to review improvement options for dualling of the A5 between the M42 Junction 10 and M69 Junction 1 to deliver economic growth whilst relieving congestion. This work was undertaken to feed potential improvements into the RIS programme of works. The study concentrated on solutions close to the existing A5 with options based on provision of dual carriageway alignments between the M42 and M69 junctions, taking into account the suggestion in RIS for an “A5 Expressway” in relation to the wider A5 corridor between M6 and M1. This will assist in clarifying the scheme objectives and whether other potential options exist to address the identified issues in the corridor. The scheme was not included in the current RIS programme but RIS funding appeared to be available to develop the scheme for inclusion in the second RIS period. However, this does not now appear to be the case. The scheme was previously developed using SPA and partner funding. SPA funding in 2015/16 is available for an Improvement Study to further develop the A5 scheme. This will assist on-going constructive engagement with partners and the clarification of scheme options and requirements for feeding into the future RIS programmes. Aecom undertook the initial stage of the Improvement Study in July 2015 to review previous A5 Study work in light of the government’s Road Investment Strategy, including the aspiration for the A5 to become an “Expressway” between M1 and M6, identifying other potential scheme options. This initial stage comprised a preliminary review of route options and a workshop with Highways England to discuss initial work outputs and to clarify the future study approach and output requirements. This workshop took place on 10th September 2015. Redacted of expenses are included as part of this task. This figure accounts for the following: Site Visit 1 - (from Birmingham) 2 passengers. 140 miles (40 to/from site, 100 on site) @ Redacted petrol per mile = Redacted Subsistence Redacted x 2 = Redacted Site Visit 2 - (from Birmingham) 2 passengers. 140 miles (40 to/from site, 100 on site) @ Redacted petrol per mile = Redacted Subsistence Redacted x 2 = Redacted Site Visit 3 - (from Birmingham) 2 passengers. 140 miles (40 to/from site, 100 on site) Redacted petrol per mile =Redacted Subsistence Redacted 2 = Redacted Site Visit 3 - (from Leeds) 2 passengers. 140 miles (40 to/from site, 100 on site) @ Redacted petrol per mile = Redacted Subsistence Redactedx 2 =Redacted Site Visit 3 - (from Leeds) 2 passengers. 140 miles (40 to/from site, 100 on site) @ Redacted petrol per mile = Redacted Subsistence Redacted x 2 = Redacted
Task Objectives and Milestones
The objectives of the task are to progress the PCF Stage 0 for an A5 Improvement (M42-M69), reviewing previous A5 Study work in light of the government’s Road Investment Strategy, including the aspiration for the A5 to become an “Expressway” between M1 and M6, identifying and assessing potential scheme options, particulalry taking into account scheme affordability and deliverability, including potential for phasing of scheme elements. The task comprises two main elements: the development of a Transport Summary Report, reviewing and considering further the initial high level review of potential options, rationalising these into more specific options for consultation and evaluation; and a Solutions Summary report which will gather further data regarding the refined options, with particular consideration given to economic impact and route performance, to inform the appraisal and identification of a preferred option. These two reports comprise the first stages of the PCF Stage 0. The Transport Summary report will comprise the following elements: • Consideration of the study area in the wider context of the whole route M1 to M6. • Rationalisation of the initial outline options to include the on-line improvement, A5 expressway and northern routes. • Identification of potential phasing and inter-route connectivity. The Solution Summary report will comprise evaluation of the refined options with regard to the following elements: • Engineering assessment Horizontal and vertical alignment, widening and environmental and traffic work will be undertaken on the northern route options commensurate with work already undertaken on the on-line improvement and A5 expressway options as part of the initial study work. Site visits and gathering and collation of further development and other information will be required. • Environmental impact (separate AECOM task) • Traffic and route performance (using LLITM outputs from LCC) • Identification of key development proposals, such as the Enterprise Zone at MIRA • Identification of potential programme issues. • Identification of potential option costs (Highways England MP team). • Identification of recommended scheme. It is anticipated that the traffic and route performance assessment will be informed by scenario tests in LLITM at no cost to the task.
Expected Project Outcomes
The task will take the proposed A5 improvement scheme M42-M69 through part of the PCF Stage 0 with the production of a Transport Summary Report and Solutions Summary Report to progress option identification and assessment to support a preferred scheme to feed into future Route Strategies and next RIS programme. The preferred scheme should represent an affordable and deliverable scheme. To be completed, the task will require inputs on environmental imapcts (separate task) and outputs from LLITM options testing (to be supplied by LCC). Once the task is completed, it is anticipated that a subsequent task will follow to enable PCF Stage 0 to be completed for the proposed A5 major scheme. The individual elements of the task and their associated costs are summarised below. Transport Summary Report Sub Total Redcated Solutions Summary Report Elements Project Management Redcated Optioneering Redcated Engineering issues Redcated Statutory Undertakers Redcated Environmental issues Redcated Traffic issues Redcated Land and development issues Redcated Stakeholder engagement (separate task as required)Redcated Programme issuesRedcated Risks and IssuesRedcated Solutions Summary Report preparationRedcated Solutions Summary Report Sub TotalRedcated Total Task CostRedcated
Project Risk and Management
Overall task direction will be provided byRedcated .Redcated will provide day to day task management. Task direction and management will include setting up the task in TAPE, liaison with the task sponsor, task delivery, checking and approval of task outputs and task closure. Redcated will provide highway design input, supported by Redcated . This work will be reviewed byRedcated . Redcated (subject to confirmation) will provide specialist environmental input with other envirnmental specialists as required. Redcated will provide specialist input on modelling and appraisal as required. (It is assumed that traffic modelling and reporting of outputs will be undertaken by Redcated through the LLITM model.) It is envisaged that the Transport Summary Report will be provided by 31 October 2015 with the Solutions Summary report completed by 31 January 2016, based on a start date of 23rd September 2015. Cost estimation is expected to be undertaken by Major Projects team and therefore no costs have been allowed for. Some task inputs (LLITM outputs and scheme costings from Highways England MP Directorate) are beyond AECOM's control and this could affect proposed task delivery deadline. Task progress and costs will be monitored weekly and reported monthly to the task sponsor. Any issues such as perceived scope change or issues with delivery of task inputs from third parties will be discussed with the task sponsor. Should the task be able to be completed under the estimated task cost, AECOM will discuss using the underspend to progress further work. Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
HA Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: