[image: image3.png]w HIGHWAYS
AGENCY

Safe roads, reliable journeys, informed travellers





ASC Performance Management Manual

Appendix E1
ASC Contract Extension Metrics and OPI
Version 2.0 April 2013
PERFORMANCE MANAGEMENT MANUAL
APPENDIX E1
ASC CONTRACT EXTENSION METRICS AND OPI
CONTENTS AMENDMENT SHEET

	Amend. No.
	Issue Date
	Amendments
	Initials
	Date

	0
	May 11
	First Issue
	TW
	11/5/11

	1
	Dec 11
	Second Draft
	WH
	20/12/11

	2
	Dec 11
	Third Draft
	WH
	21/12/11

	3
	Feb 12
	Fourth Draft – Revised CEM 13
	WH
	2/3/12

	4
	Mar 12
	Fifth Draft – Slightly amended wording for aspects 14 and 15
	WH
	22/3/12

	5
	Mar 12
	Sixth Draft – Removal of Annex 1 (Scoring Guidance)
	WH
	28/3/12

	6
	Mar 12
	Seventhth Draft – correct typos and formatting
	TW
	31/3/12

	7
	Apr 12
	Eighth Draft – Removal of incorrect evidence from Aspects 5 and 6 (Time and Cost)
	WH
	10/4/12

	8
	May 12
	Ninth draft – update CEM 5 and 6
	TW
	16/5/12

	9
	Apr 13
	V 2.0
	JB
	08/02/13


PMM App E1.1 Operation Performance Index (OPI) Matrix
The Operation Performance Index is an overall measure of Provider performance to be calculated at regular intervals. The OPI is a weighted sum of several individual performance measures independent of the ASC Performance Management Framework (or similar) although some measures may be the same or similar.

The individual measures that make up the OPI include:

Table PMM App E.1.1 OPI Metrics and Weightings
	
	Service Area
	Description 
	Weighting (100) 

	1 
	We provide a service that our customers can trust 
	Incidents are cleared rapidly
	5

	2 
	We provide a service that our customers can trust 
	Minimising the lane space devoted to works 
	7.5

	3 
	We set the standard for delivery
	QMS Performance (QMPs)
	12.5 

	4 
	We set the standard for delivery
	Number of Compensation Events raised by the Provider which are rejected by the Service Manager
	5

	5 
	We set the standard for delivery
	Close correlation between predicted duration of design and construction periods
	5

	6 
	We set the standard for delivery
	Close correlation between target cost and actual cost of Schemes
	5

	7 
	We set the standard for delivery
	Quality management reporting delivered on time
	2.5

	8 
	We set the standard for delivery
	High quality asset data fit for its intended purposes entered into the relevant asset database in a timely manner
	2.5

	9 
	We set the standard for delivery
	Efficiency savings are generated as tendered
	5 

	10 
	Our roads are the safest in the world
	Number of AMOR performance targets meeting or exceeding threshold 
	17.5 

	11 
	Our roads are the safest in the world
	Road Worker Safety 
	5 

	12
	We deliver sustainable solutions
	Site waste management plan compliance
	2.5 

	13 
	Our network is a dynamic and resilient asset
	Lane availability maximised during severe weather 
	7.5 

	14
	Our network is a dynamic and resilient asset
	Salt stocks are maintained at levels sufficient to support winter service
	7.5 

	15
	Our network is a dynamic and resilient asset
	Inspection Management Programme delivered
	5

	16
	Our network is a dynamic and resilient asset
	Work which the Provider has undertaken is defect free
	5


PMM App E1.2 OPI Aspects Scoring Methodology
Table PMM App E1.2 OPI Metrics Scoring Methodology

	Metric
	Description
	Evidence 
	Green
	Amber

	Red


	1
	We provide a service that our customers can trust – 

Incidents are cleared rapidly


	Demonstrate
- Incidents are cleared rapidly 
Measure

- AMOR Part 3 and Table 3.1

Evidence
- Incident management records and/or Provider-initiated Operational Data 
	100% compliance with AMOR Table 3.1 Performance Metrics 1, 2 and 3 since last OPI review 
	<100% and >= 90% compliance with AMOR Table 3.1 Performance Metrics 1, 2 and 3 since last OPI review


	<90% compliance with AMOR Table 3.1 Performance Metrics 1, 2 or 3 since last OPI review



	2
	We provide a service that our customers can trust – 

Minimising lane space devoted to works 
	Demonstrate
- Network availability is maximised

Measure
- AMOR Part 2 SRW Performance Indicators  (PI) 1, 2 and 3a 
	All SRW Performance Indicators – 1, 2a and 3a – achieved Green scores (as per SRW definition) since last OPI review
	One or more of SRW Performance Indicators achieved an Amber score (as per SRW definition) since last OPI review

	One or more of SRW Performance Indicators achieved a Red score (as per SRW definition) since last OPI review

	3
	We set the standard for delivery –
Quality Management System Performance (QMPs)


	Demonstrate
- Performance of the Provider's Quality Management System (QMS).
Measure
- Quality Management Points accrued for a range of QMS failures, whether arising from audits by the Provider, Service Manager or relevant certification body. 

Evidence
- Provider’s register of Quality Management Points

	Sum of Quality Management Points did not exceed 25 at any time since the last OPI review.


	Sum of Quality Management Points was > 25 but <=70 at any time since last OPI review.

And

A quality warning notice was not issued or in effect at any time since the last OPI review.


	Sum of Quality Management Points exceeded 70 at any time since last OPI review.

Or 

 A quality warning notice was issued or in effect at any time since the last OPI review.


	4
	We set the standard for delivery –

Number of Compensation Events raised by the Provider which are rejected by the Service Manager 
	Demonstrate
- The Service Provider is seeking only valid compensation event claims as defined in Conditions of Contract Clause 60.1 (1-27)
Evidence 
- Service Manager Compensation event records 
	No Provider initiated compensation events have resulted in the Service Manager notifying that the “Prices are not to be changed”  since last OPI review as defined in Clause 61.4
	1 - 2 Provider initiated compensation event resulted in the Service Manager notifying that the “Prices are not to be changed” since last OPI review as defined in Clause 61.4
And

No more than 1 instance in any individual month within the quarter
	> 2 Provider initiated compensation events have resulted in the Service Manager notifying that the “Prices are not to be changed”  since last OPI review as defined in Clause 61.4

	5
	We set the standard for delivery –

Close correlation between target duration and actual duration of Schemes


	For Capital Schemes with planned cost (by PIN) >= £100k.

Demonstrate

- Meeting the HA Strategic Goal of setting the standard for delivery in relation to target time and actual time for Schemes that were Live (i.e. from Actual Design Completion to 11 months after the month in which PCCR is reported) in the OPI period.

Evidence

- Available supporting evidence at milestones 1, 2, 5 and 6. See ASC CEM Service Manager Guidance.

Measure

- Total Time Variance: Net variance of actual time over all Live Schemes for both design and construction phases 
	Total Time Variance of all Live Schemes is <= -2 days 
	Total Time Variance of all Live Schemes is <= 3 days 
	Total Time Variance of all Live Schemes is > 3 days 

	6
	We set the standard for delivery –
Close correlation between target cost and actual cost of Schemes


	For Capital Schemes with planned cost (by PIN) >= £100k.

Demonstrate

- Meeting the HA Strategic Goal of setting the standard for delivery in relation to target cost and actual costs for Schemes that were Live (i.e. from Actual Design Completion to 11 months after the month in which PCCR is reported) in the OPI period.

Evidence

- Available supporting evidence at milestones 1, 3 and 7. See ASC CEM Service Manager Guidance.

Measure

- Total Percentage Cost Variance: Net variance of predicted/actual cost over all Live Schemes at either milestone 3 or milestone 7 versus predicted costs at milestone 1.
	Net costs of all Live Schemes is 5% or more below the predicted costs 
	Net costs of all Live Schemes is on or below predicted costs by less than 5% 
	Net costs of all Live Schemes is above predicted costs 

	7
	We set the standard for delivery –

Quality management reporting delivered on time


	Demonstrate
- All Provider-initiated reports produced as required and in accordance with Annex 19.

Evidence
- All reports produced as required by Annex 19 since last OPI review 
- Where appropriate, evidence of recommendations for further actions
	0 reports required by Annex 19 were overdue at any point within the OPI quarter 
	A total of 1 - 2 reports required by Annex 19 were overdue at any point within the OPI quarter

And 

no more than 1 was overdue within any individual month
	> 2 reports  required by Annex 19  were overdue at any point within the OPI quarter


	8
	We set the standard for delivery –

High quality asset data, fit for purpose, entered into the relevant asset database in a timely manner


	Demonstrate

- High quality asset data fit for its intended purpose entered in the relevant asset database in a timely manner. 
Measure

- Compliance with the Asset Data Management Manual Provider Requirements and Annex 25 
Evidence

- Date of completion for all Schemes on site

- As-Built records for all Schemes
- Survey results prior to being loaded into the relevant asset database

- Inspection records prior to being loaded into the relevant asset database

- Evidence of changes in the relevant asset databases for all Schemes

- Manage Asset Data Annex 24 Sub Process(s) in the Provider’s Quality Management Plan
	100% of database updates since the last OPI review completed within required timeframe and accuracy.
	<100% and >=90% of database updates since the last OPI review completed within required timeframe and accuracy.
	<90% of database updates since the last OPI review completed within required timeframe and accuracy.

	9
	We set the standard for delivery –

Efficiency savings are generated as tendered
	Demonstrate

- Efficiency savings are generated as tendered. 
Evidence

-Provider Tender Contract Data Part 2

Note 
- This metric will only be able to be scored once a year. That score should remain in place until the following year.
	Lump sum annual discount >= percent tendered + 1% 
	Lump sum annual discount < percent tendered + 1%
	N/A 

	10
	Our roads are the safest in the world –

Number of AMOR performance targets meeting or exceeding threshold


	Demonstrate
- AMOR Performance Requirement Levels are being met.
Evidence
- Contractor inspection summaries.
Note 
- If the Provider cannot demonstrate compliance with a Performance Requirement Level then the Level is assumed to be failed. 
	All AMOR Performance Requirement Levels are met since last OPI review
	>=1 and <=17 AMOR Performance Requirement Levels failed since last OPI review

And

No more than 6 PRLs failed in any individual month in the OPI quarter

And 

At least one month in the quarter = 0 PRLs failed

	> 17 AMOR Performance Requirement Levels failed since last OPI review

	11
	Our roads are the safest in the world –

Road Worker Safety


	Demonstrate
- Accident Frequency Rate target set by HA Board met

Measures
- AFR in AIRSWeb
	AFR <= Annual AFR target

	AFR <= Annual AFR target + 0.05

	AFR > Annual AFR target + 0.05


	12
	We deliver sustainable solutions – 

Site waste management plan compliance 
	Demonstrate
- Delivery of Site Waste Management Plan (SWMP) in accordance with current regulations.

Evidence
- Active Site Waste Management Plans
- Quality system records 
	100% of required SWMPs submitted and accepted
	100% of required SWMPs submitted but one or more is rejected
	<100% of required SWMPs submitted and accepted

	13
	Our network is a dynamic and resilient asset –

Lane availability maximised during severe weather


	Demonstrate
- Lane availability is maximised during severe weather conditions 

Evidence
-Severe Weather Plan 
-Lane availability during severe weather conditions 
	0 instances of a lane being unavailable and not in accordance with the Severe Weather Plan since last OPI review
	> 0 and <=5 instances of a lane being unavailable and not in accordance with the Severe Weather Plan since last OPI review

And

No more than 2 instances in any individual month in the OPI quarter


	>5 instances of a lane being unavailable and not in accordance with the Severe Weather Plan since  since the l since the last OPI review.
Or
More than 2 instances in any individual OPI quarter

	14
	Our network is a dynamic and resilient asset –

Salt stocks are maintained at levels sufficient levels to support winter services

	Demonstrate 
- Precautionary treatments delivered within the response and treatment times specified in Severe Weather Plan
- Salts stocks are maintained in excess of minimum contracted limits.
Measure
- Compliance with the minimum contracted salt stocks

Evidence
- Provider’s salt stock records 

	Salt stocks remained in excess of minimum contracted quantity at all times since last OPI review

	Salt stocks dropped below  the contract minimum level  at any time since last OPI review but remained above 80% of contract minimum 
AND 
Salt stocks did not drop below contract minimum for more than 12 days in OPI quarter

	Salt stock dropped to <=80% of the contract minimum level at any time.
OR

Salt stock dropped below contract minimum level for more than 12 days 


	15
	Our network is a dynamic and resilient asset –

Inspection Management Programme delivered


	Demonstrate
- Inspection Management Programme documented and operating
- All inspections in accordance with the Maintenance Requirements Plan
- Opportunities to combine inspections at the same time as works are maximised to reduce network closures
- Escalation of findings in accordance with the ASC Part 0.

Evidence
- Quality Plan

· Maintenance Requirements Plan
- Inspection records 

	All inspections required by Maintenance Requirements Plan since last OPI review undertaken and recorded 
	<100% and >=95% of inspections required by Maintenance Requirements Plan since last OPI review undertaken and recorded 
	< 95% of inspections required by Maintenance Requirements Plan since last OPI review undertaken and recorded 

	16
	Our network is a dynamic and resilient asset –

Work which the Provider has undertaken is defect free
	Demonstrate

- Work which the Provider has undertaken is defect free throughout the Contract period 
Evidence

-Quality system records
- Provider’s Routine and Planned Maintenance System
-SRW

-HAPMS
Note

- Defects are deemed to be as a result of the Provider’s workmanship unless proven otherwise by the Provider i.e. accident site, normal deterioration.
	The number of unplanned defect repairs requiring traffic management since last OPI review within Scheme areas constructed since Contract commencement = 0 
	The number of unplanned defect repairs requiring traffic management since last OPI review within Scheme areas constructed since Contract commencement >0 and <= 2 
	The number of unplanned defect repairs requiring traffic management since last OPI review within Scheme areas constructed since Contract commencement > 2 


OPI Calculation Method

The OPI is a weighted sum of individual metric RAG scores. With reference to Table PMM App E.2 each metric is to be scored either: red; amber; or green. Once each metric is scored the overall OPI Score can be calculated as follows:

[image: image1.png]16
OPI = z RAG; X Weighting;

i=1




Where

[image: image2.png]—6.00, RED
RAG; = 11.00, AMBER
1.40, GREEN




Weightingi = Table PMM App E.1
A simulation of the likely score to be gained from the OPI methodology has been undertaken. To gauge average performance the proportion of red, amber and green Aspects for all Managing Agent Contractors (MAC) from the MAC Performance Management Framework (PMF) version 5 for a four month period to January 2011 were calculated. 
A number of simulations using the OPI metrics and the measured proportion of red, amber and green Aspects, as described above, were trialled from which it was observed that there is approximately 50% likelihood of a score > 120 and approximately 20% likelihood of a score < 80. 
It should be noted that this simulation is only approximate as the metrics used in the OPI differ from those used in the MAC PMF version 5. Despite this difference it does show a bias towards awarding contract extension should performance be better than average.

� In circumstances that no “event” occurs to allow a metric to be scored then it shall be scored as if it were “Amber” i.e. neither a penalty nor a bonus.


� In circumstances where data has not been gathered to support the measurement of a metric and subsequent scoring then it shall be scored as if it were “Red”. 








April 2013
Page E1-1

