CONTENTS

1.	PURPOSE	2

2.	BACKGROUND TO THE CONTRACTING aUTHORITY	2

3.	Background to requirement/OVERVIEW of requirement	3

4.	definitions	6

5.	scope of requirement	7

6.	The requirement	8

7.	key PROJECT milestones	13

8.	authority’s responsibilities	14

9.	reporting	14

10.	volumes	15

11.	continuous improvement	15

12.	Sustainability	15

13.	quality	15

14.	PRICE	15

15.	STAFF AND CUSTOMER SERVICE	16

16.	service levels and performance	16

17.	Security requirements	16

18.	intellectual property rights (ipr)	16

19.	payment	16

20.	additional information	17

21.	Location	17

22.	Annex A: List of Proposed Measures	18

# PURPOSE

## The government is committed to ensuring that the aviation sector makes a cost-effective contribution towards reducing global carbon emissions. The UK, along with 190 other states, has signed an unprecedented global agreement to combat aviation emissions.  This Global Market-Based Measure (GMBM) requires airlines to offset their emissions with reductions from other sectors to deliver carbon neutral growth for the aviation sector from 2020. It complements existing mitigation measures being undertaken by the air transport community.

## Alongside this global offsetting agreement, the Department for Transport (DfT) wants to better understand the cost and potential for abating emissions from within the UK aviation sector itself. To this end, the DfT is developing Marginal Abatement Cost Curves (MACCs) for measures to reduce carbon emissions from UK international and domestic flights. The Department also wants an independent assessment of the current baseline within the Aviation Model to reflect the latest thinking with respect to the underlying assumptions about aviation emissions. We are therefore commissioning two projects. The first is to assess the abatement cost of technical measures around engine design, fleet retrofitting and operational improvements within the control of airlines (‘technical measures’) - the project described in this document. The other is to assess the cost and abatement potential of less technical measures such as behaviour change, air traffic management and biofuels (‘non-technical measures’) – detailed in a separate Statement of Requirements (Ref: CCCC16B05). These are being procured as two separate projects as it is anticipated that each project may require different areas of expertise, although prospective bidders are welcome to bid for both. It is also recognised that within each project, different measures may require different expert knowledge. Potential Providers are welcome to subcontract specific tasks or draw on external knowledge where necessary but the lead Potential Provider will be responsible for overseeing any subcontractors and ensuring delivery of the final project.

## The Potential Providers will be expected to assess the cost and carbon abatement potential of the measures they are investigating, as agreed with the DfT project officer, and to provide this information to the DfT to enable it to develop MACCs that include both technical and non-technical measures, on a cumulative emissions reduction basis.

## DfT will use the costs and carbon abatement potential to create a set of MACCs for the UK aviation sector that show the (cumulative) abatement potential and cost per tonne of CO2 saved from each measure. These MACCs will help to inform policy decisions and wider strategy in relation to options for achieving carbon reductions in the aviation sector.

## The Potential Providers carrying out the technical measures project (‘technical Potential Provider’) will be required to do some additional work to peer review some of the data and assumptions in the Fleet Mix Model (FMM) within the Department’s aviation modelling suite (‘DfT aviation model’). This will involve reviewing the data and assumptions used in the latest update of the FMM and commenting on their robustness and appropriateness.

# BACKGROUND TO THE CONTRACTING aUTHORITY

## The DfT works with its agencies and partners to plan, invest in and support the transport network to enable people and goods to travel around the country and internationally. Transport policy measures are developed based on a consideration of, among other things, their economic, social, and environmental impacts. The DfT continually strives to ensure it bases policy on the latest available evidence and regularly commissions external research to fill critical knowledge gaps.

## This project is being commissioned by the ‘Aviation Appraisal and Modelling Team’ that works alongside the Aviation Directorate at the DfT. The team provides analytical support on issues such as demand forecasting, airport capacity expansion and economic appraisal, as well as carbon emissions from aviation. It does this, in part, using a sophisticated modelling suite, to which this work will both relate to, and draw on.

# Background to requirement/OVERVIEW of requirement

## Background to the carbon abatement analysis

## The Government is committed to ensuring the UK aviation sector contributes to help the UK meet its climate change goals. Given its international nature, the government’s emphasis is on taking strong action at a global level as the best means of addressing carbon emissions from aviation. A major agreement was reached in October at the UN’s International Civil Aviation Organization (ICAO) assembly to introduce a global carbon offsetting scheme. The DfT needs to better understand what other measures are available to reduce carbon from within the aviation sector itself.

## This project seeks to build on previous work completed by the DfT in 2011 in response to the Committee on Climate Change’s (CCC) 2009 report on UK Aviation Emissions to estimate the potential for, and cost of, carbon abatement from flights within and departing from the UK. Whilst the 2011 work is a useful basis for our current project, technology, cost and abatement potential data has developed since then. The purpose of this project is to update the list of available abatement measures (including identification of any additional measures) and assess (and where applicable refresh) their costs and abatement potential. The 2011 work also included a number of measures that are only practical to implement on an international level. This project’s focus will be on measures that are solely within the control of the UK i.e. that don’t require international agreement.

## Background to the Fleet Mix Model review

## The DfT aviation modelling suite is a well-established and peer reviewed framework used to produce analysis for policy development. The flowchart below shows the various components and dependencies, one of which is the FMM (circled below).

## The methodology underpinning the FMM was previously reviewed in 2010, and the DfT is now undertaking an internal update of the FMM. This will modify some assumptions and inputs. The Potential Provider will be required to carry out a review of this update and comment on its robustness. It is envisaged that the Potential Provider for the Carbon Abatement technical measures analysis work is likely to have the relevant expertise to carry out the FMM review component, but sub-contractors may be employed if this is not the case.

## The FMM predicts the types of aircraft that will be used to meet the passenger demand that is forecast in earlier modelling stages. Some background on the FMM methodology can be found in Chapters 2 and 3 of UK Aviation Forecasts 2013. The 2011 DfT forecasts also contain useful background material on the FMM and CO2 models. The DfT’s latest forecasts of passengers, air transport movements (ATMs) and carbon dioxide emissions (CO2) can be found in the 2013 document.

## The FMM is an excel spreadsheet tool (incorporating Visual Basic Macros) and uses forecasts of ATM’s from the passenger allocation model to forecast the composition of the fleet at UK airports between 2015 and 2055 by:

- using proportional breakdown of UK ATMs by aircraft type, carrier type and seat class; and

- utilising data about retirement of old aircraft and their replacement in the fleet by new aircraft types.

## The composition of aircraft types is forecast for six different seat classes (aircraft size bands) and three carrier types (full service, low cost and charter). This results in a total of 18 individual models. The FMM is designed primarily to deal with passenger aircraft.

# definitions

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## APF | ## DfT’s Aviation Policy Framework |
| ## AvAM | ## Aviation Appraisal and Modelling – the aviation analysis team at DfT that is commissioning this work |
| ## CCC | ## Committee on Climate Change |
| ## DfT | ## Department for Transport |
| ## DfT Aviation Model | ## DfT’s modelling suite used for forecasting factors relating to the UK aviation sector including passenger demand, airline fleet composition and carbon emissions |
| ## FMM | ## (DfT) Fleet Mix Model |
| ## GMBM | ## Global Market Based Measure |
| ## ICAO | ## International Civil Aviation Authority |
| ## MACCs | ## Marginal abatement cost curves that present the cost and cumulative abatement potential of carbon reduction measures. |
| ## Non-technical Potential Provider | ## The Potential Provider responsible for delivering the project examining non-technical measures. See definition of non-technical measure below |
| ## Non-technical measures | ## For the purposes of this aviation MACC work as a whole, carbon abatement measures have been split into two groups for potentially two different Potential Providers to analyse – ‘technical’ and ‘non-technical’. Non-technical measures include: demand management, air traffic management improvements, consumer offsetting, biofuels and other measures that don’t relate to technical aircraft design or operation. |
| ## Technical Potential Provider | ## The Potential Provider responsible for delivering the project examining technical measures. See definition of technical measure below. |
| ## Technical Measures | ## For the purposes of this aviation MACC work as a whole, carbon abatement measures have been split into two groups for potentially two different Potential Providers to analyse - ‘technical’ and ‘non-technical’. Technical measures include improvements to engine and aircraft design to improve fuel efficiency as well as operational measures that are within the control of the airline such as load weight and flight trajectories |
| ## UK aviation | ## Commercial flights within the UK and departing from the UK. |

# scope of requirement

## The main requirement of the project is to critically assess the relevant assumed carbon efficiency measures in the DfT model baseline, and identify a series of technical measures to further reduce carbon emissions from within the UK aviation sector, including the identification of any barriers to their uptake in practice. This should include measures that are within the control of the UK and do not require international agreement. They should be described clearly in a project report, alongside the private and social costs of the measure, and any benefits in addition to the carbon savings, monetised wherever possible using the Department’s appraisal guidance. The estimates and final report should be quality assured to a level agreed with the DfT project officer before being submitted to the DfT.

## The quantified estimates of carbon savings and net costs should be in such a form as to enable the DfT to create a set of MACCs that illustrate the cost and cumulative abatement potential of measures to reduce UK aviation emissions out to 2050. This means that any interactions between measures should be highlighted. For example, one measure might have a constant cost per tonne of carbon saved, whereas other measures may cost less (more) per tonne of carbon saved if they are implemented before (after) another measure.

## The analysis for this, the technical measures project, will involve five tasks:

### critical assessment of the assumed carbon efficiency measures relevant to this specification in the DfT model baseline, along with justification for any proposed improvements; identification of the potential measures that could be used to help deliver emission reductions from within the aviation sector, with an emphasis on those that can be implemented most effectively at a UK level;

### once the baseline and measures are agreed with the DfT project officer, estimation of the potential level of emissions savings that each measure might deliver, having taken account of any barriers (as agreed with the DfT project officer) to realising the full technical potential and potential carbon leakage;

### estimation of the total (social) cost and any other benefits to the UK associated with each measure, in order to determine the relative cost-effectiveness (in terms of cost per tonne of CO2 saved) of the different measures;

### scenario analysis to provide a range of potential costs and benefits under different situations; and

### production of a full report detailing the analysis and work that has been carried out.

## Additionally, the Potential Provider will be required to produce a report which details the peer review of the DfT’s Fleet Mix Model which has been carried out. This should cover the elements specified in section 6.28 shown below.

# The requirement

## Task 1: Assessment of Baseline and Definition of Additional Policy Measures

## The intention of this exercise is to consider a wide range of potential measures in addition to those in the DfT baseline, in order to ensure that the analysis identifies the most cost-effective options for reducing emissions from aviation. UK emissions are defined as those from commercial flights departing UK airports, including domestic flights. The DfT baseline assumes aviation’s continuing inclusion in the EU Emissions Trading System (EU ETS) or similar emissions trading arrangement, a gradual improvement in fleet efficiency, and some use of biofuels over the longer term. The specification of the model baseline will be discussed at the initial project meeting and the Potential Provider should assess whether the relevant (technical) assumptions in the baseline continue to be reasonable. Low, medium and high impact scenarios analysed in the later task should be considered in comparison to the baseline.

## The DfT will provide the Potential Provider with a list of technical measures (attached at annex A) that could be implemented unilaterally within the UK which the Potential Provider can use as a starting point for the project. The Potential Provider is invited to include in their bid comments on, and amendments or additions to the measures listed. The final list of measures to be assessed will be agreed in the initial project meetings.

## The DfT will be able to provide specific policy detail in the initial project meetings as required to inform cost calculations for each of the measures. This could include, for example, potential ways to implement each measure, possible barriers or suggestions of policies which are unlikely to be considered implementable.

## For your bid submission please discuss each of the measures on the list. This is not an exhaustive list and additionally identified measures can also be included. This will be carried out in conjunction with the DfT project officer and the Potential Provider is required to:

### Provide a description of the measure and whether it reduces emissions through improvements to airframe and engine technology or operational improvements;

### Explain how it could be implemented by the UK unilaterally;

### Identify who would be responsible for implementing and monitoring the measure (e.g. DfT, CAA, airlines);

### Suggest the timeframe associated with each measure e.g. if it were implemented today, would emissions savings be achieved straight away, or would they increase over time? How long would it take for the measure to reach its maximum effectiveness? (Completion of the subsequent tasks may be required to provide specific answers to these questions);

### Identify any pre-requisites or barriers to the adoption of the measure e.g. requires industry agreement to implement effectively; and

### Carefully consider the level of potential carbon leakage which could occur from each measure. Carbon leakage occurs when emissions reductions at the national level do not lead to emissions reductions globally. Where relevant to the measure in question, the Potential Provider should provide a qualitative assessment of the potential level of carbon leakage and the impact on the total potential carbon abatement of that measure.

## Once the measures have been defined and fully agreed with the DfT Project Officer, the key tasks identified separately below will be required. It would be expected that the following tasks would need to be undertaken concurrently, due to the potential interaction between tasks.

## Task 2: Assessment of Potential Emissions Savings

## For each measure defined for Task 1, the Potential Provider is required to assess the potential CO2 emissions savings from that measure in 2020, 2030, 2040 and 2050, under each scenario (scenarios A to G identified in table 1, over and above the emissions savings in the DfT aviation model baseline. The Potential Provider will be able to request runs from the DfT aviation models as necessary to an agreed timescale in order to help with this task – the Potential Provider is not expected to produce their own model of the UK aviation sector. However, the Potential Provider will be required to generate the necessary assumptions to input into the DfT model. For example, the DfT model is able to forecast emissions savings up to 2050 from a given improvement in fuel efficiency for given generations and models of aircraft, or from a given impact on demand. The Potential Provider would be required to determine the improvement in fuel efficiency, or impact on demand implied by a given carbon reduction measure, which could then be fed into the model as changes in the rate of fuel burn for particular aircraft, or changes in the number of passengers.

## Task 3: Assessment of Costs and Benefits

## The costs (private and social) and any benefits of the measures, in addition to the carbon savings, should be presented separately. These should include the impact on air quality, non-CO2 emissions, noise and so on, consistent with the Department’s transport appraisal guidance. This should enable the Potential Provider is to assess the cost-effectiveness of each measure, measured as the cost per tonne of CO2 saved, as well as the Net Present Value (NPV) of each measure (the present value of the benefits minus the present value of the costs).

## DfT will then use this NPV along with the carbon emissions savings estimated in Task 2 to calculate the cost effectiveness of each measure. This will be calculated as:

## Cost Effectiveness= Net Present ValueCarbon Emissions Saving

## Costs and benefits should be presented separately so that measures that are within the control of airlines, such as airframe retrofitting and accelerated fleet turnover can also be assessed in terms of their financial cost and expressed as the financial cost per tonne of CO2. This will enable the DfT to determine what measures industry might choose to implement itself, if, for example, the price of kerosene or carbon were to rise significantly.

## In assessing the costs it will be important for the bidders to consider the barriers to take up that might exist and the costs of overcoming them. As part of their tender the bidders should propose the method they would use to value this cost. The Potential Provider should also consider potential overlap between measures and place careful consideration on the order in which measures are calculated and presented.

## The Potential Provider will be required to share with DfT copies of all data, analytical workings, spreadsheets and models which are used to carry out the analysis. The data should be provided in a form which is compliant with the existing DfT aviation models and can be used as an additional input. The exact form of this will be discussed in initial project meetings and throughout the project.

## Task 4: Scenario Analysis

## DfT will ultimately be responsible for producing the set of MACCs but the technical Potential Provider will be required to contribute information for this relating to the measures they have analysed. This includes the costs of the measures and the emissions savings. The format of these MACC inputs will be discussed at the initial project meetings and should be agreed with the DfT project officer.

## DfT recognises that there is far greater uncertainty surrounding the estimates of cost and abatement potential of measures further into the future. All assumptions and sources of data should be clearly noted in the final report.

## For each measure, DfT will require a central, lower and upper estimate of the breakdown of values which comprise the Net Present Value of implementing the measure and the abatement potential of measures to reduce emissions from UK aviation to 2050, in order to generate the MACCs. Specifically, the DfT anticipate that the inputs defined below will be required. The key consideration is that the MACC inputs represent a reasonably robust central case and capture the full extent of the uncertainty around the cost and abatement potential of different measures to reduce emissions from UK aviation out to 2050.

## Some measures may be able to deliver different amounts of emissions savings depending on how they are implemented, either by government or by industry. For example, early fleet retirement could be done by the airline industry or regulated by the government to achieve different levels of impact. We therefore envisage that there should be three ambition scenarios demonstrating a low, central and high level of ambition (hereafter termed “low”, “central” and “high” ambition scenarios) associated with each measure. Despite this scenario approach, the assumptions used for each measure will still be based on a subjective assessment of what is considered to be realistic under each scenario, and should therefore be agreed with the DfT project officer before a full assessment is undertaken.

## Further uncertainty derives from the projected values of the input assumptions, such as GDP or fossil fuel prices, out to 2050. The full set of input assumptions to be amended, and their values, should be agreed in advance with the DfT project officer. It is proposed that for the central ambition scenario only, two additional sets of input assumptions should be agreed that represent the full range of uncertainty.

## To encompass the full range of uncertainty, two further sets of MACC inputs should be produced that assume a) the low ambition scenario and b) the high ambition, scenario and again, the appropriate values for the input assumptions to encompass the full set of potential results.

## Table 1 below sets out the set of MACCs that the DfT intends to produce from the analysis provided by the Potential Provider.

## Table 1: Proposed set of MACC s

| ## MACC input set (including abatement and cost) | ## Ambition scenario | ## Input assumptions e.g. fuel prices1 | ## Comment |
| --- | --- | --- | --- |
| ## A | ## Low | ## Central | ## Reflects ambition uncertainty |
| ## B | ## Central | ## Central |  |
| ## C | ## High | ## Central |  |
| ## D | ## Central | ## Low | ## Reflects input assumption uncertainty |
| ## E | ## Central | ## High |  |
| ## F | ## Low | ## Low | ## Reflects the full range of uncertainty |
| ## G | ## High | ## High |  |

## Note: The fuel price assumptions refer to DECC’s published fossil fuel price scenarios to 2050

## Additionally, from a subset of the data provided, the DfT will produce a set of MACCs taking account of the private costs and benefits only. This will be used to inform what measures might be taken up voluntarily by the industry in response to different scenarios, e.g. fuel or carbon price rises.

## These 7 sets of MACC input assumptions are required for 2020, 2030, 2040 and 2050. This is intended to inform the extent to which different measures could be utilised over time (in terms of the date they should be introduced, whether individual measures should be introduced gradually and the speed of any ramping up of measures), consistent with the estimate of cost-effectiveness for 2050.

## DfT should be provided with all the data used to generate the results of the project, including those provided for inclusion in the MACC tool, all spreadsheets, input assumptions and a record of the source of all the data used. The Potential Provider must make clear where any data used is confidential. The spreadsheets should be quality checked by the Potential Provider before submission to the DfT, and should be provided separately to the analytical reports.

## Task 5 – Producing a full report

## The technical Potential Provider is required to produce a report and provide inputs to the MACCs being developed by DfT. The report must include:

### an executive summary;

### the description of the measures from Task 1;

### an explanation of the methodology and assumptions used; and

### the results of the assessment of abatement potential, cost-effectiveness and NPV for each measure under each of the input assumption and measure ambition scenarios considered.

## The draft report should be revised following any comments from DfT, and will not be considered finalised until agreed with the DfT project officer.

## The report must be clearly written in a way that is easily accessible to a non-technical audience as far as is possible. Technical jargon and terminology must be fully explained, and plain English must be used throughout. We intend to publish the final report on the DfT website.

## Task 6 - Reviewing the data and assumptions in the FMM

## The methodology underpinning the FMM was last reviewed as part of a wider review by QinetiQ into Future Aircraft Fuel Efficiencies in 2010. Chapter 2 of the QinetiQ report summarises the existing methodology and the review that took place in 2010. Chapter 6 of the same document describes some of the changes made to the calculations that were recommended to improve overall accuracy. The FMM review element of this contract should repeat much of the analysis described in this document.

## Bidders are welcome to subcontract this task if they do not feel they have the expertise in this area.

## The following table shows the most significant model inputs or assumptions that have been updated in the model. Only the model inputs (including parameter assumptions) have been changed as part of this update and not the modelling methodology itself.

## Table 2: FMM updated items/assumptions

| ## Updated item | ## Description and assumptions | ## Source |
| --- | --- | --- |
| ## Base year (2015) aircraft supply pool | ## UK based ATMs per aircraft type (e.g. Airbus A300-600 or Boeing 747-700) from across major UK airports segmented by seat class and carrier type | ## CAA Airport Stats (2015) ## Data has been assembled |
| ## Aircraft specific information | ## Whether in production or not ## Assumed phase out year ## Assumed typical retirement age | ## Airline order books ## Aircraft manufacturer ## In some cases adopted from existing FMM |
| ## Base year aircraft age | ## Age distribution of all individual aircraft types in current fleet | ## CAA 2015 ATM data – averaged across tail numbers across thirty years |
| ## Replacement aircraft supply pool | ## Known and generic future aircraft types ## Population (based on manufacturing assumptions) of future fleet composition | ## Internal analysis using QinetiQ report and airline order books. |
| ## Output weighted ATM | ## Weighted ATMs 2015-2050 (Proportion of aircraft types comprising all carrier types) | ## Model calculations. |
| ## New assumption – ## Few ATMs | ## Any existing aircraft type with combined UK ATMs in 2015 of under 1000 is ignored | ## N/A |
| ## New assumption – ## Retirement age | ## Typical retirement age of 22 years for Scheduled and Low Cost Carriers and 25 years for Charter reused, except when better and freely accessible information available | ## QinetiQ report |

## The purpose of the independent peer review is to produce a report that addresses the following tasks:

### Set out the level of assurance that the DfT can attach to changes that we have made to inputs, including parameter assumptions, as part of our internal update (as shown in table 2 above).

### Review the appropriateness (fit-for-purpose) of the existing methodology and inform the future direction of any update that could be made to the methodology.

### Provide suggestions to improve the Excel interface (not necessarily the methodology underlying it) and the supplied draft documentation with the intention of improving end-user experience (likely to be analysts working within DfT).

# key PROJECT milestones

## Carbon abatement analysis

## The Potential Provider should note the following fixed project milestones that the Authority will measure the quality of delivery against:

| ### Milestone | ### Description | ### Deliverables | ### Timeframe |
| --- | --- | --- | --- |
| ### 1 | ### Specification of the abatement measures and a detailed critical assessment of the current DfT baseline, along with any suggested improvements as set out in Task 1 above. | ### List of measures and brief summary of details; written recommendations on any suggested changes to the baseline as set out in Task 1 above, to be agreed with the DfT Project Officer | ### 31st March ### 2017 |
| ### 2 | ### Assessment of potential emissions savings and NPV calculations, as described in Tasks 2 and 3 above. ### Provision of the inputs required to enable the DfT to produce the MACCs, as specified in Task 4 above. | ### Excel file with data tables showing cost and abatement potential for each measure under each scenario set out above. Must be in format suitable for use as input to DfT MACC tool. | ### 30th June 2017 |
| ### 3 | ### Completion of technical measures report | ### Full report completed and agreement with the DfT Project Officer that it meets agreed objective. | ### 31st July 2017 |

## Fleet Mix Model review

## Tenderers should note the following project milestones that the Authority will measure the quality of delivery against:

| ### Milestone | ### Description | ### Timeframe |
| --- | --- | --- |
| ### 1 | ### Peer reviewer to be supplied with an up-to-date copy of the model and draft documentation, as specified in Task 6 above. | ### 15th March 2017 |
| ### 2 | ### Peer reviewer to provide a draft peer review document | ### 15th April 2017 |
| ### 3 | ### Final peer review document | ### 28th April 2017 |

# authority’s responsibilities

## Once a Potential Provider is decided, a DfT official will be in charge of the day-to-day running and project management of the contract. They will be the first point of contact in the case of any potential disputes, with support from other senior DfT officials as required.

# reporting

## Four formal meetings are anticipated; an inception meeting at the start, two meetings during Tasks 2 and 3, and a final meeting near the end of the project. Additional informal meetings may be arranged as required, including teleconferences.

## The Potential Provider will be expected to maintain contact with the DfT, including updates on their progress by phone once every two weeks or more often as required.

## The Potential Provider will be expected to share information with the Potential Provider of the Non-Technical Contract CCCC16B05.

# volumes

## This work is expected to be completed within 5 months from award of Contract.

# continuous improvement

## The Potential Provider will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

## Wherever practicable, the Potential Provider should present new ways of working to the Authority during monthly Contract review meetings if there is an opportunity for improved efficiency and/or effectiveness in the way the relationship is managed or the requirements are delivered.

## Proposed changes to the way in which the Services are to be delivered must be brought to the Authority’s attention and agreed prior to any changes being implemented.

## It may become necessary to revise the tasks tendered and contracted or to extend the contract. The DfT project officer will consult with the Potential Provider and the DfT contract office.

## Delivery of the agreed work will be monitored as required by telephone and email discussions with the project officer.

# Sustainability

## Not applicable.

# quality

## The Potential Providers submissions will be expected to provide full confidence to the DfT that they are capable of carrying out the work to the high quality expected. The DfT places a high importance on the quality assurance of our analysis and that done by any Potential Providers. Potential Providers should follow the Department’s Analytical Assurance Framework when carrying out their work and specify in their bid how they will incorporate this throughout the analysis.

# PRICE

## The budget set for this project is to be capped at £80,000 (excluding VAT), including the FMM elements and inclusive of expenses.

## Prices are to be submitted via the e-Sourcing Suite in Appendix E, excluding VAT. See Appendix D for evaluation criteria.

# STAFF AND CUSTOMER SERVICE

## The Authority requires the Potential Provider to provide a sufficient level of resource throughout the duration of the Aviation MACC Technical Measures Requirements Contract in order to consistently deliver a quality service to all Parties.

## Potential Provider’s staff assigned to the Aviation MACC Technical Measures Requirements Contract shall have the relevant qualifications and experience to deliver the Contract.

## The Potential Provider shall ensure that staff understand the Authority’s vision and objectives and will provide excellent customer service to the Authority throughout the duration of the Contract.

# service levels and performance

## DfT expects the analysis produced to be reliable, thorough and of a high quality. Close communication throughout the project and clear initial requirements will enable early identification of any potential issues, allowing for them to be easily resolved.

## Once milestones and deadlines are agreed, DfT expects the Potential Provider to meet them. Any delays may result in payment being withheld until tasks are completed to a sufficient standard.

# Security requirements

## The DfT takes data security extremely seriously and applies agreed government security procedures to all Contracts involving the handling of data and ‘Official Sensitive’ and ‘Commercial Sensitive’ information.

## Potential Providers will be conducting their own analysis, using outputs from DfT models provided by DfT officials where necessary. Therefore, there are not considered to be any security requirements.

# intellectual property rights (ipr)

## The Intellectual Property Rights on all work undertaken under this contract, including to the project reports and any spreadsheets developed will be in line with the contracts standard terms and conditions.

## The Potential Provider should not under any circumstances publish any results from the DfT aviation model. These remain the property of the Crown and should only be used in order to complete this project. Once the project is completed, the Potential Provider should delete any outputs provided by the DfT to prevent future misuse. The winning Potential Provider will be expected to complete a Non-Disclosure Agreement NDA as part of this work.

## The contract should include a license to use any data provided under this project in any revised versions of the model, and DfT will retain the right to publish any reports and results of the model or subsequent versions.

# payment

## Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables, as agreed by the DfT Project Officer

## Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

## Payments will be made as follows:

### 20% once the finalised FMM review report is received to the satisfaction of the DfT (FMM milestone 3).

### 25% on formal agreement of the measures to be assessed and completion of the written critical assessment of the baseline (milestone 1).

### 40% once the MACC inputs and emissions calculations are received to the satisfaction of the DfT (Carbon abatement analysis milestone 2).

### 15% once a finalised version of the project report is received to a standard that DfT are content with (Carbon abatement analysis milestone 3).

# additional information

## This contract may require experts from more than one organisation. Proposed partners should be named as part of any proposal.

# Location

## The main base location for the project and any joint meetings will be the offices of the Authority (Department for Transport, Great Minster House, 33 Horseferry Road, London, SW1P 4DR)

## Services will also be carried out at a range of other premises including:

- The offices of the Potential Provider

- The offices of the relevant company

- Any other location as required

## Any costs incurred by the Potential Provider in travelling to or from the offices of the Authority are to be borne solely by the Potential Provider and included as part of their price submission. Any costs associated with travel to other locations will be subject to the Department for Transport’s standard Travel and Subsistence arrangements.

# Annex A: List of Proposed Measures

## This annex contains a list of the measures proposed by DfT to be evaluated for their carbon abatement potential. It is not exhaustive and should only be used as a guide. Additional measures are encouraged in bids, as well as reasons why suggested measures may not be feasible. This document contains lists of both technical and non-technical measures but contracts will be awarded separately. Both types are included to give examples of the types of measures which would fall into each category.

## Non-Technical Measures - The following table sets out the non-technical and operational measures to be considered, along with potential policy levers which could be used to implement them and any additional notes for consideration. These relate to measures which can be carried out to encourage behavioural changes, improvements in operational efficiency and the use of biofuels.

### Table 1: Non-Technical Measures

| Measure | Possible Policy Levers |
| --- | --- |
| Advances in communication technology and demand management, e.g. increased use of video conferencing resulting in fewer business flights. | Government finance to promote video-conferencing Information campaigns to raise awareness of CO2 footprints Targets to reduce company flights |
| Air traffic management, e.g. incentives to reduce stacking of planes waiting to land. | Financial incentives to encourage airports to land planes sooner Airport regulation to enforce |
| Consumer offsetting, e.g. option to donate to a charity which reduces the impact of carbon emissions when purchasing the flight. | Measures to encourage passengers to offset carbon at point of purchase, including nudging |
| Changes to flight paths and take-off and landing trajectories. | Financial incentives for airlines to use more efficient routes Green slots, eligible only to those who meet certain efficiency standards |
| More efficient ground movements, e.g. more electric power whilst taxiing. | Airport regulation |
| Increased use of biofuels, e.g. mandating a certain proportion of biofuels must be used when departing from UK airports. | Government funding support Regulation or voluntary agreements to mandate or incentivise biofuels / low carbon fuels uptake R&D funding for biofuel / low carbon fuels supply chain developments |

## Technical Measures - The following table sets out the technical measures to be evaluated, along with potential policy levers which could be used to implement them and any other additional notes. These relate to measures which could be carried out to alter the engine design, encourage fleet retrofitting and other aeroplane operational improvements.

### Table 2: Technical Measures

| Measure | Possible Policy Levers |
| --- | --- |
| Accelerating the development of more fuel efficient aircraft | Green slots Financial incentives |
| Bringing forward the development of more fuel efficient engines | Green slots Financial incentives |
| Retrofitting | Green slots Financial incentives |
| Incentives to increase R&D in mode efficient engines and aircraft | Financial incentives and funding |
| Operational measures that are within the control of the airlines, such as flight speed and altitude, and reduced cabin weight | Financial incentives Regulation |

## Proposed MACC Scenarios

### The following table presents the scenarios for marginal abatement cost curves this research is aiming to calculate. This should be used as a guide to reflect the range of potential scenarios and should not be considered as a complete or fixed list.

### Table 3: Proposed set of MACC inputs

| #### MACC input set (including abatement and cost) | #### Ambition scenario | #### Input assumptions e.g. fuel prices1 | #### Comment |
| --- | --- | --- | --- |
| A | Low | Central | Reflects ambition uncertainty |
| B | Central | Central |  |
| C | High | Central |  |
| D | Central | Low | Reflects input assumption uncertainty |
| E | Central | High |  |
| F | Low | Low | Reflects the full range of uncertainty |
| G | High | High |  |

Note 1: The fuel price assumptions refer to DECC’s published fossil fuel price scenarios to 2050, available through https://www.gov.uk/government/publications/fossil-fuel-price-projections-2015

http://www.icao.int/environmental-protection/Documents/ActionPlan/UK_AbatementModel_en.pdf

https://www.theccc.org.uk/publication/meeting-the-uk-aviation-target-options-for-reducing-emissions-to-2050/

## https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/223839/aviation-forecasts.pdf

WebTAG, available here: https://www.gov.uk/guidance/transport-analysis-guidance-webtag

For further information on the DfT aviation models, see DfT (January 2009), UK Aviation Forecasts, available at https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/223839/aviation-forecasts.pdf.

Available at http://www.dft.gov.uk/webtag/index.php.

https://www.gov.uk/government/publications/fossil-fuel-price-projections-2015

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/4515/future-aircraft-fuel-efficiency.pdf

Information on DfT’s Analytical assurance Framework can be found here: https://www.gov.uk/government/publications/dft-analytical-assurance-framework-strength-in-numbers