3

NEC Engineering and Construction Short Contract

The NEC3 Engineering and Construction Short Contract is an alternative to 
NEC3 Engineering and Construction Contract and is for use with contracts 
which do not require sophisticated management techniques, comprise 
straightforward work and impose only low risks on both the Employer 
and the Contractor

An NEC document

June 2005 (with amendments September 2011and April 2013)

|  | OGC endorsement of NEC3 |
| --- | --- |
|  | OGC advises public sector procurers that the form of contract used has to be selected according to the objectives of the project, aiming to satisfy the Achieving Excellence in Construction (AEC) principles. |
|  | This edition of the NEC (NEC3) complies fully with the AEC principles. OGC recommends the use of NEC3 by public sector construction procurers on their construction projects. |
|  | OGC logo |

|  | NEC is a division of Thomas Telford Ltd, which is a wholly owned subsidiary of the Institution of Civil Engineers (ICE), the owner and developer of the NEC. |
| --- | --- |
|  | The NEC is a family of standard contracts, each of which has these characteristics: |
|  | - Its use stimulates good management of the relationship between the two parties to the contract and, hence, of the work included in the contract. |
|  | - It can be used in a wide variety of commercial situations, for a wide variety of types of work and in any location. |
|  | - It is a clear and simple document -- using language and a structure which are straightforward and easily understood. |
|  | NEC3 Engineering and Construction Short Contract is one of the NEC family and is consistent with all other NEC3 documents. Also available are the Engineering and Construction Short Contract Guidance Notes and Flow Charts. |
|  | ISBN (complete box set) 0 7277 3382 6 |
|  | ISBN (this document) 0 7277 3372 9 |
|  | ISBN (Engineering and Construction Short Contract Guidance Notes and Flow Charts) 0 7277 3373 7 |
|  | First edition 1999 |
|  | Second edition June 2005 |
|  | © Cover photo, Golden Jubilee Bridge, courtesy of City of Westminster |
|  | 9 8 7 6 5 4 3 2 1 |
|  | British Library Cataloguing in Publication Data for this publication is available from the British Library. |
|  | Copyright nec 2005 |
|  | All rights, including translation, reserved. The owner of this document may reproduce the Contract Data for the purpose of obtaining tenders, awarding and administering contracts. Except as permitted by the Copyright, Designs and Patents Act 1988, no part of this publication may be otherwise reproduced, stored in a retrieval system or transmitted in any form or by any means, electronic, mechanical, photocopying, recording or otherwise, without the prior written permission of the NEC Director, NEC, Thomas Telford Ltd, 1 Heron Quay, London E14 4JD. |
|  | Typeset by Academic + Technical, Bristol |
|  | Printed and bound in Great Britain by Bell & Bain Limited, Glasgow, UK |

ACKNOWLEDGEMENTS

|  | The first edition of the NEC Engineering and Construction Short Contract was produced by the Institution of Civil Engineers through its NEC Panel. It was mainly drafted by Dr Martin Barnes, Tom Nicholson and Nigel Shaw based on work by Andrew Baird with the assistance of Peter Higgins and advice from Professor Phillip Capper of Masons Solicitors and David Maidment of Willis Corroon Construction Risks Ltd. Contributions were also made by Ross Hayes and Jon Broome of the University of Birmingham. |  |
| --- | --- | --- |
|  | The second edition of the NEC Engineering and Construction Short Contract was mainly drafted by Professor J. G. Perry with the assistance of members of the NEC Panel. The Flow Charts were produced by Robert Gerrard with assistance from Ross Hayes and Tom Nicholson. |  |
|  | The original NEC was designed and drafted by Dr Martin Barnes then of Coopers and Lybrand with the assistance of Professor J. G. Perry then of The University of Birmingham, T. W. Weddell then of Travers Morgan Management, T. H. Nicholson, Consultant to the Institution of Civil Engineers, A. Norman then of the University of Manchester Institute of Science and Technology and P. A. Baird, then Corporate Contracts Consultant, Eskom, South Africa. |  |
|  | The members of the NEC Panel are: |  |
|  |  | P. Higgins, BSc, CEng, FICE, FCIArb (Chairman) |
|  |  | P. A. Baird, BSc, CEng, FICE, M(SA)ICE, MAPM |
|  |  | M. Barnes, BSc(Eng), PhD, FREng, FICE, FCIOB, CCMI, ACIArb, MBCS, FInstCES, FAPM |
|  |  | A. J. Bates, FRICS, MInstCES |
|  |  | A. J. M. Blackler, BA, LLB(Cantab), MCIArb |
|  |  | P. T. Cousins, BEng(Tech), DipArb, CEng, MICE, MCIArb, MCMI |
|  |  | L. T. Eames, BSc, FRICS, FCIOB |
|  |  | F. Forward, BA(Hons), DipArch, MSc(Const Law), RIBA, FCIArb |
|  |  | Professor J. G. Perry, MEng, PhD, CEng, FICE, MAPM |
|  |  | N. C. Shaw, FCIPS, CEng, MIMechE |
|  |  | T. W. Weddell, BSc, CEng, DIC, FICE, FIStructE, ACIArb |
|  | NEC Consultant: |  |
|  |  | R. A. Gerrard, BSc(Hons), MRICS, FCIArb, FInstCES |
|  | Secretariat: |  |
|  |  | A. Cole, LLB, LLM, BL |
|  |  | J. M. Hawkins, BA(Hons), MSc |
|  |  | F. N. Vernon (Technical Adviser), BSc, CEng, MICE |

| # 3 |  |  | # Engineering and Construction |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| ## Short Contract |  |  |  |  |  |  |
| A contract between |  |  |  |  |  |  |
| and |  |  |  |  |  |  |
| for |  |  |  |  |  |  |
|  | #### Contents |  |  |  | #### Page |  |
|  | Contract Forms |  |  |  |  |  |
|  |  | Contract Data |  |  | 2 |  |
|  |  |  |  | The Contractor’s Offer | 4 |  |
|  |  |  |  | The Employer’s Acceptance | 4 |  |
|  |  |  |  | Price List | 5 |  |
|  |  |  |  | Works Information | 6 |  |
|  |  |  |  | Site Information | 9 |  |
|  | Conditions of Contract |  |  |  | CC1 |  |
|  | Notes about this Contract are printed in boxes like this one. They are not part of the contract. |  |  |  |  |  |

| # Contract Data |  |  |  |
| --- | --- | --- | --- |
|  | The Employer is |  |  |
| ### Name |  |  |  |
| Address |  |  |  |
| Telephone | Fax |  |  |
| E-mail address |  |  |  |
| ### The works are | …………………………………………………………………………... …………………………………………………………………………... |  |  |
| The site is | …………………………………………….… |  |  |
| The starting date is | ………………………………………………. |  |  |
| The completion date is | ………………………………………………. |  |  |
| The period for reply is |  |  | weeks. |
| The defects date is | ………………………………………………. |  | weeks after Completion. |
| The defect correction period is | ………………………………………………. |  | weeks. |
| ### The delay damages are | ………………………………………………. |  | per day. |
| The assessment day is the | ………………………………………………. |  | of each month. |
| The retention is | ………………………………………………. |  | %. |
| Does the United Kingdom Housing Grants, Construction and Regeneration Act (1996) as amended by the Local Democracy, Economic Development and Construction Act 2009 apply? |  | Yes / No (delete as appropriate) |  |
|  | The Adjudicator is |  |  |
| ### Name |  |  |  |
| Address |  |  |  |
| Telephone | ……………………………………… Fax ..………………..………………………….. |  |  |
| E-mail address | ………………………………………………………………………….…………………. |  |  |
| 1 |  |  |  |

| # Contract Data |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| The interest rate on late payment is …………………………………… % per complete week of delay. |  |  |  |  |  |  |
|  |  |  | Insert a rate only if a rate less than 0.5% per week of delay has been agreed. |  |  |  |
| The Contractor is not liable to the Employer for loss of or damage to the Employer’s |  |  |  |  |  |  |
| property in excess of |  | ……………………………………………………….. for any one event. |  |  |  |  |
| The Employer provides this insurance |  | Only enter details here if the Employer is to provide insurance. |  |  |  |  |
|  |  | ……………………………………………………………………………………………… …………………………………………………………………………… |  |  |  |  |
| The minimum amount of cover for the third insurance stated in the |  |  |  |  |  |  |
| Insurance Table is |  | ……………………………….……………………………………………………………. |  |  |  |  |
| The minimum amount of cover for the fourth insurance stated in the |  |  |  |  |  |  |
| Insurance Table is |  | ……………………………………….……………………………………………………... |  |  |  |  |
| The Adjudicator nominating body is |  | ……………………………………….……………………………………………………... |  |  |  |  |
| The tribunal is |  | ……………………………………………………………………………………………… |  |  |  |  |
| If the tribunal is arbitration, the arbitration procedure is |  | ……………………………………………………………………………………………… |  |  |  |  |
| The conditions of contract are the NEC3 Engineering and Construction Short Contract (June 2005 with amendments September 2011) and the following additional conditions |  |  |  |  |  |  |
| Only enter details here if additional conditions are required. |  |  |  |  |  |  |
| ……………………………………………………………………………………………………………………………………………… Z clauses Z1 to Z17 inclusive |  |  |  |  |  |  |
| ………………………………………………………………………………………………… |  |  |  |  |  |  |
| ……………………………………………………………………………………………………………………………………………… |  |  |  |  |  |  |
| ……………………………………………………………………………………………………………………………………………… |  |  |  |  |  |  |
| ………………………………………………………………………………………………………………………………………………. |  |  |  |  |  |  |
| ………………………………………………………………………………………………………………………………………………. |  |  |  |  |  |  |
| ……………………………………………………………………………………………………………………………………………… |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |

| # Contract Data |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| The Contractor’s Offer |  |  |  |  |  |  |
| The Contractor is |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |
| Address |  |  |  |  |  |  |
| Telephone |  | ………………………………. Fax ………………………………………… |  |  |  |  |
| E-mail address |  |  |  |  |  |  |
| The percentage for overheads and profit added to the Defined Cost for people is %. The percentage for overheads and profit added to other Defined Cost is %. |  |  |  |  |  |  |
| The Contractor offers to Provide the Works in accordance with the conditions of contract for an amount to be determined in accordance with the conditions of contract. |  |  |  |  |  |  |
| The offered total of the Prices is |  |  |  |  |  |  |
|  | Enter the total of the Prices from the Price List. |  |  |  |  |  |
| Signed on behalf of the Contractor |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |
| Position |  |  |  |  |  |  |
| Signature |  |  | Date |  |  |
| # The Employer’s Acceptance |  |  |  |  |  |  |
| The Employer accepts the Contractor’s Offer to Provide the Works Signed on behalf of the Employer |  |  |  |  |  |  |
| Name |  |  |  |  |  |
| Position |  |  |  |  |  |
| Signature |  |  | Date |  |  |
| 3 |  |  |  |  |  |  |

| # Contract Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Price List |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Entries in the first four columns in this Price List are made either by the Employer or the tenderer. If the Contractor is to be paid an amount for the item which is not adjusted if the quantity of work in the item changes, the tenderer enters the amount in the Price column only; the Unit, Quantity and Rate columns being left blank. If the Contractor is to be paid an amount for the item of work which is the rate for the work multiplied by the quantity completed, the tenderer enters the rate which is then multiplied by the expected quantity to produce the Price, which is also entered. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Item number |  | Description |  |  |  | Unit |  |  | Quantity | Rate |  |  | Price |  |  |  |
|  |  |  |  |  |  | The total of the Prices |  |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # Contract Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| # Works Information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | The Works Information should be a complete and precise statement of the Employer’s requirements. If it is incomplete or imprecise there is a risk that the Contractor will interpret it differently from the Employer’s intention. Information provided by the Contractor should be listed in the Works Information only if the Employer is satisfied that it is required, is part of a complete statement of the Employer’s requirements and is consistent with the other parts of the Works Information. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 Description of the works |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Give a detailed description of what the Contractor is required to do and of any work the Contractor is to design. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 Drawings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | List the drawings that apply to this contract. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Drawing number |  | Revision |  | Title |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |

| # Contract Data |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| # Works Information |  |  |  |  |  |
| 3 Specifications |  |  |  |  |  |
|  | List the specifications which apply to this contract. |  |  |  |  |
|  | Title |  | Date or revision | Tick if publicly available |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
|  | …………………………………………… |  | ……………………….. | ……………………………… |  |
| 4 Constraints on how the Contractor Provides the Works |  |  |  |  |  |
|  | State any constraints on the sequence and timing of work and on the methods and conduct of work including the requirements for any work by the Employer. |  |  |  |  |
| 6 |  |  |  |  |  |

| # Contract Data |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # Works Information |  |  |  |  |  |  |  |  |  |  |
| 5 Requirements for the programme |  |  |  |  |  |  |  |  |  |  |
|  | State whether a programme is required and, if it is, state what form it is to be in, what information is to be shown on it, when it is to be submitted and when it is to be updated. State what the use of the works is intended to be at their Completion as defined in Clause 11.2(1). |  |  |  |  |  |  |  |  |  |
| 6 Services and other things provided by the Employer |  |  |  |  |  |  |  |  |  |  |
|  | Describe what the Employer will provide, such as services (including water and electricity) and “free issue” Plant and Materials and equipment. |  |  |  |  |  |  |  |  |  |
|  | - Item |  |  |  |  | Date by which it will be provided |  |  |  |  |
|  |  |  | 7 |  |  |  |  |  |  |  |

| # Contract Data |  |  |  |
| --- | --- | --- | --- |
| # Site Information |  |  |  |
|  | Give information about the site such as the ground conditions and any other information which is likely to affect the Contractor’s work such as limitations on access and the position of adjacent structures. |  |  |
| 8 |  |  |  |

3 Engineering and Construction Short Contract

CONDITIONS OF CONTRACT

1 General

| Actions |  | 10 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | 10.1 |  |  | The Employer and the Contractor shall act as stated in this contract and in a spirit of mutual trust and co-operation. |  |
| Identified and defined |  | 11 |  |  |  |  |
| terms |  | 11.1 |  |  | In the conditions of contract, terms identified in the Contract Data are in italics and defined terms have capital initials. |  |
|  |  | 11.2 |  |  | (1) Centre for Civil Society means Centre for Civil Society Limited registered company in England (Company Number 07333734) whose registered office is at 136 Cavell Street, London, E1 2JA. |  |
|  |  |  |  |  | (2) Certified Ethical Labour provider means a labour provider who meets the qualifying requirements of a Certified Ethical Labour Scheme and who is verified, at or within six months (or such longer period as the Employer may agree, acting reasonably) of the starting date , by a competent and independent third party as meeting such qualifying requirements. |  |
|  |  |  |  |  | (3) Certified Ethical Labour Scheme means any of the following |  |
|  |  |  |  |  | - the BRE Ethical Labour Sourcing standard BES 6002 ("BRE Standard"). |  |
|  |  |  |  |  | - the Clearview Global Labour Provider Certification Scheme ("Clearview Scheme") |  |
|  |  |  |  |  | - an alternative standard or scheme, which in the reasonable opinion of the Employer, is an acceptable substitute to the BRE Standard or Clearview Scheme ("Alternative Labour Scheme"). |  |
|  |  |  |  |  | and references to the BRE Standard, Clearview Scheme and Alternative Labour Scheme are to such standard or schemes as updated from time to time. |  |
|  |  |  |  |  | (4) Completion is when the Contractor has completed the works in accordance with the Works Information except for correcting notified Defects which do not prevent the Employer from using the works and others from doing their work. |  |
|  |  |  |  |  | (5) The Completion Date is the completion date unless later changed in accordance with this contract. |  |
|  |  |  |  |  | (6) Connected Persons means all and any of the Contractor's employees, directors, contractors, agents, Subcontractors, suppliers, shareholders, professional advisors (including lawyers, auditors, financial advisers, accountants and technical consultants) or underwriters. |  |
|  |  |  |  |  | (7) Data Controller has the meaning given to it in the Data Protection Legislation, noting that under the General Data Protection Legislation this would be using the definition of "Controller". |  |
|  |  |  |  |  | (8) Data Processor has the meaning given to it in the Data Protection Legislation, noting that under the General Data Protection Legislation this would be using the definition of "Processor". |  |
|  |  |  |  |  | (9) Data Protection Impact Assessment means a process used to identify and mitigate the privacy and data protection risks associated with an activity involving the Processing of Personal Data. |  |
|  |  |  |  |  | (10) Data Protection Legislation means: - any legislation in force from time to time in the United Kingdom which implements the European Community's Directive 95/46/EC and Directive 2002/58/EC, including but not limited to the Data Protection Act 1998 and the Privacy and Electronic Communications (EC Directive) Regulations 2003; - from 25 May 2018 only, the General Data Protection Regulations; - any other legislation in force from time to time in the United Kingdom relating to privacy and/or the Processing of Personal Data; and any statutory codes of practice issued by the Information Commissioner in relation to such legislation. |  |
|  |  |  |  |  | (11) Data Protection Officer has the meaning set out in the Data Protection Legislation. |  |
|  |  |  |  |  | (12) Data Subject means has the meaning given to it in the Data Protection Legislation. |  |
|  |  |  |  |  | (13) A Defect is a part of the works which is not in accordance with the Works Information or is not in accordance with the applicable law or other requirements of this contract. |  |
|  |  |  |  |  | (14) The Defects Certificate is either a list of notified Defects which the Contractor has not corrected by the defects date or a statement that there are no such Defects. |  |
|  |  |  |  |  | (15) Defined Cost is the amount paid by the Contractor in Providing the Works (excluding any tax which the Contractor can recover) for |  |
|  |  |  |  |  | - people employed by the Contractor, |  |
|  |  |  |  |  | - Plant and Materials, |  |
|  |  |  |  |  | - work subcontracted by the Contractor and |  |
|  |  |  |  |  | - Equipment. |  |
|  |  |  |  |  | The amount for Equipment includes amounts paid for hired Equipment and an amount for the use of Equipment owned by the Contractor which is the amount the Contractor would have paid if the Equipment had been hired. |  |
|  |  |  |  |  | (16) Documentation means all documents, items of information, data, reports, drawings, specifications, plans, software, designs, inventions and/or other material produced or supplied by or on behalf of the Contractor in the performance of the contract. |  |
|  |  |  |  |  | (17) [Employer Data means all data, text, drawings, diagrams, images or sounds (together with any database made up of any of these) which are embodied in any media (including without limitation electronic, magnetic, optical and tangible media) and which are supplied to the Contractor by or on behalf of the Employer and any IPR relating to the same which are vested in the Employer.] |  |
|  |  |  |  |  | (18) Employer Personal Data means Personal Data and/or Sensitive Personal Data Processed by the Contractor (including any Subcontractor and Indirect Subcontractor) on behalf of the Employer, pursuant to or in connection with the contract as set out in the Processing Statement. |  |
|  |  |  |  |  | (19) Equipment is items provided by the Contractor, used by him to Provide the Works and not included in the works. |  |
|  |  |  |  |  | (20) Fair Processing Notice means such information as the Employer deems reasonably necessary to comply with its legal obligations in terms of fair, lawful and transparent Processing under the Data Protection Legislation. |  |
|  |  |  |  |  | (21) FOI Legislation means the Freedom of Information Act 2000, all regulations made under it and the Environmental Information Regulations 2004 and any amendments or re-enactment of any of them; and any guidance issued by the Information Commissioner, the Department of Constitutional Affairs or the Department for Environment Food and Rural Affairs (including in each case its successors or assigns) in relation to such legislation. |  |
|  |  |  |  |  | (22) GLA Act means the Greater London Authority Act 1999. |  |
|  |  |  |  |  | (23) Indirect Subcontractor means any subcontractor or subconsultant of whatever tier beneath any Subcontractor appointed in relation to the works. |  |
|  |  |  |  |  | (24) Information means information recorded in any form held by or on behalf of the Employer. |  |
|  |  |  |  |  | (25) Information Request means a request for any Information under the FOI Legislation. |  |
|  |  |  |  |  | (26) IPR means intellectual property rights including patents, trade marks, service marks, trade names, design rights, copyright (including rights in computer software and databases), moral rights, rights in know-how, rights in domain names and other intellectual property rights (including any professional, manufacturer's or supplier's warranties and/or indemnities) in each case whether registered or unregistered and including, applications for the grant of any such rights and all rights or forms of protection having equivalent or similar effect anywhere in the world. |  |
|  |  |  |  |  | (27) London Living Wage means the London rate for the basic hourly wage as updated and published annually by the Living Wage Foundation (or any relevant replacement organisation) on its website (www.livingwage.org.uk), |  |
|  |  |  |  |  | (28) Mayor means the person from time to time holding the office of Mayor of London as established by the GLA Act. |  |
|  |  |  |  |  | (29) The Parties are the Employer and the Contractor. |  |
|  |  |  |  |  | (30) Personal Data has the meaning given to it in the Data Protection Legislation. |  |
|  |  |  |  |  | (31) Plant and Materials are items intended to be included in the works. |  |
|  |  |  |  |  | (32) The Price for Work Done to Date is the total of |  |
|  |  |  |  |  | - the Price for each lump sum item in the Price List which the Contractor has completed and |  |
|  |  |  |  |  | - where a quantity is stated for an item in the Price List, an amount calculated by multiplying the quantity which the Contractor has completed by the rate. |  |
|  |  |  |  |  | (33) The Prices are the amounts stated in the Price column of the Price List. Where a quantity is stated for an item in the Price List, the Price is calculated by multiplying the quantity by the rate. |  |
|  |  |  |  |  | (34) Processing has the meaning given to it in the Data Protection Legislation. |  |
|  |  |  |  |  |  | (35) Processing Statement is in the form set out in Schedule [ ] of this contract. |
|  |  |  |  |  |  | (36) To Provide the Works means to do the work necessary to complete the works in accordance with this contract and all incidental work, services and actions which this contract requires. |
|  |  |  |  |  |  | (37) Responsible Procurement Principles means the seven principles of responsible procurement more particularly described in the GLA Group Responsible Procurement Policy dated March 2006, as updated in January 2008 and as may be further updated from time to time. |
|  |  |  |  |  |  | (38) Restricted Countries means any country outside the European Economic Area as may be constituted from time to time by the UK. |
|  |  |  |  |  |  | (39) Sensitive Personal Data means sensitive or special categories of Personal Data including criminal allegations, offences and outcomes data (as defined in the Data Protection Legislation) which is Processed pursuant to or in connection with this contract. |
|  |  |  |  |  |  | (40) Site Information is information which describes the site and its surroundings and is in the document called ‘Site Information’. |
|  |  |  |  |  |  | (41) Standards means the following standards listed in order of priority with a lower ranking standard only applicable where a higher ranking standard is not applicable |
|  |  |  |  |  |  | - First: European Standards, which means those standards ratified by the European Committee for Standardization (CEN) of Avenue Marnix 17, B-1000 Brussels, Belgium. |
|  |  |  |  |  |  | - Second: International Standards, which means those standards produced by the International Standards Organisation (IS) 1, ch. De la Voie-Creuse, CP 56, CH-1211 Geneva 20 Switzerland, and associated codes of practice. |
|  |  |  |  |  |  | (42) Statutory Undertaker means any governmental or local authority or statutory undertaker |
|  |  |  |  |  |  | - which has any jurisdiction with regard to the works including any jurisdiction to control development of the Site or any part of it |
|  |  |  |  |  |  | - with whose requirements the Employer is accustomed to comply; or |
|  |  |  |  |  |  | - with whose systems and/or utilities the works will be connected. |
|  |  |  |  |  |  | (43) A Subcontractor is a person or organisation who has a contract with or is appointed by the Contractor (including any contract which has been novated to the Contractor) to |
|  |  |  |  |  |  | - construct, design or install part of the works |
|  |  |  |  |  |  | - provide a service necessary to Provide the Works or |
|  |  |  |  |  |  | - supply Plant and Materials which the person or organisation has wholly or partly designed specifically for the works. |
|  |  |  |  |  |  | (44) Subject Access Request means a request made by a Data Subject to access his or her own Personal Data in accordance with rights granted in Data Protection Legislation. |
|  |  |  |  |  |  | (45) Works Information is information which either |
|  |  |  |  |  |  | - specifies and describes the works or |
|  |  |  |  |  |  | - states any constraints on how the Contractor Provides the Works |
|  |  |  |  |  |  | and is either |
|  |  |  |  |  |  | - in the document called ‘Works Information’ or |
|  |  |  |  |  |  | - in an instruction given in accordance with this contract. |
|  |  |  |  |  |  | (46) CDM Regulations are the Construction (Design and Management) Regulations 2015 and any amendment, consolidation, revision and/or replacement thereto and related code of practice together with any requirements issued from time to time by the Health and Safety Executive. |
| Law |  |  | 12 |  |  |  |
|  |  |  | 12.1 |  |  | This contract is governed by the law of the country where the site is. |
|  |  |  | 12.2 |  |  | No change to this contract, unless provided for by the conditions of contract, has effect unless it has been agreed, confirmed in writing and signed by the Parties. |
|  |  |  | 12.3 |  |  | This contract is the entire agreement between the Parties. |
| Communications |  |  | 13 |  |  |  |
|  |  |  | 13.1 |  |  | Each communication which this contract requires has effect when it is received in writing at the last address notified by the recipient for receiving communications. |
|  |  |  | 13.2 |  |  | If this contract requires the Employer or the Contractor to reply to a communication, unless otherwise stated in this contract, he replies within the period for reply. |
| The Employer’s authority |  |  | 14 |  |  |  |
| and delegation |  |  | 14.1 |  |  | The Contractor obeys an instruction which is in accordance with this contract and is given to him by the Employer. |
|  |  |  | 14.2 |  |  | The Employer may give an instruction to the Contractor which changes the Works Information. |
|  |  |  | 14.3 |  |  | The Employer’s acceptance of a communication from the Contractor or of his work does not change the Contractor’s responsibility to Provide the Works or his liability for his design. |
|  |  |  | 14.4 |  |  | The Employer, after notifying the Contractor, may delegate any of the Employer’s actions and may cancel any delegation. A reference to an action of the Employer in this contract includes an action by his delegate. |
| Access to the site and |  |  | 15 |  |  |  |
| provision of services |  |  | 15.1 |  |  | The Employer allows access to and use of the site to the Contractor as necessary for the work included in this contract. |
|  |  |  | 15.2 |  |  | The Employer provides services and other things as stated in the Works Information. |
| Early warning |  |  | 16 |  |  |  |
|  |  |  | 16.1 |  |  | The Contractor and the Employer give an early warning by notifying the other as soon as either becomes aware of any matter which could |
|  |  |  |  |  |  | - increase the total of the Prices, |
|  |  |  |  |  |  | - delay Completion or |
|  |  |  |  |  |  | - impair the performance of the works in use. |
|  |  |  |  |  |  | The Contractor may give an early warning by notifying the Employer of any other matter which could increase his total cost. Early warning of a matter for which a compensation event has previously been notified is not required. |
|  | 16.2 |  |  | The Contractor and the Employer co-operate in making and considering proposals for how the effect of each matter which has been notified as an early warning can be avoided or reduced and deciding and recording actions to be taken. |  |  |

2 The Contractor’s main responsibilities

| Providing the Works | 20 |  |
| --- | --- | --- |
|  | 20.1 | The Contractor Provides the Works in accordance with this contract and the Works Information. |
|  | 20.2 | The Contractor does not start work which the Contractor has designed until the Employer has accepted that the design complies with the Works Information. |
|  | 20.3 | The Contractor designs the parts of the works which the Works Information states he is to design in accordance with the requirements stated in this contract and the Works Information. |
|  | 20.4 | In designing those parts of the works for which it has design responsibility as detailed in the Works Information the Contractor shall use all the reasonable skill, care and diligence normally used by an appropriate and competent professional designer experienced in carrying out design works similar to those included in the works in connection with projects of a similar size, scope and complexity to the works to ensure that its design complies with the Works Information. |
|  | 20.5 | (1) Subject to the Works Information and any changes to it the Contractor warrants that to the extent the Contractor either is obliged to specify or approve products or materials for use in the works or does so specify or approve, the Contractor does not specify, approve or use any products or materials which are generally known within the construction industry to be deleterious at the time of use in the particular circumstances in which they are used, or those identified as potentially hazardous in or not in conformity with: (a) the guidance published by the British Council for Offices and the British Property Federation current at the time of undertaking the works entitled “Good Practice in the Selection of Construction Materials”, (b) relevant British or European Standards or Codes of Practice, or (c) any publications of the Building Research Establishment related to the specification of products or materials. (2) If in the performance of its duties under this contract, the Contractor becomes aware that he or any other person has specified or used, or authorised or approved the specification or use by others of, any such products or materials, the Contractor notifies the Employer in writing immediately. This clause does not create any additional duty for the Contractor to inspect or check the work of others which is not required by this contract. |
| Subcontracting and | 21 |  |
| people | 21.1 | If the Contractor subcontracts work, he is responsible for Providing the Works as if he had not subcontracted. |
|  | 21.2 | This contract applies as if a subcontractor’s employees and equipment were the Contractor’s. |
|  | 21.3 21.4 | The Employer may, having stated reasons, instruct the Contractor to remove an employee. The Contractor then arranges that, after one day, the employee has no further connection with the work included in this contract. The Contractor shall demonstrate to the satisfaction of the Employer that it has in place, and shall procure that its Subcontractors shall have in place, appropriate procedures for ensuring the welfare of their respective employees or other persons engaged in the works, including procedures for reporting and handling instances and perceived instances of fraudulent behaviour and procedures protecting whistleblowers. |
|  | 21.5 | On or before the starting date, the Contractor shall notify the Employer of the name, contact details and details of the legal representatives of each Subcontractor and Indirect Subcontractor, to the extent that such information has not already been provided by the Contractor to the Employer under this contract. |
|  | 21.6 | The Contractor shall promptly notify the Employer of any changes to the information notified under clause 21.5 and provides the name, contact details and details of the legal representatives of any Subcontractor who is engaged after the starting date. |
|  | 21.7 | The Contractor shall ensure that each subcontract with a Subcontractor or between a Subcontractor and an Indirect Subcontractor complies with Regulation 113 of the Public Contracts Regulations 2015. |
| Access for the Employer | 22 |  |
|  | 22.1 | The Contractor provides access for the Employer and others notified by the Employer to work being done for this contract and to stored Plant and Materials. |
| CDM Regulations | 23 |  |
|  | 23.1 | The Contractor takes full responsibility for the adequacy, stability and safety of all site operations and methods of construction and complies fully with the requirements of the CDM Regulations, including without limitation those as: - set out in the Works Information; - set out in guidance published by the Health and Safety Executive in relation to the CDM Regulations; - required of a “principal contractor” (where the Contractor is the Principal Contractor); - required of a “contractor” (where the Contractor is not the Principal Contractor); - required of a “principal designer” (where the Contractor is the Principal Designer); and - required where the Contractor is responsible for design, but is not the Principal Designer, a “designer”. For the purpose of this clause 23.1, “principal contractor”, “principal designer”, “contractor” and “designer” are all as defined in the CDM Regulations. |

3 Time

| Starting and Completion | 30 |  |
| --- | --- | --- |
|  | 30.1 | The Contractor does not start work until the starting date and does the work so that Completion is on or before the Completion Date. |
|  | 30.2 | The Contractor submits a forecast of the date of Completion to the Employer each week from the starting date until Completion. |
|  | 30.3 | The Employer decides the date of Completion and certifies it to the Contractor within one week of the date. |
|  | 30.4 | The Employer may instruct the Contractor to stop or not to start any work and may later instruct him to re-start or start it. |
| The programme | 31 |  |
|  | 31.1 | The Contractor submits programmes to the Employer as stated in the Works Information. |

4 Defects

| Searching for and | 40 |  |
| --- | --- | --- |
| notifying Defects | 40.1 | Until the defects date, the Employer may instruct the Contractor to search for a Defect. |
|  | 40.2 | The Employer may notify a Defect to the Contractor at any time before the defects date. |
| Correcting Defects | 41 |  |
|  | 41.1 | The Contractor corrects a Defect whether or not the Employer notifies him of it. |
|  | 41.2 | Before Completion, the Contractor corrects a notified Defect before it would prevent the Employer or others from doing their work. |
|  | 41.3 | After Completion, the Contractor corrects a notified Defect before the end of the defect correction period. This period begins at the later of Completion and when the Defect is notified. |
|  | 41.4 | The Employer issues the Defects Certificate to the Contractor at the later of the defects date and the end of the last defect correction period. |
| Uncorrected Defects | 42 |  |
|  | 42.1 | If the Contractor has not corrected a notified Defect within its defect correction period, the Employer assesses the cost of having the Defect corrected by other people and the Contractor pays this amount. |
| Repairs | 43 |  |
|  | 43.1 | Until the Defects Certificate has been issued and unless otherwise instructed by the Employer, the Contractor promptly replaces loss of and repairs damage to the works, Plant and Materials. |

5 Payment

| Assessing the amount | 50 |  |
| --- | --- | --- |
| due | 50.1 | The Contractor assesses the amount due and, by each assessment day, applies to the Employer for payment. There is an assessment day in each month from the starting date until the month after the Defects Certificate has been issued. |
|  | 50.2 | The Contractor’s application for payment includes details of how the amount has been assessed. The first application for payment is for the amount due. Other applications are for the change in the amount due since the previous payment. |
|  | 50.3 | The amount due is |
|  |  | - the Price for Work Done to Date |
|  |  | - plus other amounts to be paid to the Contractor (including any tax which the law requires the Employer to pay to the Contractor) |
|  |  | - less amounts to be paid by or retained from the Contractor. |
|  | 50.4 | The Employer corrects any wrongly assessed amount due and notifies the Contractor of the correction before paying the Contractor. |
|  | 50.5 | The Contractor pays delay damages for each day from the Completion Date until Completion. |
|  | 50.6 | An amount is retained from the Contractor in the assessment of each amount due until Completion. This amount is the retention applied to the Price for Work Done to Date. The amount retained is halved in the first assessment made after Completion and remains at this amount until the assessment day after the Defects Certificate is issued. No amount is retained in the assessment made after the Defects Certificate has been issued. |
|  | 50.7 | If the Employer requires a programme to be submitted, one quarter of the Price for Work Done to Date is retained in assessments of the amount due until the Contractor has submitted a first programme to the Employer showing the information which the Works Information requires. |
| Payment | 51 |  |
|  | 51.1 | The Employer pays within three weeks after the next assessment day which follows receipt of an application for payment by the Contractor. |
|  | 51.2 | Interest is paid if a payment is late or includes a correction of an earlier payment. Interest is assessed from the date by which the correct payment should have been made until the date when it is paid. Interest is calculated at the rate stated in the Contract Data or, if none is stated, at 0.5% of the delayed amount per complete week of delay. |

6 Compensation events

| Compensation events | 60 |  |
| --- | --- | --- |
|  | 60.1 | The following are compensation events. |
|  |  | (1) The Employer gives an instruction changing the Works Information unless the change is in order to make a Defect acceptable. |
|  |  | (2) The Employer does not allow access to and use of the site to the Contractor as necessary for the work included in this contract. |
|  |  | (3) The Employer does not provide something which he is to provide by the date for providing it stated in this contract. |
|  |  | (4) The Employer gives an instruction to stop or not to start any work. |
|  |  | (5) The Employer does not work within the conditions stated in the Works Information. |
|  |  | (6) The Employer does not reply to a communication from the Contractor within the period required by this contract. |
|  |  | (7) The Employer changes a decision which he has previously communicated to the Contractor. |
|  |  | (8) The Employer instructs the Contractor to search for a Defect and no Defect is found. |
|  |  | (9) The Contractor encounters physical conditions which |
|  |  | - are within the site, |
|  |  | - are not weather conditions and |
|  |  | - an experienced contractor would have judged, at the date of the Contractor’s Offer, to have such a small chance of occurring that it would have been unreasonable to have allowed for them. |
|  |  | Only the difference between the physical conditions encountered and those for which it would have been reasonable to have allowed is taken into account in assessing a compensation event. |

|  |  |  |  | (10) The Contractor is prevented by weather from carrying out all work on the site for periods of time, each at least one full working day, which are in total more than one seventh of the total number of days between the starting date and the Completion Date. In assessing this event, only the working days which exceed this limit and on which work is prevented by no other cause are taken into account. |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | (11) The Employer notifies a correction to an assumption which he has stated about a compensation event. |  |  |
|  |  |  |  | (12) An event which |  |  |
|  |  |  |  | - stops the Contractor completing the works or |  |  |
|  |  |  |  | - stops the Contractor completing the works by the Completion Date |  |  |
|  |  |  |  | and which |  |  |
|  |  |  |  | - neither Party could prevent, |  |  |
|  |  |  |  | - an experienced contractor would have judged at the date of the Contractor’s Offer to have such a small chance of occurring that it would have been unreasonable for him to have allowed for it and |  |  |
|  |  |  |  | - is not one of the other compensation events stated in this contract. |  |  |
|  |  |  |  | (13) A difference between the final total quantity of work done and the quantity stated for an item in the Price List. |  |  |
|  |  |  |  | (14) A loss of or damage to the works, Plant and Materials which |  |  |
|  |  |  |  | - is not the fault or responsibility of the Contractor or |  |  |
|  |  |  |  | - could not have been prevented by any reasonable action of the Contractor. |  |  |
|  | 60.2 |  |  | In judging the physical conditions for the purposes of assessing any compensation event, the Contractor is assumed to have taken into account |  |  |
|  |  |  |  | - the Site Information, |  |  |
|  |  |  |  | - publicly available information referred to in the Site Information, |  |  |
|  |  |  |  | - information obtainable from a visual inspection of the site and |  |  |
|  |  |  |  | - other information which an experienced contractor could reasonably be expected to have or to obtain. |  |  |
| Notifying compensation | 61 |  |  |  |  |  |
| events | 61.1 |  |  | The Contractor notifies the Employer of an event which has happened or which he expects to happen as a compensation event if |  |  |
|  |  |  |  | - the Contractor believes that the event is a compensation event and |  |  |
|  |  |  |  | - the Employer has not notified the event to the Contractor. |  |  |
|  |  |  |  | If the Contractor does not notify a compensation event within eight weeks of becoming aware of the event he is not entitled to a change in the Prices or Completion Date unless the event arises from an instruction of the Employer. |  |  |
|  | 61.2 |  |  | If the Employer decides that an event notified by the Contractor |  |  |
|  |  |  |  | - arises from a fault of the Contractor, |  |  |
|  |  |  |  | - has not happened and is not expected to happen, |  |  |
|  |  |  |  | - has no effect upon the Defined Cost or upon Completion or |  |  |
|  |  |  |  | - is not one of the compensation events stated in this contract, |  |  |
|  |  |  |  | he notifies the Contractor of his decision that the Prices and the Completion Date are not to be changed. |  |  |
|  |  |  |  | If the Employer decides otherwise, he instructs the Contractor to submit a quotation for the event. The Employer notifies the decision to the Contractor or instructs the Contractor to submit a quotation within one week of the Contractor’s notification to the Employer of the event. |  |  |
|  | 61.3 |  |  | If the Employer decides that the Contractor did not give an early warning of the event which the Contractor could have given, the Employer notifies that decision to the Contractor when instructing the Contractor to submit a quotation. |  |  |
|  |  |  | 61.4 |  |  | If the Employer decides that the effects of a compensation event are too uncertain to be forecast reasonably, the Employer states assumptions about the event when instructing the Contractor to submit a quotation. Assessment of the event is based on these assumptions. If any of them is later found to have been wrong, the Employer notifies a correction. |
|  |  |  | 61.5 |  |  | A compensation event is not notified after the defects date. |
| Quotations for |  |  | 62 |  |  |  |
| compensation events |  |  | 62.1 |  |  | A quotation for a compensation event comprises proposed changes to the Prices or rates and any delay to the Completion Date assessed by the Contractor. The Contractor submits details of his assessment with each quotation. The Contractor submits a quotation within two weeks of being instructed to do so by the Employer or, if no such instruction is received, within two weeks of the notification of a compensation event. |
|  |  |  | 62.2 |  |  | The Employer may instruct the Contractor to submit a quotation for a proposed instruction or a proposed changed decision. The Contractor does not put a proposed instruction or a proposed changed decision into effect. |
|  |  |  | 62.3 |  |  | The Employer replies within two weeks of the Contractor’s submission. |
|  |  |  |  |  |  | For a proposed instruction or proposed changed decision, the Employer’s reply is |
|  |  |  |  |  |  | - notification that the proposed instruction will not be given or the proposed changed decision will not be made, |
|  |  |  |  |  |  | - notification of the instruction or changed decision as a compensation event and acceptance of the quotation or |
|  |  |  |  |  |  | - notification of the instruction or changed decision as a compensation event and notification that the Employer does not agree with the quotation. |
|  |  |  |  |  |  | For other compensation events, the Employer’s reply is |
|  |  |  |  |  |  | - acceptance of the quotation or |
|  |  |  |  |  |  | - notification that the Employer does not agree with the quotation. |
|  |  |  | 62.4 |  |  | If the Employer does not agree with the quotation, the Contractor may submit a revised quotation within two weeks of the Employer’s reply. If the Employer does not agree with the revised quotation or if none is received, the Employer assesses the compensation event and notifies the assessment. |
|  |  |  | 62.5 |  |  | After discussing with the Contractor different ways of dealing with the compensation event which are practicable, the Employer may instruct the Contractor to submit alternative quotations for a compensation event. |
| Assessing compensation |  |  | 63 |  |  |  |
| events |  |  | 63.1 |  |  | For a compensation event which only affects the quantities of work shown in the Price List, the change to the Prices is assessed by multiplying the changed quantities of work by the appropriate rates in the Price List. |
|  |  |  | 63.2 |  |  | For other compensation events, the changes to the Prices are assessed by forecasting the effect of a compensation event upon the Defined Cost or, if the compensation event has already occurred, the assessment is based upon the Defined Cost due to the event which the Contractor has incurred. Effects on Defined Cost are assessed separately for |
|  |  |  |  |  |  | - people employed by the Contractor, |
|  |  |  |  |  |  | - Plant and Materials, |
|  |  |  |  |  |  | - work subcontracted by the Contractor and |
|  |  |  |  |  |  | - Equipment. |
|  |  |  |  |  |  | The Contractor shows how each of these effects is built up in each quotation for a compensation event. The percentages for overheads and profit stated in the Contractor’s Offer are applied to the assessed effect of the event on the Defined Cost. |
|  |  | 63.3 |  |  | The effects of compensation events upon the Defined Cost are assessed at open market or competitively tendered prices with deductions for all discounts, rebates and taxes which can be recovered. The following are deducted from the Defined Cost for the assessment of compensation events |  |
|  |  |  |  |  | - the cost of events for which this contract requires the Contractor to insure and |  |
|  |  |  |  |  | - other costs paid to the Contractor by insurers. |  |
|  |  | 63.4 |  |  | A delay to the Completion Date is assessed as the length of time that, due to the compensation event, Completion is forecast to be delayed. |  |
|  |  | 63.5 |  |  | If the Employer has decided and notified the Contractor that the Contractor did not give an early warning of a compensation event which an experienced contractor could have given, the event is assessed as if the Contractor had given early warning. |  |
|  |  | 63.6 |  |  | Assessment of the effect of a compensation event includes risk allowances for cost and time for matters which are at the Contractor’s risk under this contract. |  |
|  |  | 63.7 |  |  | Assessments are based on the assumptions that the Contractor reacts competently and promptly to the compensation event and that any additional cost and time due to the event are reasonably incurred. |  |
|  |  | 63.8 |  |  | A compensation event which is an instruction to change the Works Information in order to resolve an ambiguity or inconsistency is assessed as if the Prices and the Completion Date were for the interpretation most favourable to the Party which did not provide the Works Information. |  |
|  |  | 63.9 |  |  | The assessment of a compensation event is not revised if a forecast upon which it is based is shown by later recorded information to have been wrong. |  |

7 Title

| Objects and materials | 70 |  |
| --- | --- | --- |
| within the site | 70.1 | The Contractor has no title to an object of value or of historical or other interest within the site. The Contractor does not move such an object unless instructed to do so by the Employer. |
|  | 71 | [Not Used] |
| Anti-Corruption | 72 |  |
|  | 72.1 | Unless defined elsewhere in this contract, the defined terms have the meaning set out below: Anti-Bribery Laws means any and all statutes, statutory instruments, bye laws, orders, directives, treaties, decrees and laws (including any common law, judgement, demand, order or decision of any court, regulator or tribunal) which relates to anti-bribery and/or anti-corruption, including the Bribery Act 2010 as amended. |
|  | 72.2 | The Contractor shall, and shall procure that its officers, employees, agents and any other persons who perform the works for or on behalf of it in connection with this contract shall: - comply with all applicable Anti-Bribery Laws; - not offer, promise, give, request, agree to receive, receive or accept a bribe or financial or other advantage or commit any corrupt act; - not do or omit to do any act or thing which constitutes or may constitute an offence under Anti-Bribery Laws; - not do or omit to do any act or thing which causes or may cause the Contractor to be in breach of and/or to commit an offence under any Anti-Bribery Laws; - the above, not do or omit to do any act or thing which causes or may cause the Contractor to be guilty of an offence under section 7 Bribery Act (or would or may do so if the Contractor was unable to prove that it had in place adequate procedures designed to prevent persons associated with it from undertaking such conduct); and - provide the Employer with such reasonable assistance as it may require from time to time to enable it to perform any activity required by any relevant government or agency in any relevant jurisdiction for the purpose of compliance with any Anti-Bribery Laws. |
|  | 72.3 | - The Contractor shall: - promptly report to the Employer any request or demand for any financial or other advantage of any kind received in connection with the performance of this contract by it or by its officers, employees, agents or any other person who performs the works for or on behalf of it in connection with this contract; and - upon request, certify to the Employer in writing signed by a director of the Contractor that the Contractor has complied with all of its obligations under this Clause 79 The Contractor shall provide such supporting evidence of compliance as the Contractor may request. |
|  | 72.4 | The Contractor shall immediately give written notice to the Employer upon a breach, or suspected breach, of any of its obligations at this Clause 72.4 occurring. |
|  | 72.5 | Without prejudice to Clause 72.4, the Contractor shall immediately give written notice to the Employer of any financial or other advantage, inducement or reward it has given or intends to give (whether directly or through any third party) to any person (including any employee of the Employer and/or the Employer) in connection with the awarding or continuation in force of this contract. |
|  | 72.6 | The Contractor shall keep, for a minimum of six years and at its normal place of business, detailed, accurate and up to date records and books of account showing all payments made and received and all other advantages given and received by the Contractor in connection with this contract and the steps taken by the Contractor to comply with Anti-Bribery Laws. The Contractor shall ensure that those records and books of account are sufficient to enable the Employer to verify the Contractor’s compliance with this Clause 72.6. |
|  | 72.7 | - The Contractor shall permit the Employer and any person nominated by it for this purpose, to have such access on demand to the Contractor ‘s premises, personnel, systems, books and records as the Contractor may require to verify the Subcontractor’s compliance with this Clause 72. |
|  | 72.8 | The Employer may terminate this contract immediately by giving written notice to that effect to the Subcontractor if the Subcontractor is in breach of any of its obligations under this Clause 72 or if the Employer has reasonable cause to believe that such a breach has occurred or may occur. |
|  | 72.9 | If the Employer terminates this contract in accordance with Clause 72.8, the Contractor shall not be entitled to claim compensation or any further remuneration from the Employer, regardless of any activities carried out or agreements with third parties entered into before termination. |
|  | 72.10 | The Employer shall be entitled, by giving written notice to that effect to the Contractor to require the Contractor to remove from the performance of this contract any of the Contractor’s officers, employees or agents in respect of whom the Contractor is in breach of any of its obligations or warranties under Clause 72. |
|  | 72.11 | The Contractor shall indemnify, keep indemnified and hold harmless the Employer in full and on demand from and against all liabilities (including any tax liability), direct, indirect and consequential losses, damages, claims, proceedings and legal costs (on an indemnity basis), judgments and costs (including costs of enforcement) and expenses which the Employer incurs or suffers directly or indirectly in any way whatsoever as a result of any proceedings under section 7 Bribery Act being brought against the Contractor as a result of the conduct of the Employer or any of its officers, employees, agents or any other persons who perform the works for or on behalf of it in connection with this contract, where such proceedings do not result in a conviction against the Employer, including the costs of procuring the Contract Works from a person other than the Contractor (including the costs of interim service provision, the costs of any re-tender and the amount by which any new supplier’s prices exceed the Charges payable to the Contractor under this contract). |
|  | 72.12 | The Contractor shall procure that its sub-contractors comply with the provisions of clause 72. |
| Transparency | 73 |  |
|  | 73.1 | Unless defined elsewhere in this contract, the defined terms have the meaning set out below: Contract Information (i) this contract is its entirety (including from time to time agreed changes to the contract) and (ii) data extracted from the invoices submitted pursuant to Clause 51 which shall consist of the Contractor’s name, the expenditure account code, the expenditure account code description, the clearing date and the invoice amount; Transparency Commitment means the Employer’s commitment to public its contracts, tender documents and data from invoices received in accordance with the Local Government Transparency Code 2015 and the Employer’s own published transparency commitment. |
|  | 73.2 | The Contractor acknowledges that the Employer is subject to the Transparency Commitment. Accordingly, the Contractor hereby gives its consent for the Employer to publish the Contract Information to the general public. |

8 Indemnity, insurance and liability

| Limitation of liability | 80 |  |
| --- | --- | --- |
|  | 80.1 | For any one event, the liability of the Contractor to the Employer for loss of or damage to the Employer’s property is limited to the amount stated in the Contract Data. The Contractor is not liable to the Employer for the Employer’s indirect or consequential loss except as provided for in the conditions of contract. Exclusion or limitation of liability applies in contract, tort or delict and otherwise and to the maximum extent permitted in law. |

| Indemnities | 81 |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 81.1 | The Employer indemnifies the Contractor against claims, proceedings, compensation and costs payable which are the unavoidable result of the works or of Providing the Works or which arise from |  |  |  |
|  |  | - fault, |  |  |  |
|  |  | - negligence, |  |  |  |
|  |  | - breach of statutory duty, |  |  |  |
|  |  | - infringement of an intellectual property or |  |  |  |
|  |  | - interference with a legal right |  |  |  |
|  |  | by the Employer or by a person employed by or contracted to the Employer except the Contractor. |  |  |  |
|  | 81.2 | The Contractor indemnifies the Employer against other |  |  |  |
|  |  | - losses and claims in respect of |  |  |  |
|  |  |  | - death of or injury to a person and |  |  |
|  |  |  | - loss of and damage to property (other than the works, Plant and Materials) and |  |  |
|  |  | - claims, proceedings, compensation and costs payable arising from or in connection with the Contractor’s Providing the Works. |  |  |  |
|  | 81.3 | The liability of one Party to indemnify the other is reduced to the extent that events which are the other Party’s responsibility contributed to the losses, claims, proceedings, compensation and costs. |  |  |  |
| Insurance cover | 82 |  |  |  |  |
|  | 82.1 | The Contractor provides, in the joint names of the Parties and from the starting date, the insurances stated in the Insurance Table. The Contractor does not provide an insurance which the Employer is to provide as stated in the Contract Data. |  |  |  |
|  |  | INSURANCE TABLE |  |  |  |
|  |  | Insurance against |  | Minimum amount of cover or minimum limit of indemnity | Cover provided until |
|  |  | Loss of or damage to the works |  | The replacement cost | The Employer’s certificate of Completion has been issued |
|  |  | Loss of or damage to Equipment, Plant and Materials |  | The replacement cost | The Defects Certificate has been issued |
|  |  | The Contractor’s liability for loss of or damage to property (except the works, Plant and Materials and Equipment) and for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor’s Providing the Works |  | The amount stated in the Contract Data for any one event with cross liability so that the insurance applies to the Parties separately |  |
|  |  | Liability for death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with this contract |  | The greater of the amount required by the applicable law and the amount stated in the Contract Data for any one event |  |
|  | 82.2 | The Contractor does not by any act or fault prejudice or forgot the parties' rights or the right of either of them to make or proceed with a claim against any insurer. |  |  |  |
|  | 82.3 | The insurances provided pursuant to this contract do not relieve the Contractor from any of his obligations and liabilities under this contract. |  |  |  |
|  | 82.4 | The Contractor submits to the Employer upon request evidence that the insurances which the Contractor is required to maintain pursuant to this contract are in force. |  |  |  |

9 Termination and dispute resolution

| Termination and reasons | 90 |  |
| --- | --- | --- |
| for termination | 90.1 | If either Party wishes to terminate the Contractor’s obligation to Provide the Works, he notifies the other Party giving details of his reason for terminating. The Employer issues a termination certificate promptly if the reason complies with this contract. After a termination certificate has been issued, the Contractor does no further work necessary to Provide the Works. |
|  | 90.2 | Either Party may terminate if the other Party has become insolvent or its equivalent (Reason 1). |
|  | 90.3 | The Employer may terminate if the Employer has notified the Contractor that the Contractor has defaulted in one of the following ways and the Contractor has not stopped defaulting within two weeks of the notification. |
|  |  | - Substantially failed to comply with this contract (Reason 2). |
|  |  | - Substantially hindered the Employer (Reason 3). |
|  |  | - Substantially broken a health or safety regulation (Reason 4) - Breached clause 71 and/or 72 (Reason 4A) - Following the occurrence of any of the circumstances described in Regulation 73 (1) of the Public Contracts Regulations 2015 (or any equivalent provisions in the regulations implementing the EU Utilities Directive 2014/25). (Reason 4B), |
|  |  | The Employer may terminate for any other reason (Reason 5). |
|  | 90.4 | The Contractor may terminate if |
|  |  | - the Employer has not made a payment within ten weeks of the assessment day which followed receipt of the Contractor’s application for it (Reason 6) or |
|  |  | - the Employer has instructed the Contractor to stop or not to start any substantial work or all work for a reason which is not the Contractor’s fault and an instruction allowing the work to re-start or start has not been given within eight weeks (Reason 7). |
|  | 90.5 | The Employer may terminate if an event which the Parties could not reasonably prevent has substantially affected the Contractor’s work for a continuous period of more than thirteen weeks (Reason 8). |
| Procedures on | 91 |  |
| termination | 91.1 | On termination, the Employer may complete the works himself or employ other people to do so. The Contractor leaves the site and removes the Equipment. |
| Payment on termination | 92 |  |
|  | 92.1 | The amount due on termination includes |
|  |  | - an amount due assessed as for normal payments, |
|  |  | - the cost of Plant and Materials provided by the Contractor which are on the site or of which the Contractor has to accept delivery and |
|  |  | - any amounts retained by the Employer. |
|  | 92.2 | If the Employer terminates for Reason 1, 2, 3, 4, 4A or 4B the amount due on termination also includes a deduction of the forecast additional cost to the Employer of completing the works. |
|  | 92.3 | If the Contractor terminates for Reason 1, 6 or 7 or if the Employer terminates for Reason 5, the amount due on termination also includes 5% of any excess of a forecast of the amount due at Completion had there been no termination over the amount due on termination assessed as for normal payments. |
| Dispute resolution | 93 |  |
|  | 93.1 | A dispute arising under or in connection with this contract is referred to and decided by the Adjudicator. |
| The Adjudicator | 93.2 | (1) The Parties appoint the Adjudicator under the NEC Adjudicators Contract current at the starting date. The Adjudicator acts impartially and decides the dispute as an independent adjudicator and not as an arbitrator. |

|  |  | (2) If the Adjudicator is not identified in the Contract Data or if the Adjudicator resigns or is unable to act, the Parties choose a new adjudicator jointly. If the Parties have not chosen an adjudicator, either Party may ask the Adjudicator nominating body to choose one. The Adjudicator nominating body chooses an adjudicator within four days of the request. The chosen adjudicator becomes the Adjudicator. |
| --- | --- | --- |
|  |  | (3) The Adjudicator, his employees and agents are not liable to the Parties for any action or failure to take action in an adjudication unless the action or failure to take action was in bad faith. |
| The adjudication | 93.3 | (1) A Party may refer a dispute to the Adjudicator if |
|  |  | - the Party notified the other Party of the dispute within four weeks of becoming aware of it and |
|  |  | - between two and four further weeks have passed since the notification. |
|  |  | If a disputed matter is not notified and referred within the times set out in this contract, neither Party may subsequently refer it to the Adjudicator or the tribunal. |
|  |  | (2) The Party referring the dispute to the Adjudicator includes with his referral information to be considered by the Adjudicator. Any more information is provided within two weeks of the referral. This period may be extended if the Adjudicator and the Parties agree. |
|  |  | (3) The Adjudicator may take the initiative in ascertaining the facts and the law related to the dispute. He may instruct a Party to take any other action which he considers necessary to reach his decision and to do so within a stated time. |
|  |  | (4) A communication between a Party and the Adjudicator is communicated to the other Party at the same time. |
|  |  | (5) If the Adjudicator’s decision includes assessment of additional cost or delay caused to the Contractor, he makes his assessment in the same way as a compensation event is assessed. |
|  |  | (6) The Adjudicator decides the dispute and notifies the Parties of his decision and his reasons within four weeks of the referral. This period may be extended by up to two weeks with the consent of the referring Party, or by any period agreed by the Parties. |
|  |  | If the Adjudicator does not notify his decision within the time allowed, either Party may act as if the Adjudicator has resigned. |
|  |  | (7) Unless and until the Adjudicator has notified the Parties of his decision, the Parties proceed as if the matter disputed was not disputed. |
|  |  | (8) The Adjudicator’s decision is binding on the Parties unless and until revised by the tribunal and is enforceable as a matter of contractual obligation between the Parties and not as an arbitral award. The Adjudicator’s decision is final and binding if neither Party has notified the other within the times required by this contract that he intends to refer the matter to the tribunal. |
| Review by the tribunal | 93.4 | A Party may refer a dispute to the tribunal if |
|  |  | - the Party is dissatisfied with the Adjudicator’s decision or |
|  |  | - the Adjudicator did not notify a decision within the time allowed and a new adjudicator has not been chosen, |
|  |  | except that neither Party may refer a dispute to the tribunal unless they have notified the other Party of their intention to do so not more than four weeks after the end of the time allowed for the Adjudicator’s decision. |

Z clauses

The following additional conditions apply.

| Marketing and Branding | Z1.1 | - Identified and defined terms: - Act: the Olympic Symbol etc (Protection) Act 1995, as amended; - Ambush Marketing: any activity, commercial or non-commercial, undertaken by any person or entity, whether public or private, that creates, implies or refers to a direct or indirect association of any kind (including any association in the minds of members of the public) with the London 2012 Olympic Games, the BOA or Team GB; - BOA: the British Olympic Association; - Brand Manual: the written guidelines prescribing the permitted form and manner in which the Park Name may be used as may be amended by the Employer in writing to the Contractor from time to time; IOC: the International Olympic Committee; - LOCOG: The London Organising Committee of the Olympic Games and Paralympic Games Limited; - London 2012 Games: the Games of the XXX Olympiad held principally in and around London; - Olympic IP: all rights of the BOA and the IOC in relation to the Olympic Word and all other designations, words and logos relating to the Olympic Movement, including anything which is a ‘controlled representation’ or a ‘protected word’ for the purposes of the Act; - Olympic Movement: includes the IOC, the BOA, other National Olympic Committees, LOCOG and any other organising committee of the Olympic Games, any Olympic team and any other person or entity who is recognised by or required to comply with the Olympic Charter (as published by the IOC from time to time); - Olympic Word: the word “Olympic”; Park Name: The Queen Elizabeth Olympic Park; - Protected Marks: any trade mark, trade names, logos or other intellectual property of the BOA and/or the IOC, including marks and designs relating to the London 2012 Games, the Olympic Symbol (i.e. the five interlocking rings of the International Olympic Committee), the Paralympic Symbol (i.e. the three agitos of the International Paralympic Committee), the words "Olympic", "Olympian", "Olympiad", "Paralympic", "Paralympian", "Paralympiad" (and their plurals) and/or any other word(s), motto, symbol or representation protected by the Olympic Symbol etc. (Protection) Act 1995, the London Olympic Games and Paralympic Games Act 2006 (whether as now in force or as amended replaced or substituted in the future) or by any other relevant legislation enacted (whether as now in force or as enacted amended replaced or substituted in the future) in relation to the London 2012 Games; - Rights Owner(s): the BOA, the IOC, any other owner of the Protected Marks, Her Majesty Queen Elizabeth II and the Royal Household; - Site: The Queen Elizabeth Olympic Park, Stratford, London Territory: the United Kingdom of Great Britain and Northern Ireland. |
| --- | --- | --- |
|  | Z1.2 | Clauses Z1 to Z4 define the manner and circumstances in which the Contractor is entitled to make use of the Park Name. The Contractor does not use the Park Name, other than as set out in this clause without the prior written agreement of the Employer. |
|  | Z1.3 | The Contractor uses the Park Name on a non-exclusive and non-transferable basis for the purpose of identifying the location of the Site, subject to the terms and conditions of clauses Z1 to Z4. The rights granted under clauses Z1 to Z4 shall continue for so long as the Employer is entitled to permit the Contractor to use the Park Name upon the terms set out in clauses Z1 to Z4. If the Employer ceases to be so entitled, it notifies the Contractor immediately in writing, explaining the basis on which it has ceased to be so entitled, whereupon all rights and licences granted pursuant to clauses Z1 to Z4 shall cease. The Employer warrants to the Contractor that the Employer is entitled to, as at the date of this contract, grant to the Contractor the rights granted hereunder. |
|  | Z1.4 | - The Contractor does not - use the Olympic Word other than as part of the Park Name, - use the Park Name in stylised or logo form, or giving any particular word or words therein prominence over any other word or words therein, - use the Park Name (or any part of it) as part of any trade name, corporate title or name, or domain name, - produce, market and sell (either itself or through authorised distributors and partners) merchandise to which the Park Name (or any part of it) is applied, - other than using the Park Name in accordance with the terms of clauses Z1 to Z4, use in its business any trade mark which is confusingly similar to the Park Name or Olympic Word or seek to incorporate any other Olympic IP into any name or logo, - sub-license all or any of the rights granted to it under clauses Z1 to Z4 to any third party, without the prior written agreement of the Employer. |
|  | Z1.5 | The Contractor complies with the terms of the Brand Manual regarding its use of the Park Name. |
|  | Z1.6 | When referring to the Park Name, the Contractor refers to the Park Name in full. |
|  | Z1.7 | The Contractor acknowledges that the Employer’s rights in relation to the Park Name are limited to the Territory and that use of the Park Name outside the Territory may be regulated by laws of other countries and the rights of third parties. The Contractor is responsible for obtaining any licences and permissions required to use the Park Name outside the Territory and for paying any associated costs and fees. |
| Advertising Materials and Goodwill | Z2.1 | The Contractor ensures that written materials it uses to advertise, market and promote the works which make use of the Park Name (“Advertising Materials”) do not reduce or diminish the reputation, image and prestige of the Olympic Word or any Rights Owner or of products sold under or by reference to the Olympic Word. |
|  | Z2.2 | The Contractor ensures that all Advertising Materials meet the requirements of the Brand Manual and no approval is required where the Advertising Materials meet the Brand Manual. Where proposed Advertising Materials do not comply with the Brand Manual, the Contractor obtains the prior written approval of the Employer (the Employer does not unreasonably withhold or delay such approval) before any such Advertising Materials are used or distributed in any medium. |
|  | Z2.3 | The Contractor acknowledges that the BOA is the proprietor and rights owner of the Olympic Word in the Territory by virtue inter alia of the ‘Olympic association right’ under the Act and shall not dispute or challenge any rights to the Olympic Word. |
|  | Z2.4 | The Contractor ensures that all of its Advertising Materials and all other materials it intends to use which carry the Park Name be branded with such specific wording or statement as is set out in the Brand Manual or that is reasonably requested by the Employer in writing from time to time. |
|  | Z2.5 | The Contractor does not apply for, or obtain, registration of any trade or service mark or domain name in any country which consists of, or comprises, or is confusingly similar to, the Park Name (or any part of it). |
|  | Z2.6 | Any goodwill derived from the use by the Contractor of the Park Name belongs to the Employer. If the Employer requests, the Contractor enters into an assignment to confirm that such goodwill belongs to the Employer, provided that the assignment is on reasonable terms. |
|  | Z2.7 | ## The Contractor does not, directly or indirectly, assist any other person to - use the Park Name except as authorised by clauses Z1 to Z4 and - do anything to diminish the rights of the Employer or any Rights Owner in the Park Name. |
|  | Z2.8 | - The Contractor does not undertake any activity, commercial or non-commercial, which makes or implies a direct or indirect association of any kind (including an association in the minds of members of the public) between - the Olympic Movement or any Rights Owner more generally and - its goods, services or its businesses generally, without the authorisation of the Employer and the relevant Rights Owner. |
|  | Z2.9 | The Contractor agrees that the exercise of any right granted to it under clauses Z1 to Z4 is subject to all applicable laws, enactments, regulations and other similar instruments in the world (“Laws”), and the Contractor agrees to be solely liable and responsible for acting in accordance with such Laws and for ensuring that third parties with whom it has a contractual relationship do the same. |
|  | Z2.10 | The Contractor does not do anything which will or is likely to weaken, damage or be detrimental to the Park Name or the reputation or goodwill associated with the Olympic Movement or any Rights Owner. |
|  | Z2.11 | The Contractor promptly provides the Employer with copies of all communications it receives from any regulatory, industry or other authority relating to the Park Name. |
| Brand Protection | Z3.1 | - The Contractor promptly notifies the Employer in writing giving details of the following matters coming to its attention - any actual, suspected or threatened infringement by a third party of the Olympic Word, - any use of the Park Name by any third party which has not been authorised by the Employer or - any other form of attack, charge or claim to which the intellectual property rights in the Olympic Word may be subject. |
|  | Z3.2 | - In respect of any of the matters listed in clause Z3.1 above - the Employer decides what action to take (if any), - the Employer has exclusive control over, and conduct of, all claims and proceedings and - the Contractor does not make any admissions other than to the Employer and provides the Employer with all assistance, at the Employer’s cost, that the Employer may reasonably require in the conduct of any claims or proceedings. |
| No Marketing Obligations | Z4.1 | - The Contractor does not - save to the extent permitted in clauses Z1 to Z3 use any trade marks, trade names, logos or other intellectual property of the BOA or the IOC (including the London 2012 logos) (including the Protected Marks) or to use any trade marks, trade names or logos so resembling the Protected Marks as to be likely to cause confusion with the Protected Marks, - represent, directly or indirectly, that it or its services are in any way associated with the London 2012 Games or any Rights Owner or that any services provided have been endorsed or approved by any Rights Owner, - undertake any form of Ambush Marketing, - cause or permit to be done, anything which might damage or endanger the validity or distinctiveness of, or the goodwill in, the Protected Marks or other intellectual property rights of any Rights Owner or - use its connection with the Employer or the Site (or any premises in the Site) in a manner that makes or implies a direct or indirect association of any kind (including an association in the minds of the public) with the Olympic Movement or any Rights Owner. |
|  | Z4.2 | - The Contractor agrees - to take reasonable steps to ensure that its sub-contractors or agents shall also abide by the provisions of this clause Z4 (as if references in this paragraph to the Contractor included references to such sub-contractors or agents), - that any Rights Owner shall have the right to enforce the terms of clauses Z1 to Z4 directly against the Contractor and - that this clause Z4 shall continue to apply after termination of this contract without limit of time. |
| Indemnity | Z5.1 | The Contractor indemnifies the Employer against any actions, claims, demands and proceedings taken or made against the Employer and all costs, damages, expenses, liabilities and losses incurred by the Employer arising from any breach of the Contractor’s obligations in clauses Z1 to Z4. |
| Warranties and Undertakings | Z6.1 | The Contractor warrants and undertakes to the Employer as a condition of this contract that: |
|  |  | - he has all the resources including financial, technical and human resources as are required to carry out and complete the works in accordance with the conditions of contract, - all design, workmanship, manufacture and fabrication will be in accordance with the Works Information and applicable law, - the works will be carried out using only materials and goods which are of sound and good quality and that he will only specify substances and materials for incorporation in the works and only incorporate substances and materials which are in accordance with the Standards, general good building and engineering practice and the requirements of the Works Information, - the Plant and Materials will on Completion be capable of being used, operated and maintained in a safe, economic and efficient manner, free from any unreasonable risk to the health and well-being of persons using it and free from any unreasonable or avoidable risk of pollution, nuisance, interference or hazard, - [neither the functionality nor the performance of the works, or any computer product, application or system forming part of the works, or any Plant, Materials or Equipment is affected, made inoperable, difficult or suffers any abnormality by reason of any software defect,] - the Plant and Materials will at take-over operate safely and efficiently in combination with any plant, equipment or system to which it is connected, - [he will maintain a sufficient supply of the spare parts (including software) necessary for the operation and maintenance of the works as specified in the Works Information, and] - the proceeds of insurance taken out by the Contractor pursuant to clause 82 of the conditions of contract will be used solely for the purposes of the works and for no other purpose. |
| Nuisance | Z7.1 | The Contractor at all times prevents any public or private nuisance (including, without limitation, any such nuisance caused by noxious fumes, noisy working operations or the deposit of any material or debris on the public highway) or other interference with the rights of any adjoining or neighbouring landowner, tenant or occupier or any Statutory Undertaker arising out of the carrying out of the works or of any obligation under clauses 40 to 43 and assists the Employer in defending any action or proceedings which may be instituted in relation to the same. The Contractor is responsible for and indemnifies the Employer from and against any and all expenses, liabilities, losses, claims and proceedings whatsoever resulting from any such nuisance or interference, except only where such nuisance or interference is the consequence of an instruction of the Employer. |
|  | Z7.2 | Without prejudice to the Contractor's obligations under clause Z7.1 if the carrying out of the works is likely to necessitate any interference (including the oversailing of tower crane jibs) with the rights of adjoining or neighbouring landowners, tenants or occupiers, the Contractor without cost to the Employer obtains the prior written agreement of such landowners, tenants or occupiers subject to the approval of the Employer. The Contractor complies (at his own cost) in every respect with the conditions contained in such agreements. |
| Intellectual Property Rights | Z8.1 | Contractor’s IPR (a) All IPR in any Documentation created by the Contractor belongs to and remains vested in the Contractor, subject to the provisions of this contract. (b) To the extent that (1) IPR in any Documentation are vested in the Contractor or (2) IPR in any Documentation are vested in the Subcontractors or any other third parties or (3) any licences from third parties are required in order to lawfully exploit any IPR (or to incorporate any material in the Documentation), the Contractor grants or procures the grant in the case of (2) or (3) to the Employer a worldwide, irrevocable, royalty-free, non-exclusive perpetual and irrevocable licence to use, exploit, modify and incorporate any material into the Documentation (and do any act restricted by copyright or otherwise restricted by law in respect of any IPR in the Documentation) in each case for any purpose. (c) The Contractor procures from the third party provider of the IPR referred to above the grant of a licence to the Employer, or if the third party is itself a licensee of those rights, an authorised sub-licence, in each case to use, exploit, reproduce, maintain and make any modifications, adaptations or alterations to the material to which the IPR relates (and the works) and to combine and incorporate such material with any other material, in each case for any purpose and to do any act restricted by copyright or otherwise restricted by law in respect of any IPR and such licence or sub-licence is worldwide, royalty-free, non-exclusive perpetual and irrevocable. |
|  |  | (d) The licences granted pursuant to this clause Z8 includes the right to grant sub-licences, transfer, novate to or assign for the foregoing purposes on like terms to any person without further limitation and at no cost to the Employer or any such person. (e) [To the extent that the materials licensed pursuant to clause Z8 include any computer software, the Contractor continues to provide maintenance and support services in connection with such software in accordance with the terms of this contract for the duration of the works and until the defects date notwithstanding any termination of this contract. [The Contractor claims its costs of providing such maintenance and support in Providing the Works in accordance with this contract.] (f) The licences granted pursuant to this clause Z8 enable the Employer (and any sub-licensee, transferee, or assignee) to use and reproduce the Documentation for any extension of the works but do not include a licence to reproduce the IPR in the Documentation for any extension of the works. (g) The Contractor waives and does not assert, and ensures that its Subcontractors and any relevant third parties waive and do not assert, any moral rights in respect of the works or the Documentation which it or they might be deemed to have under Chapter IV of the Copyright, Designs and Patents Act 1988 (and to the extent such waiver is legally possible, any equivalent rights anywhere in the world). (h) The Contractor warrants to the Employer that - the Documentation created by the Contractor is original, - the use of the Documentation by the Employer in accordance with this clause Z8 will not infringe upon the rights of any third party nor create any other liability for the Employer nor otherwise be unlawful and - [it shall not act in any way which prejudices or compromises the IPR in the Employer Data.] - The Contractor is not liable for any use of the Documentation by the Employer for any purpose other than that for which it was prepared. (j) The provisions in this clause Z8 apply during the Provision of the Works and after Completion, expiry or termination of this contract and there is no end of liability date in respect of this clause Z8. |
|  | Z8.2 | The Contractor agrees to provide to the Employer or any person nominated by the Employer access as soon as reasonably practicable to all Documentation in whatever form requested by the Employer at any time but at the latest on termination or expiry of this contract. |
|  | Z8.3 | IPR Claims (a) The Contractor promptly notifies the Employer upon becoming aware of an infringement, alleged infringement or potential infringement of any IPR (including any claims, demands or actions (collectively “Claims”) relating to the same) which affects or may affect the provision of the works (b) Subject to the Employer’s proper observance of its obligations under this contract, the Contractor indemnifies the Employer against all Claims and losses that arise from or are incurred by reason of any infringement or alleged infringement of any IPR. (c) The Employer, at the request of the Contractor, gives the Contractor all reasonable assistance for the purpose of contesting any such Claim. The Contractor reimburses the Employer for all losses incurred in doing so and/or the Contractor conducts any litigation and all negotiations at its own expense arising from such Claim. The Contractor consults with the Employer in respect of the conduct of any Claim and keeps the Employer regularly and fully informed as to the progress of such Claim. |
|  | [Z8.4 | Employer Data All IPR in the Employer Data belongs to and remains vested in the Employer. The Employer grants to the Contractor a licence to use and reproduce any Employer Data for the purpose of Providing the Works which is subject to the Employer's IPR solely for the purpose and to the extent and for the duration necessary to Provide the Works in accordance with this contract and the Works Information. Such licence - is non-exclusive and is subject to such restrictions as the Employer notifies from time to time and - includes the right for the Contractor to sublicense the material to Subcontractors to the extent and for the duration necessary to Provide the Works in accordance with this contract and the Works Information. The Employer is not liable for any use of the Employer Data by the Contractor for any purpose other than that for which it was prepared.] |
| [Escrow | Z8A.1 | Identified and defined terms: Escrow means the deposit with, and retention by, the Escrow Agent of, the Escrow Information. Escrow Agent means [NCC Escrow International Limited] or any successor or replacement to all or any of its functions. Escrow Agreement means an agreement in the form of the [NCC Group Single Licensee Software Escrow Agreement] between the Contractor, the Employer and the Escrow Agent. Escrow Information means: - with respect to any Software, all logic, logic diagrams, flow charts, orthographic representations, algorithms, routines, sub-routines, utilities, models, file structures, coding sheets, coding, source codes, listings, functional specifications and program specifications and all other materials and documents necessary to enable a reasonably skilled programmer to support, maintain, amend and enhance that Software without reference to any other person or document, all in human eye-readable or machine-readable form; and • all information necessary to enable a reasonably skilled technician to operate, maintain, support, service, repair, overhaul and enhance the Hardware (including to manufacture parts), including details of its system architecture. Hardware means hardware and IT system components comprised in, installed in, or used for the operation, maintenance, servicing, repairing or overhauling of, the works or any equipment to be used in conjunction with the works and supplied by the Contractor under this Contract. Software means any computer programme installed in, or used for the operation, maintenance, servicing, repairing or overhauling of, the works or any equipment to be used in conjunction with the works and supplied by the Contractor under this Contract. |
|  | Z8A.2 | The Employer and the Contractor shall enter into the Escrow Agreement no later than the Completion Date. |
|  | Z8A.3 | The Contractor shall place the Escrow Information in Escrow with the Escrow Agent on the terms set out in the Escrow Agreement no later than Completion. The Contractor acknowledges that it shall be a condition of achieving Completion that all Escrow Information has been deposited in Escrow in accordance with this clause Z8. The Contractor and the Project Manager shall, each acting reasonably, agree from time to time the scope of the Escrow Information including arising from design development, changes to the Works Information or otherwise which are in the nature of Escrow Information and which shall be deposited in Escrow. In the event agreement cannot be reached prior to the dates on which deposit into Escrow is required by this clause the scope of the Escrow Information may be determined by the dispute resolution procedure set out at Clause 93. |
|  | Z8A.4 | The Contractor undertakes to ensure that the Escrow Information deposited in Escrow is up to date at all times (including as a minimum at Completion) up to and including the issue of the Defects Certificate and that the Employer has been notified of any updates. |
|  | Z8A.5 | The Contractor and the Employer mutually undertake to abide by the terms of the Escrow Agreement. |
|  | Z8A.6 | The Contractor shall pay all fees of the Escrow Agent in connection with the placement, storage and release of the Escrow Information. |
|  | Z8A.7 | The parties agree that, for the purposes of the Escrow Agreement, the [Release Events] are: (a) a material breach by the Contractor in Providing the Works which (i) is not remedied within such reasonable period of time as the Employer may specify, having regard to the nature of the breach and its impact on the works or the use of the works and the Programme, of a written notice from the Employer identifying the breach and requiring it to be remedied; and (ii) impairs the Employer's [and/or London Stadium 185 Limited's] ability to use, maintain, operate, develop or repair the works following Completion or takeover; (b) a material failure by the Contractor to correct a Defect within the defect correction period in accordance with Clause 41 where such Defect impairs the Employer's and/or [London Stadium 185 Limited's] ability to use, maintain, operate, develop or repair the works following Completion or takeover; (c) the Contractor is unwilling or unable to develop, enhance, supplement, modify and/or maintain the works in accordance with this Contract or otherwise on request by the Employer on reasonable terms; (d) termination of this Contract by the Employer for reasons R1 (insolvency of the Contractor), R2 (substantial failure to comply with this Contract), R4 (substantially broken health and safety regulations) or under clause 72.8 (No Marketing Rights); (e) termination by the Escrow Agent of the Escrow Agreement, if such termination is occasioned by any breach or default by the Contractor of its obligations under the Escrow Agreement and the Contractor fails to put an alternative and equivalent escrow arrangement in place within 14 days of the termination of the Escrow Agreement; (f) the Contractor has done one of the actions listed in Clause 90.2 or its equivalent; or (g) the Contractor assigns its IPR in any Escrow Information to a third party (“Assignee”) and the Assignee fails, within 60 days of such assignment, to continue escrow protection for the benefit of the Employer by failing to enter into either: (i) a novation agreement with the Escrow Agent for the assumption of the Contractor’s rights and obligations under the Escrow Agreement in respect of the relevant Escrow Information by the Assignee; or (ii) a new escrow agreement with the Employer for the relevant Escrow Information which offers the Employer substantially similar protection to that provided by the Escrow Agreement without significantly increasing the overall cost to the Employer. |
|  | Z8A.8 | The Employer may use any Escrow Information delivered to it in under the terms of the Escrow Agreement accordance with the terms of the licence granted under this Clause Z8A, save that the licence granted will also include a right to manufacture the Software and Hardware or any part of it. |
|  | Z8A.9 | The Contractor shall maintain a catalogue, in a format approved by the Employer, of all Escrow Information deposited in Escrow and update that catalogue whenever any such material is deposited in Escrow. The catalogue must identify all the Escrow Information deposited in Escrow, a brief description of its purpose or function, its owner and, where applicable, its version number and its configuration state (including where relevant the configuration baseline for the Software or Hardware with which such material interfaces). |
|  | Z8A.10 | The Employer may request the Escrow Agent to audit (at the Employer’s cost) the contents of the material deposited in Escrow against the catalogue established pursuant to Clause Z8A and if the audit reveals that any Escrow Information is incomplete, the Contractor shall deposit within ten (10) working days of completion of such audit the missing Escrow Information. |
|  | Z8A.11 | The provisions in this Clause Z8A apply during the Provision of the Works and after Completion and expiry or termination of this Contract and there is no end of liability date in respect of this Clause Z8A.] |
| Assignment [and Novation] | Z9.1 | The Contractor does not assign, transfer, novate, charge or otherwise deal with this contract (or any of his rights or obligations under it). |
|  | Z9.2 | The Employer may assign in whole or in part any benefit or right under this contract at any time to any person on two occasions only without the consent of the Contractor. Any further assignments shall be subject to the Contractor's consent (such consent not to be unreasonably withheld or delayed). Without prejudice to the foregoing, the Employer may transfer, novate, charge or otherwise deal in whole or in part any benefit, right or obligation under this contract at any time to any person. [The Contractor, within 21 days of a request from the Employer identifying the relevant person to whom this contract will be novated, duly executes and delivers to the Employer a novation agreement in the form prescribed by the Employer.] |
| Confidentiality | Z10.1 | The Contractor treats, and ensures that his Subcontractors (and sub-subcontractors of any tier) treat all information obtained under, arising from or in connection with this contract and the works as confidential. Other than for the purpose of providing the works the Contractor does not disclose any information or documents concerning this contract to any other person. |
|  | Z10.2 | The Contractor and his Subcontractors (and sub-subcontractors of any tier) do not without the prior written consent of the Employer disclose any information obtained by the Contractor concerning the Employer or to any other person. |
|  |  | The Employer may require as a precondition to the granting of such consent, that any such third party provides a confidentiality undertaking to the consenting party in terms satisfactory to the consenting party. |
|  | Z10.3 | Clause Z10.1 does not apply to the disclosure of: - any information which is already in the public domain at the time of its disclosure other than by breach of these provisions, - any information disclosed by the Contractor to any Connected Persons provided that such recipients agree in writing to be bound by the terms of this confidentiality provision; - any information which is required to be disclosed by any applicable law, the regulations of any stock exchange, any taxation authorities or by an order of a court or other tribunal of competent jurisdiction or any relevant regulatory body. |
|  | Z10.4 | The Contractor procures that the Connected Persons comply with the provisions of this clause Z10 and is responsible to the Employer for any act or omission of any Connected Person in breach of such obligations. |
|  | Z10.5 | The Contractor notifies the Employer promptly if the Contractor becomes aware of any breach of confidence by a Connected Person and gives the Employer all assistance the Employer may reasonably require in connection with any proceedings the Employer may bring or other steps the Employer may take against that Connected Person or any other person for such breach of confidence. |
|  | Z10.6 | The Contractor acknowledges that damages would not be an adequate remedy for any breach of this Clause by the Contractor and that (without prejudice to all other remedies to which the Employer may be entitled to as a matter of law) the Employer is entitled to any form of equitable relief to enforce the provisions of this Clause. |
|  | Z10.7 | At the Employer's request and in any event upon the termination or expiry of the contract, the Contractor promptly delivers to the Employer or destroys as the Employer may direct all documents and other materials in the possession, custody or control of the Contractor (or the relevant parts of such materials) that bear or incorporate the whole or any part of the confidential information and if instructed by the Employer in writing, remove all electronically held confidential information, including the purging of all disk-based confidential information and the reformatting of all disks. |
|  | Z10.8 | The Contractor does not (and procures that the Connected Persons do not) without the prior written approval of the Employer at any time for any reason disclose to any person or publish or make any statement concerning this contract or the works. |
| Modern Slavery Act | Z11.1 | In performing his obligations under this contract, the Contractor - complies with the Anti-Slavery Policy, which means a policy implemented by the Contractor which sets out the procedures the Contractor has put in place to comply with section 54 of the Modern Slavery Act 2015 and any guidance issued by the Secretary of State under section 54 of that Act; - complies, and procures that his Subcontractors and sub-subcontractors of any tier comply, with the Modern Slavery Act 2015, and - unless otherwise agreed in writing by the Employer (at the Employer's sole and absolute discretion), only procures, and ensures that his Subcontractors and sub-subcontractors of any tier only procure, labour from a Certified Ethical Labour Provider. Where the Contractor, a Subcontractor or a sub-subcontractor of any tier is procuring labour from a Certified Ethical Labour Provider who prepares audit reports, such reports are made available to the Employer (at no additional cost) and, where possible, through the Sedex platform. |
|  | Z11.2 | On each 12 month anniversary of the starting date, until the Defects Certificate has been issued, the Contractor submits a report to the Employer which confirms that all labour used to Provide the Works has been procured from a Certified Ethical Labour Provider and includes such evidence as the Employer may reasonably require to evidence compliance. |
|  | Z11.3 | A failure by the Contractor to comply with his obligations under clauses Z11.1 to Z11.2 constitutes a substantial failure by the Contractor to comply with his obligations for the purpose of Clause 90.3 of this contract. The Employer may refuse any labourer employed or engaged by the Contractor, a Subcontractor or sub-subcontractor of any tier entry onto any property that is owned, occupied or managed by the Employer if that labourer has not been procured from a Certified Ethical Labour Provider or if the Employer has reasonable grounds to suspect that such employee or agent has not been procured from a Certified Ethical Labour Provider. Any losses arising from such refusal of entry shall not constitute a compensation event. |
| Responsible Procurement | Z12.1 | The Contractor has regard to the Responsible Procurement Principles and complies at all times with the obligations with regard to the Responsible Procurement Principles set out in the Works Information. Compliance with such obligations does not constitute a compensation event unless the Employer issues an instruction and states in his instruction that it constitutes a compensation event. |
| London Living Wage | Z13.1 | The Contractor acknowledges and agrees that the Mayor, pursuant to section 155 of the GLA Act, has directed the Employer to ensure that the London Living Wage is paid to anyone engaged by the Employer who is required to discharge contractual obligations (whether as a direct contractor or a subcontractor (of any tier) of that direct contractor) on the Employer’s estate in the circumstances set out in sub-clause Z13.2(a). |
|  | Z13.2 | Without prejudice to any other provision of this contract, the Contractor: |
|  |  | - ensures that his employees and procures that the employees of his Subcontractors and sub-subcontractors (of any tier) engaged in the performance of the works: - for two (2) or more hours of work in any given day in a week, for eight (8) or more consecutive weeks in a year and - on the Employer’s estate including (without limitation) the Site and premises and land owned or occupied by the Employer, is paid an hourly wage (or equivalent of an hourly wage) equivalent to or greater than the London Living Wage, |
|  |  | - ensures that none of - his employees nor - the employees of his Subcontractors or sub-subcontractors (of any tier), engaged in the performance of the works is paid less than the amount to which they are entitled in their respective contracts of employment, |
|  |  | - provides to the Employer such information concerning the London Living Wage as the Employer or his nominees may reasonably require from time to time, including (without limitation): - all information necessary for the Employer to confirm that the Contractor is complying with his obligations under this clause Z13 and - reasonable evidence that sub-clause Z13.2(a) is implemented, |
|  |  | - in connection with sub-clause Z13.2(c), - acknowledges and agrees that the Centre for Civil Society (or any relevant replacement organisation notified to the Contractor from time to time) may contact and meet with any trade unions representing the Contractor’s employees and the employees of his Subcontractors and sub-subcontractors (of any tier) in order to establish that the obligations in sub-clause Z13.2(a) have been complied with and - liaises and cooperates with the Employer and the Centre for Civil Society (or any relevant replacement organisation notified to the Contractor from time to time) in order to establish that the obligations in sub-clause Z13.2(a) have been complied with, |
|  |  | - disseminates on behalf of the Employer to: - his employees and - the employees of his Subcontractors and sub-subcontractors (of any tier), engaged in the performance of the works such perception questionnaires as the Employer may reasonably require from time to time and promptly collates and returns to the Employer responses to such questionnaires, and |
|  |  | (f) co-operates and provides all reasonable assistance in monitoring the effect of the London Living Wage. |
|  | Z13.3 | For the avoidance of doubt the Contractor: - implements the annual increase in the rate of the London Living Wage and - procures that his Subcontractors and sub-subcontractors (of any tier) implement the annual increase in the rate of the London Living Wage, on or before 1 April in the year following the publication of the increased rate of the London Living Wage. |
|  | Z13.4 | The Employer reserves the right to audit (acting by itself or its nominee(s)) the provision of the London Living Wage to the Contractor’s staff and the staff of his Subcontractors and sub-subcontractors (of any tier). |
|  | Z13.5 | Any breach by the Contractor of the provisions of this clause Z13 is treated as the Contractor having substantially failed to comply with his obligations for the purpose of Clause 90.3 of this contract. |
|  | Z14 | [Not Used] |
| Data Protection | Z15.1 | Each of the Parties complies at all times with its obligations under the Data Protection Legislation, and the Parties acknowledge that the Employer is a Data Controller solely responsible for determining the purposes and manner in which Personal Data is to be Processed and the Contractor is a Data Processor. |
|  | Z15.2 | Details of the Employer Personal Data to be Processed by the Contractor and the purposes of such Processing are as set out in the Processing Statement, which the Parties complete before any Processing takes place. |
|  | Z15.3 | The Contractor: - Processes the Employer Personal Data only in accordance with documented instructions from the Employer to perform its obligations under this Contract; - uses its reasonable endeavours to assist the Employer in complying with its obligations under Data Protection Legislation and does not perform its obligations under this Contract in such a way as to cause the Employer to breach any of its obligations under Data Protection Legislation to the extent the Contractor is aware, or ought reasonably to have been aware, that the same would be a breach of such obligations; - notifies the Employer immediately if it determines or is notified that an instruction to Process Personal Data issued to it by the Employer is incompatible with any obligations under Data Protection Legislation to the extent the Contractor is aware, or ought reasonably to have been aware, that the same would be a breach of such obligations; (d) maintains, and makes available to the Employer on its request, documentation which describes the Processing operations for which it is responsible under this Contract including: • the purposes for which Employer Personal Data is Processed, • the types of Personal Data and categories of Data Subject involved, • the source(s) of the Personal Data, • any recipients of the Personal Data, • the location(s) of any overseas Processing of Employer Personal Data, • retention periods for different types of Employer Personal Data, and • where possible a general description of the security measures in place to protect Employer Personal Data; - where requested to do so by the Employer, or where Processing Employer Personal Data presents a specific risk to privacy, carries out or assists the Employer to carry out a Data Protection Impact Assessment in accordance with guidance issued from time to time by the Information Commissioner (and any relevant requirements detailed in Data Protection Legislation) and makes the results of such an assessment available to the Employer and assists with consultations with regulators as required by the Data Protection Legislation; - without prejudice to any cyber security and/or payment card industry data security standard obligations in this Contract, takes appropriate technical and organisational security measures that are satisfactory to the Employer from time to time, against unauthorised or unlawful Processing of Employer Personal Data and against accidental loss, destruction of, or damage to such Employer Personal Data; - without prejudice to any cyber security and/or payment card industry data security standard obligations in this Contract, provides the Employer with such information as the Employer may from time to time require to satisfy itself of compliance by the Contractor (including any Subcontractor and Indirect Subcontractor) with clauses Z15.3(f) and Z15.3(h), including, protocols, procedures, guidance, training and manuals. For the avoidance of doubt, this includes a full report recording the results of any privacy or security audit carried out at the request of the Contractor itself or the Employer; - notifies the Employer without undue delay and in any event within 24 hours by written notice with all relevant details reasonably available of any actual or suspected breach of this clause Z15.1 to Z15.4 including the unauthorised or unlawful Processing of Employer Personal Data, or its accidental loss, destruction or damage; (i) having notified the Employer of a breach in accordance with clause Z15.3(h), keeps the Employer properly and regularly informed in writing until the breach has been resolved to the satisfaction of the Employer; (j) fully cooperates as the Employer requires with any investigation or audit in relation to Employer Personal Data and/or its Processing including allowing access to premises, computers and other information systems, records, documents and agreements as may be reasonably necessary (whether in relation to Processing pursuant to this Contract, in relation to compliance with Data Protection Legislation or in relation to any actual or suspected breach), whether by the Employer (or any agent acting on its behalf), any relevant regulatory body, including the Information Commissioner, the police and any other statutory law enforcement agency, and does so both during the Contract and after its termination or expiry (for so long as the Contractor retains and/or Processes Employer Personal Data); (k) notifies the Employer within two (2) business days if the Contractor (including any Subcontractor or Indirect Subcontractor), receives: • from a Data Subject (or third party on their behalf): o a Subject Access Request (or purported Subject Access Request), o a request to rectify, block or erase any Employer Personal Data or o any other request, complaint or communication relating to the Employer’s obligations under Data Protection Legislation; • any communication from the Information Commissioner or any other regulatory authority in connection with Employer Personal Data; or • a request from any third party for disclosure of Employer Personal Data where compliance with such request is required or purported to be required by law; (l) provides the Employer with full cooperation and assistance (within the timescales reasonably required by the Employer) in relation to any complaint, communication or request made as referred to in clause Z15.3(k), including by promptly providing: • the Employer with full details and copies of the complaint, communication or request; • where applicable, such assistance as is reasonably requested by the Employer to enable it to comply with the Subject Access Request within the relevant timescales set out in Data Protection Legislation; and • where applicable, such assistance as is reasonably required by the Employer to enable it to comply with a request from a Data Subject to rectify, block or erase any Employer Personal Data. (m) when notified in writing by the Employer, supplies a copy of, or information about, any Employer Personal Data. The Contractor supplies such information or data to the Employer within such time and in such form as specified in the request (such time to be reasonable) or if no period of time is specified in the request, then within two (2) business days from the date of the request; (n) prepares and securely maintains a record of all categories of Processing activities carried out on behalf of the Employer in relation to the Employer Personal Data, as a minimum: (i) its name and contact details and details of a Data Protection Officer (if appointed) or other person with responsibility for data protection compliance; (ii) the categories of Processing it carries out on behalf of the Employer; (iii) transfers to Restricted Countries; (iv) a general description of the technical and organisational security measures referred to in these clauses Z15.1 to Z15.4 (inclusive); and (v) the same information in relation to any Subcontractor and Indirect Subcontractor, together with its name and contact details and when notified in writing by the Employer, complies with any agreement between the Employer and any Data Subject in relation to any Processing which causes or is likely to cause substantial and unwarranted damage or distress to such Data Subject, or any court order requiring the rectification, blocking, erasure or destruction of any Employer Personal Data; (o) if required to do so by Data Protection Legislation, appoints a designated Data Protection Officer; (p) provides all Connected Persons (and any other worker and/or visitor who may enter the Site on behalf of the Contractor) a copy of the Fair Processing Notice provided by the Employer prior to any Connected Person (or any other worker and/or visitor) entering the Site, and the Contractor acknowledges that, if a Connected Person (or any other worker and/or visitor of the Contractor) refuses or withdraws consent to use of any security system in place at the Site without proper and reasonable circumstance, they may be denied access at the Employer’s discretion, and (q) makes available to the Employer all information necessary to demonstrate compliance with the obligations set out in clauses Z15.1 to Z15.4 (inclusive). |
|  | Z15.4 | The Contractor does not share Employer Personal Data with any Subcontractor or Indirect Subcontractor without prior written consent from the Employer and only where there is a written contract in place between the Contractor and the Subcontractor or Indirect Subcontractor (as applicable) which requires the Subcontractor or Indirect Subcontractor (as applicable) to: - only Process Employer Personal Data in accordance with the Employer’s documented instructions to the Contractor and - comply with the same obligations which the Contractor is required to comply with under these clauses Z15.1 to Z15.14 (inclusive) (and Clause Z17). The Contractor remains responsible and liable to the Employer for all acts and omissions of any Subcontractor and Indirect Subcontractor as if they were its own. |
|  | Z15.5 | The Contractor itself, and procures that any Subcontractor and Indirect Subcontractor: - only Processes Employer Personal Data in accordance with the Employer’s documented instructions to the Contractor and as reasonably necessary to perform this Contract in accordance with its terms; - does not Process Employer Personal Data for any other purposes (in whole or part) and specifically, but without limitation, reproduce or refer to it in training materials, training courses, commercial discussions and negotiations with third parties or in relation to proposals or tenders with the Employer; - does not Process Employer Personal Data in such a way as to: • place the Employer in breach of Data Protection Legislation, • expose the Employer to the risk of actual or potential liability to the Information Commissioner or Data Subjects, • expose the Employer to reputational damage including adverse publicity; - does not allow its personnel to access Employer Personal Data unless such access is necessary to Provide the Works; - takes all reasonable steps to ensure the reliability and integrity of the Contractor's employees, directors, contractors, agents, Subcontractors, Indirect Subcontractors, suppliers, shareholders, professional advisers (including lawyers, auditors, financial advisers, accountants and technical consultants) or underwriters who can access Employer Personal Data; - ensures that all personnel who can access Employer Personal Data: • are informed of its confidential nature, • are made subject to an explicit duty of confidence, • understand and comply with any relevant obligations created by either this Contract or Data Protection Legislation, and • receive adequate training in relation to the use, care, protection and handling of Personal Data on an annual basis; - does not disclose or transfer Employer Personal Data to any third party without the Contractor having obtained the prior written consent of the Employer (save where such disclosure or transfer is specifically authorised under this Contract); - without prejudice to clause Z15.3, wherever the Contractor uses any mobile or portable device for the transmission or storage of Employer Personal Data, ensures that each such device encrypts Employer Personal Data; and - complies during the course of this Contract with any written retention and/or deletion policy or schedule provided by the Employer to the Contractor from time to time. |
|  | Z15.6 | The Contractor does not, and procures that any Subcontractor or Indirect Subcontractor does not, Process or otherwise transfer any Employer Personal Data in or to any Restricted Countries without prior written consent from the Employer (which consent may be subject to additional conditions imposed by the Employer). |
|  | Z15.7 | If, after the Contract Date, the Contractor (including any Subcontractor and Indirect Subcontractor) wishes to Process and/or transfer any Employer Personal Data in or to any Restricted Countries, the following provisions apply: - the Contractor submits a written request to the Employer setting out details of the following: • the Employer Personal Data which will be transferred to and/or Processed in any Restricted Countries, • the Restricted Countries which the Employer Personal Data will be transferred to and/or Processed in, • any Subcontractor or other third parties who will be Processing and/or receiving Employer Personal Data in Restricted Countries, • how the Contractor ensures an adequate level of protection and adequate safeguards in respect of the Employer Personal Data that will be Processed in and/or transferred to Restricted Countries so as to ensure the Employer’s compliance with Data Protection Legislation, - in preparing and evaluating such a request, the Parties refer to and comply with applicable policies, procedures, guidance and codes of practice produced by the Parties and/or the Information Commissioner in connection with the Processing of Personal Data in (and/or transfer of Personal Data to) any Restricted Countries; - the Contractor complies with any instructions and carries out such actions as the Employer may notify in writing when providing its consent to such Processing or transfers, including: • incorporating standard and/or model clauses (which are approved by the European Commission as offering adequate safeguards under the Data Protection Legislation) into this Contract or a separate data processing agreement between the Parties and • procuring that any Subcontractor and Indirect Subcontractor) or other third party who will be Processing and/or receiving or accessing the Employer Personal Data in any Restricted Countries enters into a data processing agreement with the Contractor on terms which are equivalent to those agreed between the Employer and the Contractor in connection with the Processing of Employer Personal Data in (and/or transfer of Employer Personal Data to) any Restricted Countries, and which may include the incorporation of the clauses referred to in the bullet point above. |
|  | Z15.8 | The Contractor and any Subcontractor and Indirect Subcontractor (if any), acknowledges: (a) the importance to Data Subjects and the Employer of safeguarding Employer Personal Data and Processing it only in accordance with the Employer’s instructions and this Contract; (b) the loss and damage the Employer is likely to suffer in the event of a breach of this Contract or negligence in relation to Employer Personal Data; (c) any breach of any obligation in relation to Employer Personal Data and/or negligence in relation to performance or non-performance of such obligation is deemed a material breach of this Contract and a substantial failure by the Contractor to comply with his obligations; (d) without limiting clause 90.3, if the Contractor has committed a material breach under paragraph Z15.8(c) on two or more separate occasions, the Employer may at its option withdraw authorisation for Processing by a specific Subcontractor by immediate written notice. |
|  | Z15.9 | Compliance by the Contractor with clause Z15.1 to Z15.8 (inclusive) is without additional charge to the Employer and compliance with this clause Z15 is not a compensation event. |
|  | Z15.10 | Following termination or expiry of this Contract or termination of the Contractor’s obligation to Provide the Works, in each case howsoever arising, the Contractor: - may Process the Employer Personal Data only for so long and to the extent as is necessary to properly comply with its non-contractual obligations arising under law (and will then comply with clause Z15.10(b); - subject to clause Z15.10(a) • on written instructions from the Employer either securely destroys or securely and promptly returns to the Employer or a recipient nominated by the Employer (in such usable format as and to the extent the Employer may reasonably require) the Employer Personal Data or • in the absence of instructions from the Employer after 12 months from the expiry or termination of this Contract or termination of the Contractor’s obligation to Provide the Works securely destroys the Employer Personal Data. |
|  | Z15.11 | Employer Personal Data may not be Processed following termination or expiry of this Contract or termination of the Contractor’s obligation to Provide the Works save as permitted by clause Z15.10. |
|  | Z15.12 | For the avoidance of doubt, and without prejudice to clause Z15.10, the obligations in clause Z15 apply following termination or expiry of this Contract or termination of the Contractor’s obligation to Provide the Works to the extent the Party concerned retains or Processes Employer Personal Data. |
|  | Z15.13 | [The Contractor takes reasonable precautions to preserve the integrity of the Employer Data and to prevent any corruption or loss of the Employer Data.] |
|  | Z15.14 | The Contractor is responsible for and indemnifies the Employer and members of the Employer's group of companies from and against any and all fines, court awards, settlements, legal costs, expenses, liabilities, losses, claims and proceedings whatsoever resulting from any breach by the Contractor or any Subcontractor or any Indirect Subcontractor of the Data Protection Legislation or clauses these clauses Z15.1 to Z15.14 (inclusive). Without prejudice to clause 80.1, the Contractor’s liability in respect of any breach of clauses these clauses Z15.1 to Z15.14 (inclusive) insofar as they relate to fines, court awards, settlements and legal costs is unlimited. |
| Conflict of Interest | Z16.1 | The Contractor acknowledges and agrees that he does not have any interest in any matter where there is or is reasonably likely to be a conflict of interest with Providing the Works, save to the extent fully disclosed to and approved in writing by the Employer. |
|  | Z16.2 | The Contractor undertakes ongoing and regular conflict of interest checks throughout the duration of the contract and in any event not less than once in every six months and notifies the Employer in writing immediately on becoming aware of any actual or potential conflict of interest with Providing the Works and works with the Employer to do whatever is necessary (including the separation of staff working and/or data relating to the works from the matter in question) to manage such conflict to the Employer's satisfaction and provided that, where the Employer is not so satisfied (in his absolute discretion), the Employer is entitled to terminate the contract. |
| Freedom of Information | Z17.1 | The Contractor acknowledges that the Employer: |
|  |  | - is subject to FOI Legislation and agrees to assist and co-operate with the Employer to enable the Employer to comply with his obligations under the FOI Legislation, and - may be obliged under the FOI Legislation to disclose Information without consulting and/or obtaining consent from the Contractor. |
|  | Z17.2 | Without prejudice to the generality of Clause Z17.1, the Contractor agrees and procures that his Subcontractors will agree to: |
|  |  | - transfer to the Employer or such other persons as may be notified by the Employer to the Contractor each Information Request relevant to this contract or the works that the Contractor or his Subcontractor (as the case may be) receive as soon as practicable and in any event within 3 days of receiving such Information Request; and - in relation to Information held by the Contractor on behalf of the Employer, provide the Employer with details about and/or copies of all such Information that the Employer requests and such details and/or copies are provided within 6 days of a request from the Employer (or such other period as the Employer may reasonably specify), and in such forms as the Employer may reasonably specify. |
|  | Z17.3 | The Employer is responsible for determining whether Information is exempt or excepted information under the FOI Legislation and for determining what Information (if any) will be disclosed in response to an Information Request in accordance with the FOI Legislation. The Contractor does not himself respond to any person making an Information Request, save to acknowledge receipt, unless expressly authorised to do so in writing by the Employer. |
|  | Z17.4 | The Contractor acknowledges that the Employer may be obliged under FOI Legislation to disclose Information without consulting or obtaining consent from the Contractor. |

If the United Kingdom Housing Grants, Construction and Regeneration Act 1996 as amended by the Local Democracy, Economic Development and Construction Act 2009 (the Act) applies to this contract, the following additional conditions apply.

| Definitions | 1.1 | (1) The payment due date for an application for payment by the Contractor is the assessment day which follows receipt of that application. (2) The final date for payment is three weeks after the payment due date. |
| --- | --- | --- |
| Assessing the amount due | 1.2 | The Contractor's application for payment is the notice of payment specifying the sum that the Contractor considers to be due at the payment due date (the notified sum). The Contractor’s application states the basis on which the amount is calculated and includes details of the calculation. |
|  | 1.3 | The following replaces sub-clause 50.4 If the Employer intends to pay less than the notified sum, he notifies the Contractor of the amount which the Employer considers to be due not later than seven days (the prescribed period) before the final date for payment. The Employer’s notification states the basis on which the amount is calculated and includes details of the calculation. A Party pays the notified sum unless he has notified his intention to pay less than the notified sum. |
| Compensation event | 1.4 | If the Contractor exercises his right under the Act to suspend performance, it is a compensation event. |
| The Adjudication | 1.5 | The following replaces sub-clause 93.3(1) A Party may issue to the other Party a notice of his intention to refer a dispute to adjudication at any time. He refers the dispute to the Adjudicator within one week of the notice. |
|  | 1.6 | The Adjudicator may in his decision allocate his fees and expenses between the Parties. |
|  | 1.7 | The Adjudicator may, within five days of giving his decision to the Parties, correct the decision to remove a clerical or typographical error arising by accident or omission. |
|  | 1.8 | If the Adjudicator’s decision changes an amount notified as due, payment of the sum decided by the Adjudicator is due not later than seven days from the date of the decision or the final date for payment of the notified amount, whichever is the later. |