### CONTRACT DATA

Part One - Data provided by Employer

1.	General

1.1	The conditions of contract are the Model Conditions of Contract for The Asset Support Contract.

1.2	The Employer is:	The Secretary of State for Transport of Great Minster House, 33 Horseferry Road, London, SW1P 4DR.

1.3	The Service Manager is:	Name 		Guy Berresford

Address 	Highways Agency

Federated House

London Road

Dorking

RH4 1SZ

1.4	The Area Network is Highways Agency Area 3 as more particularly described in the Network Information.

1.5	The Adjudicator is a person to be chosen in accordance with clause 91.1 when a dispute arises.

1.6	The Service Information is in the Highways Agency e-tendering address, which is https://highways.bravosolution.co.uk, as an attachment in the listed project: Area 3 Asset Support Contract (ASC) 2013.

1.7	The Network Information is in the Highways Agency e-tendering address, which is https://highways.bravosolution.co.uk, as an attachment in the listed project: Area 3 Asset Support Contract (ASC) 2013.

1.8	The Pricing Schedule is in the Highways Agency e-tendering address, which is https://highways.bravosolution.co.uk, as an attachment in the listed project: Area 3 Asset Support Contract (ASC) 2013.

1.9	The period for reply to a communication is two weeks.

1.10	The threshold range is £4,000,000 (four million pounds) to £8,000,000 (eight million pounds).

1.11	The threshold is £5,000,000 (five million pounds).

1.12	The following matters will be included in the Risk Register:

- Effective winter service;

- Satisfy Special Defence test under Section 58 of the Highways Act 1980;

- Network availability to maintain free flow of traffic;

- Understanding of the Area Network, its condition, traffic using the network, maintenance requirements, stakeholder expectations and minimising impact to On Time Reliability;

- Operating as an integrated team (Traffic Officer Service, RCC, RTMC, Area Team, Service Providers);

- Management of third party contracts including the RTMC and the Asset Support Framework

- Operation and Maintenance of the Hindhead Tunnel and its complex safety systems

1.13	The Employer’s representatives on the Network Board are Guy Berresford (nominated chair) and Barry Westwood.

1.14	The limits of authority of the Employer’s representatives are:

- Financial Guy Berresford - Service Manager –  £9,000,000 for highway projects and £5,000,000 for traffic technology projects

- Contractual - Mark Kumar – Procurement Manager £250,000,000

1.15	Named Suppliers have the right under the Contracts (Rights of Third Parties) Act 1999 to enforce the provisions of clauses 59.4, 59.6, 59.8, 59.10 and 59.13 of the conditions of contract.

## 1.16 	An Incoming Provider has the right under the Contracts (Rights of Third Parties) Act 1999 to enforce the provisions of clauses 36.9 and 42.6 of the conditions of contract.

3.	Time

3.1	The starting date is 31 May 2013

3.2	The access date is 1 November 2013

3.3	The contract period is five years commencing on the access date.

3.4	The extension period is up to three years.

3.5	The Provider submits revised programmes at intervals no longer than one month.

4.	Management and audit

4.1	Quality table

Quality Management Points accrue for the failures listed in the quality table below.     Subject to clause 41.6 Quality Management Points in respect of failures 1, 3, 4, 5, 7, 9, 10, 11, 12, 13 and 14 which are  identified other than by audit accrue from the date of identification and Quality Managements Points which accrue from an audit accrue from the date of the audit.

| Failure |  | Quality Management Points | Period of effect |
| --- | --- | --- | --- |
| 1 | No Quality Manager in post | 25 | Until a Provider’s audit confirms the Failure is rectified and this is accepted by the Service Manager |
| 2 | Failure to identify a Nonconformity | 5 per Nonconformity | 2 months |
| 3 | Failure to raise a Nonconformity report in accordance with annex 19 | 5 per Nonconformity | 6 months |
| 4 | Failure to raise a corrective action report | 5 per Nonconformity | 6 months |
| 5 | Failure to rectify a Nonconformity in the time set out in a corrective action report (see note 1 below) | 5 per Nonconformity | Until a Provider’s audit confirms the Failure is rectified and this is accepted by the Service Manager |
| 6 | Failure to correct Quality Plan in manner set out in a corrective action report (see note 1 below) | 10 per failure | Until a Provider’s audit confirms the Failure is rectified and this is accepted by the Service Manager |
| 7 | Failure to prevent repeat Nonconformities | 5 per repeat Nonconformity | 6 months |
| 8 | Failure to implement recommendations in audit report (see note 1 below) | 5 per recommendation | Until a Provider’s audit confirms the Failure is rectified and this is accepted by the Service Manager |
| 9 | Failure to carry out internal audit | 25 per audit | Until a Provider’s audit confirms the Failure is rectified and this is accepted by the Service Manager |
| 10 | Carrying out work without release of hold point | 10 per item | 6 months |
| 11 | Failure to make records available for inspection by the Service Manager | 10 per failure | Until the records are made available |
| 12 | Failure to allow access for Employer audits | 10 per failure | Until access is allowed |
| 13 | Failure to notify the Service Manager of change to Processes and Procedures | 10 per failure | 6 months |
| 14 | Failure by Provider to accrue Quality Management Points that should have been accrued or where the Provider has been instructed to accrue Quality Management Points by the Service Manager | The number of Points that should have been accrued | The period applicable to the Failure that should have accrued Points |
|  |  | PLUS |  |
|  |  | An additional number of Points equivalent to the Points that should have been accrued | 6 months from the actual accrual date of the Quality Management Points that should have been accrued |

# Note 1:  For this failure additional Quality Management Points equal to the number already accrued for the failure are accrued at each audit until a Provider’s audit confirms that rectification/correction/implementation/action has taken place and this is accepted by the Service Manager.

5.	Payment

5.1	The currency of this contract is the pound sterling (£).

5.2	The first invoice date is the 15th day of the month following the starting date.

5.3	The assessment interval is one calendar month.

5.4	The interest rate is, unless the provisions of the Late Payment of Commercial Debts (Interest) Act 1998 otherwise require, 3% per annum above the Bank of England base rate in force from time to time.

5.5	The Provider’s share percentages and share ranges are:

Share ranges					Provider’s share percentage

less than	80 %						   0 %

from	 80 % to 100 %			 25 %

from		100 % to 105 %				 50 %

from		105 % to 110 %				 75 %

greater than	110 %						100 %

5.6	The index is the All Items Index of the General Index of Retail Prices as published in Table 3.5 of the Central Statistical Office publication “Monthly Digest of Statistics”.

5.7	The base date is 1st November  2012.

8.	Risks and insurance

8.1	The amount of the minimum limit of indemnity for insurance in respect of loss of or damage to property (except the Area Network, Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Provider) caused in connection with this contract for any one event is £40,000,000 (Forty Million Pounds).

8.2	The amount of the minimum limit of indemnity for insurance in respect of death of or bodily injury to employees of the Provider arising out of and in the course of their employment in connection with this contract for any one event is £10,000,000 (Ten Million Pounds).

8.3	The amount of the minimum limit of indemnity for insurance in respect of claims made against the Provider arising out of his failure to use the skill and care normally used by professionals providing services similar to the Services is £5,000,000 (Five Million Pounds).  The minimum limit of indemnity applies in the aggregate in any one period of insurance for claims arising out of pollution or contamination.

8.4	The Employer does not provide any of the insurances stated in the insurance table.

8.5	There are no additional Employer’s risks.

9.	Disputes and termination

9.1	The adjudicator nominating body is the President for the time being of the Institution of Civil Engineers or his nominee.

9.2	The tribunal is arbitration.

9.3	The arbitration procedure is the Institution of Civil Engineers Arbitration Procedure (2006).

9.4	The place where the arbitration is to be held is to be agreed on a case by case basis

Part Two - Data provided by Provider

1	General

1.1	The Provider is:

Name ………………………………………………………………………

Address .……………………………………………..……………………

………………………………………………………………………………

1.2	The Principal Design Consultants are …………………………………..………………

.

and ………………………………………………………………………………………….

1.3	The Quality Statement is in …………………………………………..………………….

1.4	The direct fee percentage is ……………. %

1.5	The subcontracted fee percentage which shall not exceed 4% is ……………. %

1.6	The Fee Schedule is in …………………………………………………………………..

1.7	The lump sum annual discounts are

Contract Year		lump sum annual discount

2			    ………%

3	  ………%

4			    ………%

5			    ………%

The schedule of rates annual discounts are

Contract Year		schedule of rates annual discount

2			    ………%

3	  ………%

4			    ………%

5			    ………%

1.8	The Area Network Alteration Schedule is in…………………………………………….

1.9	The Area Service Alteration Schedule is in ……………………..………………………

1.10	The Provider’s representatives on the Network Board are ……………………………

and ………………………………………………………………………………………….

1.11	The limits of authority of the Provider’s representatives are:

- Financial…………………………………………………………………………………

- Contractual………………………………………………………………………………

……………………………………………………………………………….………………

1.12	The premises document is in ……………………………………………………………

1.13	The following matters will be included in the Risk Register:

………………………………………………………………………………………………...

2	Data for Schedule of Cost Components

2.1	The percentage for people overheads is ………………%

3	Project Bank Account

3.1	The project bank is……………………………………………..…

3.2	named suppliers are ………………………………………………

………………………………………………………….…..……….

………………………………………………………………………