OFFICIAL-SENSITIVE (COMMERCIAL)

	HM REVENUE & CUSTOMS SERVICE ORDER

SOCIAL AND ECONOMIC RESEARCH FRAMEWORK AGREEMENT


	1.
	HMRC Information

Purchase Order to be issued under separate cover

	Project Information 
	Project Reference: 16-17 EC. 11

	Purchase / Limit Order No:
	8500005427

	HMRC – Social and Economic Research Framework – Commercial Contact

	Name:
	Stuart Bishop

	Contact Tel No:
	03000 587 851

	Email:
	stuart.bishop@hmrc.gsi.gov.uk

	HMRC Budget Manager & invoice enquiries

	Name: 
	Mike Crumpton

	Contact Tel. No:
	03000 515 268

	Email:
	mike.crumpton@hmrc.gsi.gov.uk

	HMRC – Invoice payment 

All invoices should be sent to the HMRC Invoice Processing Centre

	Address:
	HMRC Invoice Processing Centre
PO Box 2092, J Spur, Barrington Road
Worthing, BN12 9AN

	Contact Tel No:
	01903 509224 

	Email:
	payments.team@hmrc.gsi.gov.uk 

	HMRC – Budget Authorising Officer

	Name:
	Brian O’Callaghan

	Contact Tel No:
	03000 589 686

	Email:
	brian.o’callaghan@hmrc.gsi.gov.uk

	HMRC Project Manager

	Name:
	Matilda Kinnersly

	Contact Tel No:
	03000 514582

	Email:
	Matilda.kinnersly@hmrc.gsi.gov.uk


	2.
	Contractor Information



	Vendor (Supplier):
	Ipsos MORI

	Contact:
	Kelly Maguire

	Contact Tel No:
	020 3059 4979

	Contact Address:
	1st Floor

3 Thomas More Square

London

E1W 1YW 


	Email:
	 kelly.maguire@ipsos.com

	Consultant / Key Personnel:
	Kelly Maguire


	3.
	Contractual Detail



	Contract Ref:

Incl. Framework name e.g. Catalist, and relevant section. Also include URN for Catalist and Cipher call offs. 
	DWP Social and Economic Research Framework 2013
This Service Order is subject to the DWP Social and Economic Research Research Framework (2013) Terms and Conditions of contract and Clause D3 and D4 relating to the Official Secrets Acts and related Legislation, and Confidentiality, as detailed in Annex B – additional contractual information.


	Special Terms and Conditions:

e.g. overtime, expenses, travel & subsistence, notice period.
	HMRC will review its position after each of the milestones detailed in the specification on an ongoing basis and reserves the right to terminate the contract (for any reason) prematurely. For the purpose of this engagement the notice period will be 1 month.


	4.
	Project Information



	Project Title:
	Understanding the attitudes and behaviours of digital tech businesses towards tax requirements - and how HMRC can support their growth.


	Start Date:
	19 December 2016

	End Date:
	1st June 2017


	5.
	Payment Schedule

	#
	Milestone
	Anticipated delivery date*
	Total charge (excluding VAT)
(£)

	1
	Project set-up; manual sample building; development of topic guide and stimulus material
	01/02/17
	8,820

	2
	Completion of first 50% of fieldwork; interim findings presentation
	01/03/17
	13,258.75

	3
	Completion of final 50% fieldwork and ¾ of analysis work
	24/03/17
	17,016.25

	4
	Completion of analysis and delivery of final findings presentation; final report; planning workshop 
	01/06/17
	11,925

	* - The anticipated delivery date is not a fixed invoice point. Payment is made upon satisfactory receipt of services, certified by the Project Manager.
	Grand Total (£)

exclusive of VAT:
	£51,020

	Invoices relating to this Service Order should be sent to the HMRC Invoice Processing Centre (provided at 1. above) by email in pdf format, unless otherwise indicated.  All invoices must quote the Purchase Order Number.

Invoices received without a Purchase Order number may be rejected.




	6. Summary of Requirements / Role Description / Deliverables



	The section below should be used to provide clear summary of the requirements for delivery of the project/assignment.  It should include, where appropriate, milestones / key deliverables with dates, and any proposals for skills transfer (where relevant).


	Summary of Requirements 
HMRC’s specification of requirements are as set out in the Invitation to Tender issued to the supplier on 09/11/16.

Summary of supplier’s proposal 

Services will be provided by Ipsos MORI as set out in their tender dated 29/11/2016 (this document was redacted under section 41 of the Freedom of Information Act) [subject to the following clarifications]:
· The supplier was asked to increase the number of face-to-face interviews and to reduce the number of phone/skype interviews (75%/25%) – and therefore new pricing was provided. (this document was redacted under section 41 of the Freedom of Information Act)
Deliverables and payment milestones

Payment Milestone 1 - £8,820 + VAT 
Payable upon satisfactory receipt of the following deliverables, anticipated milestone date: 01/02/2017. 

· Set-up meeting
· Manual sample building
· Development of topic guide and stimulus

Payment Milestone 2 - £13,258.75 + VAT 

Payable upon satisfactory receipt of the following deliverables, anticipated milestone date: 01/03/17 

· Completion of first 50% of fieldwork
· Interim findings presentation

Payment Milestone 3 - £17,016.25 + VAT 

Payable upon satisfactory receipt of the following deliverables, anticipated milestone date: 24/03/17
· Completion of final 50% of fieldwork
· ¾ of analysis work
Payment Milestone 4 - £11,925 + VAT 

Payable upon satisfactory receipt of the following deliverables, anticipated milestone date: 01/06/17

· Completion of analysis

· Delivery of final findings presentation

· Delivery of final report

· Planning workshop

Any subsequent amendments or clarifications to the original response are to be delivered as agreed with the HMRC Project Leader or his/her nominated representative.



	


	7. Confidential Information



	As part of the Government’s Transparency Agenda, this agreement and any associated winning tender may be published.  The contractor must notify the project manager (provided at 1. above) of any commercially sensitive information to be considered for redaction prior to publication.  

(7.1) The following information shall be deemed Commercially Sensitive Information or Confidential Information:-

· detailed cost breakdowns including day rates (given on page 10 of the bid to tender) be excluded from Freedom of Information requests as this content is commercially sensitive. 

· discussion on our design, including why we propose particular methods
(7.2) Duration that the information shall be deemed Commercially Sensitive Information or Confidential Information:-

5 years



By signing and returning this Order Form the Provider agrees to enter a legally binding contract with the Authority to provide the Service specified in this Order Form together with, where completed and applicable, the mini-competition order (additional requirements) set out in section 3 of this Order Form.  Incorporating the rights and obligations in the Call-Off Terms and Conditions set out in the Framework Agreement entered into by the Provider and the Authority on 1st July 2013 and any subsequent signed variations to the terms and conditions.   

	For and on behalf of the Provider:-

	Name
	Jayesh Navin Shah

	Capacity
	Associate Director

	Signature
	(written signatures were used for this contract rather than electronic)

	Date
	13/12/2016


	For and on behalf of the HMRC:-

	Name
	Brian O’Callaghan

	Capacity
	Head of Research

	Signature
	(written signatures were used for this contract rather than electronic)

	Date
	14/12/2016


PAGE  
2
	HMRC Professional Services Team

Service Order 
	Page  of 4



