STATEMENT OF SERVICE REQUIREMENT FOR THE PROVISION OF TECHNICAL SUPPORT WITH THE DETAILED ASSESSMENT OF THE FAULT STUDIES  ASPECTS OF HINKLEY POINT C SAFETY SUBMISSIONS

1		BACKGROUND TO THE PROJECT

1.1	The HPC site has recently been licensed by the ONR to allow the Licensee, to construct and operate two EPRs. The HPC safety case documentation to support this activity is large and complex and a full assessment by ONR of Fault Studies aspects requires input from a number of specialists and skill areas.

1.2	Nuclear safety aspects of the construction, commissioning and operation of the site will be regulated by ONR via a series of regulatory permissioning points under specific Licence Conditions attached to the HPC site licence.  The assessment work that supports the different permissioning points, up to granting of the Consent for Nuclear Island Concrete, is split into a number of stages.

1.3	NNB have recently completed what they term the “Adjusting Phase” analyses for HPC.  The objective of the Adjusting Phase is not to provide a safety case update but to perform an internal validation of the detailed assumptions that will be considered in the “Realisation Phase” (supporting production of PCmSR).  The Adjusting Phase therefore supported the feasibility of the fuel management, the NSSS operating parameters and the modes of operation to identify risks and mitigations for the Realisation Phase with regards to fault analyses.  Assessment of this analysis is therefore important for the forthcoming permissioning points.

1.4	The work associated with the assessment of the Fault Studies aspects of the HPC safety submission is recognised as important in ONR’s programme of assessment of HPC safety documentation.  ONR therefore require additional assessment resource in the Fault Studies topic area to provide an adequate, efficient and timely assessment of the HPC safety submissions.

2	SCOPE OF THE SERVICES REQUIRED

2.1	The scope of the service requirement is to provide technical resources to assist ONR with the detailed assessment of the Fault Studies aspects of Hinkley Point C (HPC) safety submissions including:

- Submissions supporting the resolution of Generic Design Assessment (GDA) Step 4 Assessment Findings;

- Submissions supporting the resolution of Assessment Findings arising from GDA Issues closure activities;

- Submissions supporting the resolution of Issues arising from ONR’s review of the Pre-Construction Safety Report (PCSR) 2012; and

- Submissions supporting the claims made within PCSR3, and other safety justification documents.

2.2	The scope also includes provision of support to the Project Officer, as required, to interface with the ONR Fault Studies team and to assist in face-to-face meetings with the Licensee, including attendance at Fault Studies Level 4 meetings. It is therefore expected that a combination of a variety of levels of expertise, providing the resource effort of one full time equivalent, would constitute the most effective project team.

2.3	The scope of the proposed assessment work will also take full account of work by NNB GenCo (and ONR) that is still underway and which may affect the design of the HPC EPR.  In particular,

- Licensee’s responses to the Assessment Findings arising from ONR’s Generic Design Assessment of the UK- EPR design;

- Licensee’s responses to the issues raised from ONR’s assessment of PCSR 2012;

- Additional submissions by the licensee to justify the design changes resulting from the assessment or design evolution, and the associated design substantiation reports and justifications.  Currently no fixed date has been advised for completion of these deliverables; and

- Independent confirmatory analysis to examine the plant performance in accident conditions may be required to support the assessment of the safety justification provided by the Licensee.  The scope of this work is to be defined at a later stage.  The respondents may therefore wish to also include details of their experience in this area.

3	PROGRAMME OF WORK

3.1	The proposed programme of work for TSC support up to the granting of Consent for Nuclear Island Concrete, will be split into the following four stages:

Stage 1	Familiarisation with the GDA PCSR and the assessment findings arising from ONR’s assessments of these documents.  A review of the Licensee’s resolution plans to gain an understanding of the overall approach to the closure of these findings.  Development of an understanding of ONR’s sampling rationale and support preparation of a scope of work for subsequent Stages.  In addition, an initial review of the Licensee’s “Adjusting Phase” analysis will take place during this phase.

Stage 2	Detailed assessment of the sampled Assessment Findings closure packs and supporting documents available at the time and the Adjusting Phase analyses; completion by the end of March 2015. To include support for preparation of the draft ONR Assessment Report as part of the First Non-Permissioning Convergence Point.

Stage 3	Detailed assessment of Construction Safety Justification 01 (CSJ01) according to ONR sampling rationale. To include support for preparation of the draft ONR Assessment Report in June 2015 as part of granting Consent for FNSC.  This stage will also include the provision of confirmatory analysis in support of the overall Fault Studies assessment activities.

Stage 4	Detailed assessment of PCSR3 according to ONR sampling rationale. To include support for preparation of the draft ONR Assessment Report in August 2016 as part of granting a Consent for NIC.

3.2	Stages 1 and 2 are included in the scope of this current Invitation to Tender.

3.3		The bulk of the work will involve technical assessment of the HPC safety case and supporting documents from a Fault Studies perspective.  However a number of other aspects may also need to be considered, although Stage 2 will only consider some of these points, as indicated below. The following provides further detail of the work packages:

- Technical assessment of the HPC safety case and supporting safety documents according to the sampling regime developed by ONR’s Fault Studies Lead Inspector.  Review of the PCSR and related documents available at the time are part of Stage 2, to confirm that the safety submissions meet ONR’s expectations in line with the latest Safety Assessments Principles (SAPs).

- Inspection of NNB's Licence Condition 14 (LC14) arrangements as they affect the Fault Studies technical area, to confirm that the PCSR will meet the test of adequacy required by LC23(1) – not part of Stage 2.

- Contribution to the following discipline areas to ensure that any issues relevant to HPC design evolution are consistent with the intent of their definition and any issues raised by the Fault Studies assessment of the submissions.

  - Control and Instrumentation - Assisting with C&I related enquiries to ensure that the affected design modifications are adequate and consistent with any issues raised as part of this workstream – is part of Stage 2.

  - PSA - Assisting with PSA related enquiries to ensure that the PSA plant models, fault schedules etc., controlling the plant's response to initiated faults are adequate and consistent with any issues raised – is part of Stage 2.

  - Supporting the Fault Studies input to cross-discipline inspection activities by ONR on Licence compliance issues – not part of Stage 2.

  - Inspection of site construction works relevant to Fault Studies PCSR claims – not part of Stage 2.

  - Inspection of NNB GenCo’s supply chain, which are providing fault Studies SQEP resource to the HPC PCSR and supporting documents – not part of Stage 2.

4	OBJECTIVES

4.1	The required outcome of this work package will be a written report presenting an assessment of the Fault Studies aspects of the HPC safety submissions, and specified supporting documents for each activity. This may identify potential areas that will require additional regulatory attention for sampling during subsequent assessment.

4.2	The proposed resource will also support the Project Officer, interface with the ONR Fault Studies team and assist in face-to-face meetings with the Licensee, including attendance at Fault Studies Level 4 meetings.  This will include, but not be limited to, the provision of notes and presentations required for meetings with NNB GenCo, ONR inspectors and other team members for each stage of activity.

4.3	The report is expected to make recommendations to ONR and may form the focus of any potential independent confirmatory analysis.

4.4	This should enable ONR to produce an authoritative Fault Studies assessment of the HPC PCSR and supporting documentation, providing efficient and timely input to decision making associated with the regulatory hold points for HPC.

5	CONSTRAINTS

5.1	The Fault Studies assessment of documentation supporting the HPC safety submission will need to be carried out by suitably qualified and experienced persons and is covered by the TSF framework and thus subject to the necessary constraints.  The work covered by this request should be completed by the end of contract.

5.2	Conflict of Interest Considerations

- The potential risk of a conflict of interest for the individual(s) undertaking the work for ONR with regards to NNB GenCo should be avoided.

5.3	Relevant Skills and Experience

- The services require should be delivered by resource(s) with relevant knowledge and experience. In particular, the individual(s) should have a sound knowledge and understanding of ONR’s Safety Assessment Principles and their application by ONR inspectors.  Furthermore, familiarity with ONR and the UK regulatory environment would be highly beneficial.

5.4	Security Considerations

- Relevant documentation provided by NNB GenCo and ONR must be handled in accordance with the relevant security markings.  These will be provided by ONR.

5.5	Impact on or Interface with other Work or Systems

- There should be no impacts on ONR resulting from the work undertaken by the individual(s).

- There may be elements of the Fault Studies workstream, such as the confirmatory analysis, that may be performed by another Contractor; exchange of information and interface between the two organisations will be managed by ONR’s Project Officer.

5.6	Confidentiality Considerations

- A specific confidentiality agreement is not required, however, it is recognised that the output could be commercially sensitive. The appropriate security classification will be applied to documentation produced if required.

5.7	Working Arrangements

- The individual(s) will need to work closely with the ONR Project Officer and provide regular feedback and updates on the work.  In the course of the work the individual(s) will also need to engage with other ONR inspectors involved in the assessment of the HPC safety submissions.  It is expected that a significant proportion of this interaction will be undertaken in ONR’s offices in Bootle, in order to facilitate close engagement with the Project Officer and other specialist inspectors involved in the assessment of the HPC safety submissions.

5.8	Timescales

- The provision of resource under this contract should last for the duration of contract.

6	TIMESCALES AND IMPORTANT DATES

6.1	The permissioning dates for the First Nuclear Safety Concrete (FNSC) and Nuclear Island Concrete (NIC) are provisional but should be used, with the other milestone dates listed, to develop a proposal in response to the scope of work.

| First Non-Permissioning Convergence Point Draft ONR Progress Report (Complete) Deliverable from this scope of work | Oct 2014 Dec 2014 |
| --- | --- |
| First Nuclear Safety Concrete NNB GenCo issue of the 1st Construction Safety Justification (CSJ 01) to ONR Contractor Report Draft ONR Assessment Report CONSENT granted for FNSC | Apr 2015 To be Defined Jun 2015 Sep 2015 |
| Nuclear Island Concrete NNB GenCo issue PCSR3 to ONR Contractor Report Draft ONR Assessment Report CONSENT granted for NIC | Jun 2016 To be defined Aug 2016 Dec 2016 |

7	SUBMISSION OF TENDERS

7.1	To submit a compliant proposal in response to this specification Bidders must :

- Clearly address all aspects of the specification (including scope, objectives and constraints);

- Include a project plan and timetable covering each of the proposed tasks;

- Provide a description of the Technical Support Contractor team’s appropriate experience to undertake this work package, and how it will go about the task;

- Provide CVs of the key staff proposed. It is anticipated that the work will principally undertaken by a very small number of high calibre and experienced individuals with appropriate technical support, management oversight and quality assurance applied;

- Provide an anticipated cost and spend profile for the task, assuming a late November 2014 start date;

- Provide confirmation of availability of the key staff for the period of proposal;

- Provide the names and contact details of the Project and Contract Managers proposed for this task.

- Identify the anticipated engagement with ONR, including any progress meetings;

8	EVALUATION

8.1	Tenders will be evaluated across three stages of the procurement process :

- Compliance

- Quality

- Value for Money

as detailed in the Instructions to Bidders document which accompanies this Statement of Service Requirements (Schedule A) and the Evaluation Criteria and scoring mechanism outlined in  Schedule B.

www.onr.org.uk/new-reactors/reports/step-four/technical-assessment/ukepr-fsdbf-onr-gda-ar-11-020a-r-rev-0.pdf

www.onr.org.uk/new-reactors/uk-epr/gda-issues-res-plan.htm

www.onr.org.uk/new-reactors