Research specification: exploring the economics of land use change for increasing resilience to climate change in England

Tender Reference Number: ……………

Specification of Requirements

Invitation to Tender for research to explore the economics of land use change for increasing resilience to climate change in England

Tender Reference Number: ………………………

Deadline for Tender Responses: 21 November 2017

Contents

1.	Introduction and summary of requirements / Preamble	3

2.	Background	3

3.	Aims and Objectives	4

4	Methodology	4

5	Outputs Required	6

6	Ownership and Publication	6

7	Quality Assurance	6

8	Timetable	6

9	Challenges	7

10	Ethics	7

11	Working Arrangements	7

12	Skills and experience	8

13	Consortium Bids	8

14	Budget	8

15	Evaluation of Tenders	9

Criterion	9

Description	9

Weighting	9

# Introduction and summary of requirements / Preamble

The Committee on Climate Change (CCC) is an independent, statutory body established under the 2008 Climate Change Act. The Adaptation Sub-Committee (ASC), which is part of the CCC, was also established under the Act to advise the UK government and report to Parliament on progress on adaptation to climate change.

The CCC and ASC are tasked with:

- Providing independent advice to government on setting and meeting carbon budgets in line with the UK’s longer term target to reduce greenhouse gas (GHG) emissions by at least 80% by 2050 compared with 1990 levels, and reporting to Parliament on the progress made.

- Providing independent advice to the government on risks and opportunities to the UK from climate change, in part through the statutory UK Climate Change Risk Assessment, and reporting to Parliament on progress in adapting to climate change.

To do this the CCC and ASC conduct independent analysis into climate change science, economics and policy, and engage with a wide range of organisations and individuals to share evidence and analysis. The CCC and ASC’s past reports are available at http://www.theccc.org.uk/publications/.

The Adaptation Sub-Committee is planning to publish a report in 2018 on potential long-term outcomes for the natural environment in a changing climate.  As part of the work to support this report, we are interested in collecting evidence on how (actual or hypothetical) land use changes in specific parts of rural England could increase the level of resilience and stock of natural capital in the natural environment.

The aim of this contract is to determine a set of land use case study scenarios that would increase both the resilience of non-developed land to climate change, and the stock of natural capital, and quantify the costs and benefits of these scenarios compared to a ‘business as usual’ baseline.

# Background

The ASC has a statutory duty to report to Parliament with an independent assessment of the UK government’s progress in implementing its National Adaptation Programme.  This programme, published in July 2013, sets out the government’s objectives and policies for adaptation primarily in England, addressing the risks and opportunities identified by the UK Climate Change Risk Assessment (CCRA), first published in January 2012. The ASC published an Evidence Report to inform the second CCRA in July 2016, with the key findings subsequently presented by the government to Parliament in January 2017. One of the six priority risks identified by the ASC as needing urgent further action relates to the provision of natural capital, including terrestrial, coastal, marine and freshwater ecosystems, soils and biodiversity.

In 2015, the ASC produced its first statutory assessment of the National Adaptation Programme, followed by a second assessment in June 2017. These reports consider what actions are being taken to adapt to the current and future impacts of climate change across a number of sectors, and how vulnerability to climate hazards is changing over time. Both reports found that while much action is underway, vulnerability to climate change across a number of indicators in the natural environment is increasing.

Work is ongoing within government to better define desired outcomes for the natural environment and natural capital, in part through the work of the Natural Capital Committee and preparations for a government 25-year Environment Plan.  These outcomes have yet to be articulated by the government, but the 25-year Environment Plan is due to be published in the next few months. There is a question over how climate change will influence what is achievable and desirable for the natural environment over the long-term (up to 2100 and beyond).

The ASC is interested in understanding whether and how different land management and land use choices in specific geographical areas in England, compared to the situation today, could deliver net benefits for both resilience to climate change and maintenance and enhancement of natural capital including wildlife, soils and water.

# Aims and Objectives

The aim of this research is to understand how different land use and/or land management choices in specific locations in rural England could deliver benefits in terms of resilience to climate change and the provision of natural capital. The types of case study scenarios that might deliver such benefits include, for example, re-wetting of lowland peatlands; restoration of upland peatlands; afforestation; diversification of farmland; or integrated water management.

The project has two parts:

- The project team should determine a plausible set of land use change or land management case study scenarios, for particular geographical areas in England, that would likely deliver net benefits for climate change adaptation and the stock of natural capital under different future climate scenarios, out to 2100.  The land use scenarios need to be realistic and measurable but do not need to represent an optimised future (i.e. other plausible scenarios could exist that are not assessed as part of this contract).

- The project team should characterise these scenarios using metrics from the ASC’s indicator framework. As far as possible, the social costs and benefits of these scenarios should also be quantified to show how the net benefits from a social perspective differ compared to a baseline scenario where land use and management stays as it is today.

# Methodology

Bids should include a suggested methodology to address the aims of the project stated above, within the budget provided.  As well as detailing the number of case study scenarios that could be assessed, bids should set out:

For part a):

- A method for determining the set of land use change or land management scenarios to analyse.  It is suggested that bids consider the use of the following in determining the scenarios:

  - An expert panel. Bids could set out suggestions of who would be on this panel and what criteria the panel would use to determine the scenarios (for example, the case studies chosen could be justifiable on the basis that they are technically and financially feasible; and are known to have high net benefits for climate change resilience and the provision of natural capital).

  - A call for evidence, requesting published evidence on the benefits and costs  of different land use options for climate change adaptation and/or natural capital.

  - The government’s 25-year Environment Plan is expected to include proposed outcomes for the natural environment over the medium-term. Bids should include some discussion of how the project could ensure consistency between the land use or land management case studies used for this project and the intended outcomes of the 25-year Environment Plan, assuming it is published before the end of 2017.

For part b):

- A methodology for characterising each case study scenario. The analysis should focus on first quantifying the physical characteristics of each scenario for a limited set of key metrics that are of interest to the ASC. Bids should set out what sources of evidence could be used to characterise each scenario; for example using real world case studies. Some possible metrics to draw from are those used in the ASC’s indicator framework:

  - Area of agricultural land by Agricultural Land Classification grade

  - Carbon sequestration in soil

  - Carbon sequestration in trees

  - Proportion of [different habitat types] in favourable condition

  - Total area of specific habitat types

  - Connectivity of specific habitat types

  - Species abundance and occupancy

  - Proportion of water bodies meeting good ecological status

  - Total water demand for agriculture

  - Total yield by crop type/ tree type

- The ASC is also interested in understanding, as far as possible, the social costs and benefits associated with each scenario, in particular the benefits related to climate change resilience and natural capital improvements.  Bids should set out how far it might be possible to undertake a cost-benefit analysis for each scenario, compared to a ‘business as usual’ baseline, including a discussion on what constraints might limit the analysis of costs and benefits.  Any cost-benefit analysis undertaken should be in line with the HM Treasury Green Book.

- The characteristics and costs/benefits for each scenario should be analysed assuming a global temperature rise of approximately 2ºC and 4ºC by the end of the century.

- The analysis should take into account the timing of when changes in land use or land management would be made, for example in 2030, 2050 or 2080, to see how this affects the costs and benefits.  Bids should also include a description of how far it would be possible to sensitivity test the scenarios to other assumptions such as population growth.

The report write-up should include a discussion at the end on the potential for realising each scenario; for example what are the incentives and barriers are that exist.

Bids should also set out how the project findings will be reviewed. Time needs to be allocated in the proposed project plan for stakeholder meetings and review of the report by the ASC and external peer reviewers. In addition to any expert panel led by the project team, the ASC will set up a small government stakeholder panel to feed ideas into the project as it progresses and review its findings.  Time should be allocated in the bid for three meetings of the stakeholder panel and dealing with review comments (on methodology, emerging results and final results respectively).  Resource should also be allocated for minute taking for these meetings.

The Committee on Climate Change is undertaking a second project to derive land use and land use change scenarios that deliver deep emissions reductions.  The specification for this project is available here.  Bids should set out how they intend to work with the successful contractors on this mitigation project to ensure consistency of approach.

# Outputs Required

The ASC expects that the project will deliver the following outputs:

- A report outlining the aims of the project, method, and results of the assessment.

- An annex to the report describing how the method and outputs have been reviewed.

- A spreadsheet detailing costs and benefits for each scenario, including supporting calculations or evidence.

- Graphical representations, such as infographics, maps or charts, that describe the results, with visuals optimised for use on social media.

# Ownership and Publication

The results of the analysis and all outputs produced will be owned by and published at the discretion of the Adaptation Sub-Committee.

# Quality Assurance

The QA process to be followed to ensure the robustness of findings should be outlined in the bid.

# Timetable

An indicative timeline for deliverables is presented below. The contractors can propose modifications to the timeline to better suit their analysis if appropriate, though the final submission date must remain the same. Any proposed modifications should be set out in the bid and will require approval from the ASC secretariat.

| Phase | Deliverable | Date |
| --- | --- | --- |
| Bidding | Bids received | 21 November 2017 |
|  | Interviews conducted | w/c 27 November 2017 |
|  | Contract awarded | 1 December 2017 |
| Project development | Kick off meeting with ASC | w/c 4 December 2017 |
|  | Scenarios chosen | By end January 2018 |
|  | Analysis conducted | January – March 2018 |
| Reporting | Draft report to ASC and government review group for initial feedback | By 6 April 2018 |
|  | Second draft report to ASC and peer reviewers | 30 April 2018 |
|  | Final report submitted | 30 May 2018 |

# Challenges

The specific challenges that the ASC envisage with this project include:

- Justifying the choice of land use scenarios analysed, based on the likely benefits for resilience and natural capital.  The final report will have to explain why some scenarios and not others have been chosen for analysis, with reasons why.

- Making best use of the expertise and literature available in the time allowed for the project.  It is expected that the project team will already have an established network of experts to draw on and an in depth knowledge of the literature on land use and land use change.

- Ensuring consistency with the government’s forthcoming 25-year Environment Plan, as the timing for its release it unclear.

- Obtaining evidence to explore the social costs and benefits of different land use choices.

# Ethics

All applicants will need to identify and propose arrangements for initial scrutiny and on-going monitoring of ethical issues. The appropriate handling of ethical issues is part of the tender assessment exercise and proposals will be evaluated on this as part of the ‘addressing challenges and risks’ criterion.

We expect contractors to adhere to the following GSR Principals:

- Sound application and conduct of social research methods and appropriate dissemination and utilisation of findings

- Participation based on valid consent

- Enabling participation

- Avoidance of personal harm

- Non-disclosure of identity and personal information

# Working Arrangements

The successful contractor will be expected to identify one named point of contract through whom all enquiries can be filtered. A ASC project manager will be assigned to the project and will be the central point of contact.

# Skills and experience

The ASC would like you to demonstrate that you have the experience and capabilities to undertake the project. Your tender response should include a summary of each proposed team member’s experience and capabilities.

Contractors should propose named members of the project team, and include the tasks and responsibilities of each team member. This should be clearly linked to the work programme, indicating the grade/ seniority of staff and number of days allocated to specific tasks.

Contractors should identify the individual(s) who will be responsible for managing the project.

# Consortium Bids

In the case of a consortium tender, only one submission covering all of the partners is required but consortia are advised to make clear the proposed role that each partner will play in performing the contract as per the requirements of the technical specification.  We expect the bidder to indicate who in the consortium will be the lead contact for this project, and the organisation and governance associated with the consortia.

Contractors must provide details as to how they will manage any sub-contractors and what percentage of the tendered activity (in terms of monetary value) will be sub-contracted.

If a consortium is not proposing to form a corporate entity, full details of alternative proposed arrangements should be provided. However, please note CCC reserves the right to require a successful consortium to form a single legal entity in accordance with Regulation 28 of the Public Contracts Regulations 2006.

CCC recognises that arrangements in relation to consortia may (within limits) be subject to future change. Potential Providers should therefore respond in the light of the arrangements as currently envisaged. Potential Providers are reminded that any future proposed change in relation to consortia must be notified to CCC so that it can make a further assessment by applying the selection criteria to the new information provided.

# Budget

The budget for this project is up to £50,000 including VAT, with 95% of the project costs

to be paid in the 17/18 financial year and 5% in the 18/19 financial year.

Contractors should provide a full and detailed breakdown of costs (including options where appropriate). This should include staff (and day rate) allocated to specific tasks.

Cost will be a criterion against which bids which will be assessed.

Payments will be linked to delivery of key milestones. The indicative milestones and phasing of payments can be adjusted and agreed with the contractor and Project Manager. Please advise in your tender response how this breakdown reflects your usual payment processes.

In submitting full tenders, contractors confirm in writing that the price offered will be held for a minimum of 60 calendar days from the date of submission. Any payment conditions applicable to the prime contractor must also be replicated with sub-contractors.

The CCC aims to pay all correctly submitted invoices as soon as possible with a target of 10 days from the date of receipt and within 30 days at the latest in line with standard terms and conditions of contract.

# Evaluation of Tenders

Contractors are invited to submit full tenders of no more than 25 pages, excluding declarations. Tenders will be evaluated by at least three CCC staff.

The ASC will select the bidder that scores highest against the criteria and weighting listed below, see the ITT for further information.

EVALUATION CRITERIA AND SCORING METHODOLOGY

| #### Criterion | #### Description | #### Weighting |
| --- | --- | --- |
| 1 | RELEVANT EXPERIENCE / DEMONSTRATION OF CABABILITY | 20% |
| 2 | MANAGING YOUR RELATIONSHIP WITH THE CCC | 5% |
| 3 | QUALITY ASSURING THE SERVICES YOU PROVIDE | 10% |
| 4 | MANAGEMENT STRUCTURE | 10% |
| 5 | PROJECT TEAM – SKILLS AND KNOWLEDGE | 15% |
| 6 | METHOD, ABILITY AND TECHNICAL CAPACITY | 20% |
| 7 | UNDERSTANDING OF REQUIREMENTS | 10% |
| 8 | RISK AND CHALLENGES | 10% |
|  |  | 100% |

Scoring Method

Tenders will be scored against each of the criteria above, according to the extent to which they meet the requirements of the tender. The meaning of each score is outlined in the table below.

The total score will be calculated by applying the weighting set against each criterion, outlined above; the maximum number of marks possible will be 100.  Should any contractor score 1 in any of the criteria, they will be excluded from the tender competition.

| Score | Description |
| --- | --- |
| 1 | Not Satisfactory: Proposal contains significant shortcomings and does not meet the required standard |
| 2 | Partially Satisfactory: Proposal partially meets the required standard, with one or more moderate weaknesses or gaps |
| 3 | Satisfactory: Proposal mostly meets the required standard, with one or more minor weaknesses or gaps. |
| 4 | Good: Proposal meets the required standard, with moderate levels of assurance |
| 5 | Excellent: Proposal fully meets the required standard with high levels of assurance |

Structure of Tenders

Contractors are strongly advised to structure their tender submissions to cover each of the criteria above and supply a price schedule specifying the daily rates (ex-VAT) you will charge for each level of your staff.

Evaluation for Interviews, if held

CCC reserves the right to award the contract based on applicants’ written evaluation only if one candidate emerges from the evaluation stage as significantly stronger than the others.

Should interviews go ahead, they are provisionally expected to be held on the week commencing 27th November. If this date changes, the ASC will notify applicants.

The areas to be covered in the interview will be sent to the shortlisted supplier prior to interview.

Further details of interviews will be sent to successful applicants on selection.

Feedback

Feedback will be given by email.

The scope of this project is land outside of urban areas

See the ASC’s indicator dashboards at https://www.theccc.org.uk/publication/2017-report-to-parliament-progress-in-preparing-for-climate-change/

https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/220541/green_book_complete.pdf