## Nr 1A Antique Shop
Schedule of Works 18.01.24 updated 12.09.24
Multiplier | Length | Width | Depth | Sum | Total | Nr 1A The Strand, Newlyn | Quantity | Units | Rate | TOTAL
Antique Shop
based upon D.Tregear Building Reg Notes dated 11/9/24 and RGC 2209/114 issue 10/9/24
Sand and seal existing wood block flooring
Lift woodblocks from WC,excavate areas of cement infill to wood block floor in retail rear area and screed WC gaps created
Remove floor over line of new partition footing as RGC drawing 200 ( provisional item)
Remove WC/rear store partition if structurally inadequate ( provisional)
Remove door and frame
Remove windows, internal and external cills and infill with insulated cavity blockwork and 2 x 12,5 plasterboard both sides, skim plaster finish
Remove partition walls
Make good walls, floor and ceiling where walls removed
New studwall infill, 100x50 studs, 50 mineral wool insulation, 12.5 Gyproc 10 plasterboard and skim both sides
new skirtings Gfloor
Remove existing wc and wash basin
Install ceramic tiles over wash basin
New WC pan and wash basin ( Doc M pack presumed)
Self level compound over wood blocks in WC and install Palio Click Flooring
[6 empty] | Provide new serving/display counterwith glass top and glass panel both above worktop level with shelves/cupboards under as image shown, size 2400 x 600x 900 or to suit understairs headroom. | 1 | Provisional | 2000
Sum
Remove ceiling to main shop area
new 100mm 7N block parttion tied to masonry each end and strapped to joists as RGC detail 5 ( provisional)
New steel columns C1 & C2, bolt to beam over, dry resin bolt to existing masonry as RGC detail 6, fire box with 2 x 12,5 fireline and plaster skim
New steel beams B5 to B8 , connect to other beams/columns as RGC details, fire box with 2 x 12,5 fireline and plaster skim
padstones inserted into existing walls P1.2 & 3, make good to structure and 2 x coats RIW LAC to beam ends built into masonry.
Timber shaped bearers in web of steel bolted, and joist hangers to pick up floor joists
Levelling timbers over steel beams where joist depth less/greater than steel beam to level boarding over
Provide ceiling joists 195x44 C24
Joist hangers
Joist strutting/noggin 3/4 depth
Pole plates bolted to existing walls, separate from masonry with dpm
30x5 restraint straps at 2 m centres between joists at perimeters and masonry existing
Triple Trimming for stairwell and wall alcoves
50x50 noggins
Chipboard 22mm
Laminate flooring
Skirting
Acoustic quit in floor void 100mm 10kg/m3
12.7mm gyproc 10 plasterboard and plaster skim
New staircase, pine strings, square spindle balustrade, pine risers and treads,
Handrail wall mounted
Parapet wall/landing balustrade
Stair Soffit board and skim, batten supports
Screw shut door pair behind stairs
Insulation between pitched roof rafters, 80mm PIR insulation board, 50x25 noggins and 60mm PIR insulation under, with plsyerboard and plaster skim
Bare stone gable above ceiling- stud off and install insulated plasterboard and plaster skim
foil isolation mat under underfloor heating
[6 empty] | Electrical works- downlighters first floor, 5 double sockets, light switches top and bottom of stairs, smoke detector, bathroom light switch relocated, replacement lights in rear retail area, fused spur for and to include heating mat, wire in thermostat, rear of counter outlets. | 1 | provisional | 7000
sum
Builders work in connection with the electrical work, including tile adhesive bedding of underfloor heating mat
Guarding up to 800mm high in front of first floor windows
Remove slates to lean to roof
Remove abutment flashings
Remove stepped flashings
Remove eaves boards and gutters
Add 2 coat external render to wall previously internal now external
render stop bead
Remove rafters, purlins and ceiling ties
Remove ceiling and any insulation
New 140x50 wall plate and straps
Bolted pole plate 170x72 C24
New flat roof joists 170x44 C24
Joist strutting/blocking 3/4 depth
Double Trim joists for latern light 170x44 C24
Wrap ends of joists/timbers in dpm where they touch masonry walls
Firrings
22mm ply decking above and below insulation
150mm thermaroof TR27 bonded insulation on 2nd ply layer
single ply membrane
ditto dressed to upstands
ditto dressed to new box gutter ( supplied under Gallery contract)
Joist hangers
Plasterboard and skim ceilings
50x50 noggins
Lantern light with upstand and insulated shaft 1mx 1m
Ditto 1.5mx1m
New Code 4 lead flashing chased into stone walls,
Rear retail room and WC- strip plaster, point and one render coat, tanking slurry, plasterboard on battens and plaster
Remove and replace skirting
Decoration to:-
Ceilings
Walls internal
Walls external
Internal doors and inside face of external doors
Mouldings/linings ne 300wide
Prime only back of mouldings
Inside face of windows
Decoration to stairs
Preliminaries, including Principal Contractor duties under CDM regs
Overhead and Profit
Contractor costs only Total exc vat
Vat at 20%
Total for Contractors costs inc vat

## Gallery & Cafe at Nr 1
Schedule of Works 18.01.24 updated 12.09.24
N1, The Strand, Newlyn
Multiplier | Length | Width | Depth | Sum | Total | Gallery and Café | Quantity | Units | Rate | TOTAL
based upon D.Tregear Building Reg Notes dated 11/9/24 and RGC 2209/114 issue 10/9/24
Remove ground floor ceiling
Replace ceiling with 2 x 12.5 soundbloc plasterboard., on RB1 resilient bars & skim plaster finish. Fill joist void with 10kg/m3 100mm Isover APR1200 quilt and overlay floor above with acoustilay15 matting
Remove flat roof covering, deck, insulaion, joists, firrings and ceiling under
Remove flat roof eaves
Remove flat roof perimeter abutments
Remove kitchen units
Walls previously external now internal, rake out,repoint, dub, 2 coats RIW LAC-75 x50 stud, 60mm celotexGA4000 insulation, vapour barrier, 12.5 plasterboard dry line, and plaster skim
hack off render bellcasts
Remove doors and linings
Remove windows, internal and external cills
Remove wall panel- external wall and prop
Remove internal wall and prop
Remove internal wall and prop
Remove floor slab and build up for Ground beam and column pad foundation
Form ground beam 400x300 with rebar as schedule, 50 concrete blinding under, reinstate floor make up and dpm
Form column pad foundation 900x900x450 with rebar as schedule, 50 concrete blinding over, reinstate floor make up and dpm over
2 nr brick piers 225 x 225 tied to existing masonry partition built off new ground beam and cast padstones on top to underside of steel beam
Steel beam B1, dry pack grout to masonry over & 2 x 12.5 fireline plasterboard & skim fire box in
Steel beam B2, dry pack grout to masonry over &2 x 12,5 Fireline plasterboard & skim fire box in
Steel beam B3, dry pack grout to masonry over & 2 x 12.5 fireline plasterboard & skim fire box in
Steel beam B4 galvanised, dry pack grout to masonry over & 2 x 12.5 fireline plasterboard & skim fire box in
Steel Column & 2 x 12.5 fireline plasterboard and skim fire box in, bolt to pad and dry pack under base plate
Break out wall top/ recess into wall and insert 2 padstones, 700x200x300 and 400x200x100
First floor joists propped and cut for new beam insertion, shaped new joist inserted into beam web, bolted back to back and connected to existing joists by joist hangers
Remove wc and washbasin
Excavate yard slab and cart away, compact
150mm hardcore, 50mm sand blind, 1600 gauge dpm 100mm celotex GA4000 insulation, A142 mesh, 100mm concrete and 22mmT&G chipboard .
Dowel edge of new slab to old
Radon sump 600x600
Radon pipe and bedding
radon bend and riser to above flat roof level and box in with 38x38sw framing, 2 x 12.5 plastwerboard and skim, void filled with 25mm quilt
Replace manhole cover with double seal type and raise manhole kerbs to new slab level
Extra surround shallow drains in concrete
New stud partition, 100x50 studs, dpc, insulation, gyproc 10 plasterboard and skim both sides. 50mm mineral wool between studs
Make good floor, walls and ceilings where walls removed
RIW or similar epoxy coating to existing floor slab as dpm
Hack off plaster, point, render, tanking slurry, plasterboard, batten and skim plaster
Remove and replace skirtings
Hole 450 thick wall for waste pipe
Rearrange drains to new wc and basin
New connection of waste pipe onto existing yard foul drain.mini manhole or similar arrangement
New pole plates 200x44 xC24 and wall plates with straps
Flat roof joists 220x44 C24
Joists/ends touching walls to be wrapped in dpm
Joist strutting
Joist hangers
Firrings
Box gutter
Trim joists for lantern light
Lantern Light, upstand and shaft
22mm ply decking
150mm thermaroof TR27 bonded insulation
Single ply membrane on 2nd 22mm ply layer
12,5 Plasterboard and plaster skim to ceiling with vapour barrier
50x50 noggins
Code 4 Flashing and bellcast at abutments
new skirtings
Stairwell 30 minute partition 75 x50 stud wall, 2 x 12.5 Soundbloc plaster board each side with plaster skim.resilient bars RB1 one side, mineral wool 10kg/m3 between studs.
30minute fire door and frame to lobby/stairs
WC, cupboard and lobby doors 30minute rated
2 x 12.5 Plasterboard on RB1 resilient bars and plaster skimng to underside of stairs/boiler room
Levelling screed over electric underfloor heating mat ( inc in electrical provisional sum)
Vinyl sheet or LVT to all areas
Servery hygienic wall panelling
[6 empty] | Servey counter with lift up flat |  | Provisional | 5000
sum
[6 empty] | Preparation counters and cupboards over and under- mostly refrigerated display units in client seaparate budget |  | Provisional | 1000
sum
Hob/oven/sink/dishwasher/washing machine- direct by client, except plumb to sink/dishwasher/water heaters only now
Doc M disabled WC pack with basin and grab/hand rails
[6 empty] | Electrical works- downlights surface mounted, switches, power outlets, water heaters and kitchen supplies, extract fans, smoke and co2 detectors, ceiling edge lighting for art display, fire alarm to BS55839, underfloor heating mat etc | 1 | provisional | 7000
sum
Builders work in connection with electrical work to include tile adhesive bedding for underfloor heating mat and cutting down external door for increase in floor levels.
Builders work in connection with plumber
Decoration to:-
Ceilings
Internal walls
Mouldings less than 300 wide
Mouldings- prime back
Decoration to doors internal
Inside face of windows
Preliminaries, incluiding Principal Contractor role duties under CDM Regs
Overheads and Profit
Contractor costs only Total exc vat
Vat at 20%
Total for Contractors costs inc vat