## Sheet1
|  | Construction Cost Plan To Complete Refurbishment of The Greenham Control Tower |  |  |  |  | UPDATED FEB 19TH 2017
A | External Building Works Work |  |  | £ | Source Of Price
| Pointing Repair To Brickwork |  |  | 25000 | Reduction from Original Bill of estimates
| Refurbish Exterior Metal Doors |  |  | 2000 | Original Bill of estimates
| Paint External Doors |  |  | 1500 | Original Bill of estimates
| Commission window shutters |  |  | 3640 | costello quote 280+vat per shutter not on original schedule
| Main Entrance security shutter |  |  | 2800 | costello quote
| Emergency Lighting at Exits |  |  | 1000 | ESTIMATE not in original schedule |  |  | More accurate quote waited for
| Electrics to door shutter |  |  | 1200 | ESTIMATE not in original schedule |  |  | More accurate quote waited for
| Minor repair to window mastic |  |  | 100
| costello shutter reapir to one shutter |  |  | 350 | costello know of repair need
B | External Works Non Building
| Concerte ramps to entance x 2 |  |  | 300 | Ballast and cement known price
| reinforcing bar for concrete |  |  | 120 | Buildbase estimate
| Removeable disable ramp x 1 with rail |  |  | 500 | Bentley Fielden instead of a concrete ramp due to manhole
| Bike racks x 2 |  |  | 682 | Falco
| Bike rack bases |  |  | 475 | ballast and cement known price
| 300m2 turf |  |  | 600 | known price
| 18t soil full load x 2 |  |  | 406 | moulds | 11.50 tonne
| Muck Away x 2 |  |  | 640 | 320 + vat load no test
| Material for path |  |  | 225 | scalpings known price
| coxwell path gravel |  |  | 300 | grundon price
| concrete base for bomb |  |  | 500 | Original Bill Of Quants
| metal frame for Bomb |  |  | 500 | Original Bill Of Quants
| Hand rail for ramps |  |  | 450 | Interclamp estimate
| Post and mesh fencing 160m |  |  | 983.7 | Mcveigh parker
| Gates 2 |  |  | 620 | centrewire original supplier
| Labour for ramps |  |  | 1620 | Four corners |  |  | More accurate quote waited for
| labour for turf and paths |  |  | 3888 | Four corners
| labour for new fence |  |  | 4212 | Four corners
| Labour to remove existing fence |  |  | 2700 | Four corners
| Labour for ground levelling, manholes, french drain |  |  | 2520 | Four corners
| Recycling waste bins x3 |  |  | 1167 | Derby E double Recycling Bin
| rejcts for fernch drain |  |  | 100 | known price
| BT manhole reparis |  |  | 450 | New to the schedule
C | Internal Works
| Fire Doors - remedial work |  |  | 5071 | Good original work
| Flooring inc levelling andn internal café raMPS |  |  | 9750 | Good original work
| Plumbing |  |  | 1650 | Original Bill Of Quants
| Cubicles For ladies and gents |  |  | 2000 | Original Bill Of Quants
| Painting Internal |  |  | 5000 | good original work
| Supply and fit missing door furniture and locks |  |  | 300 | Original Bill Of Quants
| Refurb of door on viewing gallery |  |  | 600 | Original Bill Of Quants
| Telecome cabling all offices |  |  | 3500 | New idea based on proposal from GCT. Need to review and consider
D | Interpretation
| Artefacts reinstatement |  |  | 2500 | Increase on origainal estimate meeting greenham common trust
| Monitors and wiring for viewing gallery and café |  |  | 2608 | original bill of quants
| Interpretation displays |  |  | 7500 | original bill of quants
| Website |  |  | 100
E | Professional Fees
| Listed Building Fees discharge |  |  | 400 | revised from Bill of quants
| Provision site visist x2 |  |  | 550 | Revised Pro vision quote
| Provision drawings and time charges provision |  |  | 2000 | Revised Pro vision quote
| Project Manager - ? |  |  | 18000 | estimate not in original proposal
| Fees for promoting café and Offices - Vitalsix? |  |  | 3500 | mid estimatwe from Vitalsix
| Legal Fees on leases to café and offices |  |  | 1000 | Estimate
| Fees for forming and registering new entity with commission |  |  | 500 | on line estimate
| Legal Fees for drafting lease between GPC nad new entiity |  |  | 2000 | Estimate
| Public Consultation Cost |  |  | 550 | comms plan
| Horsey Lighley Letter |  |  | 500 | Quote Not in original estimate
| Brown Road Signs |  |  | 1000 | estimate not in original proposal
| asbestos revew |  |  | 1000 | estimate if needed
| Hand over fund to Operating trust |  |  | 10000 | What do we handover to the operating company?
F | Contingency @10% |  |  | 143127.7
| Contingency @10% of build |  |  | 13000
|  |  | Total with contingency | 156127.7
All Cost are subject to VAT
Notes
The outside layout could change due to planning but these figures assume post and rail stock fence and gate similar to those on site
Rather than a concrete path a 'binding path gravel' one has been allowed for - this could change
|  | in red are extra items not on the original schedule which we may wish to consider |  |  |  |  | 44857