## Slide 1: Warm Homes: Social Housing Fund Warm Homes: Local Grant
Sept 25 – Pre ITT Launch Notice Pack

## Slide 2: Indicative Procurement Timetable
Procurement Activity | Date
ITT Launch | Monday 6th October
Deadline for bid submission | 17th November (6-week window)
Evaluation & Moderation Concludes | Late December 25
Contract Award Date | 20/3/26
Indicative Contract Signature & Start of Mobilisation | 30/3/26
Mobilisation/Implementation Ends | 22/6/26
Please note:
All indicative dates and activities listed are pending subject to receiving departmental, Cabinet Office and ministerial approval. The Department is NOT considering options to extend the ITT from the six weeks noted above. DESNZ reserves the right to change or halt the procurement process at any stage.

## Slide 3
Pre ITT Publication Update
In October 2025, the Department for Energy Security & Net Zero will launch its invitation to tender for a Delivery Partner to work in partnership with the Department in overseeing delivery of the following flagship domestic energy efficiency and clean heat Government schemes: Warm Homes: Social Housing Fund Wave 3” (WH:SHF Wave 3) Warm Homes: Local Grant” (WH:LG) Part of the Government’s Warm Homes Plan, these schemes represent over £2bn of capital investment into energy efficiency and clean heat measures. The schemes will contribute towards the Government’s legally binding commitments on carbon reduction and generate significant energy bill savings for some of the lowest income households in the country. Both schemes launched in April 2025 and are now well underway with delivery up and down the country. Delivery support for scheme grant recipients is currently being delivered under interim arrangements by Turner & Townsend (T&T). Scheme delivery & grant recipients will transfer to oversight of the successful bidder from around May 2026, following handover from T&T.

## Slide 4
Requirements Overview
The below slides provide a high-level overview of the delivery requirements and are largely unchanged since the market was last briefed at the end of 2024.
In spring 2025, the Department published a draft version of its requirements (‘Schedule 20’), and this remains available as an attachment to download pre-ITT on the last Prior Information Notice (PIN) issued. The link to the PIN can be found below. N.B. this draft was produced at a period in time and has evolved in the intervening six months. The draft should not be considered definitive to the latest requirements:
Delivery Partner 2 (DP2) - WH:SHF and WH:LG - Contracts Finder
Further to the publication of the draft Schedule 20 document in spring, the Department also established its DP2 Data Room. A wide range of relevant documents have been added to the Data Room since it was created and a series of further publications, including detailed ‘Play Books’ for both schemes (outlining in detail all of our scheme processes) will be issued before the ITT publication date. The Department aims to ensure the Data Room resource is comprehensive to bidder requirements and forms part of its ambition to ensure a competitive and level playing field for all bidders.
The Department continues to develop and roll out its ‘Grant Management System’, a Salesforce based solution for use by the Dept, Grant Recipients, and the Delivery Partner, to effectively manage end to end delivery processes covering project change requests, grant drawdown, fraud and error, and many more. The Department will issue all training videos and user requirements for the solution as part of the publications to the DP2 data room.

## Slide 5: Allocation of Funding: Phase Requests and Batch Processes (previously Application Process Management)
Summary of Service Package
Outlines the potential requirements for managing and executing the application and assessment stages of the Schemes with key objectives of:
Ensuring that only Projects that meet the Schemes’ minimum criteria thresholds and are deemed deliverable are awarded a Grant.
Ensuring that the process for assessing and awarding Grants is completed in a fair, transparent, and timely manner.
As the schemes are different in nature, it will be essential to process the requirements and policies differently.
Supplier responsibilities | Mobilisation Period (approx. 12 weeks) | Delivery Period (once onboarded)
WH: LG | Develop in-depth understanding of Scheme and Memorandum of Understanding (MoU) obligations utilising policy guidance and Scheme Playbook (to be provided by the Buyer) Review Grant Recipient EOI applications (Buyer led), Mid-Mobilisation Reviews and Delivery Assurance Checks (Buyer led) that have been completed prior to Onboarding. Work with existing Suppliers and the Buyer to understand delivery progress, forecasts and GR performance to date. | Manage Grant Recipient monthly engagement Manage the Batch Assessment process: assess and approve batch applications submitted by the Grant Recipient, freeze batch applications to ensure policy compliance where applicable.
WH: SHF | Develop in-depth understanding of Scheme and GFA conditions, and policy determinations. Review handover pack of W3 Applications and Early Delivery documentation/stats to develop knowledge of GRs’ initial baselines, delivery plans, changes and performance to date. Design end-to-end process for the management of Phase Requests in consultation with the Scheme, based on the arrangements employed during Early Delivery. Submit it for the Buyer’s approval. | Implement and manage the Phase Requests Process (i.e., support GRs to produce quality Phase Requests, assess detailed plans for each phase of Challenge Fund GRs’ delivery, recommend on approvals to unlock GR access to grant funds for each phase, update initial baselines with phase details, monitor and report on the delivery of phases, etc.). Provide full assessment services for additional rounds of Applications, if any takes place (i.e., provide assessment team, carry out assessments and moderation, recommend on assessment decisions, etc.)
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 6: Application Process Management
Key Changes from initial briefing:
Greater clarity on cross-cutting roles and responsibilities, including detailed and specific process maps to enhance understanding of interdependencies between Supplier and the Department.
Greater clarity and simplification of the Grant Recipient (GR) journey to outline roles and responsibilities of the Supplier during the Mobilisation phase until they are onboarded. This includes the Mid-Mobilisation Review. The DAC (Delivery Assurance Check) process has been de-scoped.
These processes will assess Grant Recipient readiness to begin delivery and draw down further funding via the Batch Process.
Expanded detail on Phase Request Process – outline of info/metrics to be assessed, breakdown of Supplier’s activities for the management of the end-to-end process, outline of reporting and governance requirements (monthly + quarterly).
Removal of the Service Package to facilitate future rounds of application, assessment and award of funding under the EOI (WH:LG) and Application (WH:SHF) processes.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 7: Application Process Management (R&R)
Department
Application/EOI process management
MoU/GFA, DSA, and NDA issuing and signing
Governance and Payments
Assessment criteria and assessor training - where additional round of applications takes place during term of the contract
Managing and facilitating DACs, supporting GRs through the process and providing recommendations and escalations to the Buyer.
Supplier
Review and familiarisation with documentation and systems to enable takeover of the relationship management with GRs.
Supports GRs in batch submissions, application revision and clarifications. Escalations, tracking trends, approve/reject applications and informing both GRs and buyer of outcomes.
End-to-End management of Phase Requests Process for Challenge Fund GRs, including support for development of submissions.
Application assessment services - where additional round of applications takes place during term of the contract.
Grant Recipient
Submit the required accurate and timely submissions.
Adhere to and meet schemes criteria and requirements in line with the policy guidance, MoU and GFAs.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 8: Project Performance and Management
Summary of Service Package
Outlines the requirements for the provision of an oversight framework to ensure the effective programme management of the Schemes and GR Projects.
This service package will involve designing, implementing, and managing operational structures, processes and procedures for the coordination and integration of all Supplier responsibilities and activities, across all service areas.
The supplier will forecast and drive delivery by:
Monitoring, controlling and reporting on performance and trending of outputs and outcomes;
Managing risks and issues;
Building and supporting GR capability
Identifying and mitigating early indicators of underperformance, supporting GR development and implementation of ‘nursing back to green’ activity as necessary;
Identifying and managing necessary change;
Maximising and tracking overall benefits.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 9: Project Performance and Management
Key Changes from initial briefing:
Recognition of varied GR capability, capacity and maturity levels; acknowledgement of subsequent differences in breadth, complexity and engagement demands for the provision of support to different GRs and schemes.
  Clarity on the distinct nature and purpose of BAU/regular support activities, Direct Advisory Support and ‘Nursing back to Green’ activity.
  Definition of Direct Advisory Support categories to build capability outside of BAU PSO engagement (i.e., Technical Compliance and Specialist support).
  Clarity on Supplier’s delegated authority for prompt deployment of Direct Advisory Support, where appropriate.
Enhanced breakdown of BAU/regular engagements and support activities required as part of the monthly cycle to guide and monitor GRs, including their scalability and flexibility, aligned to a ‘risk-based approach’.
Enhanced description of PSO role; clarity on balance of support, challenge and monitoring responsibilities, as well as on essential skills and experience required:
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 10: Project Performance and Management (R&R)
DEPARTMENT (BUYER)
Sets out the principles that will inform the programme management of the Schemes and GR Projects.
Approve processes designed by the Supplier before implementation.
Hand over templates, records and details associated with all interim processes implemented during Early Delivery.
Approve Direct Advisory Support and ‘Nursing back to Green’ plans.
Advise the Supplier on Scheme conditions and policy determinations.
Agree and approve DCA recommendations from Supplier
SUPPLIER
Design, implement and manage an oversight framework for overall programme management, adapting processes and products to the requirements of each Scheme.
Provide dedicated PSOs for each GR Project to lead all BAU/regular engagement and support with GRs, as well as all other monitoring and control activities (e.g., quality assurance of regular reporting returns).
Provide administrative services, assessments and reviews, performance and financial monitoring, and reporting on outputs, outcomes and benefits.
Conduct monthly Delivery Confidence Assessments, and Performance Status evaluation of every GR Project, including management of associated governance forums.
Assess need for and deploys Direct Advisory Support to address early indication of GR Project underperformance.
Monitor need for and supports GR development of ‘Nursing back to Green’ activity to address evidenced consistent underperformance.
Conduct quarterly Monitoring and Performance Patterns and Trends Reviews, and annual Benefits Reviews and Strategic Partners (SHF only) Reviews, including management of associated governance forums and production of associated reports.
GRANT RECIPIENT
Engage with PSOs for all regular monitoring, communication and queries.
Comply with grant conditions and policy determinations.
Adhere to regular reporting return conditions (timelines, completeness, quality).
Collaborate fully with Delivery Confidence Assessments and Performance Status evaluations.
Produce and implement Remediation Plans, where required.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 11: Change Control of GR Projects
Summary of Service Package
Outlines the requirements for the provision of a Change Control Process to ensure that changes to GR Project baselines and delivery plans are managed effectively and transparently.
This requirement will involve driving a culture of change control as last resort, acting as a critical friend to advise and support Grant Recipients to develop and implement early mitigations to minimise the number of required changes, managing the risk of need for change.
The supplier will manage necessary change by:
Advising and supporting Grant Recipients on the production of high-quality Change Requests, according to Scheme conditions and defined quality criteria.
Designing and implementing a Quality Assurance (QA) process to validate change request quality before progressing on to decision-making stage.
Managing the end-to-end process to approve/reject Change Requests (i.e., receipt, acknowledgement, quality assurance, review and evaluation, decision-making within delegated thresholds, escalation with recommendation for decision-making of cases exceeding delegated thresholds, outcome notification, and management of records).
Managing all change control forums, including production of necessary documentation and artefacts.
Developing and maintaining a surge capacity plan for the provision of flexible and scalable resource levels to manage fluctuations in the volume of change requests.
Monitoring the performance of the Change Control Process and tracking change patterns and trends, utilising reported findings to inform continuous improvement.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 12: Change Control of GR Projects
Key Changes from initial briefing:
Enhanced definition of quality standards for Change Requests that will inform supplier advice and support, and quality assurance activities.
Recognition of potential need for SME resource to address PSO capability gaps in the quality assurance and evaluation of Change Requests.
Recognition of process stages outside the supplier’s control to inform the determination of turnaround times for specific actions.
Clarity on the distinction of steps for the processing and decision-making for change requests within delegated thresholds.
Clarity on monthly and quarterly reporting requirements and associated metrics.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 13: Change Control of GR Projects (R&R)
Department (Buyer)
Set tolerance levels and associated trigger points for intolerable change for each Scheme and funding model – Policy red lines.
Set thresholds for the Supplier’s delegated authority.
Defines escalation routes and required governance structure.
Decide on change requests that exceed Supplier’s delegated thresholds.
Hand over templates, records and details associated with change requests processed during Early Delivery.
Supplier
Drive a culture of change control as a last resort in the management of the change control process.
Understand GR Project conditions and risks to advise, challenge, and influence GRs to minimise instances of change.
Provide guidance, advice, support, and clarification to GRs regarding all aspects of the change control process, including on the production of change requests.
Ensure high-quality change request submissions which make a clear case for change (i.e., include comprehensive rationale and impacts) to inform effective decision-making.
Evaluates all change requests, taking decision within delegated thresholds, and escalating recommended outcome for decision by the Department where thresholds are exceeded.
Monitor the performance of the change control process and change patterns and trends.
Conduct monthly and quarterly reviews against defined metrics, including management of associated governance forums and production of associated reports.
Grant Recipient
Manage risks under the Supplier’s advice to minimise need for change.
Understand Policy red lines which inform change control decisions.
Produce high-quality change requests under the Supplier’s advice.
Collaborate fully with the change control process, further developing change requests when advised to by the Supplier.
Commits to delivery against updated baselines and targets as per the outcomes of agreed changes.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 14: Grant Spending Compliance and Forecasting
Summary of Service Package
This service is set up primarily to ensure that all Grant Recipients comply with the Scheme’s Grant Spend conditions and processes.
This includes:
Monitoring the spend of allocated funding in line with specific scheme requirements;
Working with GRs to confirm receipt of payment.
The payment processes for the schemes vary due to the distinct mechanisms used to award funding; consequently, the model of support used for each will differ.
Key Changes from initial briefing
Greater clarity regarding the distinct payment processes for each scheme:
Step-by-step process for individual scheme payment claim procedures and associated SLAs
Scheme specific reporting requests, payment reconciliation and evidence check requirements
Spend and forecasting requirements and how these link with other service package requirements
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 15: Grant Spending Compliance and Forecasting R&R
Buyer (Department)
The decision-making authority, endorsing payment decisions, and managing transfer of funds to GRs upon completion of the relevant financial process
Supplier
Receive drawdown requests, process grant claims reviewing completeness and quality of submissions, and issue recommendation to the Buyer to trigger payments.
Acts as main point of contact for any payment and claims processes, ensuring all GRs comply with schemes Grant spend conditions and processes
Sets out evidence requirements, assess GR financial forecasts, financial summaries/spend, carries out sample/full evidence checks of GR spending
Conducts reconciliation of grant payments, ensuring evidence provided is appropriate to confirm eligible spend, advising GRs on re-submission where evidence shared is unclear, ambiguous or insufficient.
Identifies inconsistencies and escalates to Buyer, including the provision of monthly scheme-level financial forecast.
Grant Recipient
Comply with Scheme spend conditions and processes.
Provide timely and accurate spend requests and reports to enable payments.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 16: Fraud, Error and Compliance Management
Summary of Service Package
This management function seeks to minimise mis-spend of schemes funding and ensure compliance with scheme policy rules.
The service will aim to deter, prevent, detect, and resolve cases of fraud, error, and non-compliance, assuring these functions by driving corrective action and improvement as needed.
The function will ensure public funds are correctly managed in line with the Department’s policy to tolerate no more than 2% losses to residual fraud, error and non-compliance (i.e. losses that remain even after the application of controls).
Key Changes from initial briefing:
Greater clarity on the roles and responsibilities between the Buyer, Supplier and the Grant Recipient
Clearer expectations of the escalation and governance processes
Greater clarity on levels and percentages of evidence reviews required
Greater clarity on the levels of expertise, training and qualification of personal required to conduct evidence reviews.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 17: Fraud, Error and Compliance Management R&R
Buyer (Department)
Deciding Authority, providing strategy and setting tolerances.
Conduct assurance monitoring of Supplier’s fraud management processes.
Supplier
Assuring the strategy by running a fraud, error, and compliance function, using all appropriate preventive data analysis techniques. providing insight conducting spot/eligibility sample checks, due diligence and sign offs
Conduct own fraud management and controls of bids, applications, Change requests, payment submissions etc.
Grant Recipient
Report cases of fraud, error and non-compliance
Take steps to prevent and manage fraud in their supply chain
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 18: Grant Recipient Knowledge Management and Capability Building
Summary of Service Package
This service package outlines:
The coordination of information and knowledge sharing within, and across, the WH:LG and WH:SHF stakeholders.
The activities related to the provision of a forum (i.e. Learning Communities) where delivery challenges, resolution strategies and best practice will be disseminated. The intent is to optimise scheme delivery by leveraging learnings across all Grant Recipients.
The split of roles and responsibilities for the management of the Learning Communities between the schemes, the existing accountable partner (Technical Assistance Facility – TAF2) and the DP2 Supplier.
The principles which will inform communications with Grant Recipients and the wider publicity of the Schemes.
Key Changes from initial briefing
Develop in-depth understanding of the TAF 2 resources library to signpost Grant Recipients to existing advice and support products (where appropriate), leveraging lessons learnt and avoid duplication of efforts.
Support the development and running of the Learning Communities function, ensuring knowledge is shared across GRs.
Monitor and operationally manage an electronic customer support function for GRs, enabled by the Buyer’s Grant Management Systems (GMS) which has a chat function to facilitate messaging (replacing the Help Inbox email function)
Set up and manage a secure access route (i.e. a SharePoint Site) to ensure that large files can be shared with GRs.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 19: Grant Recipient Knowledge Management and Capability Building R&R
Buyer (Department)
Sets out the communications strategy for the management of the Learning Communities.
Administrative and operational management of specific elements (Learning Communities).
Retain control and ownership of all service-related outputs including approval responsibility for any publicity of the schemes.
Supplier
Provide all required administrative and engagement support.
Contribute to the building, management and maintenance of a knowledge base of GR delivery learnings.
Capture, share, and disseminate learnings with both the Buyer and the Grant Recipient community, according to the strategy set by the schemes.
Monitor, triage and respond to incoming queries from
Grant Recipient
Communicate learnings, knowledge experiences and outputs for dissemination in knowledge management forums.
Participate in and contribute to knowledge management forums to drive successful delivery.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 20: Technology, Data Collection, Visualisation and Reporting
Summary of Service Package
This service package outlines the Supplier’s role in collecting, processing, and reporting data from Grant Recipients about the Schemes.
The Buyer will provide access to a cloud based Grant Management System which will be used by Grant Recipients and the Supplier to collect, process and report data about the Schemes.
The Supplier will provide ongoing support to Grant Recipients in how to use all data management and reporting systems to provide an accurate overview of Scheme and Project performance.
Key Changes from initial briefing:
The intended use of the provided systems and the Supplier responsibilities have been made explicit. The systems required have been consolidated into a single ‘Grant Management System’, thus removing references to prior systems such as the DMS and interim terminology like CRM.
Set out clear expectations of the Supplier and roles and responsibilities across the delivery model.
The GMS will be used by both the Buyer and Supplier to record day-to-day interactions with Grant Applicants and Grant Recipients and facilitate operational aspects such as Change Control.
Clarification on the training requirements for Supplier utilisation of the GMS.
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 21: Technology, Data Collection, Visualisation and Reporting (Key Roles & Responsibilities)
Buyer (Department)
The Supplier should assume that the GMS and Automated Batch Solution (WH:LG only) will be provided by the Buyer.
The Buyer will train the Supplier on how to use the systems during the mobilisation phase.
The Buyer will retain ownership of the GMS throughout contract delivery and will, at the discretion of the Buyer, further iterate the solution to meet Dept requirements.
Supplier
The Supplier will ensure that Grant Recipients submit their monthly reporting on time and adhere to the Data Dictionary requirements provided by the Buyer and provide support with technical queries.
The Supplier will amend baseline data as required, carry out analysis of project data and submit monthly Delivery Confidence Assessments using the GMS.
The Supplier will complete Data Quality Assurance on the project data provided by the Grant Recipients to ensure accurate reporting to the Buyer.
The Supplier will ensure that all Grant Recipient engagement and project milestones are recorded in the GMS.
The Supplier will use project data to provide a monthly report to the Buyer on scheme performance, including risks and mitigations to address underperformance for use at the Monthly Review Board with the Buyer.
Grant Recipient
The Grant Recipient will use the GMS to submit a monthly report by the 10th working day of the month in line with the Data Dictionary requirements as part of their obligations within the Memorandum of Understanding (WH:LG) and Grant Funding Agreement (WH:SHF)
Notes: Sarah K to cover main, 1. and 2., Alice to cover 3.

## Slide 22
This information is subject to final governance and assurance processes and may be subject to change.
Funding is also dependent on the outcome of Spending Reviews; this may impact the delivery duration of WH:SHF & WH:LG.
Scope of Contract
Element | Detail
Contract Duration | 3 + 1 + 1 years
Contract Value | c. £70m
Audience supported | Local Authorities, Housing Associations, Net Zero Hubs, Combined Authorities (and other similar relevant bodies)
Dept Schemes Supported | WH:SHF, WH:LG (other schemes may be included at a later date)

## Slide 23: Route to Market & ITT
Following positive market feedback, the confirmed route to market is the Crown Commercial Services’ (CCS) Fund Administration & Disbursement Services (FAADS) DPS, reference RM6322.
Eligible suppliers can join the DPS at any time, however CCS advise a minimum lead time of c.15 working days to onboard an eligible supplier.
For any consortium bids, the leading member of the Consortium must be registered as a DPS Supplier against the following filters:
  Central Government, Full Programme Management, >£5,000,000, East Midlands, East of England, Greater London, North East England, North West England, South East England, South West England, West Midlands, Yorkshire and the Humber
The competition will be carried out using the Department’s e-sourcing portal Jaggaer. Suppliers must be registered on Jaggaer to view the ITT and submit a bid - https://beisgroup.ukp.app.jaggaer.com/
  Please use the ‘Helpdesk’ function within Jaggaer for any registration issues.

## Slide 24: Next Steps
If not already registered, join RM6322 under the filters on Slide 23.
Ensure you are registered on Jaggaer to access the live Data Room and the upcoming DP2 ITT.
Get ready for the ITT launch on Monday 6th October 2025!