Contract Timetable – Mill Marsh Play Area Contract 2023.

Proposed timetable.

The table below gives indicative dates for the tendering process. The critical activities in the programme are the completion of tender documentation, the advertising and return of initial expressions of interest, the formal invitation to tender, the return of tenders and commencement of negotiations and the final tender submissions and evaluation of these.  A mobilisation period from the letter of intent until commencement in September 2023 is allowed for in the programme.

| Activity | Date |
| --- | --- |
| First draft documentation and report to Recreation and Property Cttee prepared | 14/02/23 |
| Committee Decision | 20/02/23 |
| Advertise on for expressions of interest on Contracts Finder Portal | 21/02/23 |
| Formal expressions of interest closing date | 10/03/23 |
| Draft documentation sent out to companies who have expressed an interest | 13/03/23 |
| Meeting with companies who have expressed an interest to provide clarification and receive comments | 20 -22/03/23 |
| Comply Comments on first draft documents received from interviews | 22-27/03/23 |
| Second draft documents and Cttee report prepared | 27/03/23 |
| Second draft documents agreed by Council Recreation and Property Cttee | 03/04/23 |
| Contract advertised on the Government Contract Finder Portal with PQQ | 04/04/23 |
| Deadline for return of pre-qualification documents | 02/05/23 |
| Financial evaluation of pre-qualification documents | 02 -09/05/23 |
| Technical evaluation of pre-qualification documents | 02 -09/05/23 |
| References taken up on prospective tenderers | 02 -09/05/23 |
| Selection of tenderers for next stage | 09/05/23 |
| Invitations to tender sent out to longlisted companies | 09/05/23 |
| Tenderers to visit site | 15-19/05/23 |
| Visits to inspect tenderers work on other contracts | 15-19/05/23 |
| Deadline for return of ITT proposals | 12/06/23 |
| Evaluation of ITT proposals (including identifying areas for clarification) | 13-16/06/23 |
| Clarification period, meeting(s) with each bidder | 19-22/06/23 |
| Modification of Tender documents (if required) | 23/06/23 |
| Issue Final Tender documents | 26/06/23 |
| Deadline for return of final tenders | 07/07/23 |
| Evaluation of Final Tenders (including clarification) and selection of successful tenderer, | 07 -10/07/23 |
| Prepare report to Council Recreation and Property Cttee | 10/07/23 |
| Council Recreation and Property Committee approval | 17/07/23 |
| Tenderers notified of outcome – letter of intent | 10/07/23 |
| Due diligence undertaken on successful tenderer | 10/07/23 – 01/08/23 |
| Contract award | 01/08/23 |
| Mobilisation period | 10/07/23 – 11/09/23 |
| Contract start date | 11/09/23 |

The inclusion of an invitation to tender submission of proposals provides an opportunity to assess the level of understanding of the Council’s requirements and design expertise of the tenderers. It includes a period for modification of the package on offer, before the process of inviting tenders, based on final proposals from each tenderer, takes place.

The Programmes aims at a 11th September start date from a letter of intent on 10th July and a 1st August award. (Subject to due diligence) This gives a total of nine weeks lead time from the letter of intent to a start on site.  These dates may be subject to change to allow for resource availability within the Council.