## Sheet1
PRE CONTRUCTION HEALTH AND SAFETY PLAN
Demolition and Replacement
of
Industrial Unitd
at
The Old Mushroom Farm
Halsetown, TR26 3LZ
For
St.Ives Mushrooms Limited
R.W.Abbott & Associates Ltd
Chartered Surveyors
Principal Designers
November 2020
HEALTH AND SAFETY INFORMATION PACK
Site address:- The Old Mushroom Farm, Halsetown TR26 3LZ
Project details:-Demolition of existing unit and re-construction of 8 new industrial units, with associated drains and services,
Client:-St.Ives Mushrooms Limited
The Old Mushroom Farm, Halsetown TR26 3LZ
Architectural Designer : Gary Wilson,
1 Aldreath Cottage, Aldreath Road, Madron
Pezance, Cornwall TR20 8ST
Principal Designer under CDM Regulations 2015
Richard Abbott MRICS RMaPS., of RW Abbott & Associates Ltd
Grove Cottage, Red Lane, Rosudgeon, Penzance TR20 9PU
Tel. 01736- 762082/07966-527140
Email:- richard.w.abbott@talk21.com
Infrastructure Engineer-
Jan Clark of EDS Ltd
10 Penstraze Business Park
Penstraze, Truro
Cornwall TR4 8PN
Tel. 01872-306311
Programme for work:-
Commencement: anticipated as April 2021
Mobilisation period:- 2 weeks
Contract Period:- 18 working weeks or as per Contractors proposals
Section A | General
A1 | The client has appointed R.W.Abbott & Associates Ltd. as Principal Designer under the CDM Regulations 2015 on this project.
A2 | In the operation of this Health and Safety Plan it is the Principal Designers role to assimilate information from the Client, designers and Contractors relating to the health and safety issues affecting this project and report this information before construction commences in the Health and Safety Plan.
A3 | The Health and Safety Plan is intended to highlight significant potential hazards and risks as far as they can be identified before construction commences. It remains incumbent on the Contractor to remain vigilant in identifying health and safety risks, complying with all statute and recognized good practice (e.g. as recommended by the Health & Safety Executive).
A4 | After Contract negotiations are finalized, the prospective Principal Contractor shall prepare his formal response to the pre-Construction Health and Safety Plan . The response shall be included within the Contractor’s Construction Phase Health and Safety Plan and shall be submitted to the Principal Designer within three days of having been requested to do so.
A5 | The prospective Principal Contractor shall prepare his Construction Phase Health and Safety Plan in a format consistent with Appendix 3 of ‘A guide to Managing Health and Safety in Construction’ published by HSE and available from HMSO.
A6 | Work shall not commence on site until the Principal Designer has confirmed in writing to the Client that the prospective Principal Contractor’s Health and Safety Plan is subject to ‘Checked and no further health and safety comment’ and suitable welfare facilities are in place.
A7 | Method statements prepared by or received and reviewed by the Principal Contractor shall be incorporated in the Construction Phase Health and Safety Plan.
Section B | Nature of the project
The project consists of the demolition of an existing unit and reconstruction of eight new units, storm drainage and services on existing infrastructure
Section C | Surrounding Land Use
C1.1 | The site is located between existing operational industrial units/workshops, a rear orchard with grassland, neighbours garden and office facilities on an industrial site of 12 tenanted workshops.
C1.2 | No waste disposal is available on site for works arisings or workmens/tenants rubbish, all to be removed offsite
C2.0 | Existing services
C2.1 | The service authorities have responded to enquiries regarding their equipment in the vicinity of the works as follows:-
C2.2 | There are BT, Water and Electric services in the approach road adjacent hardstandings plus electric and BT overhead. Foul and surface water drain runs cross the site, with storm drainage to two sides of new building existing slab. Site distribution electrics are overhead at present.
C2.3 | A water Borehole exists in vicinity of start of electric trench, identify before digging.
C3.0 | Site Access and Traffic Systems
C3.1 | Access to the site will be from the existing access which remains unaltered. Storm drain outfall will be across a short length of neighbours field to a minor leat watercourse
C3.2 | The unadopted and poorly maintained access track from the main village through road, is narrow and consideration to the size of larger delivery vehicles is needed or a banksman when deliveries are due
C3.3 | Maintaining access across the north west corner of the construction site for adjacent workshop users with vehicles and on foot is required
C4.0 | Ground conditions
C4.1 | The following information has been provided:-
An Environmental risk certificate has not been acquired for the site. The land does not meet the criteria as to be described as contaminated. SI reports for the site are not available, but with high levels of naturally occuring minerals, caution should be noted of potential contamination within the excavations.
Deeper excavations are anticipated for the storm soakaways plus silt and outfall structures..
Underpinning is not anticipated to be required,
Section D | Existing Drawings
D1.0 | Existing drawings are only available in respect of the topographical survey and services searches which are included on the Tender drawings
Section E | The Design
E 1.1 | The Designers who undertook the New units & drain designs have been contacted to obtain there consideration of the scheme under Regulation 8 & 9 of the Construction (Design and Management) Regulations 2015. The Designers have made their own assessment of Design Risk criteria.
E 1.2 | The wider existing site will be in continual use, with resultant consequences for pedestrian and traffic management at delivery times. Members of the public using the access road and public footpath path could be adjacent to the wider site entrance at any time of the day
E1.3 | All large material deliveries ( steel frame/cladding) may well have to be transferred to smaller vehicles
E1.4 | Special care will have to be taken whilst undertaking service cable works adjacent to existing workshop units and crossing existing services
E 1.5 | There are quantities of concrete involved in the construction of the project and therefore precautions need to be taken to avoid concrete burns etc.
E1.6 | The site excavations may involve the removal of hard materials. The contractor should explain how the workforce will be protected from noise and the possibility of flying chips of masonry in the confined spaces.
E1.7 | The contractor is required to provide proposals for dealing with the items raised above
Section F | Construction Materials
F 1.1 | We have not been notified by the designers of any health hazards associated with the construction materials specified on this project
F 1.2 | Asbestos containing materials have been identified within the project work area. These materials will require proposals to determine removal method .
F1.3 | The contractor will be expected to hold COSHH records of materials used on site
Section G | Site Wide Elements
G 1.0 | The contractor is to submit details of:-
1 | Size of temporary site accommodation required and its allocated position
2 | Size, location and layout of storage areas.
3 | Traffic and pedestrian control measures.
4 | How material deliveries will be scheduled
5 | Site security.
6 | Manual Handling
Section H | Overlap With Neighbours Undertakings
H 1.0 | Some work is required to boundaries. The contractor will need to provide evidence of how this work will be undertaken to avoid unnecessary disruption and damage to adjacent surfaces.
H1.1 | Some of the work provides the possibility of building operations damaging live mains or private estate shared services. The contractor must show how this is to be prevented
H1.2 | There is a possibility of the site generating a considerable amount of noise mud/slurry run off, which will be of considerable inconvenience to other site users
The contractor is required to provide proposals for dealing with the items raised above
Section J | Site Rules
J 1.0 | Primarily determined by the Principal Contractor in line with CDM Regulation 2015 clauses 12-15
Section K | Principal designers Contract Duties/ Principal Contractor’s Response
K 1.0 | The duties of the Principal Designer during the construction phase can be summarised as:
K1.1 | Ensure designers comply with their duties under CDM regulations concerning ongoing design work
K1.2 | Be in a position to advise the client on the competence and resources of contractors to undertake or manage work
K 1.3 | Ensure designers continue to co-operate with each other and on this contract the Principal Designer shall remain reliant on the Principal Contractor to monitor co-operation between designers
K 1.4 | Continue to prepare the Health and Safety File and issue this to the client. In this respect information required to be supplied by the Principal Contractor for inclusion in the H & S file is listed as:-
a) As built drawings and plans produced by or on behalf of the Contractor
throughout the construction process. These should include at least:-
A site plan
Surface drainage, inverts and cover levels, rodding points.
Details of the location, depth and nature of utility or domestic services.
Structural calculations
b) All specification, installation and layout drawings, operating and maintenance manuals and information on electrical and mechanical installations. These shall include at least:-
K 1.5 | Design Concept
Manufacturers instructions and literature
Details of all components and units
c) Construction methods used and a schedule of materials used including hazard data sheets where materials may be hazardous ( COSHH) in service, during maintenance or during demolition.
d) Maintenance procedures and requirements for the new structures.
e) Originals of all certificates, guarantees and warranties.
K 1.6 | Environmental Restrictions
The usual care must be taken to prevent ground contamination or the pollution of any drains/sewers/paths/adjacent gardens/rver from run off
Site dust emerging onto the road or adjoining properties should be controlled. Prevention measures should be enacted.
K 1.7 | Welfare
Suitable and adequate temporary welfare facilities as described in the CDM regulations 2015 should be established on site before work commences. As fscilities in this respect have been offered by the clients the contractor should ensure that they are suitablr.
K1.8 | Noise
Prevention methods should be put in place to limit the amount of noise emanation from the site
Appendices
Asset Plan- Western Power Distribution
Copy of F10 ( initial)
Asbestos Survey Lab Analysis
Asbestos Survey Bulk Analysis
Asbestos Survey Location of sample plan