## Sheet1
Contract No: IWM/DCM/1454
Repair to Starboard Deckhouse, HMS Belfast
COST TABLE
Item | Description | Cost
1 | The Contracted Works comprise of the Starboard deckhouse, located on 1 deck, which consist of five compartments, namely, 1M1 Ready Use store, 1M1 Office, 1M3 Office, 1M1 Passage and 1M1 SCC Wardroom
2 | The deckhouse roof is leaking into the compartments below. A previous repair has been carried out by plating over the existing roof. The areas which have failed cannot be identified from above or below. The whole deck needs to be replaced
The Contractor will be required to:
2a | Fence off all work areas in the vicinity of the works. IWM will advise and supply barriers and signage
2b | Inside the compartment, secure all cable trays, light fittings and ventilation trunks in preparation for cutting them away from the deckhead. These are to be protected from burning from future operations
2c | Once isolated move the fire alarm detectors out of the way. These are to be protected from burning from future operations
2d | Remove Navy board lagging from the deckhead inside all four rooms
2e | Remove all tiling and screed from the four rooms that comprise the deckhouse
2f | Remove awning and rigging
2g | Remove 5 awning stanchions. These are to be retained and refitted to the new deck
2h | Remove 23 guardrail stanchions. These are to be retained and refitted to the new deck
2i | Remove plating, there are thought to be two layers, being careful not to damage the beams and girders below. This will normally be a carried out in small sections across the area
2j | Clean all beams and girders to a bright finish and apply holding primer
2k | Fit new plating and secure by welding to the beams and girder support structure. Plating to be 6mm Cold rolled mild steel, supplied blasted and primed
2l | Once all plating has been installed and is sealed by full welds, a drain is to be fitted at the lowest point and connected to the original drain pipework. The drain is to be fitted with a removable strainer flush with the deck
2m | Re-secure the ventilation trunks, cable trays and other fittings to the new deckhead
2n | Paint the internal compartments. 1 coat of Zinc Phosphate primer L489, 1 coat white undercoat and a coat of Dulux Trade High Gloss White. This is to include cable trays, vent trunking and other fittings. The bronze surrounds to the scuttles are not to be painted
2o | Apply Navy Board insulation IAW manufacturer’s instructions on deckhead and any areas damaged elsewhere for all compartments. Finish in white gloss
2p | Screed and retile deck in four spaces, store excluded. Tiles are Dove Grey and Burgundy chequer using 12” tiles. The deck in the store will be finished using paint. 1 coat of Zinc Phosphate primer L489, one undercoat and one coat of Brunswick Green Gloss. A Four inch upstand is to be applied around the periphery of the compartment
2q | Refit the Awning and Guardrail stanchions. These are to be tested and pronounced fit for purpose
2r | Prepare and paint the deck. Remove all traces of corrosion. 1 coat of Zinc Phosphate primer L489. Apply Aramine 2 pack resin(32-546) in accordance with manufacturer’s instructions using Arapox 60-600 additive. Blind surface with 16 gauge grit. Prime gritted deck with Leighs L489 primer, apply gloss finish Leighs Epigrip M262 (2 Pack) High Build Finish
2s | Prepare and paint Guardrail and awning stanchions. Remove all traces of corrosion. 1 coat of Zinc Phosphate primer L489. Two coats of Hemucryl Light Aircraft grey (BS 38 1C 627) topcoat
2t | Replace awning and rigging, ensure that it is tight all round
3 | Contractors Design Responsibilities:
3.1 | The Contractor will be responsible for confirming all site dimensions, setting out and sizing of replacement plating
3.2a | The Contractor shall provide everything necessary to execute the Works, including but not limited to the following:
3.2b | All necessary plant, tools, tackle, vehicles, temporary work materials, screens, props, additional and temporary lighting, etc
3.2c | Staging and access equipment to carry out the Works, which shall comply with current regulations and legislation
3.3 | The Contractor will allow for all costs associated with complying with his responsibilities under Health and Safety Regulations together with all costs associated with liaison, access requirements and programming of these described works to ensure the smooth running of the contract and compliance with completion dates
4 | Site Protection
4a | Allow for suitable protection within works areas to protect retained structures & finishes and include for adequate protection within access/egress routes
4b | Adequately protect all types of work and all parts of the Works, including work carried out by others, throughout the Contract. Wherever work is of an especially vulnerable nature or is exposed to abnormal risks provide special protection to ensure that damage does not occur
4c | Prevent damage to existing property including works undergoing completion alteration, adaptation or extension and make good to match existing any defects so caused
4d | The Contractor should note that he will be held responsible on completion for reinstating any areas he has occupied
4e | Allow for protection of all drains and drainage gullies within the defined works area. The Contractor should note that he will be responsible for all costs incurred to clear/repair blocked or damaged drains and gullies resulting from his works
5 | Protection of river & environment
5.1 | Allow for the controlled containment of all contaminants, debris, etc. resulting from the works, ensuring that resultant materials are not discharged into the river
5.2 | The Contractor will be responsible for the removal of all site spoil resulting from his works, including all packaging materials
5.3 | Designated emergency escape routes are to be kept clear at all times
5.4 | The Contractor will note that all deliveries/collections are to be supervised by the Contractor’s nominated operative
5.5 | Disposal certificates, as required by current legislation covering disposal of waste, for all site spoil removed from the site will be required for inclusion within the O&M Manual on completion of the contract
6 | Health and Safety
6.1 | IWM operates a Permit scheme, covering both ‘Access Permit’ and ‘Permits to Work’. The Contractor will allow for all costs associated with the preparation and submission of Method Statements and Risk Assessments, specific to the scope of his works
6.2 | Risk Assessments and Method Statements are to be submitted to both the Principal Designer and IWMs nominated representative in good time to enable assessment, comment and amendment
6.3 | CDM Regulations 2015 are to be used as a good practice guideline and Contractor submitted Health and Safety documentation should comply with these statutory requirements
6.4 | The nature and condition of the compartment cannot be fully and certainly ascertained before it is opened up. The accuracy and sufficiency of this information is not guaranteed by IWM, and the Contractor must ascertain for himself any information he may require to ensure the safety of all persons and works
7 | Welfare Facilities
7.1 | Unless agreed in advance with IWMs nominated representative, the Contractor is not permitted to make use of the staff mess room. Alternative arrangements should be made
7.2 | Arrangements for designated lavatories for Contractors staff must be as agreed with IWMs nominated representative
7.3 | Where facilities are agreed, the Contractor shall ensure that areas are kept clean and tidy at all times
8 | O&M Manuals
8.1 | Within one week of Practical Completion, the Contractor will submit two A4 bound O&M Manuals together with an electronic issue, to the Clients nominated representative, which will include but not be limited to:
8.1a | H&S File
8.1b | COSHH sheets
8.1c | Copies of all Permits to Work
8.1d | Details of all applied finishes
8.1e | Maintenance regime i.e. requirements for periodic testing of mechanical fixings, cleaning etc.
8.1f | Warranties and Guarantee documentation
8.1g | Copies of all structural survey and alteration works documentation
8.1h | Waste certificates
8.2 | Allow for unimpeded access by IWMs nominated representative to undertake the inspection of ongoing and completed works
9 | Scaffold
9.1 | Allow for all required design, supply and erection of scaffold to facilitate the works
9.2 | Allow for scaffold modifications to enable the safe handling of materials and the correct preparation of surfaces and application of coatings to areas where scaffold may obscure surfaces
9.3 | Striking of the scaffold upon the completion of the works, including related costs, is covered under current contracted inspection works
10 | Replacement plating
10.1 | Where on site drilling, cutting, grinding, etc. is undertaken all resultant exposed steelwork is to be primed, undercoated & top coated as per the overall finishing specification
10.2 | The Contractor will be responsible for checking and final sizing of all required component parts, including required material gauges, prior to incorporation within the works
10.3 | Allow for all temporary propping as required, both during removal and installation works
10.4 | As the preparation work progresses, report back to IWMs nominated representative, any additional structural issues that may be exposed. Advise the Client of recommended remedial treatment and associated costs
11 | Steelwork Preparation and Coatings
11.1 | Manually clean, remove rust, degrease & treat existing main structure, by hand and power tool cleaning, using wire rotary brushing, scrabble hammer, grinding and disc sanding to ISO-St2
11.2 | The Contractor is to include within his tender return a full specification of his proposed marine grade corrosion protection coating system, which is to include:
Manufactures specifications
Guarantee period for applied coatings
Type of finish and number of application coats covering: Zinc Phosphate Primer, Overcoat and Topcoat
11.3 | Top coat finishes are required in colour reference
P.R. Blue BS 38 1C 636
Light Aircraft Grey BS 1C 627
Dark Admiralty Grey BS 1C 632
Light Admiralty Grey BS 1C 697
11.4 | All application work is to be in full accordance with the manufacturers requirements and certified as accepted by them, including guarantee for the corrosion protection system employed
11.5 | The Contractor is to allow for, if the paint guarantee requires, for the attendance on site of the manufacturer’s representative to undertake checks of preparatory works and coating applications to ensure application is in full accordance with their recommendations and guarantee
11.6 | Should the Contractor feel that climatic conditions are likely to be unsuitable to ensure compliance with guarantees for the finished works, they are to clearly highlight their concerns/comments within their tender return
| TOTAL SUM | 0
This Tender is submitted on behalf of:
Signed
Name
Position
Date