14th May 2020 | v0.3

DIO Government Soft Landings Guidance

DRAFT

# MOD & Government Soft Landings

Introduction

- The need to improve the value offered by public sector construction has been a key objective of HM Government for many years, including the goal ‘to align interests between those who design and construct an asset and those who subsequently use it’, as part of the 2011 Government Construction Strategy (GCS), as a way to improve performance of buildings and to meet the requirements of those that use them.

- To support these aims Government Soft Landings (GSL) have been developed to help drive a structured and consistent approach to the delivery of operational led requirements. The term ’soft landing’ exists in many parts of the construction industry and reflects the need for a smooth transition from the design and construction phase to the operational phase of a built asset.

- The ongoing maintenance and operational cost of a building during its lifecycle far outweighs the original capital cost of construction; GSL identifies the need for this to be recognised through early end-user engagement in the design and construction process. Essentially, GSL drives better outcomes for our built assets throughout their full lifecycle, by addressing this requirement during the design and construction stages, through a process that is supported by Information Management, which can include the delivery of a specified data set as part of the Building Information Modelling (BIM) process, to ensure that value is achieved and also measured in the operational lifecycle of an asset.

- GSL is aligned and supported by BS 8536-1:2015: Briefing for design and construction. Code of practice for facilities management (Buildings infrastructure). BS 8536-1:2015 gives recommendations for briefing for design and construction, to ensure that designers consider the expected performance of a building in use. The standard applies to all new infrastructure projects and major refurbishments.

- BS 8536-1 aims to:

  - Involve the operator, the operations team and their supply chain from the outset; and

  - Extend the involvement of the supply chain for the project’s delivery through to operations and defined periods of aftercare.

- In order for MOD to achieve these Information Management objectives GSL needs aligned with DIO’s emerging BIM standards and agreed processes, in order to provide fully populated trusted asset information/data set, that in turn supports delivery of asset/facilities management through the use of this information/data once it is transferred to the DIO’s Asset Information Model Common Data Environment (AIM CDE) and then into various of the businesses enterprise systems.

- GSL is dependent on collaborative working and engagement in a structured process with a common purpose and goals focussed around long-term business benefits and required performance outcomes. By following the GSL approach, business and performance targets should be reviewed throughout project briefing, design and construction. Commissioning should be more effective and transition from construction to operation should be smoother, more structured and effective.

- For MOD GSL covers:

  - Engagement Strategy: between the Project Teams with those responsible for the Use and Maintenance of the asset(s).

  - Inspection, Commissioning, Training, Acceptance and Handover of the asset(s)

  - Aftercare: Support required in the Use and Maintenance of an Asset(s) post-handover.

  - Post Occupation/Operation Evaluation: Measurement of functionality of an asset(s) against the design intent.

- In implementing GSL MOD recognises the cost of maintenance and use of an asset far outweighs the cost of the design development and construction costs of the asset itself  (between 20 times and 50 times greater).

MOD’s guiding principles of GSL are as follows:

- GSL will play a key part in the design and construction process, in that it maintains a ‘golden thread’ of the building’s purpose and also required performance standards through delivery and into operation.

- Early engagement of both FM provider, end user and inclusion of a GSL Champion, on behalf of the client, to direct this engagement with the project team during both the project development and construction phases.

- The early and ongoing development of the Handover, including commissioning, processes and procedures of an asset (or assets).

- Confirmation of the Roles and Responsibilities of those delivering the project and those accepting the asset (or assets) into use.

- The early and ongoing development of the “Aftercare” post acceptance and handover of an asset (or assets).

- The early and ongoing development of the Post Occupation/Operation Evaluation (P.O.E.) to enable feedback to departmental teams (to capture of learning from experience (LFE) to inform future projects). P.O.E. data will be stored on the Asset Information Model Common Data Environment (AIM CDE).

- Information exchanges, as part of BIM, will allow the early testing of maintainability and performance targets as the design develops, additionally BIM will help provide a fully populated Asset Information Model which can then be maintained to provide and ongoing understanding of the performance of an asset against an assets original design criterion.

The purpose of GSL

- The purpose of GSL:

  - Understand the adequacy of the Asset(s);

  - Understand and optimise the operating performance of an asset;

  - Align the operating performance with the required performance outcomes that were set and developed during the design concept, development and construction phases;

  - Understand Information as a result of P.O.E.to further develop designs and their design parameters.

- GSL recognises that the on-going business benefits, maintenance, operational cost and usage of an asset during its lifecycle far outweigh the original capital cost of construction. The need to optimise in-use performance is recognised and sought through early engagement with the maintainers and end users in the design development and construction process, and by learning from previous experience.

- The operational costs and impacts of a building can be understood and considered in both design development and construction by working closely with operators and maintainers, this reduces whole life cost and supports improved operational delivery. Optimal operational performance will also be achieved more quickly through dialogue and continued engagement between designers and operators.

- The key to achieving this understanding will be through a defined and implemented GSL process.

The Benefits of GSL

- Applying GSL will bring benefits to all stages of asset construction and operation. Effort put in at the front end of construction and design has significant impact on the outcomes achieved and long-term cost of running and using an asset. The use of GSL supports this front-end focus for long-term business benefits.

- Some of the key benefits of GSL are listed below:

  - The GSL process will help to define the required performance outcomes and support asset design to meet the end users’ needs and required operational outcomes.

  - End user involvement at the early stage and throughout the project is undertaken to deliver improved operational performance.

  - Early challenge of design by operators is supported through the use of GSL; this can bring long-term cost savings in the operation and maintenance of an asset.

  - Lifecycle operational expenditure rather than just capital expenditure is considered. GSL brings forward the importance of operational costs in the decision-making process.

  - Earlier engagement with end users and operators to support the client in identifying the determining data and information requirements for their asset management system and to support their asset management strategy at the beginning of the project.

  - Data transfer in the form of Construction to Operations Building Information Exchange (COBie) to Supplier Systems, is required to reduce the cost and time of data input to FM Systems.

  - Training, commissioning and handover are provided in a timely manner reducing the cost of protracted handover and enabling optimal performance to be reached sooner.

  - Clear measurements of building performance are conducted for up to 3 years post completion to compare actual performance against required performance.

  - Through the use of BIM and its required information exchanges, coupled with simulation techniques, early testing of the design to determine if it aligns with the proposed performance targets.

  - Strategic briefing for clients will be informed by previous project experience for example desktop assessment of case studies, lessons learned from previous “project review meetings” and P.O.E. surveys.

  - GSL will capture information on the performance of assets within DIO/MOD and this can be used to support clients, designers, constructors and operators to improve their knowledge and expectations of future performance.

  - Information on asset performance will inform future project strategies and portfolio investment and management.

  - Optimisation of asset performance is maintained through the continued involvement of main-contractors and key suppliers during an aftercare period.

  - Designers and constructors get to understand the outcomes of their design and how they can narrow the gap between design intent and actual performance.

Key actions in achieving GSL

- Clear targets are to be set for required business outcomes at the start of the project. These targets need to be aligned with strategic objectives and they should be cascaded through the supply chain. These targets and their measures need to be reviewed during the design, construction and operation. Targets and measures should consider statutory requirements, government policy, previous experience, operational knowledge and end user needs.

- Appropriate end users (defined though stakeholder mapping and categorisation) should be involved to represent the client during design, construction and handover.

- The transition from construction to operation must be planned throughout the project and should be a smooth process enabling optimum performance to be reached as quickly as possible. The transition needs to consider the transfer of operational data as well as training, commissioning, handover and aftercare.

- Performance reviews should, where appropriate, be undertaken post completion for up to 3 years and lessons learnt from this should be recorded and shared for future projects.

GSL and key project roles

- The roles of the Project Sponsor, Project Manager, and Government Soft Landings Champion (GSL Champion) are fundamental to the delivery of GSL and are identified within the sections of this guide.

- These roles have been explained further below:

  - GSL Senior Responsible Owner (SRO): This person is the senior leader who is tasked with implementing the principles and practice of Government Soft Landings across the organisation/department.

  - GSL Champion: Is appointed from within the Regional delivery team or a commissioned representative. The GSL Champion is responsible for ensuring that the implementation of GSL is delivered by ensuring that briefing and design take account of the business, end users and operators’ requirements. These need to be translated into the performance targets that are assessed during the project and post completion.

  - Project Sponsor: This individual should be from the client side; they have personal accountability and overall responsibility for the delivery of the successful outcome; this individual must be able to commit adequate time to the project.

  - GSL Project Manager: This individual(s) will be appointed by the client either directly or from an external organisation. The Project Manager has responsibility to liaise with the various members of the project team to ensure that a clear plan for project delivery is developed and project items such as risk, budgeting and change are managed. They are responsible for ensuring GSL process is embedded into project.

GSL Champion

- The GSL Champion is appointed as part of the wider project team, and should ensure that the following are agreed, and facilitated:

  - To define required performance outcomes and operational budget;

  - To enable the management of two process streams;

    - Facilities & Asset Management (early strategy and planning);

    - The commissioning, training, acceptance and handover of Assets.

  - To define and implement the delivery the requirements of the projects “Aftercare” requirements;

  - Facilitate Post Occupation/Operation Evaluation;

  - Compare actual against planned performance outcomes for:

    - Functionality and Effectiveness (Social)

    - Environmental (Environment)

    - Financial/Cost (Economic)

  - Coordinate the preparation of an advisory report (LFE), including results against planned and baselined objectives and possible corrective actions.

- The appointed GSL Champion may change depending on the project development phase.

  - Stage 0 & 1 the GSL Champion will be appointed from ……………….

  - Stage 2 – 7 inc, the GSL Champion will be appointed from ……………

GSL Stage Tasks

- The following tables illustrate the typical tasks that will need to be executed on a project as part of its GSL strategy.

- A RACI should also be allocated against the tasks to describe who is:

R = 	Responsible

A = 	Accountable

C = 	Consulted

I = 	Informed

Stage 0 Strategic Definition - Initiate

- Designing built assets to meet desired functional needs is a complex process. To be effective and ultimately deliver the required product, the first stage is to establish high level objectives – thinking of the operational and performance delivery from the very start. Key activities to support a GSL approach during this stage are illustrated below:

| - Ref | - GSL Task | - RACI | - Completed By Date |
| --- | --- | --- | --- |
|  | Establish the operational vision and strategy for the project aligned with the project business case, including the required performance targets (outcomes) of the proposed asset/ facility utilising where possible Post Occupation/Operation Evaluation (P.O.E.) data benchmarks. If needed propose an occupant survey to identify baseline measures. |  |  |
|  | - Establish GSL roles and responsibilities for the project both for the client and supply chain including a GSL RACI matrix (this section should be read in conjunction with GSL document number 3, GSL Roles and Responsibilities). |  |  |
|  | - Review lessons learned and feed-back from other projects, legislative or Departmental guidance and design / financial constraints. Pre-occupancy surveys may also be commissioned. |  |  |
|  | - Appoint a Project GSL Lead with suitable skills and responsibility level. |  |  |
|  | Identify and map all relevant stakeholders – both internally and externally. |  |  |
|  | - Prepare aligned BIM and GSL strategy and implementation plan (including data exchanges from AIM to PIM and PIM to AIM). |  |  |
|  | - Develop a Facilities Management Strategy and Plan for the project aligned with operational objectives, service level requirements and operational budget. |  |  |
|  | - Establish P.O.E. mandatory asset performance measurements. |  |  |

Stage 1 Preparation and Brief – Concept

- The key output at this stage is a well-defined Project Brief which ensures the Maintainers and Operators needs are aligned to measurable performance targets. Key activities to support Government Soft Landing during this stage are illustrated below:

| - Ref | - GSL Task | - RACI | - Completed By Date |
| --- | --- | --- | --- |
|  | Establish Maintenance Provider/Operator functional requirements and ensure that these are embedded in the brief. |  |  |
|  | - GSL opportunities and risks schedule to be generated by the GSL Project Manager in conjunction with GSL Champion and wider project team using lessons learnt from previous projects. |  |  |
|  | - Establish Environmental Targets. Projects are to determine, measure and record the actual performance figures for energy consumption, carbon dioxide emissions, water usage and waste production: - Total Energy use - including both regulated and unregulated consumption; - Carbon dioxide emissions - calculated from the energy use; - Waste - this needs to address operational use (work with departmental sustainability department to establish); - Water - consumption and waste figures. - These need to be considered against departmental targets, policy and objectives, operating budgets and critical project targets. These will need to be constantly reviewed and evaluated as the project progresses. |  |  |
|  | - Establish Functional and Effectiveness targets to ensure that the built asset has comfortable, manageable and maintainable environments that are conducive to occupant usage and productivity. |  |  |
|  | Establish Economic Targets. Both Capex and Opex budgets should be benchmarked, agreed and monitored. |  |  |
|  | - Review of any environmental management plan (EMP) highlighting any performance objectives that will be informed by various information sources such as any Environmental Impact Analysis. |  |  |
|  | - The post Occupation/Operation evaluation strategy for the project should be established determining what should be measured, when and in what format. |  |  |
|  | - In creation of the Project Specific Information Delivery Plan information exchanges to support the GSL and decision-making processes should be established. |  |  |
|  | - Establish Aftercare Strategy for the Project |  |  |
|  | - Establish Initial Inspection, Commissioning, Acceptance and Handover Criteria. |  |  |
|  | - Embed GSL requirements into tender documentation. |  |  |
|  | Data exchanges (from PIM to Clients AIM Systems) prior to project gateways to check if Plain Language Questions (PLQs) are being achieved. |  |  |

Stage 2 & 3 Concept and Development

- The key output at this stage is a design and a completed built asset that meets the Operators and Maintenance providers needs.  Key activities to support soft landing during this stage are illustrated below:

| Ref | GSL Task | RACI | Completed By Date |
| --- | --- | --- | --- |
|  | Model and test the developing design strategy against operational targets. |  |  |
|  | Validate that the plans and specifications meet with operators and maintainers requirements. |  |  |
|  | On-going end user and engagement including project walk-arounds. |  |  |
|  | Creation of early building readiness plans and where appropriate user migration strategy; |  |  |
|  | - Review and update of Post Occupation/Operation Evaluation strategy for the project. |  |  |
|  | Review and Update Aftercare requirements. |  |  |
|  | Review Initial Inspection, Commissioning, Acceptance and Handover Criteria. |  |  |
|  | Data exchanges (from PIM to Clients AIM Systems) prior to project gateways to check if Plain Language Questions (PLQs) are being achieved. |  |  |

Stage 4 and 5 Technical Design and Construction

| Ref | GSL Task | RACI | Completed By Date |
| --- | --- | --- | --- |
|  | - Embed GSL requirements into tender documentation. |  |  |
|  | Model and test the developing design strategy against operational targets e.g. BIM (information / data) combined with simulations and 3D walkthroughs; |  |  |
|  | Validate that the plans and specifications meet with end user needs and targets; |  |  |
|  | On-going end user and engagement including project walk-arounds including inspection, commissioning, approval and Handover acceptance criteria; |  |  |
|  | Review and update of Post Occupation/Operation Evaluation strategy for the project. |  |  |
|  | Review and Update Aftercare requirements. |  |  |
|  | Creation of early building readiness plans and where appropriate user migration strategy; |  |  |
|  | Data exchanges (from PIM to Clients AIM Systems) prior to project gateway to check if Plain Language Questions (PLQs) are being achieved. |  |  |

Stage 6 Handover and Closeout – Handover and Closure

- The key outcome at this stage is to make sure that the built asset is operationally ready to commence its in-use life-cycle.  Key activities to support soft landing during this stage are illustrated below:

| Ref | GSL Task | RACI | Completed By Date |
| --- | --- | --- | --- |
|  | As-Built Project Information Model (PIM) validated and archived; |  |  |
|  | Data transferred from PIM to client AIM systems; |  |  |
|  | End user orientation and training undertaken. Facilities Management (FM) familiarisation with key systems e.g. SCADA, BMS; |  |  |
|  | Building Log Book in place; |  |  |
|  | All commissioning logged and reviewed against targets; |  |  |
|  | Aftercare plan in place and team mobilised; |  |  |
|  | Plans for Post Occupation/Operation Evaluation Process in place (Including the Provision of a P.O.E. Report detailing the Plan) |  |  |
|  | Digitised O&M, including H&S File, received. |  |  |

Stage 7 In-Use / Operational Stage

- The key outcome at this stage is to make sure that the built asset is performing as per the brief and any lessons learned captured and feedback. A key feature of this stage is post-occupancy evaluation (P.O.E.), by means of assessing performance and determining if any improvement or corrective action is required.  Key activities to support soft landing during this stage are illustrated below:

| Ref | GSL Task | RACI | Completed By Date |
| --- | --- | --- | --- |
|  | Aftercare walk-arounds instigated with aftercare and FM teams to determine and initial issues with end-users; |  |  |
|  | Monitoring of systems, actual performance against Design Objectives; |  |  |
|  | Project end review – capture lessons learned, scheme benefits review; |  |  |
|  | Seasonal commissioning; |  |  |
|  | Fine tuning of asset to ensure that targets are met; |  |  |
|  | Structured P.O.E. surveys scheduled and undertaken; |  |  |
|  | Update AIM as appropriate. |  |  |

GSL Measurements and Outcomes

### Instruction

Purpose:

      - As part of the life cycle of the project delivery process, the DIO PM will arrange for Post Occupation/Operation Evaluation to be reviewed at each phase of the project and delivered at the end of the 12-month defects liability period or after 12 months following the successful Acceptance and handover of the Asset.

      - The purpose of this P.O.E. is to establish whether the design objectives set in the business case have been successful, and to identify lessons learned for projects, standards and business benefits, including cost reduction, going forward.

      - This recognises the need for continual improvement against the expected design performance against the actual performance of an asset

Timing of Evaluation

      - The timing of the P.O.E. will be determined by the DIO PM in conjunction with the project stakeholder community. Timing will be such that it allows sufficient time to elapse to assess the degree to which benefits have been delivered and good practice to be identified. The initial assessment is will generally take place following completion of the Defects Liability Period or 12 months with a follow up assessment in year 2 and 3 (Undertaken by the Maintainer of the asset supported by the Operator of that asset.

Responsibility

      - The Projects Technical Support Provider (TSP) will be made responsible by the DIO PM for the delivery of the first P.O.E. (details of evaluation team to be provided within the P.O.E. report).

      - Based upon the first evaluation year 2 and 3 evaluations will be undertaken by the DIO FM team, or its delivery partner (details of evaluation team to be provided within the P.O.E. report).

Procedures

      - The P.O.E. will assess the entire project including Design performance parameters (including relevant Building Performance Standards (BPS)) on Structure, M&E, Actual Energy Consumption, Durability etc.

      - The P.O.E. will also form part of the projects Post Project Evaluation which will assess the benefits as forecast in the projects Main Gate Business Case. The P.O.E. will not however assess delivery of the commercial case or Project Management.

Content

      - The following shall be incorporated within the P.O.E. Report:

        - Project Brief:

          - Project Title;

          - Project Manager;

          - Type of Asset Date of P.O.E. project phase reviews;

          - Date(s) of P.O.E. evaluation;

          - Project Background;

          - Asset Design and Vision;

          - Type of Construction;

          - Use.

  - Financial Performance:

    - Capital Cost (£/m2) - the one-off construction cost and m2 GIA. and; 
Operational Cost (£/m2) - the ongoing running costs m2 GIA / NIA.  These may be based on a few areas of distinct measures / costs that are understood for the asset.
with;

    - Maintenance Cost (£/m2) - the ongoing maintenance cost m2 GIA / NIA.  This may be focused on specific elements of maintenance, e.g., significant capital maintenance.

    - Whole life costs (based on anticipated use of the asset). Costs and performance must be structured using industry standard measures, methodologies and metrics (IPMS, RICS Code of Measuring Practice and NRM1, 2 and 3) to allow auditable operational measurement and benchmarking within MoD and across industry.

  - Functionality and Utilisation:

### Using proprietary survey methods such as Design Quality Indicators and Building Use Studies, or an occupant / end user survey / focus group and;

### By measuring actual outcomes against user requirements and agreed targets defined from the business case, and;

### By establishing outcomes for capital asset performance as part of business plans and the monitoring of these post completion.

    - Has the project (for refurbishments only) changed the gross internal area of an asset;

    - Has the project (for refurbishments only) had an impact on the assets space utilisation and efficiency of an asset and how;

    - The Condition of the Estate (including dates PCF uploaded);

    - Changes in Management of asset (maintenance criteria re-categorised).

  - Environmental Performance, so that we can support forecasting and performance in Environmental Impact and operational costs.  The measures of planned versus actual should be taken from one or more of those shown below:

    - Operational waste in tonnes planned versus actual;

    - Energy use in kWh / m2 GIA for regulated loads as established by the Display Energy Certificate or another recognised methodology;

    - Carbon Dioxide Emissions in CO2 / m2 GIA for regulated loads; tonnes of emissions as established by the Display Energy Certificate or another recognised methodology;

    - % of energy from renewable; heating represented as m2 GIA

    - % of energy from renewable; electrical represented as m2 GIA

    - Water use in litres represented

    - DREAM Operation review as m2 based on GIA

- Post Operational Tools

  - Depending on the value and complexity of the project the following tools need to be considered, the reason for the decisions taken as which tools are adopted recorded and then undertaken as appropriate:

    - Occupant survey questionnaires;

    - User interviews and surveys;

    - Walk through observation.

  - Service Delivery questionnaires:

    - Metering and sub metering reviews,

    - Maintenance and operating cost reviews.

  - Qualitative methods:

    - Observation;

    - Interview;

    - Focus groups;

    - Workshops.

  - Analytical methods:

    - Questionnaire,

    - Measurement,

    - Benchmarking.

- MOD GSL Implementation:

  - The principles of GSL will be tested within all projects in, or approaching, the construction. phase.

  - All other projects will undertake the GSL procedures in accordance with this Guidance Document with any clarity required available from the GSL Champion.

GSL

Post Operational Evaluation Report

### Instruction/Guidance Template

Summary:

- A brief summary of the project and findings of the P.O.E

Purpose

- As part of the life cycle of the project delivery process, the DIO PM will arrange for P.O.E.s to be completed.

- The purpose of this P.O.E. is to establish whether the objectives set in the business case have been successful, and to identify lessons learned for projects, standards and business benefits, including cost reduction, going forward.

Timing of Evaluation

- The timing of the P.O.E. will be determined by the DIO PM in conjunction with the project stakeholder community. Timing will be such that it allows sufficient time to elapse to assess the degree to which benefits have been delivered and good practice to be identified. The initial assessment is will generally take place following completion of the Defects Liability Period or 12 months with a follow up assessment in year 2 and 3.

Responsibility

- The Projects Technical Support Provider (TSP) will be made responsible by the DIO PM for the delivery of the first P.O.E. (details of evaluation team to be provided within report).

- Based upon the first evaluation year 2 and 3 evaluations will be undertaken by the Regional Delivery team supported by their delivery partner (details of evaluation team to be provided within report).

Procedures

- The P.O.E. will assess the entire project including Design performance parameters (including relevant Building Performance Standards (BPS)) on Structure, M&E, Actual Energy Consumption, Durability etc.

- The P.O.E. will also form part of the projects Post Project Evaluation which will assess the benefits as forecast in the projects Main Gate Business Case. The P.O.E. will not assess delivery of the commercial case or project management.

Project Background

- Brief description of the project.

- Project objectives & published benefits.

Evaluation

- Overview of Evaluation (see Table 1).

- Project Evaluation details including Stakeholder Engagement.

- Lessons Learned.

- Conclusion and Recommendations.

- The P.O.E. shall hall be developed and implemented in 4 parts, Process Evaluation, Functional Performance, Environmental Performance and Financial Performance:

  - The Process Evaluation:

### The operational management of the building; how closely does the actual operation of the building align with that expected (have we had to alter our FM strategy to accommodate the design)?

### The delivery of the project;

### GSL as part of the process and how this has worked;

### training was successfully provided and met the needs of those using and managing the asset.

### Functional Performance, meeting the needs of those that commission and use the asset.

### Outcomes and targets for user needs for capital programmes are established and;

### Success against are being monitored.  Assessment against this should be by planned versus actual;

### Using proprietary survey methods such as Design Quality Indicators and Building Use Studies, or an occupant / end user survey / focus group and;

### By measuring actual outcomes against user requirements and agreed targets defined from the business case, and / or;

### By establishing outcomes for capital asset performance as part of business plans and the monitoring of these post completion.

### Environmental Performance so that we can support forecasting and performance in Environmental Impact and operational costs.  The measures of planned versus actual:

### Operational waste in tonnes planned versus actual;

### Energy use in kWh / m2 GIA for regulated loads as established by the Display Energy Certificate or another recognised methodology;

### Carbon Dioxide Emissions in CO2 / m2 GIA for regulated loads; tonnes of emissions as established by the Display Energy Certificate or another recognised methodology;

### % of energy from renewable; heating represented as m2 GIA

### % of energy from renewable; electrical represented as m2 GIA

### Water use in litres represented as m2 based on GIA

### Actual design performance (Building Performance Standards) against that specified.

### Financial Performance to improve construction and operational forecasting and efficiency.  The measures of planned versus actual should be used as shown below;

### Capital Cost (3/m2) - the one-off construction cost and m2 GIA using the Cabinet Office Methodology and;

### Operational Cost (£/m2) - the ongoing running costs m2 GIA / NIA.  These may be based on a few areas of distinct measures / costs that are understood for the asset.
with;

### Maintenance Cost (£/m2) - the ongoing maintenance cost m2 GIA / NIA.  This may be focused on specific elements of maintenance, e.g., significant capital maintenance or;

### Whole life costs (based on anticipated use of the asset).  Costs must be structured to allow auditable measurement to take place in year 1, 2 or 3 of operations and thereafter.