## COVER PAGE
SCHEDULES OF WORK
-in respect of-
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
-at-
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
-for-
THE HORNIMAN PUBLIC MUSEUM &
PUBLIC PARK TRUST
A J Oakes and Partners
Chartered Quantity Surveyors
Unit 83, Capital Business Centre
22 Carlton Road
South Croydon
May 2022 |  | Surrey, CR2 0BS

## CONTENTS
Schedules of Work
-in respect of-
Historic façade repair and redecoration works
-at-
100 London Road, Forest Hill, London, SE23 3PQ
-for-
The Horniman Public Museum &
Public Park Trust
- comprising -
Section No. 1 | - | Conditions of Contract / Preliminaries
Section No. 2 | - | Temporary access / investigation works
Section No. 3 | - | Work to the 1911 Building
Section No. 4 | - | Work to the 1901 Building
Section No. 5 | - | Work to the South Hall
Section No. 6 | - | Work at ground level
Section No. 7 | - | Addendum No. 1
Summary
Appendix A | - | Detailed terms of the Conditions of Contract
Appendix B | - | Detailed terms of the Preliminaries

## SECTION No. 1
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
SECTION No. 1
CONDITIONS OF CONTRACT / PRELIMINARIES
£ p
Following review of Appendix "A" and Appendix "B" the Contractor is to insert below his proposed costs in respect of the "Conditions of Contract" and "Preliminaries". In the event that no specific allowance is stated below the Contractor will be deemed to have covered elsewhere within the body of the pricing for the cost of fully complying with the terms detailed in Appendix "A" and "B".
1.01
1.02
1.03
1.04
1.05
1.06
1.07
1.08
1.09
1.1
1.11
1.12
1.13
1.14
1.15
SECTION No. 1 - CONDITIONS OF CONTRACT / PRELIMINARIES
|  |  | To Summary £ | 0

## SECTION No. 2
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 2
TEMPORARY ACCESS / INVESTIGATION WORKS
£ p
2.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
2.1 - Temporary works
2.2 - External survey / report
2.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 2.1 - TEMPORARY WORKS |  |  |  | 0
0
2.1.1 | Contractor Designed Portion: Provide alarmed scaffold (or access plant) in gaining access to the areas of works described in Sections 3, 4 and 5 of this document. Include for all necessary costs in respect of licences, hoists, safety netting, fans etc. Allow for altering and adapting the scaffold as required and remove on completion. In designing the scaffold the contractor is to take due regard of the following: 1) The alarm is to be designed such that the security personnel in the clock tower are alerted if triggered 2) Access ladders at ground level are to be removed whenever the scaffold is not in use 3) Fire escape routes from the museum, on both 1901 and 1911 facades, to remain unobstructed at all times. | 1 | Item |  | 0
0
2.1.2 | in pricing the item above, given the scope of works so described in this document, the Contractor is requested to state how many weeks hire has been duly allowed for. |  | weeks |  | 0
0
2.1.3 | in the event that the CA instructs additional works (over and above that described below) thereby requiring the extended hire of the scaffold then the Contractor is requested to quote here his additional cost per week for such an eventuality. Should the Contractor elect to claim prolongation costs on this basis then he is reminded that the Contract provisions are to be followed and as such due 'cause and affect' will need to be demonstrated before the inclusion of costs will be considered. |  | / week |  | 0
0
0
2.1.4 | Note: The Contractor is to allow the Horniman Museum access to the scaffolding for the repositioning of site security cameras as required. | 0 | 0 | 0 | 0
0
2.1.5 | Note: The Museum will require any temporary access towers to be dismantled at the end of each day and stored securely overnight. | 0 | 0 | 0 | 0
0
0
0
| 2.2 - EXTERNAL SURVEY / REPORT |  |  |  | 0
0
2.2.1 | Allow for undertaking a condition survey, by a suitably qualified professional, to all elements of the existing external fabric of the building located on the elevations described in this section of the document (i.e. external stone / brick walls, windows, doors, roof, chimneys etc.) in identifying where repair works are necessary to allow the building to be made fully weatherproof. In pricing this item, the Contractor is to allow for all necessary liaison in gaining access into the building as required. Upon completion of the survey allow for producing a detailed written report for subsequent handing to the CA / Employer. | 1 | Item |  | 0
0
0
0
0
SECTION No. 2 - TEMPORARY ACCESS / INVESTIGATION WORKS
|  |  |  | To Summary £ | 0

## SECTION No. 3
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 3
WORK TO THE 1911 BUILDING
£ p
3.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
3.1 - Structural repairs
3.2 - Stonework repairs
3.3 - Roofing / leadwork repairs
3.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 3.1 - STRUCTURAL REPAIRS |  |  |  | 0
0
3.1.1 | Note: In pricing the below the Contractor is to note that repair work to the existing slate roof finishes (as disturbed by the works) and the new lead cover flashings have both been measured separately in Section 3.3 | 0 | 0 | 0 | 0
0
0
| Temporary works |  |  |  | 0
0
3.1.2 | In accordance with the 'Structural Conservation Repair Notes' 1 and 2 on drawing 211042-CON-XX-03-DR-S-4000 the Contractor is to allow for the design and installation of all temporary support / weatherproofing works in undertaking the items of work so described under this heading | 1 | Item |  | 0
0
0
| New works |  |  |  | 0
0
| Allow for the following works in undertaking a structural repair to an existing steel beam located on the right hand tower; as indicated on drawings 211042-CON-XX-RF-DR-S-1102; 211042-CON-XX-XX-DR-S-3000 and 211042-CON-XX-03-DR-S-4000 |  |  |  | 0
0
3.1.3 | careful removal of temporary protection, lead flashings, slates, existing doulting stone facing blocks etc. in exposing the front face of the existing corroded steel beam (7 x 4 x 16 BSB) | 1 | Item |  | 0
0
3.1.4 | cleaning existing steel beam and drilling pilot holes through web of the steel to gauge the remaining thickness; report findings to the engineer | 1 | Item |  | 0
0
3.1.5 | treating exposed surfaces of steel with macropoxy M902 primer by Sherwin Williams Paints | 1 | Item |  | 0
0
3.1.6 | new 125 x 65 x 15 PFC; Grade S275; hot dip galvanised; approximately 1400mm long; bolted alongside existing beam with M12 hot dip galvanised hollo bolts by Lindapter at 200mm centres | 1 | Item |  | 0
0
3.1.7 | new micro-concrete infill around steelwork (class R3/C30) equivalent; concrete either to be hand applied or flowable grout with shuttering | 1 | Item |  | 0
0
3.1.8 | new matching stone infill; stone to be sourced from Doulting stone quarry and matched as closely as possible; bedded in NHL 3.5 lime mortar | 1 | Item |  | 0
0
3.1.9 | extra for providing samples to site for approval by the CA | 1 | Item |  | 0
0
0
0
| 3.2 - STONEWORK REPAIRS |  |  |  | 0
0
| Coping cramps |  |  |  | 0
0
| Allow for rebedding the existing coping cramps to the following locations; as indicated on drawings 211042-CON-XX-RF-DR-S-1102 and 211042-CON-XX-XX-DR-S-3000 |  |  |  | 0
0
3.2.1 | left hand tower coping | 1 | Item |  | 0
0
3.2.2 | extra over for replacing damaged coping cramp to the left hand tower in lieu of simply rebedding the existing (APPROXIMATE) | 3 | No |  | 0
0
3.2.3 | right hand tower coping | 1 | Item |  | 0
0
3.2.4 | extra over for replacing damaged coping cramp to the right hand tower in lieu of simply rebedding the existing (APPROXIMATE) | 3 | No |  | 0
0
3.2.5 | central balcony coping | 1 | Item |  | 0
0
0
| Crack repairs |  |  |  | 0
0
3.2.6 | Allow for stone / mortar repair works to deep crack to the left hand tower; colour / standard of materials to match existing; as indicated on drawing 211042-CON-XX-XX-DR-S-3000 | 1 | Item |  | 0
0
0
| Repointing |  |  |  | 0
0
3.2.7 | Rake out defective mortar joints to facing stonework and renew pointing in a colour / standard of material to match existing (APPROXIMATE) | 300 | m |  | 0
0
0
0
| 3.3 - ROOFING / LEADWORK REPAIRS |  |  |  | 0
0
3.3.1 | The Contractor is to note that all works measured under this heading represents a Contractor Designed Portion of the works | 0 | 0 | 0 | 0
0
0
| Code 5 lead |  |  |  | 0
0
| Supply and install Code 5 leadwork to the following locations; as indicated on drawings 211042-CON-XX-RF-DR-S-1102; 211042-CON-XX-XX-DR-S-3000 and 211042-CON-XX-03-DR-S-4000 |  |  |  | 0
0
3.3.2 | abutment flashing to the left hand tower | 1 | Item |  | 0
0
3.3.3 | abutment flashing to the right hand tower (next structural repair works) | 1 | Item |  | 0
0
0
| Code 6 lead |  |  |  | 0
0
| Supply and install Code 6 leadwork to the following locations; as indicated on drawings 211042-CON-XX-RF-DR-S-1102; 211042-CON-XX-XX-DR-S-3000 and 211042-CON-XX-03-DR-S-4000 |  |  |  | 0
0
3.3.4 | cornice weathering to the left hand tower; all as details 3 & 4 on drawing 211042-CON-XX-03-DR-S-4001 | 1 | Item |  | 0
0
3.3.5 | cornice weathering to the right hand tower; all as details 3 & 4 on drawing 211042-CON-XX-03-DR-S-4001 | 1 | Item |  | 0
0
3.3.6 | cornice weathering to the central balcony; all as detail 5 on drawing 211042-CON-XX-03-DR-S-4001 | 1 | Item |  | 0
0
0
| Provisional sums |  |  |  | 0
0
3.3.7 | Provide the Provisional Sum of £1,000.00 for localised repair to the right left hand tower single ply membrane roof finish | 1 | Item | 1000 | 1000
0
0
0
0
SECTION No. 3 - WORK TO THE 1911 BUILDING
|  |  |  | To Summary £ | 1000

## SECTION No. 4
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 4
WORK TO THE 1901 BUILDING
£ p
4.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
4.1 - Stonework repairs
4.2 - Leadwork repairs
4.3 - Redecoration works
4.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 4.1 - STONEWORK REPAIRS |  |  |  | 0
0
| Hole repairs |  |  |  | 0
0
4.1.1 | Allow for stone / mortar repair works to hole in façade stonework adjacent to the North corner pediment; allow for a new stone indent sized 300 x 300 x 100mm; colour / standard of materials to match existing; as indicated on drawing 211042-CON-XX-XX-DR-S-3001 | 1 | Item |  | 0
0
0
0
| 4.2 - LEADWORK REPAIRS |  |  |  | 0
0
4.2.1 | The Contractor is to note that all works measured under this heading represents a Contractor Designed Portion of the works | 0 | 0 | 0 | 0
0
0
| Code 6 lead |  |  |  | 0
0
| Supply and install Code 6 leadwork to the following locations; as indicated on drawings 211042-CON-XX-RF-DR-S-1102 and 211042-CON-XX-XX-DR-S-3001 |  |  |  | 0
0
4.2.2 | pediment weathering; all as detail 1 on drawing 211042-CON-XX-03-DR-S-4001 | 1 | Item |  | 0
0
4.2.3 | mid level (main) cornice; all as detail 1 on drawing 211042-CON-XX-03-DR-S-4001 | 1 | Item |  | 0
0
4.2.4 | high level (secondary) cornice; all as detail 2 on drawing 211042-CON-XX-03-DR-S-4001 | 1 | Item |  | 0
0
0
0
| 4.3 - REDECORATION WORKS |  |  |  | 0
0
| Prepare and repaint all existing painted surfaces to the following existing external metalwork |  |  |  | 0
0
4.3.1 | 2No items of decorative ironwork located at either end of the stonework sign which reads "THE HORNIMAN FREE MVSEVM" | 1 | Item |  | 0
0
0
0
0
SECTION No. 4 - WORK TO THE 1904 BUILDING
|  |  |  | To Summary £ | 0

## SECTION No. 5
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 5
WORK TO THE SOUTH HALL
£ p
5.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
5.1 - External brickwork repairs
5.2 - Internal brickwork repairs
5.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
5.0.3 | Note: Access to the locations described in this section of the document can be achieved via the internal areas of the Museum. If the Contractor proposing to use this access, in lieu of creating a scaffold access route, then their submission should be made clear in this regard. If internal access is used then due consideration will need to be given on minimising dust within the museum and the proposed routes for waste. | 0 | 0 | 0
0
| 5.1 - EXTERNAL BRICKWORK REPAIRS |  |  |  | 0
0
| Brick repairs |  |  |  | 0
0
| Allow for replacing missing or damaged facing brick to face of existing chimney stack; colour / standard of material all to match existing; as indicated on drawing 211042-CON-XX-RF-DR-S-4002 |  |  |  | 0
0
5.1.1 | as described in undertaking a brick repair comprising 1No new brick (APPROXIMATE) | 20 | No |  | 0
0
5.1.2 | extra for providing samples to site for approval by the CA | 1 | Item |  | 0
0
0
| Repointing |  |  |  | 0
0
| Allow for all necessary repointing works to the existing chimney stacks that are located above the South Hall; colour / standard of materials to match existing; as indicated on drawings 211042-CON-XX-RF-DR-S-1102 and 211042-CON-XX-RF-DR-S-4002 |  |  |  | 0
0
5.1.3 | as described to chimney stack 1 | 1 | Item |  | 0
0
5.1.4 | as described to chimney stack 2 | 1 | Item |  | 0
0
5.1.5 | as described to chimney stack 3 | 1 | Item |  | 0
0
0
0
| 5.2 - INTERNAL BRICKWORK REPAIRS |  |  |  | 0
0
5.2.1 | Note: The works measured under this heading relate to an area of brickwork at Basement level adjacent to the Aquarium Room | 0 | 0 | 0 | 0
0
0
| Repointing |  |  |  | 0
0
5.2.2 | Rake out defective mortar joints to brickwork wall and renew pointing in a colour / standard of material to match existing; area not exceeding 3m2 | 1 | Item |  | 0
0
5.2.3 | extra for cleaning the brickwork and undertaking any necessary chlorine remediation work to the brickwork | 1 | Item |  | 0
0
0
0
0
SECTION No. 5 - WORK TO THE SOUTH HALL
|  |  |  | To Summary £ | 0

## SECTION No. 6
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 6
WORK EXTERNALLY AT GROUND LEVEL
£ p
6.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
6.1 - Work to Visitor entrance (North Plan)
6.2 - Work to Museum frontage (South Plan)
6.3 - Work to the Eastern site boundary walls
6.0.2 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 6.1 - WORK TO VISITOR ENTRANCE (NORTH PLAN) |  |  |  | 0
0
6.1.1 | Note: In pricing the items of work that follow the Contractor is to note that access in and an emergency exit route out of the museum is to be maintained during opening hours and after hours events. To confirm the museum opening hours, which are 10am – 5:30pm, seven days a week. Accordingly the Contractor is requested to programme these works so that they are out of hours and also on a phased basis so that disruption to the museum's operations is kept to a minimum. | 0 | 0 | 0 | 0
0
0
| Allow for the following works in replacing existing tactile stone paviours; as indicated on drawings 211042-CON-XX-GF-DR-S-1100 and LAB-649-DE-2500 |  |  |  | 0
0
6.1.2 | temporarily remove section of existing paving to confirm the thickness of the pavings for fabrication purposes; reinstate for continued access until the works commence | 1 | Item |  | 0
0
6.1.3 | carefully remove the existing stone paviours; in removing ensure that no damage is occasioned to the adjacent paving, drainage grille or architectural metalwork | 1 | Item |  | 0
0
6.1.4 | supply and install new Portland Stone paviours; upper surface of machined to create corduroy markings in line with current guidance for those with visual impairments | 1 | Item |  | 0
0
6.1.5 | extra for providing samples to site for approval by the CA | 1 | Item |  | 0
0
0
0
| 6.2 - WORK TO MUSEUM FRONTAGE (SOUTH PLAN) |  |  |  | 0
0
| Survey |  |  |  | 0
0
6.2.1 | Prior to commencement of the works allow for undertaking a detailed survey of all the low level stone walls; report findings to the Contract Administrator and as required seek instruction | 1 | Item |  | 0
0
0
| Replacement of existing stone blocks |  |  |  | 0
0
6.2.2 | Allow for replacing 1No cracked block located within low level Wall 1; scope / specification as indicated on drawings 211042-CON-XX-GF-DR-S-1100 and 211042-CON-XX-RF-DR-S-4003 | 1 | Item |  | 0
0
0
| Resetting of existing stone blocks |  |  |  | 0
0
6.2.3 | Allow for resetting 2No displaced blocks located within low level Wall 2; scope / specification as indicated on drawings 211042-CON-XX-GF-DR-S-1100 and 211042-CON-XX-RF-DR-S-4003 | 1 | Item |  | 0
0
6.2.4 | Allow for resetting 1No displaced block located within low level Wall 5; scope / specification as indicated on drawings 211042-CON-XX-GF-DR-S-1100 and 211042-CON-XX-RF-DR-S-4003 | 1 | Item |  | 0
0
0
| Repair work to existing blocks |  |  |  | 0
0
| Allow for repairing the following cracked / spalled low level walls; scope / specification as indicated on drawings 211042-CON-XX-GF-DR-S-1100 and 211042-CON-XX-RF-DR-S-4003 |  |  |  | 0
0
6.2.5 | wall 1; comprising 5No identified locations of spalling | 1 | Item |  | 0
0
6.2.6 | wall 2; comprising 1No identified location of spalling | 1 | Item |  | 0
0
6.2.7 | wall 5; comprising 2No identified locations of spalling | 1 | Item |  | 0
0
6.2.8 | wall 6; comprising 1No identified location of spalling | 1 | Item |  | 0
0
6.2.9 | wall 7; comprising 1No identified location of spalling | 1 | Item |  | 0
0
0
| Repointing |  |  |  | 0
0
| Allow for all necessary repointing works to the following low level stone walls; colour / standard of materials to match existing; as indicated on drawings 211042-CON-XX-GF-DR-S-1100 and 211042-CON-XX-RF-DR-S-4003 |  |  |  | 0
0
6.2.10 | wall 1; length approximately 12.80m | 1 | Item |  | 0
0
6.2.11 | wall 2; length approximately 18.00m | 1 | Item |  | 0
0
6.2.12 | wall 3; length approximately 3.30m | 1 | Item |  | 0
0
6.2.13 | wall 4; length approximately 6.60m | 1 | Item |  | 0
0
6.2.14 | wall 5; length approximately 8.80m | 1 | Item |  | 0
0
6.2.15 | wall 6; length approximately 3.80m | 1 | Item |  | 0
0
6.2.16 | wall 7; length approximately 10.10m | 1 | Item |  | 0
0
6.2.17 | wall 8; length approximately 7.00m | 1 | Item |  | 0
0
0
| Provisional sums |  |  |  | 0
0
6.2.18 | Provide the Provisional Sum of £2,000.00 defined works for additional repair works to existing low level stone walls | 1 | Item | 2000 | 2000
0
0
0
| 6.3 - WORK TO THE EASTERN SITE BOUNDARY WALLS |  |  |  | 0
0
| Helical bars |  |  |  | 0
0
6.3.1 | Grind out existing masonry joint and install new 6mm diameter stainless steel helical bar; bed bar in polyester resin or cementitious grout; repoint masonry joint; length not exceeding 1.00m (APPROXIMATE) | 20 | No |  | 0
0
0
| Repointing |  |  |  | 0
0
6.3.2 | Allow for all necessary brickwork repointing works to 3No separate locations on the eastern site boundary wall; colour / standard of materials to match existing; locations as indicated on drawings 211042-CON-XX-GF-DR-S-1100 | 1 | Item |  | 0
0
0
0
0
SECTION No. 6 - WORK AT GROUND LEVEL
|  |  |  | To Summary £ | 2000

## SECTION No. 7
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
= Contractor to insert pricing
SECTION No. 7
ADDENDUM No. 1
£ p
7.0.1 | In pricing the items that follow, the Contractor shall be deemed to have thoroughly inspected the tender documents and have acquainted himself with the site and the full extent / character of the items. The items have been split into the following priceable areas of work: | 0 | 0 | 0 | 0
7.1 - Cornice repair work
7.0.2 | This Errata document is based on the following additional information issued by Conisbee Structural Engineers:
211042-CON-XX-GF-DR-S-4004/T1 - 1901 Building - Cornice repair
7.0.3 | The Contractor is requested to price and submit this document electronically. In the event that the Contractor elects not to submit the tender electronically then it is requested, for ease of checking, that each printed page is individually totalled and carried forward to a summary. | 0 | 0 | 0 | 0
0
| 7.1 - CORNICE REPAIR WORK |  |  |  | 0
0
| Allow for the following works in replacing 3No sections of existing eroded stonework to the high level cornice on the 1901 building; as indicated on drawing 211042-CON-XX-GF-DR-S-4004/T1: |  |  |  | 0
0
7.1.1 | carefully cut out 3No sections of eroded existing cornice stonework; form square edged recesses of approximately 50mm depth and prepare to receive new stone | 1 | Item |  | 0
0
7.1.2 | take templates from the remaining parts of the cornice and form replacement units from Doulting stone; the replacement stones are to precisely match the dimensions of the existing | 1 | Item |  | 0
0
7.1.3 | extra for providing samples of stone for approval prior to ordering | 1 | Item |  | 0
0
7.1.4 | installation of the 3No replacement stone sections; stones to be secured using 8mm diameter dowel pins and Hilti HIT-HY 270 resin; stones to be bedded in NHL2 : stone dust : sharp sand mortar; colour and appearance mortar to match existing with flush joints | 1 | Item |  | 0
0
0
| Provisional sums |  |  |  | 0
0
7.1.5 | Provide the Provisional Sum of £2,000.00 for additional stone repairs to the existing cornices | 1 | Item | 2000 | 2000
0
0
0
0
SECTION No. 7 - ADDENDUM No. 1
|  |  |  | To Summary £ | 2000

## SUMMARY
.
HORNIMAN MUSEUM
100 LONDON ROAD, FOREST HILL, LONDON, SE23 3PQ
HISTORIC FAÇADE REPAIR AND REDECORATION WORKS
SUMMARY
£ p
| Section No. 1 | - | Conditions of Contract / Preliminaries |  | 0
| Section No. 2 | - | Temporary access / investigation works |  | 0
| Section No. 3 | - | Work to the 1911 Building |  | 1000
| Section No. 4 | - | Work to the 1901 Building |  | 0
| Section No. 5 | - | Work to the South Hall |  | 0
| Section No. 6 | - | Work externally at ground level |  | 2000
| Section No. 7 | - | Addendum No. 1 |  | 2000
|  |  |  | Sub-total £ | 5000
| - |  | Provide the Provisional sum of £3,000.00 for contingencies |  | 3000
|  |  |  | TOTAL £ | 8000 | #
Name of Contractor:
Address:
Date: