## Sheet1
CLARIFICATION LOG
Tender: | Public Toilet Replacement and Refurbishment Tender - Teignmouth Town Council
Tender Reference: | 01-(10.24)
Published Date: | 30.11.2024
Version number: | 0.5
Number | Clarification | Response | Reply date
1 | All the pricing documents in excel so we can complete and return, they are currently part of the PDF pack of each site only so cannot be completed | These have now been added to the Contracts Finder documents for the individual sites. Also included is a Total Collection Sheet for updating and including as part of any tender submission | 2024-11-17
2 | Form of tender – documents say this is in the ITT but I cannot see it can you please provide a copy | The form of Tender and accompanying declarations are to be found in Part A document of the supplier response. | 2024-11-17
3 | Funding requirements – documents say this is in the ITT but I cannot see it can you please provide a copy | The funding is solely from Teignmouth Town Council | 2024-11-17
4 | The pricing schedule sections states there are various foundation options on the architect drawings and specification but this pack has not been provided. Are we to provide the options on complete additional breakdowns or as extra over costs ? | For pricing purposes assume strip foundations. Site conditions will formally dictate actual requirements. | 2024-11-17
5 | The Den: Pre construction information says to follow, can you advise when? | This has now been uploaded onto Contracts Finder | 2024-11-18
6 | The Den: Architect information says further information to follows, can you advise what and when ? | These have now been uploaded onto Contracts Finder | 2024-11-18
7 | The Den: M&E says included in architect information but the architect section is to follow | Please refer to drawings and updated specification | 2024-11-18
8 | The Den: Employers documents says included in architect information but the architect section is to follow | Please refer to drawings and updated specification | 2024-11-17
9 | The Den: Planning information say to follow, can you advise when ? | Planning permission has been obtained and the design and building regulations are in line with the Planning Permission (see newly uploaded Building Regulations Approval). The Council are aware that the details in the price schedule are significantly different from the design drawings but in order to get competitive tender returns please price as per the schedule of works provided including the prelims based on the programme shown. | 2024-11-17
10 | The Den: Having read all the info and further we think you may have the employee requirements completely wrong ( attached). This refers to 3 unisex 1 disabled toilet whereas the planning drawing shows 19 unisex 1 disabled?? I asked the question when on site with them and they told me as per planning however there was a small planning revision. Also, the programme shows 14 weeks build time which is pretty much the same as the others but 5 times bigger | See point 9 above. | 2024-11-17
11 | With regards the replacement toilets can we offer a Modular option rather than a new build construction? | The Council would be prepared to accept a modular (offsite) construction that meets the design parameters which have been set out as a compliant tender. If this is to be provided the Council would be seeking assurances of a design life minimum of 25 years. | 2024-11-17
12 | Can you also please clarify the allowed mobilisation period ? the tender programme provided says 16/12 through to 06/01, but as this falls over the Christmas shut down period for the industry this is actually only 5 working days. More time will be required to mobilise for the project, can you please confirm that: We will not be penalised on the tender return marking for extending the mobilisation period to 15 working days (the period allotted if it did not fall over Christmas). The end date can move in line with the adjusted start date? | Yes, the timetable is indicative and the Council recognises that the dates and alignment with the Christmas shutdown. We would be prepared to accept suitable alternative programmes as long as not substantively different from what is indicatively set out. | 2024-11-17
13 | The tender programme says about the blocks being carried out one after another, is there no option to overlap any sites during the works ? | The Council's rationale for the programme is to complete a small block first to iron out any issues. We then can have an overlap in the Den and Lower Brook Street and finally finance dictates the completion of the final two blocks into the next budgetary year. | 2024-11-17
14 | In the PDF file with the information for ‘The Den’ there isn’t any detailed drawing(s) of the new, proposed, toilet block. The only drawing that we have is a drawing of the old aquarium building showing / talking about the retaining wall page 101. If you could you send the new toilet drawings through that would be ideal. | These drawings have now been issued on 18/11/2024 | 2024-11-18
15 | Have Teignmouth Town Council made contact with both or either National Grid or South West Water regarding the water and electrical connections that will be going into these toilets. | Yes, the Council have had initial contact with both utilities. Full conversations and requirements will need to follow when works commences. | 2024-11-18
16 | Regarding the water connections, will we need or be able to close down roads or at least lanes, at East Cliff, The Point and Quay Road Carparks, to be able to run new connections to the proposed toilets. Has there been any consideration of these issues with dialogue with the highway department? | No direct conversations have been held by the Council. Any statutory connections would be dealt with by the utility companies. Any utility connections within the car parks are owned by Teignbridge District Council so any connections on that land would be dealt with direct with the client. | 2024-11-18
17 | Knowing the clarification responses are scheduled for 22/11/24, but I was wondering if it would be possible to send out The Den drawings a bit earlier to give us additional time to price them accordingly. | These drawings have now been issued on 18/11/2024 | 2024-11-18
18 | With the clarification answers due to be published on the 22nd of November and no drawings for The Den having been issued yet, we kindly request an extension of time to ensure we can provide a comprehensive and accurate submission. | Teignmouth TC have amended the return date to noon on Monday 9 December 2024 - the Invitation to Tender document Volume 1 and Part A and B have been updated with the revised dates. | 2024-11-24
19 | We have reviewed the clarifications and the updated drawings for The Den toilets. However, the pricing document still reflects the BOQ as a regular toilet block. Could you please confirm if we are to adjust the quantities to match the updated drawings? | Please see 9 and 10 above. | 2024-11-25
20 | We have some questions if we could please get an urgent answer to these in order to meet the tender deadline:
(a) | Is the newspace architecture specification actually for this project? There seem to be lots of irrelevant comments such as: a) Final positions of electrics to be confirmed on site by client and installed in accordance with NEW SPACE ARCHITECTURE ACCESS TO MANUAL CONTROLS DRAWING. - this drawing is not relevant to the project, how can we install in accordance with it? This shows a domestic layout arrangement with switches etc that wont be in place in a public toilet set up b) The general electrical specification comments relate to domestic dwellings and not a public WC c) Plumbing is referencing baths, bidets and showers ? d) The electrical compliance references are out of date with industry current standards e) There is mention to lighting controls and display setting, is this relevant ? f) There is references to offices areas and small workshops and manual lighting controls ? g) Toilets to have 3 air changes per hour, should this not be 6 ? h) There is a comment to say the current drawings do not comply with current standards and M&E is contractors design. However there isn’t suitable outline specification or employers requirements to make a full assessment of what’s required i) There are numerous comments to data, what data is required as this is not clear ? j ) All sockets to be white, except where metal clad ? please clarify | For the main points raised, M&E are contractor design. There are elements listed which are therefore not required, e.g. Baths / Bidets, which can be ignored. Rain water harvesting is in all sites located under the buildings apart from Lower Brook Street which should be assumed as contractor design. For the Den M&E should be priced as per East Cliff for the purposes of price for the evaluation. Please also note, this is JCT Minor Works (with Contractor Design) not just JCT Minor Works. | 2024-11-25
(b) | There are items in the pricing document that are not covered elsewhere, or not clear, can you please clarify: a) Recessed mounted complete hand washing facility - Will this be supplied by the employer? We can't find any details on what is required, b) Alarm systems - What is required, we can't find a spec or any details? c) 4kwh Solar PV installation - Not detailed in the specification and there are no invertors etc shown ? d) BMS System - Not detailed in the specification or drawings. Is this required? To control what? Does it need to link to a remote monitoring system? e) Data Installation - Not on the drawings but mentioned within the spec (as above - so we don't believe it has any relevance to the project). Please advise if anything is required? 1) The lighting where shown on the Den seems very excessive ? there are more than double the amount of lights needed, 2) There are no power supplies shown for the wallgate hand basins, 3) There are no power supplies shown for the turnstiles, 4) There are no PV inverters or power supplies shown relating to this, 5) Considering the size of the maintenance corridoes, the number of sockets seem very excessive ? | Please see response to 20 (a) above. | 2024-11-25
(c) | Are there rainwater harvesting system required ? It is mentioned in the spec but then not shown on any drawings (except the den) its also not in the pricing document for any of the sites ? If it is required please clarify a) Is this at all the new sites ? or just the den, b) Please provide construction drawings and details relating to this, c) There is no system shown to actually utilise the rainwater ? presumably there should be a pump and header tank and so on ? d) Does it need alarms, overflow connection , e) On the den drawings it is shown on section, but then there are no indications of it on plan ? | Please see response to 20 (a) above. | 2024-11-25
(d) | Can you also please clarify the contract type ? the documents say JCT Minor Works Building Contract, but the information provided is very vague and outline performance only. This would allude more to a design and build contract, can you clarify if this should be a D&B or is a full stage 4 design going to be provided as there is currently a huge amount of information missing ? There is comments to the M&E being contractors design in full, but this would be a significant portion of the contract so I’m not sure the proposed contract type is suitable | Please see response to 20 (a) above. | 2024-11-25
(e) | Can you please clarify the full expectation on contractors design items, if this is to be let under the proposed contract type ? | Please see response to 20 (a) above. | 2024-11-25
(f) | Given the late issue of information for the largest part of the project, also the above needing urgent clarification, can we please request an extension to the tender return deadline ? | Please see response to 18 above. | 2024-11-25
21 | M&E: We appreciate you say it’s a CDP item but we need to base our price on some form of employers requirements, this isn’t currently clear. Specifics we need to know to ensure all M&E contractors are on a level footing are: Will the client be supplying the recessed mounted complete hand washing facility units as they are also supplying the other sanitary ware and these are big ticket items. If not could they please specify which units they require? | Teignmouth TC will supply the Wallgate units for contractor install. | 2024-11-30
22 | Is there any requirement for data or telephone cabling infrastructure? | No data or telephone cabling required. | 2024-11-30
23 | Is there any requirement for alarm systems? | No security alarm systems required | 2024-11-30
24 | Is there a requirement for fire alarm systems? | No fire alarm systems required | 2024-11-30
25 | Is the PV part of the M&E works or will this be procured direct by the client? | PV is to be part of the tendered costs | 2024-11-30
26 | Can you please list what items you consider to be CDP under this contract for clarity ? | This is as stated in the preliminaries, please refer to ‘preliminaries 001/8’. | 2024-11-30
27 | To be completely clear, you want us to price The Den, purely as the BOQs and ignore the design information provided ? But you then say M&E is a CDP item, so do they price what the M&E will be against the design drawings, or the comments alluding to it being similar size to the others ? Would it not make more sense to ask everyone to amend the pricing document and price The Den as designed ? There is more than enough time given the tender extension | For avoidance of doubt please price as the previous answer to this query and then no assumptions are required to be made. It is acknowledged that there are still design elements to be concluded on The Den.’ | 2024-11-30
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: