Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier will be required to make to the Buyers under this Order Contract

- PURPOSE

  - The Cabinet Office Evaluation Task Force (ETF) (also referred to as ‘the Buyer’) wishes to appoint an external supplier to conduct a scoping study for the evaluation of the Ministry of Defence’s (MoD’s) Army Single Living Accommodation (SLA) programme.

  - Suppliers should be aware that staff working on this project must receive, or have existing, Baseline Personnel Security Standard (BPSS) clearance in order to access most project documents and data. Suppliers will be expected to fund any associated expenses.

  - It is also expected that two members of staff working on the project will require Security Check (SC) clearance. The Buyer will sponsor this if SC is not already held.

- BACKGROUND TO THE Buyer

  - The Cabinet Office supports the Prime Minister, and ensures the effective running of government. Cabinet Office is also the corporate headquarters for government, in partnership with HM Treasury, and takes the lead in certain critical policy areas. More information can be found on its website at: https://www.gov.uk/government/organisations/cabinet-office

  - The ETF, a joint Cabinet Office and HM Treasury unit, was set up following the 2020 Spending Review to help ensure evidence sits at the heart of government decision making. As part of this, the ETF challenges and supports government departments to design and deliver robust evaluations. Our strategy provides more detail on who we are and what we do.

  - The ETF is supporting the MoD and the Defence Infrastructure Organisation (DIO) to put robust evaluation at the centre of the Army’s SLA rollout by commissioning an evaluation scoping study (the subject of this Statement of Requirements). As such, although Cabinet Office (ETF) is the Contracting Buyer, the supplier will be expected to work with the MoD as a primary partner.

- Background to requirement/OVERVIEW of requirement

  - REDACTED TEXT under FOIA Section 43 Commercial Interests

- definitions

| ## Expression or Acronym | ## Definition |
| --- | --- |
| ## ETF | ## Evaluation Task Force |
| ## CO | ## Cabinet Office |
| ## MoD | ## Ministry of Defence |
| ## SLA | ## Single Living Accommodation |
| ## DIO | ## Defence Infrastructure Organisation |

- scope of requirement

  - As set out in section 3 (background to the requirement/overview of requirement), the ETF wishes to commission an external partner to:

    - Collect survey data on well-being and satisfaction with living accommodation at key points, including at baseline (before/when residents enter accommodation).

    - Set out the feasibility of implementing robust evaluation designs for the SLA programme

    - Develop corresponding metrics/survey instruments that could be used to evaluate aspects of the SLA programme

    - Set out options for a proportionate process evaluation and/or any required qualitative research required to support the programme

    - Identify options for experimentation to reduce energy usage through the delivery of the programme

    - Deliver small scale pilots that test some key metrics/survey instruments and promising energy efficiency interventions

  - The requirement relates to the DIO’s rollout of Army’s new Single Living Accommodation. The Defence Estate Optimisation programme mentioned in the press release above, which is similar to SLA, is out of scope.

  - The supplier will be expected to provide the deliverables set out in this statement of requirements. These include scoping the feasibility of different evaluation approaches, developing and piloting metrics and research instruments, and developing and piloting energy efficiency interventions.

- The requirement

## Scoping study objectives

## The supplier will be expected to

  - Develop corresponding metrics/survey instruments that could be used to evaluate the SLA programme.

    - The supplier will be expected to identify the data collection methods and instruments needed to evaluate the programme. This will involve identifying existing data sources and outlining where additional data collection is needed. Improving wellbeing, increasing retention, and reducing energy consumption are goals of the SLA programme. While some of these outcomes may be tracked using administrative data, others (especially wellbeing) will require surveys. In terms of measuring wellbeing, user experience surveys are carried out annually by the Army. This includes a general satisfaction survey, which covers Messing, Services, and Accommodation.

    - Suppliers may wish to draw on approaches taken in the SLA lived experience survey and Armed forces continuous attitude survey, as well as ONS wellbeing survey measures and instruments.

  - Collect survey data on well-being and satisfaction with living accommodation at key points, including at baseline (before/when residents enter accommodation).

    - The supplier will work with DIO/MoD and Army colleagues to ensure that sufficient data from residents of SLA is collected at the right time points in order to support evaluation objectives. This will include collecting baseline survey data on wellbeing.

  - Set out the feasibility of implementing robust evaluation designs for the programme

    - The study should identify the most robust evaluation approaches that are possible within the programme context, leveraging the phased roll-out of construction and mix of buildings on sites. The MoD wishes to test the effectiveness of the choices made in SLA Wave 1, harnessing learning to improve the delivery of future waves. Wave 1 is part of the overall SLA programme that will be delivered over 10 years and across thousands of beds.

    - REDACTED TEXT under FOIA Section 43 Commercial Interests

  - Set out options for a proportionate process evaluation and/ or any required qualitative research required to support the programme

    - The study should outline proposed process and qualitative research activity required to complement the core experimental methodologies.

  - Identify options for experimentation to reduce energy consumption

    - The study should set out approaches for generating behavioural insights to support decisions about how to reduce the energy usage of the premises. This should include understanding which interventions work for which audiences (e.g. different ranks in different blocks) and could include piloting a small number of studies during the programme’s early rollout. In terms of measuring energy consumption, the new buildings will offer more opportunities for measuring energy use at sub-unit levels within the buildings. Existing buildings do not have such sub-unit metering in place.

  - Deliver small scale pilots that test some key metrics/survey instruments and energy efficiency interventions.

    - The supplier would be expected to work with MoD to agree priority survey instruments/metrics to pilot with Service people. The supplier would also be expected to agree with MoD suitable campaigns to pilot which seek to reduce the energy usage of residents in accommodation.

    - The study should produce actionable recommendations to put the MoD in a position to evaluate its future SLA Waves. The study should explore whether MoD could leverage existing data collection to support the programme evaluation, or whether new data collection is needed or beneficial.

  - Suggested approach and outputs

The following key outputs are likely to be expected from the supplier, but bidders are invited to submit additional or alternative proposals for meeting the requirement.

    - Project plan: the supplier will be expected to provide a project plan, for approval by the ETF and MoD, which outlines how they will meet the scoping study objectives. This should include a section on ethical considerations to satisfy the requirements of the MOD Research Ethics Committee (MODREC) guidelines (as outlined at section 10 below).

    - Theory of change: the supplier should begin the evaluation scoping by developing a theory of change. This will include conducting a minimum of two workshops with key programme and evaluation stakeholders.

    - Menu of options: following the theory of change development, the supplier should produce a ‘menu’ of evaluation options from which the MoD will select a preferred option for further scoping. The menu should focus on:

      - The two key thematic strands of the evaluation (energy use and wellbeing/retention)

      - The feasibility of different evaluation approaches and methodologies with the MoD’s existing data collection

      - What could be achieved with additional data collection (including indicative costings, scale, frequency, etc.)

      - The most appropriate time to evaluate the programme given the planned pace of construction delivery and outcomes of interest.

    - Feasibility report: this should explore in detail the feasibility of delivering the MoD’s preferred option from the menu outlined above. The supplier will be expected to scope out data sources, propose suitable metrics, develop associated survey instruments, and explore the practicality of incorporating randomisation within the evaluation design.

    - To deliver these outputs, the supplier will be expected to meet with DIO and Army colleagues involved in the programme, as well as prime construction contractors (e.g. REDS10 and Algeco), technical service providers and any other suppliers.

    - For guidance, when considering the feasibility of potential evaluation approaches two worthwhile areas to consider include:

      - Practicality: is the evaluation practical considering the time and resources available, and what are the constraints

      - Integration: the amount of change needed to integrate the evaluation into any existing processes or infrastructures

    - Reports on pilot findings: these should summarise results, outcomes, and learnings from piloting activities, with recommendations for future activities.

  - Outcomes

  - By delivering the SLA programme evaluation scoping study, the supplier should provide the MoD with:

    - An outline plan for the evaluation of the programme and outcomes to be achieved (energy/wellbeing)

    - An understanding of the scope of resource needed to deliver the evaluation(s)

    - The ability to time the evaluation activity in a way that maximises learning from ongoing programme delivery, whilst capturing the outcomes and impacts of the programme’s major delivery phases.

- key milestones and Deliverables

  - An indicative timetable of milestones and deliverables is shown below. Bidders should demonstrate how they will ensure that deadlines are met including time for editing and sign-off of the research design and final reports, and that they have appropriate resources to deliver this project.

  - The following Contract milestones/deliverables shall apply:

| ### Milestone/Deliverable | ### Description | ### Timeframe or Delivery Date |
| --- | --- | --- |
| ### 1 | ### Contract start-up meeting | ### Within first week of award |
| ### 2 | ### Project plan produced ### MoD Scientific Advisory Committee (SAC) application submitted | ### Within 3 weeks of Contract Award |
| ### 3 | ### Theory of change | ### Within 5 weeks of Contract Award |
| ### 4 | ### MODREC application submitted | ### Within 7 weeks of Contract Award |
| ### 5 | ### Start data collection | ### Within 8 weeks of Contract award |
| ### 6 | ### Menu of options | ### Within 12 weeks of Contract Award |
| ### 7 | ### Feasibility report (scoped version of MoD preferred options) | ### Within 16 weeks of Contract Award |
| ### 8 | ### Pilot findings | ### March 2025 |

- MANAGEMENT INFORMATION/reporting

  - Key contacts will be provided by the Buyer and the primary partner, MoD.

  - The Supplier should notify the Buyer immediately of any delivery issues or risks.

  - The Buyer, Supplier and primary partner will require a good working relationship to be developed throughout the project. This will involve regular contact between the Supplier and both the Buyer and primary partner via email correspondence and contract management meetings. Further details surrounding working arrangements will be discussed and agreed on contract award. The primary partner will provide the Supplier with a regular day-to-day contact.

- volumes

  - N/A

- continuous improvement

  - The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

  - The Supplier should present new ways of working to the Buyer during monthly Contract review meetings.

  - Changes to the way in which the Services are to be delivered must be brought to the Buyer’s attention and agreed prior to any changes being implemented.

- Sustainability / SOCIAL VALUE

  - The Supplier will be expected to demonstrate how they will tackle economic inequality over and above the requirements of the Contract.

  - The Supplier will also be expected to demonstrate how they will support environmental protection and improvement over and above the requirements of the Contract.

- quality

  - All project outputs should be quality assured before being submitted to the ETF and/or MoD. The supplier should refer to the guidance and standards set out in the Magenta Book when conducting the study.

  - Any implications that stem from the feasibility study should be practical to implement and consider the change needed to integrate the intervention into existing processes.

- PRICE

  - The total Budget for the project is £150,000.

  - Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

- STAFF AND CUSTOMER SERVICE

  - The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

  - The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

  - The Supplier shall ensure that staff understand the Buyer’s vision and objectives and will provide excellent customer service to the Buyer throughout the duration of the Contract.

- service levels and performance

  - The Buyer will measure the quality of the Supplier’s delivery by monitoring progress against the following KPIs:

| ## KPI/SLA | ## Service Area | ## KPI/SLA description | ## Target |
| --- | --- | --- | --- |
| ## 1 | - Delivery timescales | - The Supplier shall adhere to the timescales/project plans unless otherwise agreed by the ETF/MoD. | - 98% |
| ## 2 | - Supplier Attendance | - Supplier attendance at key meetings (The Supplier’s project manager will be expected to attend all project meetings, informing the Buyer and delegating responsibility where this is not possible) | - 98% |
| ## 3 | - Supplier Responsiveness | - Supplier responds in the same working day to any requests from the ETF/MoD submitted by 11am and the next working day to requests submitted after 11am | - 98% |
| ## 4 | - Supplier Responsiveness | - The supplier provides the ETF/MoD with at least five working days for reviewing drafts and providing comments | - 98% |

  - If poor Supplier performance occurs the Buyer reserves the right to seek early termination of the Contract.

- Security and CONFIDENTIALITY requirements

  - Staff working on this project must receive, or have existing, Baseline Personnel Security Standard (BPSS) clearance REDACTED TEXT under FOIA Section 43 Commercial Interests

  - It is also expected that two staff working on the project will require Security Check (SC) clearance. The Buyer will sponsor this if SC is not already held, but the Supplier would be expected to fund the process.

  - Contractors will be required to comply with relevant GDPR protocols for securely accessing MoD documents for review. Data collected during the project should not contain any personal identifying information.

- payment AND INVOICING

  - Payment milestones will be agreed with the Supplier based on the schedule of work proposed. The Supplier shall issue invoices once deliverables have been signed off by the project lead.

  - The Customer shall pay the Supplier within thirty (30) Working Days of receipt of a Valid Invoice, submitted in accordance with this section (16).

  - Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

  - Invoices should be submitted to: REDACTED TEXT under FOIA Section 43 Commercial Interests. An electronic copy of the invoice will be sent to the Contract Manager, which will be agreed prior to Contract Signature. No invoice will be accepted without a valid Purchase Order reference.

- CONTRACT MANAGEMENT

  - An initial meeting between the Buyer and Supplier will take place when the contract commences. This will either be face-to-face at the Buyer's office in London or via video call.

  - The Supplier must keep in regular contact through weekly video calls, and via email and/or telephone correspondence. The Buyer will provide contact details for MoD and DIO stakeholders and make initial introductions. The supplier will be expected to arrange subsequent meetings with these stakeholders where necessary.

  - Attendance at Contract Review meetings shall be at the Supplier’s own expense.

- Location

  - REDACTED TEXT under FOIA Section 43 Commercial Interests

  - REDACTED TEXT under FOIA Section 43 Commercial Interests

- Ethics

  - The research will be expected to meet the requirements of the MOD Research Ethics Committee (MODREC) guidelines and the Government Social Research (GSR) Professional Guidance: Ethical Assurance for Social Research in Government or equivalent.

  - The research design, produced by the Supplier, will need to be reviewed by a MoD Scientific Advisory Committee (SAC). The MoD will manage the submission and engagement with the SAC, but this will require supplier input. The process is expected to take 3 weeks. The Supplier will need to have produced final versions of surveys, etc. for the SAC review.

  - We also anticipate a MODREC review being required as this work is considered ‘Research’ based on the guidance in JSP 536 Part 2: Guidance (see Annex 1B). This review would follow the SAC review. The MoD will manage the submission and engagement with the SAC, but this will require supplier input.

  - The Supplier should state any ethical considerations and how these will be mitigated in their bid. The successful Supplier must obtain informed consent from all participants and clearly explain how the information they provide will be stored, reported, protected, shared and deleted.

- Data Security

  - The Supplier will be required to process personal data on their own IT systems. The MOD will be the Data Controller, the Supplier will be the Data Processor.

  - The Supplier will be required to assist the MOD in completing a Data Protection Impact Assessment before the start of the research.

  - Offshoring is considered to occur when any part of the service delivery relating to data is conducted outside the UK. The MOD will only allow offshoring of personal information within the European Economic Area. The Supplier must state the country in which any offshoring is likely to occur during the project.