# PAYMENT PLAN

SCHEDULE OF REQUIREMENT LINE ITEMS 1 - 8

| Payment No. | Title or description | Deliverables (including Statement of Work reference) | Delivery Due Date | Acceptance Criteria (upon which payment shall be made) | Total £ (Ex VAT) |
| --- | --- | --- | --- | --- | --- |
| 1 | Procurement of initial long-lead material: I-4S supplier payments on receipt of order, as per material supplier quotations, to ensure production schedule is met. | Invoices from key suppliers evidencing orders placed. Key suppliers: REDACTED Linked to SOW items 1.1a, 1.1b, 1.1e and 1.1f | REDACTED | Receipt of all invoices from key suppliers will be provided to the Authority | REDACTED |
| 2 | ILS Support Package | - Project management plan - Programme Plan - Risk Management Plan - CUBITO and NABBER Preliminary work - Progress Report Linked to SOW items 9.1a, 9.2a, 7.1a. | REDACTED | Written acceptance of all documents by the CBRN project manager following review by the Authority SMEs | REDACTED |
| 3 | CUBITO Critical Design Review (CDR) CUBITO Core Shelters First Article Factory Test (FAFT) report | - Final design pack. - FAFT report. Linked to SOW items 1.1e | REDACTED | Acceptance of the final design pack at the CDR in France. The Authority’s PM shall confirm acceptance of the CDR or shall reject the CDR pack at the meeting. CBRN Project Manager’s written acceptance of the FAFT report. | REDACTED |
| 4 | Successful CUBITO FAT REDACTED CUBITO systems ready for dispatch | - Completion of the CUBTIO FAT - REDACTED CUBITO systems and REDACTED. Linked to SOW items 6.1a and 1.1e | REDACTED | Written confirmation from the Authority’s PM of successful completion of the CUBITO FAT. Physical demonstration of the CUBITO system witnessed at the France site and accepted by the CBRN PM, or their delegated representative in writing. | REDACTED |
| 5 | NABITO supporting documentation | - Safety & Environmental Info Pack - Training Plan - Train the Trainer - Development - Training Aids - Packing - Handling - Storage - Transportation - Progress Meeting - Progress Reports - Obsolescence Management Linked to SOW items 2.1a, 3.1a,3.2a, 3.2b, 3.4a, 5.1a, 5.3a, 5.4a, 5.5a, 9.2a, 9.3a, 8.1b, 8.2a. | REDACTED | Delivery of and acceptance by the CBRN Project Manager of: Safety and Environment Info Pack, Jointly endorsed Training Plan REDACTED of bound hard copy T3/T3M courseware REDACTED of soft copy T3/T3M courseware Training aids PHST recommendation report including but not limited to: Handling requirements storage and shelf life transport requirements OM Plan Disposal Plan | REDACTED |
| 6 | NABBER CDR NABBER Core Shelters FAFT report | - Completion of the NABBER CDR. - NABBER FAFT report. Linked to 6.1ab | REDACTED | Acceptance of the final design pack at the CDR in France. The Authority’s PM shall confirm acceptance of the CDR or shall reject the CDR pack at the meeting. CBRN Project Manager’s written acceptance of the FAFT report. | REDACTED |
| Anchor milestone 7 (read also condition 8.1.7) | REDACTED ready for dispatch REDACTED CUBITO module ready for dispatch Initial spares pack | - REDACTED NABBER REDACTED - Test spares Pack Linked to SOW items 1.1b, and 6.1ab | REDACTED | Physical demonstration and acceptance of the NABBER system, wing of the R3 and Test Spares Pack witnessed by the CBRN PM, or their delegated representative. | REDACTED (resulting in late deliveries to the amount of REDACTED linked to contractor performance see condition 8.7.1) |
| 8 | Training delivery and NABBER R2E FAT | - Delivery of NABBER and CUBITO D SAT compliant training - Completion of the NABBER R2E FAT Linked to SOW 3.3a, 1.1b, and 6.1a | REDACTED | Acceptance of training following agreement from DCBRNC witnessing training Written confirmation by the CBRN PM of successful completion of the NABBER FAT. | REDACTED |
| 9 | REDACTED CUBITO Systems complete and ready for dispatch. Procurement of long-lead material: I-4S supplier payments on receipt of order, as per material supplier quotations, to ensure production schedule is met. | - Delivery of REDACTED CUBITO systems Invoices from key suppliers evidencing orders placed. Key suppliers: - REDACTED Linked to SOW 1.1a | REDACTED | Physical demonstration of the CUBITO system witnessed and accepted by the CBRN PM, or their delegated representative. Receipt of all invoices from key suppliers provided to the Authority’s commercial representatives | REDACTED |
| 10 | REDACTED CUBITO Systems complete and ready for dispatch. | - Delivery of REDACTED men CUBITO systems Linked to SOW 1.1a | REDACTED | Physical demonstration of the CUBITO system witnessed and accepted by the CBRN PM, or their delegated representative with inclusion of a parts list and certificate of conformity | REDACTED |
| 11 | REDACTED CUBITO Systems complete and ready for dispatch. | - Delivery of REDACTED men CUBITO systems Linked to SOW 1.1a | REDACTED | Physical demonstration of the CUBITO system witnessed and accepted by the CBRN PM, or their delegated representative with inclusion of a parts list and certificate of conformity. | REDACTED |
| 12 | NABBER REDACTED and Initial Spares Pack Progress reports year 1 | - Delivery of REDACTED NABBER REDACTED - CE marking - NABBER Initial Spares Pack - NABBER Initial Consumables Pack - Progress reports for year 1 in accordance with 9.2 of the SOW Linked to SoW 1.1b, 1.1d, 6.3a, 6.4a and 9.2 | REDACTED | Physical demonstration of the NABBER R2E system and R3 expansion kit, NABITO Initial Spares Pack and NABITO Initial Consumables Pack witnessed and accepted by the CBRN PM, or their delegated representative with inclusion of a parts list and certificate of conformity Written acceptance of all reports by the CBRN project manager | REDACTED |
| 13 | Progress Reports Year 2 | - Progress reports for year 2 in accordance with 9.2 of the SOW | REDACTED | Written acceptance of all reports by the CBRN project manager | REDACTED |
| 13 | Progress Reports Year 3 | - Progress reports for year 3 in accordance with 9.2 of the SOW | REDACTED | Written acceptance of all reports by the CBRN project manager | REDACTED |
| 13 | Progress Reports Year 4 | - Progress reports for year 4 in accordance with 9.2 of the SOW | REDACTED | Written acceptance of all reports by the CBRN project manager | REDACTED |
| 13 | Progress Reports Year 5 | - Progress reports for year 5 in accordance with 9.2 of the SOW | REDACTED | Written acceptance of all reports by the CBRN project manager | REDACTED |
| Total |  |  |  |  | REDACTED |