Mike Thompson

SPECIFICATION

NHS blood and transplant

NHSBT1190/S/SP COMMUNITY ORGANISING IN SOUTH LONDON

Summary:

Pilot of community organising in South London to promote blood donation in black African and black Caribbean communities.

Through community organising, work with NHSBT to develop and empower 30 people in south London, to form a voluntary collective of advocates who can promote blood donation and recruit at least 1,700 new donors from black African and black Caribbean communities.

Relevant data and research that will help to understand the objectives.

NHS Blood and Transplant (NHSBT) is an executive non-departmental public body of the Department of Health and Social Care.

We are responsible for the collection, manufacturing and issuing of blood products to the NHS in England. Blood is donated by altruistic donors at one of the 23,000 donation sessions held in England each year.

Each donation has the potential to save or improve up to three lives and whilst NHSBT has never suffered a shortage of blood the organisation needs to change its donor base to better reflect the needs of NHS patients.

NHSBT needs to recruit a significant number of new blood donors from black African and black Caribbean communities, due to an increase in demand from the NHS for specific types of blood to treat sickle cell patients.

Sickle cell disease is the most common inherited genetic disorder in the UK. The disease is usually found in people of African heritage (in 90 per cent of British patients), although it’s also found in those from the Caribbean, Middle East and Mediterranean regions. Sickle cell patients needing regular blood transfusions benefit from more precisely matched blood.

To get the best treatment, patients need closely matched blood, which is most likely to come from someone with the same ethnicity. Having the right mix of donors and blood types is essential to ensure we meet the needs of all patients who need lifesaving treatment.

40,000 more black African and black Caribbean donors are needed to meet growing demand for better matched blood and a special subtype of blood more common in black people. Currently, only 1% of people who give blood in England are black.

Research conducted in 2015 by ESRO Limited revealed some of the barriers and motivations of people from BAME communities towards blood donation. This research recommended engagement at a local level, as communities react well to people that they trust and who understand them. A copy of this research has been attached below for further reading:

Technical Specification

- Provide 1 FTE community organiser(s) to work with NHSBT staff to identify 30 advocates (18 in year 1 and 12 in year 2) of blood donation in South London black communities.

- Provide training, using an established and successful syllabus in community organising for the 30 identified advocates and 2 NHBT staff to develop as leaders with practical skills such as relationship building and advocacy. Please attach an outline/syllabus for the proposed training.

- Provide ongoing support and development of advocates so that they can mobilise volunteers and recruit at least 600 new black donors in year 1, increasing to 1,100 new black donors in year 2 if the contract is extended.

Reasons why service requirement may not be suitable to all potential bidders.

Organisations must have a track record in community organising. This pilot is to test the theory that community empowerment and development that focuses on one-to-one relationships and community capacity building will address health inequalities and help to recruit blood donors in black communities.

Budget range:

Although there will be no guarantee of any spend, it can be expected not to exceed £110k over the two years.

£50-55K for one year, with possible extension of another year subject to meeting KPIs.

This is merely an indicative figure – a purchase order for any expenditure would have to be approved by NHSBT

Timescales – anticipated contract award date/milestones/completed service delivery.

Oct 2018 			Contract awarded/commenced

Oct - Jan 2019		1:1 meetings to identify 18 advocates in South London

Feb 2019	Community Organiser training and co-production of materials

Mar 2019 - Sep 2019 	Ongoing 1:1s, training, coproduction and recruitment activities

Oct 2019			Possible one-year extension

Oct 2019 - Sep 2020	Growing the movement by 12 more advocates in

surrounding areas

Implementation:

Requirements. Does the requirement have to be fulfilled in a specific part of the UK?

South London. This area has been selected for the pilot as we are increasing capacity for our blood donation sessions in this area.

Is there a deadline:

Work on the project must commence in October 2018.

Management and Staffing – how NHSBT will want to work with the successful bidder – expectations of Account Team including staffing levels, expertise, regular meetings etc.

- Named 1 FTE trained community organiser(s)

- Regular contact - weekly calls and at least monthly face-to-face meetings.

- Monthly reporting of activities against agreed KPIs

- Quarterly oversight by Marketing and Communications Resources and Delivery Board

- Production of a final evaluation report and presentation

Key delivery milestones. What KPI’s will be set to measure performance.

- 100% attendance of meetings

- Completion of a yearly evaluation report and presentation

- Number of face to face meetings with potential advocates

- Number of advocates identified

- Number of advocates trained

- Number of blood donors registered from black communities

- Number of blood donors registered from ethnicities other than black

- Number of new donor attends from black communities

| KPIs - Year 1 | Oct 18 | Nov 18 | Dec 18 | Jan 19 | Feb 19 | Mar 19 | Apr 19 | May 19 | Jun 19 | Jul 19 | Aug 19 | Sep 19 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of face-to-face meetings with potential advocates | 15 | 20 | 15 | 15 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| Number of advocates identified | 2 | 4 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Number of advocates trained in community organising | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |
| Number of blood donors registered from black communities1 | 0 | 0 | 0 | 0 | 100 | 130 | 170 | 200 | 200 | 200 | 200 | 200 |
| Number of blood donors registered from other ethnicities1 | 0 | 0 | 0 | 0 | 25 | 30 | 45 | 50 | 50 | 50 | 50 | 50 |
| Number of new donor attends from black communities2 | 0 | 0 | 0 | 0 | 0 | 50 | 65 | 85 | 100 | 100 | 100 | 100 |

| KPIs - Year 2 | Oct 19 | Nov 19 | Dec 19 | Jan 20 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of face-to-face meetings with potential advocates | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| Number of new advocates identified | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Number of advocates trained in community organising | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 |
| Number of blood donors registered from black communities1 | 200 | 100 | 100 | 200 | 200 | 300 | 300 | 300 | 300 | 300 | 300 | 300 |
| Number of blood donors registered from other ethnicities1 | 50 | 25 | 25 | 50 | 50 | 75 | 75 | 75 | 75 | 75 | 75 | 75 |
| Number of new donor attends2 | 100 | 100 | 50 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

Notes:

- A registration is the successful completion of NHSBT’s paper or online registration form

- A new donor attend is when a registered blood donor successfully makes their first blood donation

This pilot is iterative and adaptive: continuous reflection and evaluation will help to create flexibility for services to be adapted to the interests, needs and assets of local people. This will be evaluated at monthly face-to-face meetings and KPIs may be adjusted accordingly.

Timescales for tender (stages/award).

June 18		Prepare specification

July 18		Advertise opportunity on Contracts Finder

Receipt of tenders

Aug/Sept 18		Evaluate tenders

Approval to award from Director for Marketing and Communications

September 18	Contracts prepared and signed

October 18		Work starts

Contract Term – including any extension options:

1st October 2018 until 30th September 2019 with the option for a further 1 x 1 year extension period 1 year - subject to meeting KPIs

General:

Any sub – contracting requirements.

No sub-contracting.

Any security requirements

Any data collected from individuals should be done so in accordance with the Data Protection Act (2018).