## Sheet1
CLARIFICATION LOG
Tender: | Exhibition Design Tender - Mineral Gallery - Royal Institution of Cornwall
Tender Reference: | 09/2023_(02)
Published Date: | 16th September 2023
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | Could you please confirm if the tender for RIC Museum Mineral gallery requires architectural services? | We do not envisage that this work will require architectural services. | 2023-09-14
2 | We note that the contract is a design build one with the scope of work running up to RIBA stage 6 (completion and handover). Would it therefore be acceptable for the team to be led by the fit out company with the design team employed as sub-consultants? | Yes. The RIC would only contract with the fit out company. | 2023-09-14
3 | Given that the tender is for a design build “turn key” solution how much detail of the design of the gallery are you expecting in the tender return? In order to price the fit out stage some level of detail will be needed and some flexibility developing a viable cost plan, within the budget envelope, will be needed during the contract. | We’re not expecting vast detail/ finished design as appreciate that for you to produce the detail you need input from our interpretation design and brand work as well as public consultation. During the evaluation, we will be looking at other schemes you have been involved with. There is a budget limit for the fitout. It will be your responsibility to ensure that your design comes within the proposed budget so will be looking at the team to project manage this accordingly. | 2023-09-14
4 | Is it possible for the RIC to provide more photographs of the gallery, collections and showcases, also plans of the building and/or a virtual tour to help us better understand the gallery and its relationship to the site? | Please find attached an extract of the Masterplan which details the current layout and relationship with the rest of the site. Additional photos also supplied of the current gallery. | 2023-09-14
5 | Could you kindly share CAD drawings and photos of the gallery please? | Additional photos supplied with this clarification. No CAD drawings are available. | 2023-09-14
6 | Please could you also advise whether there have been any discussions about what the Client would like to keep from the existing gallery, and what goes? | The client would like to retain as many of the minerals currently on display as possible. The mining material can be refreshed with other artefacts. They would like to retain the Edwardian dark wood, central cabinets, but replace the lightwood cabinets. | 2023-09-14
7 | Would you have a list of objects / artefacts available that must form part of the redeveloped gallery please? | A list of minerals is supplied with this clarification. We do not expect object mounts to be made for many/any of these. | 2023-09-14
8 | Please could you advise with reference to AV and interactive content, is the Client responsible for content / film production or would this fall within the responsibility and fee of the appointed design team please? If the latter, please could you advise whether any existing footage / content is available in the Museum’s collection that could be made available to the exhibition designer? | This would fall into the responsibility and budget of the project. There is no existing content. However, there are partners willing to support content development. | 2023-09-14
9 | Please could you confirm that building, structural and civil works would fall within the responsibility of the Client? I.e. the Exhibition Designer will be handed the gallery with finished floors, finished walls, HVAC, heating and insulation, emergency lighting, other non-show lighting (house, back of house, external, etc), fire alarm points and other safety requirements in place, internet access, telephone system in place, services (water, electricity, other power, cableways, trunking, conduit, AV cabling), electrical works to include distribution boards, contactors and power points, acoustic treatments completed etc? | There is no additional building works as part of this project. The gallery has existing LED track lighting, emergency lighting, heating and fire alarm points, wifi and electricity. This contract will need to include any changes to the existing parquet floor (polishing), painting and decorating, trunking etc. | 2023-09-14
10 | Please could you confirm whether internal walls / partitions and any windows block off/curtains (if applicable) would fall within the budget of the exhibition designer? | Not applicable | 2023-09-14
11 | Please could you share brand guidelines, if available? | These are currently being updated and will be available to the successful tenderer. | 2023-09-14
12 | The tender is for design and build. Can you confirm that you are only interested in design and build or would you consider a design and manage approach, where the designer is contracted and the fabricator appointed following a tender? | We are happy to consider alternative proposals so long as the project meets the deadline and budget constraints. In this scenario, The RIC will contract only with the designer as lead. For the purposes of evaluation we would however seek costs for the total works | 2023-09-14
13 | The brief doesn’t mention an interpretation plan. Can I assume that you do not require a plan and that all text and other content will be supplied by yourselves? | An interpretation plan is in development and will be available at a later stage. | 2023-09-14
14 | You plan to open the gallery by June 2024. This is a very tight programme for a project of this size. Is the date correct? If so are you able to consider extending the programme? | We can consider extending the deadline slightly . We are committed to our funding agteement which states open for Summer 2024. | 2023-09-14
15 | The brief refers to the re-use of the existing mineral gallery showcases and we would like to know what the status of these cases is, i.e. would it be acceptable to modify them to make them more accessible and/or improve conservation, safety and display standards? | We would like to retain the Edwardian dark wood, central cabinets, but replace the lightwood cabinets. The central cabinets are to be modified to make them more accessible and are to meet safety and display standards. This also meets with our environmental objectives to reuse and recycle. | 2023-09-16
16 | Can you clarify whether a speculative creative response to the Design Brief is required at tender stage? | We are not looking for a draft design at tender stage. We will be looking for a methodology and examples of how you would approach the design element. | 2023-09-16
17 | We are asked to provide a breakdown of costs for Manufacturing and Construction. As the scheme will have not yet been designed, can we assume that the distribution of costs between manufacturing elements can be varied within the agreed overall cost as the design develops? | There is a budget breakdown for design and build within the tender pack. Returns should identify costs within these 2 budget allocations. | 2023-09-16
18 | Tender Vol 1 identifies a maximum budget of £400,000 including VAT. For the avoidance of doubt can you confirm then that the maximum available budget is therefore £333,333.33 + VAT @ 20%? | Yes. Confirm that this is the case. | 2023-09-16
19 | Our usual approach is to design and deliver a project within the defined budget to provide best value for the client. Here we are being asked to propose a cost against which we would design and deliver the project. Clearly there is a direct relationship between the available funds and what can be delivered, so any tender price will have to be based on assumptions. Is it the RIC's intention to spend all of the available budget on this redevelopment or to look for a substantial reduction on that figure? | We have detailed the maximum budget available for the project. If you are able to design and deliver the project to the scale and quality detailed for less, then this should be detailed within your cost return. | 2023-09-16
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie@jackiegeorge.co.uk