STATEMENT OF REQUIREMENT (SOR)

For

Integrated Soldier System (ISS)

Pulse 1 – Combat Protective Equipment (CPE)

(Project PETREL)

Table of Contents

1.	Project PETREL Overview	3

1.1.	Requirement Overview	3

2.	System Delivery	3

2.1.	Tranche 1	3

2.2.	Tranche 2	3

2.3.	Tranche 1 & 2 Additional Buys	4

3.	Options	4

4.	Deliverables	5

5.	PETREL System Performance	14

5.1.	System Performance Overview	14

5.2.	PETREL System Performance Table	14

6.	Project Management	23

6.1.	Contract Management	23

6.2.	Project Management Documents	23

6.3.	Project Management Plan	23

6.4.	Project Schedule	23

6.5.	Project Progress Reports	24

6.6.	Risk Management	24

6.7.	Project Review Meetings	25

6.8.	Project Management Support	25

7.	Safety and Environmental	26

7.1.	Safety and Environmental Management Plan	26

8.	Integrated Logistic Support	27

8.1.	Introduction	27

8.2.	Integrated Support Plan (ISP)	27

8.3.	Damage Modes Effects Analysis (DMEA) Report/Failure Modes Effects & Criticality Analysis (FMECA) Report	28

8.4.	Level of Repair Analysis (LORA) Report	28

8.5.	Reliability & Maintainability (R&M) Report	28

8.6.	Maintenance Report	28

8.7.	Obsolescence Management Plan	29

8.8.	Equipment Breakdown Structure	29

8.9.	Logistic Demonstration Plan	29

8.10.	Technical Documentation	30

8.11.	Codification Plan	31

8.12.	Packaging, Handling, Storage & Transport (PHS&T)	31

8.13.	Configuration Management Plan	32

8.14.	Training Information Package	33

8.15.	Disposal Plan	33

9.	Quality Management	34

9.1.	Quality Management System	34

9.2.	Quality Management Plan	34

10.	Purchase of Additional Items	35

11.	Post Design Services	35

12.	Acceptance	36

12.1.	Deliverable Acceptance	36

12.2.	System Acceptance	36

Annex A - INTEGRATION LIST	37

# Project PETREL Overview

## Requirement Overview

    - The Authority requires an integrated Combat Protective Equipment (CPE) clothing system which enables the User to conduct Dismounted Close Combat (DCC), the Authority has named this capability PETREL. The PETREL capability is required to enhance the protection, maximise agility and reduce the physical burden on the DCC operator from the current Protective Clothing System (PCS).

    - The PETREL system is required to integrate with the VIRTUS system, enhancing the capability of the DCC operator and enabling them to operate in a wide range of climatic conditions. The PETREL system is required to provide ballistic protection to protect the operator from threats specified in the System Performance Table Section 5 within this document. The PETREL system is to consist of a minimum of 2 complete sets to enable the operator to launder the system without losing capability.

    - The PETREL system is defined as not less than 2 of each of the following:

      - Combat trousers, tier 1 pelvic protection and the long sleeve shirt.

| PETREL Item | Quantity |
| --- | --- |
| Combat Trouser | [Tender to complete] |
| Tier 1 Pelvic Protection | [Tender to complete] |
| Long Sleeve Shirt | [Tender to complete] |
| [Tender to add extra lines for additional Scalable Protective Components] | [Tender to complete] |

Table 1: PETREL System Quantities

# System Delivery

## Tranche 1

    - The Authority requires an initial delivery (Tranche 1) of 1000 PETREL systems 80 working days post Interim Design Acceptance (IDA). These systems will be issued and undergo exercise and/or training use in a range of climatic conditions by the DCC operators to ensure suitability for intended use, for a period of up to 6 months.

## Final Design Acceptance (FDA)

    - The Authority will assess feedback and identify any system modifications if required, these will be tasked to the contractor as Post Design Services (PDS), as described in Section 11 of this document. FDA will be deemed complete once all (if any) PDS tasks have been completed and accepted by the Authority.

## Tranche 2

    - The Authority requires a second delivery (Tranche 2) of 20,000 PETREL systems 100 days post completion of Tranche 1 FDA. Tranche 2 is to be delivered in accordance with Section 5 of this document.

    - All system deliveries are to be made by the contractor, no later than the agreed delivery date, to MoD Storage Warehouses Bicester/Donnington, in accordance with sections 8.11 Codification Plan and 8.12 Packaging, Handling, Storage & Transport (PHS&T) of this document.

## Tranche 1 & 2 Additional Buys

    - The Contractor shall enable the Authority to support the PETREL Tranche 1 & 2 procurements through replenishment. The contractor shall provide an additional buy of 20% of each item within the system, with each Tranche delivery.

    - Additional buys are to be available in accordance with Schedule 03 – Cost Breakdown Sheet.

    - All items are to be delivered in accordance with the System Performance Table 2 and sections 8.11 and 8.12 of this document.

    - Delivery lead times are detailed in Schedule 03 – Cost Breakdown Sheet and are broken down by banded quantity order sizes.

# Options

    - The contract duration will be for 5 years and provide 5 exercisable options of 1 year duration.

# Deliverables

| Deliverable | Delivery Date | Update interval | Acceptance Criteria | Authority Review Period | Where | References |
| --- | --- | --- | --- | --- | --- | --- |
| Tranche 1 – 1000 PETREL Systems | 80 working days post IDA | N/A | The PETREL systems shall be delivered to the satisfaction of the Authority. The Authority reserves the right to reject systems that do not meet the agreed final design. Any rework required shall be conducted by the Contractor, a timeframe for the work shall be agreed by the Authority within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | Bicester/Donnington Warehouse | Section 5 and 8 |
| Tranche 1 – Additional Buy | 80 working days post IDA | N/A | The PETREL systems shall be delivered to the satisfaction of the Authority. The Authority reserves the right to reject systems that do not meet the agreed final design. Any rework required shall be conducted by the Contractor, a timeframe for the work shall be agreed by the Authority within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | Bicester/Donnington Warehouse | Section 5, 8 and 2 |
| Tranche 2 – 20,000 PETREL Systems | 100 working days post Tranche 1 FDA | N/A | The PETREL systems shall be delivered to the satisfaction of the Authority. The Authority reserves the right to reject systems that do not meet the agreed final design. Any rework required shall be conducted by the Contractor, a timeframe for the work shall be agreed by the Authority within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | Bicester/Donnington Warehouse | Section 5 and 8 |
| Tranche 2 – Additional Buy | 100 working days post Tranche 1 FDA | N/A | The PETREL systems shall be delivered to the satisfaction of the Authority. The Authority reserves the right to reject systems that do not meet the agreed final design. Any rework required shall be conducted by the Contractor, a timeframe for the work shall be agreed by the Authority within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | Bicester/Donnington Warehouse | Section 5, 8 and 2 |
| Project Management Plan (PMP) | 10 working days post Contract Award | As required from Contract Award | The PMP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 6.3 |
| Project Schedule | 10 working days post Contract Award | Fortnightly | The Project Schedule shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 5 working days (from the date of notification by the authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 6.4 |
| Project Progress Reports | 10 working days post Contract Award | Fortnightly | The Project Progress reports shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 5 working days (from the date of notification by the authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 6.5 |
| Risk Management Plan | 10 working days post Contract Award | As required from Contract Award | The Risk Management Plan shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 6.6 |
| Risk and Issues Register | 10 working days post Contract Award | Fortnightly | The Risk and Issues Register shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 5 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 6.6 |
| Project Review Meetings | 10 working days post Contract Award | In accordance with Schedule 6 | Authority sign off/agree to meeting minutes and record of decisions made within them. Any rework required shall be conducted by the Contractor within 5 working days (from the date of notification by the authority that rework is required), at no additional cost. | 10 working days | DE&S Abbey Wood, Bristol, BS34 8JH | Section 6.7 |
| Safety & Environmental Management Plan (SEMP) | 10 working days post Contract Award | As required from Contract Award | The SEMP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 7.1 |
| Safety & Environmental Case Report (SECR) Part 2 | 30 working days post IDA | As required from Contract Award | The SECR Part 2 shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | PETREL Project Manager | Section 7.1 |
| Certificate of Conformity (CoC) | With each delivery of PETREL systems | As required from Contract Award | The CoC shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 7.1 |
| Material Safety Data Sheet (MSDS) | 30 working days post IDA | As required from Contract Award | The MSDS shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager | Section 7.1 |
| Damage Modes Effects Analysis (DMEA) | 30 working days post IDA | As required from Contract Award | The DMEA shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.3 |
| Failure Modes Effects & Criticality Analysis (FMECA) | 30 working days post IDA | As required from Contract Award | The FMECA shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.3 |
| Level of Repair Analysis (LORA) | 30 working days post IDA | As required from Contract Award | The LORA shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.4 |
| Reliability and Maintainability (R&M) Report | 30 working days post IDA | As required from Contract Award | The R&M report shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.5 |
| Maintenance Report | 30 working days post IDA | As required from Contract Award | The Maintenance report shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.6 |
| Obsolescence Management Plan (OMP) | 30 working days post IDA | As required from Contract Award | The OMP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.6 and 8.7 |
| Equipment Breakdown Structure (EBS) | 30 working days post IDA | As required from Contract Award | The EBS shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.8 |
| Logistic Demonstration Plan (LDP) | 30 working days post IDA | As required from Contract Award | The LDP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.9 |
| Logistic Demonstration (LD) | No later than 2 weeks prior to Tranche 1 Delivery | N/A | The LD shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject demonstration. Any remedial work required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | At Contractor’s Facility to PETREL ILS Manager | Logistic Demonstration Plan |
| Technical Documentation Plan (TDP) | 15 working days post IDA | As required from Contract Award | The TDP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this document. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.10 |
| Technical Documentation (TD) | 50 working days post IDA | As required from Contract Award | The TD shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this documentation. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.10 |
| Codification Plan (CP) | 20 working days post IDA |  | The CP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this documentation. Any rework required shall be conducted by the Contractor within 5 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.11 |
| Codification of the PETREL system | 50 working days post IDA | As required from Contract Award | Each PETREL system shall be codified to the satisfaction of the Authority. The Authority reserves the right to accept or reject any PETREL system based on its codification. Any rework required shall be conducted by the Contractor within 20 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.11 |
| Packaging, Handling, Storage & Transportation (PHS&T) Plan | 30 working days post IDA | As required from Contract Award | The PHS&T plan shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this documentation. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.12 |
| Configuration Management Plan (CMP) | 30 working days post IDA | As required from Contract Award | The CMP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this documentation. Any rework required shall be conducted by the Contractor within 5 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.13 |
| Training Information Package (TIP) | 70 working days post IDA | As required from Contract Award | The TIP shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this documentation. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.14 |
| Disposal Plan | 30 working days post IDA | As required from Contract Award | The Disposal plan shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this documentation. Any rework required shall be conducted by the Contractor within 5 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 10 working days | PETREL Project Manager, PETREL ILS Manager | Section 8.15 |
| Quality Management (QM) Plan | 30 working Days post IDA | As required from Contract Award | The QM plan shall be delivered to the satisfaction of the Authority. The Authority reserves the right to accept or reject this documentation. Any rework required shall be conducted by the Contractor within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | PETREL Project Manager, PETREL Quality Manager | Section 9.2 |
| Purchase of Additional Items | To be confirmed in each order | N/A | The PETREL systems shall be delivered to the satisfaction of the Authority. The Authority reserves the right to reject systems that do not meet the agreed final design. Any rework required shall be conducted by the Contractor, a timeframe for the work shall be agreed by the Authority within 10 working days (from the date of notification by the Authority that rework is required), at no additional cost. | 20 working days | Bicester/Donnington Warehouse | Section 5 and 8 |

# PETREL System Performance

## System Performance Overview

    - The PETREL System Performance Table details the specific performance criteria which the PETREL solution shall conform to, this has been created from the PETREL System Requirements Document (SRD) and is based on a combination of claimed performance levels by the Contractor during the Tendering stage and achieved performance levels verified by the Authority during the Assessment stage of the project.

## PETREL System Performance Table

Table 2: PETREL System Performance Table

| ID | System Requirement | System Performance | Remarks |
| --- | --- | --- | --- |
| SP-1 | The PETREL Clothing system shall provide protection from personal injury caused by fragments. | With an areal density of no more than [Tenderer to complete] kg.m-2 the system shall provide protection to [Tenderer to complete] against an untumbled chisel nosed [Tenderer to complete] g FSP (F1) with a V50 of no less than [Tenderer to complete] m/s iaw AEP 2920 Ed A V3 (see ref [M]). |  |
| SP-80 | The PETREL Clothing System shall provide scalable protection from personal injury caused by high velocity fragments. | With an areal density of no more than [Tenderer to complete] kg.m-2 the system shall provide protection to [Tenderer to complete] against an untumbled chisel nosed [Tenderer to complete] g FSP (F1) with a V50 of no less than [Tenderer to complete] m/s iaw AEP 2920 Ed A V3 (see ref [M]). |  |
| SP-3 | The PETREL Clothing system shall not melt or drip when exposed to the effects of flame and burning liquids. | The system shall not melt or drip when exposed to the effects of flame and burning liquids, iaw: BS EN ISO 11612:2015 Para 6.3 Limited flame spread Procedure A1 and A2 [Tenderer to complete]. |  |
| SP-4 | The PETREL Clothing system is to protect the knees from the effects of an impact with hard ground, rocks, or sharp objects. | [Tenderer to complete] Through interoperability with the VIRTUS knee pads. AND/OR Integrated removable protection to the knees to protect against: - Hard Ground - Rocks - Sharp, cutting objects (including broken glass and barbed wire). EN 14404:2004 Type 2 knee pad). Protection level: Constant rate of compression 100mm/min peak force - min 250N deflection – max 5mm BS EN 14404 level 2 performance: min force 250N internal face shall not deflect by more than 5mm. Force distribution: BS EN 14404 clause 6.6 mean force recorded less than 30N. Peak transmitted force: BS EN 14404 clause 6.7 under an impact energy of 5kJ mean of all peak transmitted force shall not exceed 3kN. Highest value of a single peak 4kN. Protection to be MTP or to blend with Beige, Olive or Medium Brown of the MTP camouflage |  |
| SP-66 | The PETREL Clothing system is to protect the elbows from the effects of an impact to the elbows. | [Tenderer to complete] 1. Protection to be MTP or to blend with Beige, Olive or Medium Brown of the MTP camouflage. 2. Dimensions of elbow protectors shall conform to the requirements of DD CEN/TS 15256:2005 clause 5.4.2. AND/OR Integrated removable protection to the elbows to protect against: - Hard Ground - Rocks - Sharp, cutting objects (including broken glass and barbed wire). EN 14404:2004 Type 2 knee pad). Protection level to be no more protective than the knee pad: Constant rate of compression 100mm/min peak force - min 250N deflection – max 5mm BS EN 14404 level 2 performance: min force 250N internal face shall not deflect by more than 5mm. Force distribution: BS EN 14404 clause 6.6 mean force recorded less than 30N. Peak transmitted force: BS EN 14404 clause 6.7 under an impact energy of 5kJ mean of all peak transmitted force shall not exceed 3kN. Highest value of a single peak 4kN. |  |
| SP-5 | The CPE Clothing system should present the lowest thermal burden possible. | [Authority to complete] Not significantly worse than the current PCS. OR No worse than the current PCS. |  |
| SP-73 | The PETREL Clothing system material shall protect the wearer against the effects of the sun: | For Knitted Mesh: BS EN 13758-1 UPF Min – 40 |  |
| SP-2 | The PETREL Clothing system shall ensure that all protection components remain correctly and securely positioned for the 1st - 99th percentile of Wearers. | Protection equipment remains in place without regular readjustment throughout representative battlefield test. |  |
| SP-6 | The PETREL Clothing System shall protect the wearer against visual detection across a range of terrain types. | Main Materials: 1. Multi Terrain Pattern (MTP) visual capability to meet Standard Pattern – [MAT0006B]. 2. The design of the image on the Disc 125 MTP/01 is correct for print on material width of 150cm as per the Standard Pattern. Pattern repeat size 75cm – 80cm. |  |
| SP-68 | The PETREL Clothing System shall enable the carriage 'on the person' and retrieval of the following military tools, in the following positions: | Military Tools: 1. The Emergency Care Bandage (ECB) & Combat Applique Tourniquet CAT on left arm. 2. Compass on right arm. 3. Standard folded military map on left leg. Dimensions: 27cm x 1.9cm x 13.5cm 4. Notebook, protractor, pencil and permanent pen on right leg. 5. Report and order-cards on right leg. - Knife / multi-tool. Positions: - Standing - Crouching - Prone position - Squatting - Kneeling |  |
| SP-7 | The PETREL Clothing system shall be compatible with systems listed on the External Integration List (Annex A to this document). | [Tenderer to complete] With all threshold and objective systems (see Annex A). The system must be compatible with equipment listed in field orders of dress (see remarks): On the Man Assault Order Patrol Order Marching Order |  |
| SP-8 | The PETREL Clothing system shall allow the wearer to undertake successfully the full range of military activities, including general tasks. | In accordance with British Military Doctrine, effectively employ and operate weapon systems and equipment in: External integration list Field orders of dress. |  |
| SP-9 | The PETREL Clothing system shall accommodate the anthropometric characteristics of the specified wearer population given in Def Stan 00-251. | The range of clothing fits [Tenderer to complete] % of the military population’s dimensions for each system component (excluding outsize). The system shall have an adjustable mechanism to ensure optimal fit to the wearer. |  |
| SP-70 | The PETREL Clothing System shall enable the wearer to urinate and defecate. | With the minimum necessary removal of clothing. Without removing boots or STV. Urination must be possible without lowering trousers. For females this can be assisted with the use of the in-service she-wee. |  |
| SP-10 | The PETREL Clothing system shall enable the wearer to undertake military parachute operations and training by day and night. | PETREL Clothing to be cleared for use by UK Airborne Forces for training and operations. System to be compatible with in service UK parachute equipment. |  |
| SP-11 | The PETREL Clothing system shall enable the wearer to perform kinematic actions when undertaking tactical manoeuvres and general military tasks. | [The Tenderer to complete] The System shall not reduce the wearer's ability to undertake the following actions over that delivered by current PCS: The ability to adopt or change between the following actions/positions: - Lying prone, Kneeling, sitting, squatting, and standing fire positions. - Traverse CBTF obstacles AND Deliver an improvement in the wearer’s ability to undertake the above kinematic actions over that achieved with the current PETREL clothing. |  |
| SP-12 | The PETREL Clothing system shall incorporate fastenings and adjustment mechanisms which are: | [The Tenderer to complete] - Intuitive and simple to use. - Quiet. - Operable with bare hands - Operable when wearing combat gloves. - Operable with cold hands. - Operable when wet. - Operable when operating in Chemical Biological Radiation and Nuclear (CBRN) Personal Protective Equipment (PPE). - Adjustable enough to allow the soldier to adjust the system due to changes in their body size and shape while deployed. |  |
| SP-57 | The PETREL Clothing System shall enable evaporation and wicking at: | For Woven fabrics: Evaporation Rate - After 3 hours mm Min – 37 Wicking: After 5 minutes min – 20 For Knitted mesh: Evaporation rate - After 3 hours mm Min – 50 Wicking: Longitudinal method After 5 minutes min – 80 Wicking: Horizontal Method Max – Back 2 |  |
| SP-58 | The PETREL Clothing System shall have a mass, in accordance with BS EN 12127, of: | For Woven Fabrics: BS EN 12127 – [The Tenderer to complete] g/m2 +/-10g For Knitted Mesh: BS EN 12127 – [The Tenderer to complete] g/m2 +/-10g |  |
| SP-59 | The PETREL Clothing System shall have an abrasion resistance of: | Abrasion Resistance: BS EN ISO 12947-2: After [The Tenderer to complete] cycles using 9kPa Load min No Breakdown |  |
| SP-60 | The PETREL Clothing System shall be permeable to air at: | For woven fabrics: BS EN ISO 9237 [The Tenderer to complete] mm/s For knitted mesh: BS EN ISO 9237 1000 mm/s (as received). |  |
| SP-61 | The PETREL Clothing System material shall have a dimensional stability of: | For Woven Fabrics: Laundering (1): BS EN ISO 5077 % Max – Warp & Weft [The Tenderer to complete] to [The Tenderer to complete]. For Knitted Fabrics: % MAX Warp & Weft [The Tenderer to complete] iaw BS EN ISO 5077 |  |
| SP-62 | The PETREL Clothing System shall have a tensile strength of: | Tensile Strength: BS EN ISO 13934-1 N Min: Warp – [The Tenderer to complete] Weft – [The Tenderer to complete] |  |
| SP-63 | The PETREL Clothing System material shall have a tear strength of: | Tear Strength: BS EN ISO 13937-3 N Min After Washing: Warp – [The Tenderer to complete] Weft – [The Tenderer to complete] |  |
| SP-71 | The PETREL Clothing System material shall have a bursting strength of: | For knitted mesh: BS EN ISO 13938-1 Min –[The Tenderer to complete] kPa |  |
| SP-64 | The PETREL Clothing System shall minimise pilling in the material. | For Woven Fabrics: 36,000 Cycles Rating – [The Tenderer to complete] iaw BS EN ISO 12945-1 For Knitted Fabrics: Grade Max – after 36,000 cycles (as received) – [The Tenderer to complete]. iaw BS EN ISO 12945-2 |  |
| SP-65 | The PETREL Clothing System material shall be colourfast: | BS EN ISO 105: For Woven Fabrics Light B02 – Rating [The Tenderer to complete] Washing C06:C2S – Change [The Tenderer to complete] Staining Cotton [The Tenderer to complete] Perspiration Acid & Alkaline E04: Change [The Tenderer to complete] Staining Cotton [The Tenderer to complete] Rubbing X12: Wet [The Tenderer to complete] Dry [The Tenderer to complete] For Knitted Mesh: Light B02 – Change [The Tenderer to complete] Washing: C06:C2S: Change – [The Tenderer to complete] Staining – [The Tenderer to complete] Perspiration: Acid & Alkaline E04: Change – [The Tenderer to complete] Staining – [The Tenderer to complete] Rubbing: X12: Wet – [The Tenderer to complete] Dry – [The Tenderer to complete] |  |
| SP-72 | The PETREL Clothing System material shall not snag: | For Knitted Mesh: PD 6527 Part 19. After 400 revolutions Min – [The Tenderer to complete] |  |
| SP-74 | The PETREL Clothing System material shall have a surface resistivity of: | For Knitted Mesh: Ω Must be less than – Measured on face or back 1 x 109 Ω |  |
| SP-75 | The PETREL Clothing System material shall have a charge decay of: | For Knitted Mesh: BS EN ISO 1149-3. Shielding Factor Seconds min – 0.2 Half Decay time t50 % Max – 4 |  |
| SP-76 | The PETREL Clothing system material shall have an absorption rate of: | For Knitted Mesh: BS 3449 % Min – [The Tenderer to complete] |  |
| SP-77 | The PETREL Clothing System material shall enable an evaporation rate of: | For Knitted mesh: After 3 hours Min – [The Tenderer to complete] mm |  |
| SP-13 | The PETREL Clothing system material shall protect the wearer against irritation from mites: | Permethrin Treatment Woolmark test TM27:2003 – Using HPLC Method Chemical Assay for Insect Resistant Agent: As Received mg/m2 Min – 1250 After 50 Wash/dry cycles to BS EN ISO 6630 PROCESS 6n, DRYING PROCEDURE f (High) mg/m2 Min – 400 Biogents Cage test (testing available through Biogents AG, Test Labor, Universitatsstrasse 31, D-93053 Regensburg Germany): Laundered for 50 wash & dry cycles to BS EN ISO 633 Process 6N, Drying procedure F (High): 2 or less bites during the 2 minute exposure. |  |
| SP-82 | The PETREL Clothing System shall have anti-microbial properties | Non-migrating, non-leaching anti-microbial agent compliant with ASTM E2149-10 After Washing: No less than 95% |  |
| SP-14 | The PETREL Clothing system shall provide comfort through minimising friction, heat retention and pressure at localised points on the body. | [The Tenderer to complete] Maximise comfort during at least 24 hours continuous use, to include at least 16 hours using load carriage and body armour. AND No friction points. |  |
| SP-15 | The PETREL Clothing system shall be simple to use. | The system shall be no more difficult, or complicated when compared to existing in service equipment, to: Size Assemble Teach how to assemble Don and doff |  |
| SP-16 | The PETREL Clothing system shall enable the wearer to operate in the temperature range: | [The Tenderer to complete] -37deg - +49deg Celsius AND -56deg - +58deg Celsius (Extreme temperatures variations experienced) |  |
| SP-78 | The PETREL Clothing system shall enable the wearer to operate effectively within the humidity range of: | 3-100% humidity. |  |
| SP-19 | The PETREL Clothing system shall be capable of storage for up to 10 years under the climatic conditions defined in SP-16, with no degradation. | 1. The system spatial envelope when stored is minimised but in a way that it will not cause damage to the material. 2. Resources used are intuitive so consumable items can be easily packed. |  |
| SP-22 | The PETREL Clothing system shall be sized to minimise the sizing and training burden on the user and provide labelling on each discrete component that provides NATO codification and descriptive information in a standardised format. | The long sleeve shirts shall be available in a minimum of 10 sizes, based on the following two measurements from VIRTUS: - Chest - Suprasternal notch to the top of the naval The trousers shall be sized in accordance with NATO sizing, based on the following 3 measurements: - Waist - Outside Leg - Seat The tier 1 pelvic protection shall be available in a minimum of 6 sizes. Labelling includes: - Item name - NSN - Size - Wearer name - Wearer Identification number Information remains attached and readable throughout the lifetime of the component. |  |
| SP-25 | The PETREL Clothing System shall comply with the Secretary of State for Defence's policy for environmental protection in accordance with JSP 418. | Disposal procedures to manage the handling, packaging of hazardous substances and restricted materials used within the system. |  |
| SP-26 | The PETREL Clothing System shall remain “safe and suitable for operational use” throughout its service life: | 1) DEF STAN 00-56 2) Safety and Environmental Management Plan. 3) Safety and Environmental Case Report (Parts 1, 2 & 3). 4) Hazard Log. |  |

# Project Management

## Contract Management

    - The Contractor shall;

      - Plan, manage, coordinate, and administer all aspects of the Contract, including the administration of any subcontractors.

      - Establish effective controls for the delivery of the Design and Deliverables.

      - Provide early indication to the Authority of problems encountered and their resolution activities to reduce risk to Performance, Time and Cost parameters.

## Project Management Documents

    - For the duration of the contract the Contractor is responsible for updating and maintaining the following Project Management (PM) Documents:

      - Project Management Plan, detailed in Section 6.3

      - Project Schedule, detailed in Section 6.4

      - Project Progress Reports, detailed in Section 6.5

      - Risk Management Plan, detailed in Section 6.6

      - Risk and Issue Register, detailed in Section 6.6

## Project Management Plan

    - The Contractor shall provide a Project Management Plan (PMP) that includes a detailed resourced Project Schedule Gantt Chart in PDF format that indicates all the activities, interdependencies, key milestones and all supporting activities necessary to deliver the project against the Delivery Schedule from the Project Commencement Date until completion of the Contract;

    - The Contractor shall provide and keep updated as part of the PMP a list identifying the Contractor’s Project Management Team who shall have the appropriate project management qualifications, competences and any necessary security clearances to discharge effectively their obligations in this Contract.

    - The Contractor shall clearly identify where an individual undertakes more than one of the Contractor’s Project Management Team roles.

    - The Contractor shall submit to the Authority for approval prior to implementation all changes to the PMP that the Contractor may propose. No changes shall be executed without such prior approval, in writing, from the Authority.

## Project Schedule

    - The Contractor shall produce and maintain a resourced Project Schedule which shall be issued fortnightly to the Authority, detailing any changes to the schedule. The schedule shall detail all activities anticipated from Contract Award. The Authority requires the ability to monitor progress and identify milestones, resources and dependencies as described.

## Project Progress Reports

    - The Contractor shall provide fortnightly schedule and progress reports to the PETREL Project Manager. This will allow the Authority’s project team to maintain current knowledge of the project progress between Project Review Meetings.

    - The Progress Report shall detail the Contractor’s progress and planned activity against each of the contract’s deliverable elements as listed below:

      - System Design

      - Equipment Manufacture

      - Technical Documentation

      - Safety Documentation

      - Project Schedule

      - Project Risk

    - Progress Reports should be issued by email fortnightly from contract award, to the PETREL Project manager. Additional progress reports are to be raised by the contractor if an issue or risk arises that will affect any aspect of project delivery before the next progress report is due.

## Risk Management

    - The Contractor shall plan and manage risks in accordance with JSP 892 and the Project Risk Management Plan. Risk Management correctly implemented will enable key cost, schedule and performance drivers to be identified enabling actions to be correctly focused to enable the PETREL Project to be successful. The Contractor is required to generate and maintain the project risk documentation for the duration of the contract.

    - The Contractor shall maintain the Risk and Issues Register which shall describe how the Contractor will identify, record and manage risks, issues and opportunities in a structured and timely manner to ensure risks are mitigated to As Low As Reasonably Practicable (ALARP), issues are addressed and agreed opportunities are exploited. A maintained Risk and Issue Register is a key document in delivering successful projects. The Authority requires visibility of all project risks / issues and their progress throughout the project.

    - The Risks and Issues Register shall contain the following as a minimum for each risk or issue:

      - ID Number – A unique identifier;

      - Owner – Person responsible for the risk or opportunity once it has been identified;

      - Description – The cause and impact of the risk or the nature of the opportunity;

      - Risk Assessment – level of risk by probability and impact (time, cost and performance as a minimum), including an assessment of the pre and post mitigation levels. The probability and impact shall include a narrative explaining the figures;

      - Actions – Action or actions that must be or have been taken to mitigate the risk or take advantage of the opportunity;

      - Status – Open/Closed, last updated date with comments.

## Project Review Meetings

    - The Contractor shall invite Authority representation at all Project Review meetings giving not less than 5 working days’ notice (See Schedule 5, Meeting Schedule). Project Review meetings shall be held at a UK venue agreed with the Authority, initially on a monthly basis. The frequency of these Project Review meetings will vary as the contract progresses. The project review agenda will be submitted by the Contractor no less than 5 working days prior to the meeting and will cover as minimum the following topics:

      - Project Schedule;

      - System Acceptance;

      - Safety and environmental;

      - Contract performance review;

      - Subcontractor performance review;

      - Supply chain activities;

      - Risk and Issues Register and RACI

      - Quality management issues (to inc. Quality Performance Indicator review);

      - Supportability / ILS;

      - Commercial;

      - Review of previous actions;

    - Project review meeting minutes shall be produced by the Contractor and submitted for Authority agreement prior to final issue within 3 working days of each meeting and shall be agreed as a standing agenda item during the next meeting.

    - The Contractor shall support the Authority in delivering a cost-effective PETREL solution by attending other relevant meetings as required by the Authority, defined in the Meeting Schedule, Schedule 5.  The Authority will provide a minimum of 5 working days’ notice where such attendance is required.

## Project Management Support

    - The PM support shall start after acceptance of the initial delivery of Tranche 1 and will take over from the Project Management meetings. This shall be focused on supporting and maintaining the PETREL capability through life. The PM support will also include the management and control of any Post Design Services that the Authority requests. The PM support meetings will be chaired by the DE&S PETREL Service Delivery manager.

    - The Project Management Support of this contract shall include the through life management of Sections 6, 7, 8, 9, 10 & 11 of this document throughout the duration of the contract.

    - PM support meetings will be held quarterly from the delivery of Tranche 1 until the end of the contract. Meetings will be held at DE&S Abbey Wood, Bristol, BS34 8JH unless the meeting necessitates being held at the Contractor’s facility.

# Safety and Environmental

## Safety and Environmental Management Plan

    - The Contractor shall provide Safety & Environmental documentation that forms a body of evidence that provides a compelling, comprehensive and valid case that the risks associated with the use of PETREL are ‘As Low as Reasonably Practicable’ (ALARP) and broadly tolerable in accordance with DEFSTAN 00-56, JSP454 and POSMS & POEMS as required under MOD policy.

    - The Contractor shall provide a Safety & Environmental Case Report (SECR) Part 2 (Design) 30 working days post IDA. A Hazard Log is to be developed and delivered in eCassandra or Excel. Environmental Impact Assessment with supported Environmental Feature Matrix for manufacture, in-service and disposal stages extracting information from the Disposal Plan to support the assessment.

    - A Certificate of Conformity (CoC) is required with each delivery of PETREL systems and additional buys to ensure products meet the minimum set of regulatory, technical and safety requirements as outlined in the System Performance Table. A CoC template has been provided at Schedule 9.

    - The Contractor shall provide a Material Safety Data Sheet (MSDS) for the PETREL System. This is to be delivered in conjunction with the SECR Part 2, 30 working days post IDA.

# Integrated Logistic Support

## Introduction

    - It is MOD policy to procure products that meet the required performance to time and cost, which are fully supportable at the optimum Through Life Cost (TLC). Guidance on the application of ILS policy, defining the disciplines which must be applied, is detailed in DEF STAN 00-600 and the Defence Logistic Framework (DLF).

    - Integrated Logistic Support (ILS) shall be applied to ensure that products shall be supportable, that the necessary support infrastructure is put in place and that availability and TLC are optimised. In circumstances where design decisions cannot be affected, then ILS shall still be required to influence the selection of equipment already developed or the way it is supported, on the grounds of delivering an optimum TLC.

    - ILS Reviews shall be incorporated within the Project Review Meetings and Project Support Meetings, not held as a separate activity.

    - Please note that this covers the maximum scope of work for said items. Please be advised that the Authority reserves the right to amend the scope at any point.

## Integrated Support Plan (ISP)

    - The Contractor shall provide full visibility of all aspects of ILS. The Contractor shall provide an Integrated Support Plan (ISP) detailing how the Authority ILS requirements are met, including an ILS Schedule of Work that integrates with the project plan and includes all ILS elements within the contract for the management and execution of the ILS programme in accordance with DEF STAN 00-600, as detailed below.

    - The Contractor shall include all sub-element Plans and Reports in the ISP, specifying how the separate elements of the support system are to be designed, implemented, integrated, operated and validated. These are as listed below and detailed later:

      - Damage Modes Effects Analysis (DMEA) Report/Failure Modes Effects & Criticality Analysis (FMECA) Report, detailed in Section 8.3

      - Level of Repair Analysis (LORA) Report, detailed in Section 8.4

      - Reliability & Maintainability (R&M) Report, detailed in Section 8.5

      - Maintenance Report, detailed in Section 8.6

      - Obsolescence Management Plan, detailed in Section 8.7

      - Equipment Breakdown Structure, detailed in Section 8.8

      - Logistic Demonstration Plan, detailed in Section 8.9

      - Technical Documentation, detailed in Section 8.10

      - Codification Plan, detailed in Section 8.11

      - Packaging, Handling, Storage & Transport (PHS&T), detailed in Section 8.12

      - Configuration Management Plan, detailed in Section 8.13

      - Training Plan, detailed in Section 8.14

      - Disposal Plan, detailed in Section 8.15

## Damage Modes Effects Analysis (DMEA) Report/Failure Modes Effects & Criticality Analysis (FMECA) Report

    - The Authority requires to be able to understand and mitigate ‘Damage Modes’ and ‘Failure Modes’ for the PETREL system. The below reports shall contain damage/failure modes, their impact, likely occurrence rate and any mitigations.

    - The Contractor shall develop and deliver an updated DMEA Report within 30 working days of IDA. This will enable the corresponding information to be incorporated within other aspects of the contract, e.g. Army Equipment Support Publications (AESPs), Training, Initial Spares pack, etc.

    - The Contractor shall develop and deliver an updated FMECA Report within 30 working days of IDA. This will enable the corresponding information to be incorporated within other aspects of the contract, e.g. AESPs, Training, Initial Spares pack, etc.

## Level of Repair Analysis (LORA) Report

    - The Authority requires to be able to understand the optimum maintenance strategy. Level 1 User maintenance for day to day equipment preparation, maintenance and care, with more in depth maintenance carried out at Level 2 by Specialist Trade Maintainers, who will work with a light logistic footprint.

    - The Contractor shall complete the LORA in full within 30 working days of IDA. This will enable the corresponding information to be incorporated within other aspects of the Contract, e.g. AESPs, Training, Initial Spares Pack, etc.

## Reliability & Maintainability (R&M) Report

    - The Authority requires assurance that the PETREL System is reliable and can be efficiently maintained, these are critical to achieving cost effective operation and logistic support for PETREL systems. Reliability is pertinent to the frequency of failures and so drives the quantity of repairs and spares that will be required over time.

    - The Contractor shall develop and deliver a detailed R&M Report within 30 working days of IDA.

    - The Report shall be in accordance with the following standards:

      - DEF STAN 00-42

      - DEF STAN 00-44

## Maintenance Report

    - The Contractor shall develop and deliver a Maintenance Report within 30 working days of IDA. This shall identify all operation and maintenance tasks that are required to be performed in supporting the PETREL system in its intended environments.

    - The Maintenance Report shall include, but not be limited to:

      - Cleaning activities

      - Maintenance activities

      - Storage restrictions, e.g. perishable items, time, COSHH, etc.

## Obsolescence Management Plan

    - The Authority requires assurance that the Contractor can supply and support PETREL Systems throughout the contract duration without the performance and availability being significantly impacted by obsolescence issues. The report shall identify all future obsolescence risks and include, where available, likely actions to mitigate the identified risk. It shall provide appropriate detail to provide the PETREL Integrated Logistic Support Manager sufficient evidence of cost and risks to allow for financial forecasting.

    - The Contractor shall develop the Obsolescence Management Plan ensuring it includes, but is not limited to:

      - Existing analysis of PETREL obsolescence

      - Obsolescence risks over the 5-years of the contract and additional Option years.

      - Existing processes to identify and resolve PETREL obsolescence risks and issues

    - The Contractor shall deliver the Obsolescence Management Plan within 30 working days of IDA.

## Equipment Breakdown Structure

    - The Authority requires to be able to understand the structure of the equipment being supplied for the PETREL system. This will be achieved through the Equipment Breakdown Structure (EBS) document. This will provide the Authority with visibility of the items of equipment entering service which will correspondingly enable supportability and sustainability issues to be identified.

    - The EBS shall include the following:

      - Pictorial representation of all items

      - Material part Numbers (MPNs) and NATO Stock Numbers (NSNs) (System, sub-system and individual parts)

      - Location of individual parts within PETREL, displayed as schematic

      - Items within the EBS which are replaceable by Users/Maintainers

    - The Contractor shall develop and deliver the EBS within 30 working days of IDA.

## Logistic Demonstration Plan

    - The Authority requires assurance that the Contractor has identified all the necessary ILS processes and can successfully present them to the Authority within the Logistic Demonstration. This will be achieved through the Logistic Demonstration (LD) Plan.

    - The Contractor shall develop and deliver the LD Plan within 30 working days of IDA.

    - The LD Plan shall include, but not be limited to:

      - Presentation of the PETREL system (complete to EBS) in its final build standard

      - Presentation of cleaning instructions for the PETREL system

      - Presentation/review of all Technical Documentation

      - Demonstration of Codification, including equipment and documentation

      - Presentation and physical inspection of packaging and labelling for delivery to the Authority

      - Presentation of storage facilities for all PETREL items to be held on Contractor premises (including storage and segregation of new (A1) and damaged/defective/used (E0) systems, etc.)

      - Demonstration of Contract Support services

      - Demonstration of Quality and Configuration Management

    - The Contractor shall deliver a LD to the Authority, presenting all items listed in the LD Plan, no later than 2 weeks prior to Tranche 1 delivery.

## Technical Documentation

    - The Authority requires to be able to ensure the Contractor has identified all the required Technical Documentation and can produce and deliver it within the agreed timescales. This shall be achieved though the Technical Documentation (TD) Plan.

    - The TD Plan shall demonstrate how the required set of Technical Documents (AESPs) will be delivered within the timeline, either internally or by Sub-Contractors. The plan shall identify activities such as internal reviews by the Contractor, reviews by the Authority, SME activity, etc.

    - The Contractor shall develop and deliver the TD Plan within 15 working days of IDA.

    - Following the strategy outlined in the TD Plan, the Contractor shall develop and deliver the following Technical Documentation, no later than 50 working days from IDA, in the recognised UK MOD format:

      - User/Operator handbook (AESP 201). This is to also include the following:

        - Pictorial representation of all items

        - Material part Numbers (MPNs) and NATO Stock Numbers (NSNs) (System, sub-system and individual parts)

        - Location of individual parts within PETREL, displayed as schematic

        - Items within the EBS which are replaceable by Users/Maintainers

        - Quick Reference User Guide

    - The Contractor shall produce all Technical Documentation in accordance with the following standards:

      - ‘Defence Technical Documentation Guidance’, (Formally JSP 543)

      - DEF STAN 00-600, ‘Integrated Logistic Support, Requirements for MOD Projects’

      - ASD-STE 100, ‘Simplified Technical English’

    - The Contractor shall produce the Technical Documents in accordance with the following approach:

      - Throughout the process, the Contractor shall provide the Authority with opportunities to review the documents to ensure the structure is acceptable and follows the required standards.

      - The Contractor shall deliver an initial draft of all documentation within 30 working days of IDA.

      - The Authority shall review documentation and return comments within 10 working days of receipt.

      - The Contractor shall implement any Authority amendments within the Master documentation.

      - The Contractor shall provide final drafts of all documentation for final review by the Authority within 50 working days from IDA.

    - The Contractor shall ensure that all documentation includes safety hazards, warnings and cautions.

    - For the duration of the contract, the Contractor shall supply the Authority with technical data as and when required to allow the Authority to maintain all technical publications.

## Codification Plan

    - The Authority requires the ability to uniquely classify all relevant parts of the PETREL system allowing the identification, management, tracking and controlling of PETREL assets within the Supply Chain. This is achieved through codification.

    - The Contractor shall develop and deliver a Codification Plan to the Authority within 20 working days of IDA. The Codification Plan shall demonstrate how the relevant parts of the PETREL system will be codified within the timeline.

    - Following the strategy outlined in the Codification Plan, the Contractor shall perform codification of the PETREL system in accordance with:

      - Defence Logistic Framework (DLF), ‘NATO Codification ISISWeb New Item’

      - DEF CON 117, ‘Supply of Information for NATO Codification and Defence Inventory Introduction’

      - STANAG 2290, ‘NATO Unique Identification of Items’

    - The codification shall be of the final production standard of the PETREL system, down to Maintenance Significant Items (MSI). The Authority reserves the right to determine the PETREL MSI that require codification.

    - The NATO Stock Numbers (NSNs) generated by codification shall be used for reference purposes for all PETREL parts and within all PETREL documentation.

    - The Authority will aid the Contractor in processing codification requests however, the Contractor shall retain full responsibility for codification.

    - Codification shall be completed within 50 working days of IDA.

## Packaging, Handling, Storage & Transport (PHS&T)

    - The Authority requires the ability to identify, manage, track and control all the PETREL assets within the Supply Chain. This is achieved by PETREL assets being correctly packaged, marked, labelled and stored.

    - The Contractor shall develop and deliver a PHS&T Plan within 30 working days of IDA. The PHS&T Plan shall demonstrate that the Contractor has sufficiently planned for this activity.

    - Packaging shall be in accordance with:

      - DEF CON 129, ‘Packaging (For Articles Other Than Munitions)’

      - DEF STAN 81-41, ‘Packaging of Defence Material’

    - Marking shall be in accordance with:

      - DEF CON 644, ‘Marking of Articles’

      - DEF STAN 05-34, ‘Marking of Service Materiel (Obsolescent)’

      - DEF STAN 05-132, ‘Marking of Service Materiel Items Using a Unique Item Identifier (UII)’

      - STANAG 2290, ‘NATO Unique Identification of Items’

    - The Contractor shall ensure packaged PETREL systems can be stored and transported on NATO Standard Pallets (dimensions 48in x 40in/1,200mm x 1,000mm) and in an efficient manner to reduce storage space. Additional guidance can be obtained in the PHS&T process contained in the DLF.

    - The Contractor shall state any storage restrictions that need to be implemented to avoid any impact on the capability of PETREL, e.g. item shelf life of component part.

    - Packaging of the PETREL system shall be, at minimum, to Military Packaging Level J.

    - Labelling shall include:

      - Item Description

      - Manufacturer Part Number (MPN)

      - NSN plus bar code

      - Month and year of manufacture

      - Batch Number

      - Contract Number

      - Certificate of Conformance Number

      - Denomination of Quantity (DofQ) plus bar code

      - Primary Package Quantity (PPQ) plus bar code

    - The Contractor shall mark all PETREL assets with the following details:

      - Equipment Usage and Care Information

      - NATO Stock Number

      - Size

      - Space for Wearer Name

      - Space for Wearer Identification Number

    - All marking shall be indelible and clearly legible, and remain so through the In-Service life of the equipment.

    - Should it not be possible to mark an item due to size, material, etc. the Contractor shall seek guidance from the Authority on the appropriate action.

    - The Contractor shall implement the procedures and processes set in the PHS&T Plan so that the PETREL system is correctly packaged for handling, transport and storage.

## Configuration Management Plan

    - The Authority requires to be able to implement a method of maintaining configuration control of the PETREL system during its in-service phase. This will be achieved through the Configuration Management Plan (CMP). Through the CMP the Contractor shall demonstrate how the PETREL configuration will be managed during its In-Service life by both the Contractor and the Authority, in an optimum manner.

    - The Contractor shall develop and deliver the CMP within 30 working days of IDA.

    - The CMP shall be developed in accordance with:

      - DEF STAN 05-57, ‘Configuration Management of Defence Materiel’

      - ACMP1-6 NATO Requirements for Configuration Version 2

## Training Information Package

    - The Authority requires the ability to provide a User and Maintainer Training Information Package (TIP) that can be cascaded to the User community so they can operate and maintain the PETREL system effectively.

    - The Contractor shall ensure that the TIP is in accordance with:

      - Defence Systems Approach to Training (DSAT)

      - JSP 822 Version 3 Part 1 and 2

    - The Contractor shall ensure that the TIP shall include, but not be limited to:

      - Quick Reference User Guides, to be packaged with each set

      - Other paper based information sources such as tri-folds, leaflets, posters and magazines, in conformance with Schedule 10, User Guide Standard Requirements spec.

    - The Contractor shall submit the final version of the TIP for review and acceptance by the Authority within 50 working days of IDA.

    - The TIP shall be delivered within 70 working days of IDA.

## Disposal Plan

    - The Authority requires to be able to fully understand all aspects of the disposal process for the PETREL system. The primary method by which this will be achieved is the Disposal Plan.

    - The Contractor shall develop and submit a Disposal Plan within 30 working days from IDA.

    - The Disposal Plan shall cover, but not be limited to, the following areas:

      - Detailed disposal options for all individual PETREL components (and where appropriate, sub-assemblies)

      - Detailed procedures for the identified disposal options

      - Identification of any components that require special disposal

      - Identification of any environmental impacts of disposal, including opportunities to reclaim or recycle component parts.

    - The Disposal Plan will act as a reference within the Safety & Environmental case Report.

    - The Disposal Plan will identify and reference all applicable European Legislations, e.g. RoHS 2002/95/EC, WEEE 2002.96/EC, etc.

# Quality Management

## Quality Management System

    - Contractors are required to hold Quality Management System (QMS) certification to ISO 9001:2008/15, with the appropriate scope to deliver contract requirements, issued by a Nationally Accredited Certification Body for the duration of the contract. The Contractor shall immediately inform the Authority of any amendments or if the QMS certification is revoked or suspended with immediate effect.

    - The Contractor is to hold this certification for the duration of the contract or as stated in the contract.

## Quality Management Plan

    - The Contractor shall supply a Project Quality Management Plan (QMP) in accordance with DEFCON 602A. It shall be written in accordance with but NOT restricted to Allied Quality Assurance Publications (AQAP) 2105. The Project QMP shall be completed within 30 working days post IDA.

# Purchase of Additional Items

    - The Authority requires the ability to purchase additional PETREL components and systems to maintain the fleet via replenishment and/or to meet the Total Fleet Requirement (TFR) of 107,254 systems.

    - Additional items are to be available in accordance with Schedule 03 – Cost Breakdown Sheet. The minimum quantity order of each item is 500, this may consist of a mixture of sizes.

    - Additional items are to be delivered in accordance with the System Performance Table 2 and sections 8.11 and 8.12 of this document.

    - Delivery lead times are detailed in Schedule 03 – Cost Breakdown Sheet and are broken down by banded quantity order sizes.

# Post Design Services

    - The Authority may choose at any point during the contract duration after System Acceptance to invoke PDS for the system. The PETREL Project Board will convene to decide on the PDS approach and issue a PDS tasking form to the Contractor as per Schedule 07. Once the PETREL Project Board have reviewed the response from the Contractor they may or may not choose to proceed with the PDS task. If approval is gained then all PDS tasks will be entered onto an approved PDS task list (Schedule 11).

# Acceptance

## Deliverable Acceptance

    - The Authority shall review all deliverables within the timescales stated in the delivery table in Section 4.

    - Acceptance of deliverables is dependent on the Authority’s assessment that the deliverable meets the Acceptance Criteria as Stated in Section 4

    - If during the review process the Authority identifies that a deliverable does not meet the acceptance criteria actions will be given to the Contractor to amend the deliverable which must be completed before it can be accepted.

Annex A to
PETREL Schedule 01 - SOR

# Annex A - INTEGRATION LIST

| Category | External System | Development Status | Integration Trials Authority |
| --- | --- | --- | --- |
| Threshold Equipment |  |  |  |
| Critical ‘On the Man’ Mission Equipment |  |  |  |
| Lethality | SA80 Individual Weapon (IW) L85A2 | In service | ITDU |
| Lethality | SA80 Individual Weapon (IW) L85A3 | In service | ITDU |
| Lethality | SA80 Carbine | In service | ITDU |
| Lethality | General Service Pistol + Training Pistol | In service | ITDU |
| Lethality | L123A3 Underslung Grenade Launcher (UGL) | In service | ITDU |
| Lethality | L110A2 Light Machine Gun (LMG) | In service | ITDU |
| Lethality | General Purpose Machine Gun (GPMG) | In service | ITDU |
| Lethality | Remington Shotgun | In service | ITDU |
| Lethality | Grenade Hand L109 + L111 Training Grenade body | In service | ITDU |
| Lethality | Smoke Grenades – Red Phos, Screening, Training, Signalling | In service | ITDU |
| Lethality | L9A1 60mm Mortar | In service | ITDU |
| Lethality | Next-generation Light Anti-armour Weapon (NLAW) | In service | ITDU |
| Lethality | L115A3 Sniper System Improvement (SSI) | In service | ITDU |
| Lethality | L129A1 Sharpshooter + L129 A2 Sniper Support Weapon | In service | ITDU |
| Lethality | Anti-Structure Munitions (ASM) | In service | ITDU |
| Non-lethal | L127 Baton gun | In service | ITDU |
| Survivability | VIRTUS | In service | ITDU |
| Survivability | Cold Weather Clothing | In service | 11 ATT Sqn RM |
| Survivability | Combat Gloves | In service | ITDU |
| Survivability | Tactical Hearing Protection System (THPS) | In service | ITDU |
| Survivability | EP ECM equipment | In service | ITDU |
| Survivability | EP ECM Load Carriage Systems | In service | ITDU |
| Survivability | Medical Stretcher | In service | ITDU |
| Survivability | Team Medic Pouch | In service | ITDU |
| Survivability | Medical Load Carriage Systems | In service | ITDU |
| Survivability | CBRN PPE | In service | ITDU |
| STANO | GS Prismatic Compass | In service | ITDU |
| STANO | Lightweight SILVA Compass | In service | ITDU |
| STANO | LUCIE | In Service | ITDU |
| STANO | Head Mounted Night Vision System 2 (HMNVS2) | In service | ITDU |
| C4I | BOWMAN Man-packable systems 354 and 355 | In service | ITDU |
| C4I | Personal Role Radio (PRR) + ezPRR | In service | ITDU |
| Survivability | Parachuting Equipment | In service | JATDU |
| DCC Mission Support Equipment |  |  |  |
| Lethality | L1A1 12.7mm Heavy Machine Gun (HMG) | In service | ITDU |
| Lethality | L134A1 Heckler & Koch 40mm Grenade Machine Gun (GMG) | In service | ITDU |
| Lethality | L16A2 81mm Mortar | In service | ITDU |
| Lethality | Light Forces ATGW (LFATGW) (JAVELIN) | In service | ITDU |
| Arty Sys | L118 105mm Light Gun | In service | RATDU |
| A Vehs | WARRIOR | In service | ITDU |
| B Vehs | MASTIFF/ RIDGEBACK | In service | ITDU |
| B Vehs | Landrover R/WIMK | In service | ITDU |
| B Vehs | Landrover WIMK | In service | ITDU |
| B Vehs | JACKAL/COYOTE | In service | ITDU |
| B Vehs | Truck Utility (Light, Medium, Heavy) TUL/TUM/TUH | In service | CSSTDU |
| B Vehs | FOXHOUND | In service | ITDU |
| B Vehs | Bv206D | In service | 11 ATT Sqn RM |
| A Vehs | PANTHER Command and Liaison Vehicle (CLV) | In service | ATDU |
| A Vehs | CVR(T) | In service | ATDU |
| A Vehs | FV432 | In service | ITDU |
| B Vehs | Logistic Cargo Vehicles (various) Support Vehicles | In service | CSSTDU |
| B Vehs | APV 1.5 SNATCH | In service | ITDU |
| B Vehs | Quad bike Grizzly 450 | In service | ITDU |
| Littoral | ATV(P) | In service | 11 ATT Sqn RM |
| Survivability | Assault Troop Life Jacket (ATLJ) Mk4 | In service | 11 ATT Sqn RM |
| Survivability | Landing Craft Life Jacket (LCLJ) Mk3 | In service | 11 ATT Sqn RM |
| Survivability | Life Jacket Royal Engineers | In service | RETDU |
| Objective Equipment |  |  |  |
| JHC | SEA KING HC Mk4 | In service | JADTEU |
| JHC | MERLIN Mk3/Mk3a | In service | JADTEU |
| NCHQ | MERLIN Mk2 | In service | JADTEU |
| JHC | CHINOOK all marks (2/2a/3/4/5/6 | In service | JADTEU |
| JHC | PUMA HC Mk1 | In service | JADTEU |
| JHC | PUMA HC Mk2 | In service | JADTEU |
| JHC | WILDCAT AH 1 | In service | JADTEU |
| STANO | Commander’s Target Locator System (CTLS) | In service | ITDU |
| STANO | Lightweight Infantry Periscope (LIP) | In service | ITDU |
| STANO | LH40C TLE Laser Range Finder | In service | ITDU |
| STANO | Ruggedized Digital Camera (RDC) | In service | ITDU |
| STANO | Nano UAV (Black Hornet) | In service | ITDU |
| STANO | Man Portable UAV (Mini UAS DH3) | In service | RATDU |
| C4I | Tactical Aid Memoires and SOPs | In service | ITDU |
| C4I | Defence Advanced GPS Receiver (DAGR) | In service | ITDU |
| C4I | Lightweight Manpack Data Terminal | In service | ITDU |
| C-IED | CIED Eqpt | In service | RETDU |
| C-IED | Dog Handling Equipment | In service | RETDU |
| EOD | Allen Enhanced Hook and Line Set | In service | RETDU |
| EOD | EOD Lightweight A Frame | In service | RETDU |
| Engr Eqpt | Combat Support Boat Mk II | In service | RETDU |
| Engr Eqpt | BR90 Automotive Bridge Launcher Equipment (ABLE) | In service | RETDU |
| Engr Eqpt | TITAN | In service | RETDU |
| Engr Eqpt | TROJAN | In service | RETDU |
| Engr Eqpt | Light Wheeled Tractor | In service | RETDU |
| Engr Eqpt | BR90 Bridging Vehicle | In service | RETDU |
| Littoral | Offshore Raiding Craft (ORC) | In service | 11 ATT Sqn RM |
| Littoral | Landing Craft Air Cushion (Replacement) (LCAC ®) | In service | 11 ATT Sqn RM |
| Littoral | In Shore Raiding Craft | In Service | 11 ATT Sqn RM |
| Air | C17 | In service | JADTEU |
| Air | C130J/K | In service | JADTEU |
| Air | VC10 | In service | JADTEU |
| Naval | PAC 24 JET Mk 3 | In service | FLEET |
| Survivability | Tactical Radiation Monitoring Equipment | In service | ITDU |
| Survivability | Lightweight Chemical Agent Detector (LCAD) | In service | ITDU |
| Survivability | Man-portable Chemical Agent Detector (MCAD) | In service | ITDU |
| Survivability | Chemical Agent Monitor (CAM) | In service | ITDU |
| Survivability | Collective Protective Monitor | In service | ITDU |
| STANO | Laser Target Designator (LTD) LF28A | In service | RATDU |
| STANO | Surveillance System & Range Finding (SSARF) | In service | RATDU |
| STANO | Man Portable Surveillance & Targeting Radar (MSTAR) | In service | RATDU |
| C4I | Battlefield Integrated Combat Capability (BICC) | In service | CISTDU |
| C4I | Lightweight Tablet Data Terminal | In service | ITDU |
| C4I | Harris Radio | In Service | CISTDU |
| C4I | SEER | In Service | CISTDU |
| C4I | FALCON | In service | CISTDU |
| A Vehs | CHALLENGER 2 | In service | ATDU |
| A Vehs | CHALLENGER ARRV | In service | ATDU |
| A Vehs | FUCHS NBC vehicle | In service | ATDU |
| B Vehs | Combat Support Tanker (Various) | In service | CSSTDU |
| Engr Eqpt | Dismounted Counter Mine Capability (DCMC) | In service | RETDU |
| Engr Eqpt | Mine Protected Vehicles | In service | RETDU |
| Engr Eqpt | TRAKKER | In service | RETDU |
| Engr Eqpt | Medium Wheeled Tractor (Case) | In service | RETDU |
| Engr Eqpt | Multi Terrain Loader (MTL) (P Cat 257) | In service | RETDU |
| Engr Eqpt | TERRIER | In- service | RETDU |
| Engr Eqpt | Medium Wheeled Tractor (Cat 938) | In service | RETDU |
| Engr Eqpt | High Mobility Engineer Excavator (HMEE) | In service | RETDU |
| Engr Eqpt | Medium Crane (TEREX 35 t) | In service | RETDU |
| Engr Eqpt | Demolition Harness | In service | RETDU |
| Arty Sys | AS90 Self Propelled Gun 155mm | In service | RATDU |
| Arty Sys | Multiple Launch Rocket System | In service | RATDU |
| Arty Sys | Rapier | In service | RATDU |
| Arty Sys | HVM | In service | RATDU |
| Arty Sys | MAMBA | In service | RATDU |
| Arty Sys | IZLID | In service | RATDU |
| Littoral | Landing Craft Utility Mk10 (LCU10) | In service | 11 ATT Sqn RM |
| Littoral | Landing Craft Vehicle & Personnel Mk5 (LCVP5) | In service | 11 ATT Sqn RM |
| Littoral | Landing Platform Helicopter (LPH) | In service | 11 ATT Sqn RM |
| Naval | River Class Offshore Patrol Vessel | In service | FLEET |
| Naval | River Class Offshore Patrol Vessel(H) | In service | FLEET |
| Naval | Offshore Survey Vessel | In service | FLEET |
| Naval | Coastal Survey vessel | In service | FLEET |
| Future Equipment to be put into Priority Order when brought into service |  |  |  |
| Lethality | SA80 Individual Weapon (IW) L85A2 | Future | ITDU |
| STANO | Dismounted Situational Awareness (DSA) | Future | ITDU |
| STANO | LSBC | Future | ITDU |
| C4I | LANDSEEKER | Future | CISTDU |
| C4I | LETacCIS | Future | CISTDU |
| C4I | Enhanced Joint Combat Identification Marking System (EJCIMS) | Future | ITDU |
| A Vehs | WARRIOR CSP | Future | ITDU |
| A Vehs | SCOUT SV | In service | ATDU |
| B Vehs | ATV(S) VIKING | Future | ASCRM |
| Littoral | Future Carriers (QEC) | Future | 11 ATT Sqn RM |
| Air | A400M | Future | JADTEU |
| Air | KC30 | Future | JADTEU |
| NCHQ | WILDCAT HMA Mk2 | Future | JADTEU |
| Arty Sys | TUAV – Watchkeeper | Future | RATDU |
| Arty Sys | Future Weapon Locating Radar (FWLR) | Future | RATDU |
| Arty Sys | Battlefield Surveillance System | Future | RATDU |
| Arty Sys | Joint Fires Integrator FIRESTORM | Future | RATDU |
| Arty Sys | Fire Control Application | Future | RATDU |
| ISTAR | BLOODHOUND (Material and Personnel Exploitation) | Future | RATDU |
| ISTAR | OUTPOST (Ground Based ISTAR) | Future | RATDU |