Special Exhibition – Object Mounts

Scope of Works and Specification

Project Brief

The National Army Museum wishes to appoint a suitably experienced mount making company to manufacture and install the object mounts for items to be displayed in a special exhibition at the National Army Museum in Chelsea for an exhibition opening in March 2018.

Included as separate documents with this tender brief are:

- Object Full Mount Schedule

- Extent of Works

The scope of this mounts package consists of a number of different types of mount to be found in the schedule.  The Contractor shall provide everything necessary for the mounting and completion of the Works.

General Comments

The schedule is separated into the following groups. This is to enable the contractor to appropriately assess costs and time allocation for the different type of mounts:

- Objects requiring a mount

- Objects requiring a plinth

- Objects requiring a 2D mount

- Objects requiring suspension

Objects inside the showcases will either be positioned on glass shelves requiring self-supporting mounts or secured directly on to the display case base or back boards, both of which will be made from Z-MDF. Full display case specifications will follow after the appointment has been made. If known the mount colour has been specified in the schedule.

Three objects will be on open display, one of which will need anchoring to a plinth and two of which will require suspension from the ceiling.

Access to Objects

The objects are currently located at combination of the NAM storage facilities in Stevenage and the lending venues (Royal Marines Museum, Combined Military Services Museum and the Airborne Assault Museum). As a high proportion of the objects will be on loan it is expected that the contractor will need to visit the lending venues as well as NAM. This will need to be considered when the object assessments, mount discussions and mount making are sequenced in the mount making programme.

Contractors are to note that there is a small workshop space at the main NAM off-site storage facility in Stevenage, which is also where the Collections Care and Standards Team are based. At this workshop Perspex could be worked, but there is currently no hot works permit or heat/extraction for working metal.

The contractor will need to describe their approach to the mount-making process including object assessments, measurement taking, mount making, checking the mount with the object prior to transfer to the museum site, and allowance within the tender price and time allocation for on-site installation of object mounts. NAM will need to see a breakdown from the contractor of the allowance for on-site work during object installation and what the approach of the successful contractor would be to making changes to mounts during this period.

Details of each type of mounts, including exemptions/particulars

Objects requiring a mount

- Mounts which support object at multiple points. Bent metal or acrylic cushioned with an   inert material. A number of objects currently noted as laying flat on the case base in the schedule will require mounts, this will be discussed on an object by object basis once appointment has been made.

Objects requiring a plinth

- Objects with flat stable bases can be displayed and supported on a flat elevated surface e.g. plinth (heights to be advised by the designer).

Paper items requiring a 2D mount

- Paper items will either require flat support or a book cradle.

Objects requiring suspension

- Mounts which will be suspended from the ceiling and support the object at multiple points.

Each type of mount will be manufactured using materials that have been subject to Oddy Testing to prove their suitability for use with museum objects.

- Liaison

The appointed contractor is to liaise closely with the Collections Care and Standards Team and contractors to ensure the works meet all the specifications.

- Client – National Army Museum – exhibitions, conservation and security, access to objects and installation, and sign-off of design proposals for each type of mount. Main contact: Ms Vicky Singleton (Conservation Manager)

- Designer – MET – detail design of the exhibition including objects, graphics and AV

- Fit-out contractor – Benchworks – installation of walling and showcases

The Contractor shall ensure that the Works are compatible with conservation and design requirements for each object.

Tenderers will be deemed to have understood the extent of work in returning a tender. The contractor appointed will be expected to make themselves familiar with the full extent of other exhibition works which will be let under separate work packages in the event that liaison is required between exhibition appointed contractors to ensure the design and conservation intent is fully met.

- Overall Quality

The mount schedule indicates the current basic requirements for each object. The successful contractor will be expected to work with the Client and Exhibition Designer to develop final treatments for approval.

The Contractor shall exercise in the design, execution and completion of the works all the skill, care and diligence to be expected of a properly qualified, experienced and competent Contractor and should have previously carried out work of a comparable scope, nature and size to the Works.

- Project Management

The Contractor shall identify and provide a person responsible for the coordination, liaison and development of the Works who shall efficiently supervise the execution of the Works using their best skill and attention. This person will be responsible for the following as well as any internal roles required:

- Liaison with team

- Liaison with Client on deliverables required to meet the programme

- Attendance at progress/interface meetings as required

- Monitoring quality and consistency across the works

- Coordinating works to meet the requirements of the programme

- Confirmation of pre- and on-site programming requirements and co-ordination necessary for successful mounting and installation

If the appointed contractor needs to replace this person, the replacement person or persons must be of equivalent competence and will need to be approved by the Client.

- Programme

The Contractor will be required to produce and work to a detailed programme within the constraints of the project programme. This programme should be compiled within two weeks of appointment.

| Task | Period | Start | Finish |
| --- | --- | --- | --- |
| Appointment (provisional) | 19/12/2017 | 05/01/2018 | 16/03/2018 |
| Object assessment and mount development (across NAM and loan venue sites) | 2-3 weeks | 15/01/2018 | 02/01/2018 |
| Production and testing | 2 weeks | 05/01/2018 | 16/02/2018 |
| Installation | 2 – 3 weeks (tbc) | 26/02/2018 | 16/03/2018 |

- Timetable/ Schedule

The tender will be awarded by the end of this year. Two deliveries of objects will be required, the first in early February of the objects requiring mounts to be made. The second will be towards the beginning of March of the objects to be installed directly into the galleries. Which objects are expected in which delivery is indicated on the object spread sheet.

- Health and safety

The company will be required to provide method statements and risk assessments for any potentially hazardous process that take place on NAM property (e.g. use of heavy lifting equipment, work at heights, etc.) and will be fully responsible for health and safety compliance for all work at lenders sites and during transit.

- Site visits

Site visits to NAM in Chelsea can be accommodated if required. To arrange these please contact Ms Vicky Singleton, Conservation Manager (vsingleton@nam.ac.uk) tel 020 7881 2481.

- Criteria on which tenders will be awarded

In order of relevance:

- Strength of tender (Consideration of specific needs of objects). (50%)

- Overall cost. (30%)

- Proven experience of similar projects. (20%)

- Deadline for tenders

All tender documents/electronic media are to be addressed to Mr J Foster - NAM Secretariat jfoster@nam.ac.uk or tenders@nam.ac.uk and annotated with “TENDER DOCUMENTS NOT TO BE OPENED BEFORE 1400hrs on 17 December 2017.  On no account are the tender documents to be passed to the requesting department before the tender board date.

Address for the return of tenders:

Mr. John Foster

National Army Museum

Royal Hospital Road

Chelsea

London

SW3 4HT

- Operation

The Contractor will be required to provide staff with the information needed, prior to completion of the works, to enable the Client to mount, dismount, install and maintain the mounted objects on a regular basis.

The appointed contractor will be required to produce two sets of final information for each mount type, explaining what the mount looks like, how it works and any maintenance notes that the Client will need to be aware of in the future.

- Defects Liability

Tenderers to allow for a Defects Liability Period of 12 months during which time they will need to rectify any issues that arise with the mounts as a result of the final design, fabrication or installation.

- Approvals

Client approval stages are an important part of the production process for all the mount and material elements. Approval stages are to be programmed and are to include the following as a minimum:

- Initial creative concept treatment

- Pre-production presentation (including materials)

- Example mounts and materials for approval with internal team

- Functionality, compatibility and interface with design/fit-out

- Method statements for general approach to different materials

- Method statements for working with objects, on site at NAM storage and conservation facility, and for working on site in galleries during installation

Due to the tight programme detailed above, it is anticipated that a number of the stages above will need to be condensed into the early stages pre- and post-appointment. The contractor will need to work with the team and communicate key deadlines for information to be passed on.

- Sustainability

The Contractor shall ensure that their working methods, performance, operational and maintenance are as sustainable as possible. For example, where possible / necessary the Contractor should:

- Use ethical and environmentally conscious technical sub-consultants

- Contribute towards Client staff skills development

- Commit to audience evaluation and testing where required

- Consider operating costs throughout design process

- Design in flexibility where required

Conservation Rating

The object schedules contain limited information on the current condition of the objects.

Many objects may be undergoing conservation work to ensure that they are suitable for display and the contractor will need to discuss each object and its requirements/relative fragility with the conservator prior to finalizing the mount design.

The contractor will need to bear this information in mind when returning their tender with regards to time allocated, materials proposed and the level of experience of the proposed team making the mounts.