## Sheet1
Highways England Confirmation of Task Order |  |  |  | Redacted under Section 43 of the FOI Act
Supplier: | AECOM | Fee Request for this CTO |  |  | 13479.77
Project Title: | A120/A133 Link Road – Technical Audit of Emme modelling
Contract Ref. | 0 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | ODE Devel Planning 19-20 | Sub Pin: | Redacted |  | PIN No.: | Redacted
HE Reference: | EE 133 19/20AECOM | Start and End Date : |  |  | 21/06/2019 - 09/08/2019
Task Overview and Expected Outcomes
Highways England wishes to respond to proposals for a Garden Community to the east of Colchester. This would be supported by a new link road connecting the A133 with the A120 to the east of the town at a new A120 junction. The proposals also include a bus-based rapid transit system linking the site with the University, town centre, rail station etc, and which would facilitate a second Park & Ride site to the east of the town. The impact of the Garden Community, the link road and the rapid transit system is to be assessed using an emme multi-modal model, which will be built on the back of a number of existing SATURN models. AECOM has been asked to technically review the Emme modelling and inputs from the emme model to appraisal. Where data from the SATURN models are used, a review of this is also in scope. This fee proposal therefore includes the following: • Discussion with Jacobs staff to get high-level overview of modelling status. • Obtain reporting. This is expected to include previous option reporting, forecasting note and base validation report for the emme model; as well as specification note and in-draft documentation for current work. We expect to be looking at around 6-7 reports. • Discuss initial view with Highways England and Jacobs, and, if appropriate, request some more detailed modelling material (such as emme macros, network coding), and/or information on one or more of the source SATURN models. The request will depend on a collective view of where the modelling most requires further scrutiny. • Undertake a review of more detailed material. This proposal does not make provision for a face-to-face meeting, as it is not obvious that one will become necessary as part of this stage of the work. However, it does include allowance for telephone calls and conferences with Highways England and Jacobs. These could include local authority staff if appropriate as well.
Task Objectives and Milestones
One or more Technical Notes will be produced to summarise our findings.
Expected Project Outcomes
• Advise Highways England as to the soundness of the emme model and its fitness for purpose as a tool to understand the impact of this proposed link road on the highway network; • If this is not the case, advise Highways England as to the further work likely to be required to reach such acceptance.
Project Risk and Management
We do not envisage any specific risks to timescale at this moment. The scope of the review is highly open-ended as it is difficult to say what we might find or wish to comment on or scrutinise further. Highways England and AECOM are both expecting the task to involve and that further review work will be required later; this proposal is for a mid-level review of the modelling work as it currently exists. As Jacob’s work progresses further review may be appropriate. – Please note that Paula Gomez Nunez is in the process of having an approved rate calculated. Her name therefore does not appear in the TAPE drop-down. For this reason, her time has been priced at the rate applicable to Imogen Atkinson, who is of similar rate and grade. Paula’s time will therefore appear in TAPE under Imogen’s name.
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  |  | Date: