## Sheet1
CLARIFICATION LOG
Tender: | Falmouth Harbour – Destination Development Feasibility Study
Tender Reference: | SPF
Published Date: | 22nd December 2023
Version number: | 2
Number | Clarification | Response | Reply date
1 | Could you confirm if you require the tender return to include all the roles listed within the brief? i.e. do we need to have a full design team in place as part of the tender submission? | Given the scope of the works, we believe that these are the skill sets required to undertake the Feasibility. If you believe that the work can be undertaken without all of the roles listed, then this should be detailed within your proposal. The proposed team should be detailed within your proposal. | 2024-01-05
2 | I am writing with regard to the above opportunity and in particular, Section 6.1, c, i of the tender submission that requires a Professional Indemnity Insurance limit of not less than five million (£5,000,000). In our experience this limit seems unduly high relative to the scope of work, fee budget and ‘risk’ at this stage of the project, and as a consequence is likely to have both financial and practical implications that are not necessarily in the interests of all parties or the project. May we request the limit be reviewed, possibly applying methodologies such as multiple of likely fee (e.g. 10 X budget). | PI Cover required to be reduced to £1.5m. | 2024-01-05
3 | Are you looking for the full design team to be presented under the tender as a consortia or could your tender be for part of this. | We are looking for a full design team. A consortia is acceptable with a lead consultant identified. FHC will only contract with the Lead organisation. As per section 7 of the ITT: Tenderers should note that a consortia can submit a tender but the sub-contracting of aspects of this commission after appointment will only be allowed by prior agreement with Falmouth Harbour Commissioners. Partnering and collaboration will be evaluated and weighted at 20% of the overall score. | 2024-01-05
4 | Point 6.5 Past experience and how you will bring this experience to Falmouth. No more than 2 sides of A4. As our proposed consortia has a great deal of experience of working in Falmouth, is it possible to include some additional past examples within a separate appendix to demonstrate this? | Yes, track record examples would be helpful max 4 sides of A4. Maximum of 4 examples. Please ensure relevance to this commission. | 2024-01-09
5 | The Site Plan indicates a boundary of the inner harbour area only. It is possible to also consider the wider Falmouth Harbour Commissioners controlled areas adjacent to, but outside of this described red line plan area? | We would expect consultants to consider the dynamic and plans in the wider Harbour, but the focus of the work has to be focused on the red line. Other development should be put into context such as Church Street Car park and Falmouth Docks. The Port of Falmouth Masterplan is still relevant for reference: https://planforfalmouth.info/wp-content/uploads/2016/12/Falmouth-Masterplan-Masterplan-Executive-Summary.pdf | 2024-01-09
6 | Is there any further programme detail/ key dates for the RIBA Stage 0-1, Stage 2a and 2b activities? | No. The whole study has to be completed by December 2024. It is up to the successful team to manage their time accordingly to ensure this end date is delivered. This is a requirement of grant funding. There will be no extensions. | 2024-01-16
7 | Environmental consultant is identified as a skill set but we would anticipate potential specialist surveys identified through the study would be supplementary to the commission, can you confirm if this is correct? | If further surveys are envisaged, they must be included in the tender price. The budget is fixed and no further funds available. Identifying detailed project work that is required post this scoping study and feasibility would be a good approach, alongside suggested specifications. | 2024-01-16
8 | We assume a list of the FHC’s assets & land registry particulars within the red line plan will be made available to the successful tender to assist the economic benefit review. | Correct, these are all available and will be provided. Including areas of fundus below MLW. | 2024-01-16
9 | Is there more detailed topographical and bathymetric survey data for the area within the red line plan? | Yes these will be made available to the succesful tender. | 2024-01-16
10 | Will there be a written project brief from the client or is this to be developed by the chosen consultant team? | The brief is as published. Obviously further conversations will be had with the client at a project kick off meeting. Ultimately we are looking for a Feasibility Study which identifies opportunities for developing Falmouth as a year-round destination for marine economic activity focussed on cruise, leisure, new green/blue tech, watersports tourism (over, on and under the water), education regarding the environment and marine/ocean conservation. | 2024-01-16
11 | What sort of stakeholder engagement is expected within this study? How many stakeholder groups will be consulted? And how many times? | We would expect the consultant to support any appropriate events that they feel should be in scope to get local community input into plans. In terms of scope we would expect as a minimum a presentation to our Board and our Harbour Users Group. In addition a single day event to support our Annual Review date in Q3 2024. | 2024-01-16
12 | Will there be a public consultation within this feasibility project? | As above - no formal consultation but a single information day and feedback with harbour Stakeholders. | 2024-01-16
13 | Is this a new piece of work or have there been previous feasibility studies carried out that will inform the project brief? | Ultimately this is a new piece of work. Previous work has been undertaken: https://www.falmouthharbour.co.uk/environment/sustainable-harbour-growth/ but times have moved on and focus changed. This previous work should be taken into consideration. These reports can be made available to the chosen consultant team. | 2024-01-16
14 | Can you define in more detail the outcomes required from the study? | The final report should include recommendations of projects to explore further which will develop Falmouth Harbour as a year round destination as per activity areas detailed in #10. It is expected to see high level costings and business case for the recommended projects including implementation plans and high level programmes. | 2024-01-16
15 | Is there an anticipated budget for the final /preferred scheme? | We believe that there are a number of potential projects that the harbour could explore as detailed in the brief. This report should explore these areas further and evidence to us if these ideas are feasible. We have no pre-conceived ideas for a preferred scheme. | 2024-01-16
16 | Are there any anticipated funding streams that the preferred scheme would lean towards or be submitted for in the future? | No | 2024-01-16
17 | Is the study to include pre-application consultation with the Local Planning authority? | Yes pre-planning advice is to be obtained. To include Listed building/ conservation officers as necessary and a view on MMO marine planning aspects. | 2024-01-16
18 | The excel spreadsheet mentions ‘the General Contingency sum’ , but there is no line item for this in table A. Is this to be included as a separate item? Is it a set figure noted by the client? | £4k | 2024-01-16
19 | What are key deliverables, and in what format, from each stage? | A report is required at the end of each stage. | 2024-01-16
20 | Is BIM, and associated 3d modelling of the proposals, a requirement for the project? | No | 2024-01-16
21 | Are there low carbon material requirements or green/renewable energy aspirations for the project? | Yes very much so. | 2024-01-16
22 | Is there a requirement for M&E input on proposed buildings, more specifically ‘building physics’ requirements? | Possibly, but this is likely to be too much detail… depends on the projects identified by the study. | 2024-01-16
23 | Are maerl beds or seagrass likely to be present or impacted within the study area? | No | 2024-01-16
24 | The hyperlink for the ‘Shared Prosperity, Branding and Publicity Guidance’ in section 6.1.e, could this document be re-shared? | https://ciosgoodgrowth.com/wp-content/uploads/2024/01/UK-SPF-_-Branding-and-Publicity-V9.pdf | 2024-01-16
24 | Have any environmental studies/surveys have previously been undertaken? | Yes see: https://www.falmouthharbour.co.uk/environment/sustainable-harbour-growth/ These reports will be made available to the chosen consultant team. | 2024-01-16
25 | Could we request an extension of the ITT return to 17.00 on the 26th January so that we can fully coordinate our team? | Unfortunately due to the tight timescales and other demands within the organisation this will not be possible. | 2024-01-16
26 | Social Value, please could you provide FHC social values so we can demonstrate how we link to them? | Our Objectives, Goals, Strategies and Plans document will be shared with there successful candidates. Our Cultural Values are set our below. | 2024-01-16
27 | With reference to questions 6.3, 6.4 and 6.5 there are differences in numbering between the criteria on pages 7 and the table on pages 8 and 9, please can we ask which takes precedent and confirm the assessment criteria? | This document has been amended and reissued on the portal as V3. | 2024-01-16
28 | We would like to provide CVs as part of the Partnering and Collaboration question, please can we include these as an appendix and outside the page count? | Yes. A maximum of 4 sides of A4. | 2024-01-16
29 | We would like to provide case studies as part of the experience question, and expertise, please can we include these as an appendix and outside the page count? | Yes, track record examples would be helpful max 4 sides of A4. Maximum of 4 examples. Please ensure relevance to this commission. | 2024-01-16
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie@jackiegeorge.co.uk
Cultural values
Wellbeing | Fundamental to consider this in all that we do and utilise the Harbour as an asset for good.
Clear Procedure | Key to improving safety and quality of work - knowing what needs to be done when key.
See it, say it, improve it! | Action and improve procedures after incidents. We all understand risks and link to returns.
Our People and Community (future) | We are liked and respected locally, transparent, and open, pride in Falmouth Harbour, colleagues feel valued, improvement programmes.
Make sustainable decisions | Culture of improvement and change in behaviours in all that we do. Ocean Health Advocates.