# Annex A

| Title of project: | A review of disaster resilience work programmes in the inhabited UK Overseas Territories in the context of nature-based solutions |
| --- | --- |
| Date and time for return of tenders: | Friday, 24 September 2021 @ 16:00 hours |
| Contract Reference No: | C21-0482-1589 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO AMANDA GREGORY or DORA IANTOSCA TO THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Amanda Gregory Joint Nature Conservation Committee Email: Amanda.gregory@jncc.gov.uk Tel: 01733 866852 And Jane Hawkridge Joint Nature Conservation Committee Email: Jane.Hawkridge@jncc.gov.uk Tel: 01733 866823 |
| Contact for any queries regarding the procurement procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk or contract queries@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | W/c 27 September 2021 |
| Proposed end-date: | 12 January 2022 |

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

- advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

- providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

- establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

- commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Aims

The UK’s Overseas Territories are highly dependent on the natural environment for their economic and social wellbeing.  They are also reliant on limited infrastructure.  In the Caribbean in particular, this infrastructure, and human life, are vulnerable to both natural and anthropogenic hazards.  The natural environment is itself susceptible to damage from human activities – resulting in loss of value to the economy and reducing its ability to protect assets and human well-being.

Since 2016 JNCC has been working with the UK Overseas Territories to understand the function and value of the natural environment in mitigating the impacts of climate change and natural disasters (see Section 3).  Prior to developing detailed proposals for implementing additional work in 2022 and beyond, JNCC wishes to undertake a review of the effectiveness of the work done to date and to identify future priority areas for investment.

The Review will need to include:

- work undertaken to date,

- the extent to which tools and data developed/acquired are being used,

- challenges and barriers to uptake of tools, their use,

- aspirations of individual OTs for future work of this kind or closely related work programmes,

- identification of science and knowledge gaps, and

- recommendations.

## Project Background

The 2016 Conflict, Stability & Security Fund (CSSF) funded programme of work, ‘Enhancing economic security through environmental resilience’ in the UK Overseas Territories (OTs) (Caribbean Territories of Anguilla, British Virgin Islands, Montserrat and Turks and Caicos Islands and the South Atlantic Territories of Falkland Islands, St Helena, Ascension and Tristan da Cunha) aimed to improve the long-term economic planning to support growth and development.

JNCC has used CSSF support, and funding from other sources, to implement a suite of projects to map and value the natural assets of partner OTs by integrating satellite data, Geographical Information Systems (GIS) and economic assessments of the priority environmental goods and services (derived from natural capital).  In the Caribbean, a GIS based model was developed to assess the vulnerability to storm surge and flooding events and their impacts on infrastructure and human life.

This work aimed to support the OTs in developing plans, policies, and procedures to deal with natural disasters by enhancing their ability to prepare for / recover from the impact of storm events with a particular focus on the functional significance and economic value of the natural environment in mitigating inshore and coastal zone flooding.

Since the inception of this work in 2016, JNCC has worked with the Caribbean/Western Atlantic Overseas Territories of Anguilla, British Virgin Islands, Cayman, Turks and Caicos and Montserrat. See https://jncc.gov.uk/our-work/natural-capital-in-the-overseas-territories/ for reports on work to date.

## Project Objectives

There are two closely related objectives from this contract:

Objective 1: establish, on a Territory-by-Territory basis, priorities and plans for future work related to the use of Nature Based Solutions (NbS) for mitigating inland and/or coastal zone flooding, including barriers to maximising the use of data and tools in this context and means to overcome these.

Objective 2: identify work programmes complementary to the JNCC programme and relevant to the UK’s inhabited Overseas Territories.  This should cover work currently in progress, or planned for the future, by UK based organisations, regional organisations (in particular with reference to the Caribbean/Western Atlantic) and international bodies.

All permanently inhabited Overseas Territories are to be included in this review, specifically:

- Anguilla

- Ascension

- Bermuda

- British Virgin Islands

- Cayman Islands

- Falkland Islands

- Gibraltar

- Montserrat

- Pitcairn

- St Helena

- Tristan da Cunha

- Turks and Caicos Islands

## Project Objectives: Detailed tasks

There are three component parts to this contract reflecting the two objectives;

Component 1:

Undertake a remote consultation with the relevant OT Government bodies in the 12 Territories listed above, and where relevant OT based NGOs, involved in disaster resilience work to identify:

- the current state of knowledge and tools available for modelling coastal storm surge and inland flooding and their current applications – for example (but not limited to) use in short term disaster responses, long term strategic planning, identifying Nature-based solutions (NbS) and opportunities etc;

- the source of funding, and the island based and ‘off island’ organisations acquiring data and making use of the data and developing or making use of tools available;

- barriers to maximising use of data or tools, for example, gaps in data, infrastructure, limited functionality of tools, capacity (training) gaps for use of tools, long-term budget to update and maintain, etc and proposed solutions to breaking down the barriers;

- priorities for future work in terms of data acquisition, modelling, training etc.

NOTE: It is assumed that this Review will include interviews with relevant organisations within or outside the Overseas Territories, supplemented by review of on-line or published material, unless otherwise proposed.  It is also assumed that this will include JNCC developed tools.

This component will be initiated first. JNCC will provide a ‘primary’ list of OT contacts.  JNCC will advise these contacts of the nature of the consultation and the identity of the contractor prior to interviews.  The contractor will be responsible for setting up interviews.  Interviews may identify ‘secondary contacts in the OTs or externally.  The contractor will be expected to follow-up on selected OT contacts subject to availability of contacts and time available.  JNCC does not expect that the contractor will need to conduct more than 25 interviews with OT based organisations.

External organisations will be contacted as part of the second component of the work programme.

Component 2:

Undertake a remote consultation with selected UK based and international organisations (eg NOAA, TNC), or, where appropriate, a ‘literature review’, to establish the scale, nature and location of similar work relevant to the Territories, specifically:

- the organisation’s remit in terms of region of operation and funding sources;

- nature of science based or economic work, including data acquisition, storm, climate change or other environmental modelling or monitoring programmes, capacity building;

- specific link to the UK OTs in terms of previous work, work in progress or planned.

NOTE:  JNCC will provide the contractor with an initial contact list, this to be supplemented by external contacts identified through Component 1. The Contractor and JNCC will agree a final list of organisations to be contacted to ensure the list is not excessive. It is not anticipated that more than 20 external organisations will need to be contacted, or their work reviewed.

Component 3:

Drawing upon Components 1 and 2, assess the effectiveness of tools across the OTs and provide recommendations for improving impact or filling necessary gaps to support disaster resilience management in the Overseas Territories.

## Potential follow-on work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2021/22.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given, that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Outputs

- A summary report by individual OT, listing all OT contacts approached (names and roles), dates interviews conducted for each Overseas Territory and details as described in Component 1 above plus any additional elements identified by JNCC;

- A report detailing relevant activities – as per Component 2 – being undertaken or planned by UK or international organisations.

- Recommendations report.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

To meet this standard, all reports and other documentation which are to be made publicly available must adhere to JNCC’s house-style and be produced using a JNCC CSSF template, unless otherwise stated.  JNCC will provide this template at project start up.  All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF.

Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

For any other outputs or products which are to be made publicly available through JNCC, evidence regarding how the accessibility standard will be reached should be included.

## Dissemination

The report or tools produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to JNCC, the UK Conservation Agencies, Defra and the UK Overseas Territories.

All documentation delivered by JNCC to the contractor regarding specification for the new system should be treated as commercial-in-confidence, the contractor should seek JNCC permission before distributing the documentation to any third parties.

Any information delivered to the contractor should not be used for any purposes outside the scope of this contract and should be destroyed on completion of the contract.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Start-up meeting (UK) | Week commencing 27 September 2021 |
| - Draft report on Component 1 | 29 October 2021 |
| - Draft report on Component 2 and 3 | 10 December 2021 |
| - Final report | 04 January, 2022 |
| - Project sign off | 12 January 2022 |

In agreeing exact dates, please note that the potential for work under this contract to be funded into 2021/22 is subject to availability of funds.

## Health and safety

## The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

## Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project management

The successful Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact point will be:

Ms Amanda Gregory

Email: Amanda.Gregory@jncc.gov.uk   Tel: +44 (0)1733 866811

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 14);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed (note for author if research project/contract. See EQA Policy Appendix 1 (Bias, Conflicting Evidence and uncertainty) and EQU Policy Appendix 3 (Quality Assurance of Expert Knowledge and Opinion).

Details of the bidder’s own internal Quality Management System;

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team representative for a virtual start-up meeting during week of the 27 September 2021.

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates).

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates.

  - Copies of any appropriate risk assessments.

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

## JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

The bid evaluation may be undertaken by a panel consisting of JNCC staff.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (55% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal (particularly work plan and deliverables) | 10 |  |
|  | Understanding of, and relevance to, the requirements in particular, the adequacy of the details of the proposed process for achieving the required outputs and clarity of proposal in respect of mechanisms to access the necessary data to undertake the work in the listed OTs in particular those identified for detailed modelling studies. | 10 |  |
|  | Soundness and logicality of methods | 10 |  |
|  | Realism and measurability of milestones | 5 |  |
|  | Evidence provided of how accessibility standards will be met | 5 |  |
|  | Identification and proposed solutions to potential problems/risks | 5 |  |
|  | Serious weaknesses which threaten success | 5 |  |
|  | Probability of success | 5 |  |
|  | Sub Totals | 55 |  |
| 2. Details of Contractor (20 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team, including demonstrable experience of working with small islands in general and the listed UK OTs in particular. | 10 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors (if any) | 5 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (30% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 10 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Appropriateness of ratio of senior to junior staff time | 5 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 25 |  |
| Total score |  | 100 |  |

## Payment

Unless a payment schedule is stated in your submission and agreed by JNCC project manager. Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The bidder is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.